## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 1152271
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | EARTH EXCAVATION | C.Y. | 3900 | 15 | 58500
2 | UNDERCUT AND BACKFILL UNSUITABLE SUBGRADE | C.Y. | 36 | 25 | 900
3 | EX. TREE REMOVAL | DIA. | 303 | 25 | 7575
4 | EX. BUSH TO BE REMOVED | EACH | 3 | 50 | 150
5 | REMOVE EX. FENCE | FT. | 22 | 5 | 110
6 | REMOVE EX. HANDRAIL | FT. | 33 | 5 | 165
7 | REMOVE & REPLACE EX. FENCE | FT. | 253 | 20 | 5060
8 | REMOVE & REPLACE GUARDRAIL | FT. | 10 | 50 | 500
9 | GUARDRAIL CONSTRUCTED ON CONCRETE BOX CULVERT | FT. | 33 | 50 | 1650
10 | PAVEMENT REMOVAL | S.Y. | 7258 | 6 | 43548
11 | SIDEWALK REMOVAL | S.F. | 616 | 2.5 | 1540
12 | EX. CONCRETE SPILLWAY TO BE REMOVED | EACH | 1 | 50 | 50
13 | COMBINATION CONCRETE CURB & GUTTER REMOVAL | FT. | 397 | 25 | 9925
14 | SAWCUT CURB TO DEPRESS | FT. | 13 | 10 | 130
15 | DRIVEWAY PAVEMENT REMOVAL CONCRETE | S.Y. | 148 | 5 | 740
16 | DRIVEWAY PAVEMENT REMOVAL HMA | S.Y. | 485 | 5 | 2425
17 | DRIVEWAY/SHOULDER PAVEMENT REMOVAL AGGREGATE | S.Y. | 3276 | 5 | 16380
18 | EX. INLET TO BE ADJUSTED | EACH | 1 | 500 | 500
19 | REMOVE EX STORM INLETS | EACH | 4 | 500 | 2000
20 | REMOVE EX. INLET SPECIAL & REPLACE 36" RCP THRU REMOVED AREA | EACH | 1 | 2500 | 2500
21 | EX. STORM SEWER REMOVAL | FT. | 378 | 10 | 3780
22 | ADJUST EXISTING VALVE & VAULT | EACH | 5 | 500 | 2500
23 | EX. WATER VALVE & VAULT TO BE RECONSTRUCTED | EACH | 2 | 2000 | 4000
24 | EX. FIRE HYDRANT & WATER VALVE & VAULT TO BE RELOCARED | EACH | 2 | 2500 | 5000
25 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 6 | 500 | 3000
26 | EX. TELEPHONE MANHOLE TO BE ADJUSTED | EACH | 2 | 500 | 1000
27 | EX. SANITARY MANHOLE TO BE RECONSTRUCTED | EACH | 2 | 2000 | 4000
28 | EX. TELEPHONE MANHOLE TO BE RECONSTRUCTED | EACH | 1 | 2000 | 2000
29 | EX. SIGN TO BE RELOCATED | EACH | 6 | 250 | 1500
30 | PROPOSED R5-11 SIGN AND POST COMPLETE | EACH | 1 | 400 | 400
31 | TRAFFIC CONTROL AND PROTECTION | L. SUM | 1 | 25000 | 25000
32 | PERIMETER EROSION CONTROL BARRIER | FT. | 1445 | 3 | 4335
33 | INLET PROTECTION | EACH | 27 | 250 | 6750
34 | TEMPORARY EROSION AND SEDIMENT CONTROL MAINT. | L. SUM | 1 | 7500 | 7500
35 | 4" TOPSOIL, CLASS 1A SEEDING & EROSION CONTROL BLANKET | S.Y. | 678 | 3 | 2034
36 | 4" TOPSOIL, CLASS 1A SEEDING & MULCH METHOD | S.Y. | 2797 | 3 | 8391
37 | CONSTRUCTION LAYOUT | LSUM | 1 | 40000 | 40000
38 | COMPACTED AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | S.Y. | 9531 | 8 | 76248
39 | SUBBASE GRANULAR MATERIAL TYPE B, CA-2, 6" | S.Y. | 9531 | 8 | 76248
40 | AGGREGATE SURFACE COURSE, TYPE A, 6" | S.Y. | 73 | 8 | 584
41 | *HMA SURFACE COURSE, MIX "D", N50, 2.0" | TON | 1067 | 80 | 85360
42 | *HMA BINDER COURSE, IL-19.0, N50, 4” | TON | 2134 | 80 | 170720
43 | *COMBINATION CONCRETE CURB AND GUTTER, MODIFIED TYPE M 6.18 | FT. | 5000 | 25 | 125000
44 | *PORTLAND CEMENT CONCRETE SIDEWALK, 4" (6" THRU DRIVEWAY) | S.F. | 24356 | 5 | 121780
45 | *DETECTABLE WARNINGS | S.F. | 302 | 35 | 10570
46 | *P.C. CONCRETE DRIVEWAY PAVEMENT, 6" | S.Y. | 810 | 50 | 40500
47 | THERMOPLASTIC PAVEMENT MARKING – LINE 24” WHITE | FT. | 117 | 5 | 585
48 | THERMOPLASTIC PAVEMENT MARKING – LINE 6” WHITE | FT. | 1044 | 2 | 2088
49 | YELLOW CURB PAINT | FT. | 22 | 10 | 220
50 | RCP STORM SEWER, 12" | FT. | 377 | 40 | 15080
51 | RCP STORM SEWER, 15" | FT. | 956 | 45 | 43020
52 | RCP STORM SEWER, 18" | FT. | 345 | 50 | 17250
53 | RCP STORM SEWER, 24" | FT. | 408 | 60 | 24480
54 | 2' DIA. STORM INLET TYPE A | EACH | 3 | 2000 | 6000
55 | 4’ DIA. STORM MANHOLE TYPE A | EACH | 2 | 2500 | 5000
56 | 6’ DIA. STORM MANHOLE TYPE A | EACH | 2 | 4000 | 8000
57 | 4’X4' INLET SPECIAL | EACH | 8 | 3500 | 28000
58 | STORM INLET 700 | EACH | 8 | 2500 | 20000
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Stenstrom Excvation |  | Northern Illinois Service |  | Fischer Excavating |  | N-Trak Group
City of Rockford | [5 empty] | Rockford, IL |  | Rockford, IL |  | Freeport, Il |  | Loves Park, IL
9th Street Reconstruction | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond
Bid No.: 622-PW-057 Vendor Notified: 102
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | EARTH EXCAVATION | C.Y. | 3900 | 15 | 58500 | 25 | 97500 | 29.5 | 115050 | 33.5 | 130650 | 25 | 97500 |  | 0 |  | 0
2 | UNDERCUT AND BACKFILL UNSUITABLE SUBGRADE | C.Y. | 36 | 25 | 900 | 106 | 3816 | 80 | 2880 | 86 | 3096 | 58 | 2088 |  | 0 |  | 0
3 | EX. TREE REMOVAL | DIA. | 303 | 25 | 7575 | 42.75 | 12953.25 | 40 | 12120 | 40 | 12120 | 40 | 12120 |  | 0 |  | 0
4 | EX. BUSH TO BE REMOVED | EACH | 3 | 50 | 150 | 32.05 | 96.15 | 30 | 90 | 30 | 90 | 30 | 90 |  | 0 |  | 0
5 | REMOVE EX. FENCE | FT. | 22 | 5 | 110 | 26.75 | 588.5 | 25 | 550 | 3.95 | 86.9 | 25 | 550 |  | 0 |  | 0
6 | REMOVE EX. HANDRAIL | FT. | 33 | 5 | 165 | 28.15 | 928.95 | 26.35 | 869.55 | 26.35 | 869.55 | 26.35 | 869.55 |  | 0 |  | 0
7 | REMOVE & REPLACE EX. FENCE | FT. | 253 | 20 | 5060 | 51.5 | 13029.5 | 48.24 | 12204.72 | 48.25 | 12207.25 | 48.24 | 12204.72 |  | 0 |  | 0
8 | REMOVE & REPLACE GUARDRAIL | FT. | 10 | 50 | 500 | 85.25 | 852.5 | 79.9 | 799 | 80 | 800 | 79.9 | 799 |  | 0 |  | 0
9 | GUARDRAIL CONSTRUCTED ON CONCRETE BOX CULVERT | FT. | 33 | 50 | 1650 | 270 | 8910 | 252.26 | 8324.58 | 252.25 | 8324.25 | 252.26 | 8324.58 |  | 0 |  | 0
10 | PAVEMENT REMOVAL | S.Y. | 7258 | 6 | 43548 | 3.7 | 26854.6 | 3 | 21774 | 8.8 | 63870.4 | 4.5 | 32661 |  | 0 |  | 0
11 | SIDEWALK REMOVAL | S.F. | 616 | 2.5 | 1540 | 2.6 | 1601.6 | 1 | 616 | 3.5 | 2156 | 1.5 | 924 |  | 0 |  | 0
12 | EX. CONCRETE SPILLWAY TO BE REMOVED | EACH | 1 | 50 | 50 | 300 | 300 | 1000 | 1000 | 881 | 881 | 750 | 750 |  | 0 |  | 0
13 | COMBINATION CONCRETE CURB & GUTTER REMOVAL | FT. | 397 | 25 | 9925 | 13.5 | 5359.5 | 4 | 1588 | 4 | 1588 | 6 | 2382 |  | 0 |  | 0
14 | SAWCUT CURB TO DEPRESS | FT. | 13 | 10 | 130 | 47.25 | 614.25 | 45 | 585 | 35 | 455 | 100 | 1300 |  | 0 |  | 0
15 | DRIVEWAY PAVEMENT REMOVAL CONCRETE | S.Y. | 148 | 5 | 740 | 19.25 | 2849 | 5 | 740 | 6 | 888 | 11 | 1628 |  | 0 |  | 0
16 | DRIVEWAY PAVEMENT REMOVAL HMA | S.Y. | 485 | 5 | 2425 | 9.75 | 4728.75 | 3 | 1455 | 9 | 4365 | 3 | 1455 |  | 0 |  | 0
17 | DRIVEWAY/SHOULDER PAVEMENT REMOVAL AGGREGATE | S.Y. | 3276 | 5 | 16380 | 8 | 26208 | 3 | 9828 | 4 | 13104 | 4 | 13104 |  | 0 |  | 0
18 | EX. INLET TO BE ADJUSTED | EACH | 1 | 500 | 500 | 1000 | 1000 | 950 | 950 | 873 | 873 | 1000 | 1000 |  | 0 |  | 0
19 | REMOVE EX STORM INLETS | EACH | 4 | 500 | 2000 | 510 | 2040 | 500 | 2000 | 549 | 2196 | 550 | 2200 |  | 0 |  | 0
20 | REMOVE EX. INLET SPECIAL & REPLACE 36" RCP THRU REMOVED AREA | EACH | 1 | 2500 | 2500 | 2500 | 2500 | 2000 | 2000 | 3643 | 3643 | 5500 | 5500 |  | 0 |  | 0
21 | EX. STORM SEWER REMOVAL | FT. | 378 | 10 | 3780 | 21.5 | 8127 | 15 | 5670 | 29 | 10962 | 25 | 9450 |  | 0 |  | 0
22 | ADJUST EXISTING VALVE & VAULT | EACH | 5 | 500 | 2500 | 710 | 3550 | 1000 | 5000 | 949 | 4745 | 1800 | 9000 |  | 0 |  | 0
23 | EX. WATER VALVE & VAULT TO BE RECONSTRUCTED | EACH | 2 | 2000 | 4000 | 1970 | 3940 | 2000 | 4000 | 1927 | 3854 | 2500 | 5000 |  | 0 |  | 0
24 | EX. FIRE HYDRANT & WATER VALVE & VAULT TO BE RELOCARED | EACH | 2 | 2500 | 5000 | 2875 | 5750 | 4500 | 9000 | 2603 | 5206 | 3000 | 6000 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 169628 |  | 234097.55 |  | 219093.85 |  | 287030.35 |  | 226899.85
| Award to Stenstrom Excvation | Total |  | As corrected | 169628 |  | 234097.55 |  | 219093.85 |  | 287030.35 |  | 226899.85
25 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 6 | 500 | 3000 | 835 | 5010 | 1000 | 6000 | 788 | 4728 | 1100 | 6600 |  | 0 |  | 0
26 | EX. SANITARY MANHOLE TO BE RECONSTRUCTED | EACH | 2 | 2000 | 4000 | 2200 | 4400 | 2500 | 5000 | 1633 | 3266 | 2300 | 4600 |  | 0 |  | 0
27 | EX. TELEPHONE MANHOLE TO BE ADJUSTED | EACH | 2 | 500 | 1000 | 1300 | 2600 | 750 | 1500 | 949 | 1898 | 1800 | 3600 |  | 0 |  | 0
28 | EX. TELEPHONE MANHOLE TO BE RECONSTRUCTED | EACH | 1 | 2000 | 2000 | 4225 | 4225 | 1500 | 1500 | 2170 | 2170 | 2300 | 2300 |  | 0 |  | 0
29 | EX. SIGN TO BE RELOCATED | EACH | 6 | 250 | 1500 | 294 | 1764 | 275 | 1650 | 425 | 2550 | 275 | 1650 |  | 0 |  | 0
30 | PROPOSED R5-11 SIGN AND POST COMPLETE | EACH | 1 | 400 | 400 | 455 | 455 | 425 | 425 | 425 | 425 | 425 | 425 |  | 0 |  | 0
31 | TRAFFIC CONTROL AND PROTECTION | L. SUM | 1 | 25000 | 25000 | 24000 | 24000 | 15000 | 15000 | 12850 | 12850 | 25000 | 25000 |  | 0 |  | 0
32 | PERIMETER EROSION CONTROL BARRIER | FT. | 1445 | 3 | 4335 | 5.35 | 7730.75 | 3 | 4335 | 5 | 7225 | 5 | 7225 |  | 0 |  | 0
33 | INLET PROTECTION | EACH | 27 | 250 | 6750 | 80.2 | 2165.4 | 150 | 4050 | 75 | 2025 | 75 | 2025 |  | 0 |  | 0
34 | TEMPORARY EROSION AND SEDIMENT CONTROL MAINT. | L. SUM | 1 | 7500 | 7500 | 3400 | 3400 | 5000 | 5000 | 1000 | 1000 | 2000 | 2000 |  | 0 |  | 0
35 | 4" TOPSOIL, CLASS 1A SEEDING & EROSION CONTROL BLANKET | S.Y. | 678 | 3 | 2034 | 7.6 | 5152.8 | 7.1 | 4813.8 | 7.1 | 4813.8 | 7.1 | 4813.8 |  | 0 |  | 0
36 | 4" TOPSOIL, CLASS 1A SEEDING & MULCH METHOD | S.Y. | 2797 | 3 | 8391 | 6.8 | 19019.6 | 6.35 | 17760.95 | 6.35 | 17760.95 | 6.35 | 17760.95 |  | 0 |  | 0
37 | CONSTRUCTION LAYOUT | LSUM | 1 | 40000 | 40000 | 12820 | 12820 | 16000 | 16000 | 7025 | 7025 | 12000 | 12000 |  | 0 |  | 0
38 | COMPACTED AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | S.Y. | 9531 | 8 | 76248 | 7.8 | 74341.8 | 8 | 76248 | 8.3 | 79107.3 | 8 | 76248 |  | 0 |  | 0
39 | SUBBASE GRANULAR MATERIAL TYPE B, CA-2, 6" | S.Y. | 9531 | 8 | 76248 | 6.5 | 61951.5 | 8 | 76248 | 7.3 | 69576.3 | 8 | 76248 |  | 0 |  | 0
40 | AGGREGATE SURFACE COURSE, TYPE A, 6" | S.Y. | 73 | 8 | 584 | 32.5 | 2372.5 | 8 | 584 | 6.2 | 452.6 | 10 | 730 |  | 0 |  | 0
41 | *HMA SURFACE COURSE, MIX "D", N50, 2.0" | TON | 1067 | 80 | 85360 | 93.5 | 99764.5 | 87.45 | 93309.15 | 87.5 | 93362.5 | 90 | 96030 |  | 0 |  | 0
42 | *HMA BINDER COURSE, IL-19.0, N50, 4” | TON | 2134 | 80 | 170720 | 79.9 | 170506.6 | 74.79 | 159601.86 | 75 | 160050 | 83 | 177122 |  | 0 |  | 0
43 | *COMBINATION CONCRETE CURB AND GUTTER, MODIFIED TYPE M 6.18 | FT. | 5000 | 25 | 125000 | 19.75 | 98750 | 21 | 105000 | 23 | 115000 | 27.5 | 137500 |  | 0 |  | 0
44 | *PORTLAND CEMENT CONCRETE SIDEWALK, 4" (6" THRU DRIVEWAY) | S.F. | 24356 | 5 | 121780 | 7.05 | 171709.8 | 8.75 | 213115 | 6.9 | 168056.4 | 7 | 170492 |  | 0 |  | 0
45 | *DETECTABLE WARNINGS | S.F. | 302 | 35 | 10570 | 28 | 8456 | 29.9 | 9029.8 | 29 | 8758 | 30 | 9060 |  | 0 |  | 0
46 | *P.C. CONCRETE DRIVEWAY PAVEMENT, 6" | S.Y. | 810 | 50 | 40500 | 76.25 | 61762.5 | 82 | 66420 | 82 | 66420 | 68.5 | 55485 |  | 0 |  | 0
47 | THERMOPLASTIC PAVEMENT MARKING – LINE 24” WHITE | FT. | 117 | 5 | 585 | 9.6 | 1123.2 | 9 | 1053 | 9 | 1053 | 9 | 1053 |  | 0 |  | 0
48 | THERMOPLASTIC PAVEMENT MARKING – LINE 6” WHITE | FT. | 1044 | 2 | 2088 | 2.4 | 2505.6 | 2.25 | 2349 | 2.25 | 2349 | 2.25 | 2349 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 985221 |  | 1080084.1 |  | 1105086.41 |  | 1118952.2 |  | 1119216.6
| Award to Stenstrom Excvation | Total |  | As corrected | 985221 |  | 1080084.1 |  | 1105086.41 |  | 1118952.2 |  | 1119216.6
49 | YELLOW CURB PAINT | FT. | 22 | 10 | 220 | 10.7 | 235.4 | 20 | 440 | 10 | 220 | 10 | 220 |  | 0 |  | 0
50 | RCP STORM SEWER, 12" | FT. | 377 | 40 | 15080 | 124 | 46748 | 122 | 45994 | 63 | 23751 | 160 | 60320 |  | 0 |  | 0
51 | RCP STORM SEWER, 15" | FT. | 956 | 45 | 43020 | 74 | 70744 | 84 | 80304 | 87 | 83172 | 93 | 88908 |  | 0 |  | 0
52 | RCP STORM SEWER, 18" | FT. | 345 | 50 | 17250 | 99 | 34155 | 86 | 29670 | 116 | 40020 | 96 | 33120 |  | 0 |  | 0
53 | RCP STORM SEWER, 24" | FT. | 408 | 60 | 24480 | 120 | 48960 | 97 | 39576 | 128 | 52224 | 117 | 47736 |  | 0 |  | 0
54 | 2' DIA. STORM INLET TYPE A | EACH | 3 | 2000 | 6000 | 1675 | 5025 | 2400 | 7200 | 1934 | 5802 | 1600 | 4800 |  | 0 |  | 0
55 | 4’ DIA. STORM MANHOLE TYPE A | EACH | 2 | 2500 | 5000 | 3450 | 6900 | 2700 | 5400 | 3617 | 7234 | 2700 | 5400 |  | 0 |  | 0
56 | 6’ DIA. STORM MANHOLE TYPE A | EACH | 2 | 4000 | 8000 | 5850 | 11700 | 5700 | 11400 | 8963 | 17926 | 10000 | 20000 |  | 0 |  | 0
57 | 4’X4' INLET SPECIAL | EACH | 8 | 3500 | 28000 | 3600 | 28800 | 3000 | 24000 | 7000 | 56000 | 3850 | 30800 |  | 0 |  | 0
58 | STORM INLET 700 | EACH | 8 | 2500 | 20000 | 2990 | 23920 | 2600 | 20800 | 3073 | 24584 | 2900 | 23200 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 1152271 |  | 1357271.5 |  | 1369870.41 |  | 1429885.2 |  | 1433720.6
| Award to Stenstrom Excvation | Bid |  | As corrected | 1152271 |  | 1357271.5 |  | 1369870.41 |  | 1429885.2 |  | 1433720.6
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to Stenstrom Excvation | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
9th Street Reconstruction
Item No. | Items | Units | Quantity | Unit Price | Total
1 | EARTH EXCAVATION | C.Y. | 3900 |  | 0
2 | UNDERCUT AND BACKFILL UNSUITABLE SUBGRADE | C.Y. | 36 |  | 0
3 | EX. TREE REMOVAL | DIA. | 303 |  | 0
4 | EX. BUSH TO BE REMOVED | EACH | 3 |  | 0
5 | REMOVE EX. FENCE | FT. | 22 |  | 0
6 | REMOVE EX. HANDRAIL | FT. | 33 |  | 0
7 | REMOVE & REPLACE EX. FENCE | FT. | 253 |  | 0
8 | REMOVE & REPLACE GUARDRAIL | FT. | 10 |  | 0
9 | GUARDRAIL CONSTRUCTED ON CONCRETE BOX CULVERT | FT. | 33 |  | 0
10 | PAVEMENT REMOVAL | S.Y. | 7258 |  | 0
11 | SIDEWALK REMOVAL | S.F. | 616 |  | 0
12 | EX. CONCRETE SPILLWAY TO BE REMOVED | EACH | 1 |  | 0
13 | COMBINATION CONCRETE CURB & GUTTER REMOVAL | FT. | 397 |  | 0
14 | SAWCUT CURB TO DEPRESS | FT. | 13 |  | 0
15 | DRIVEWAY PAVEMENT REMOVAL CONCRETE | S.Y. | 148 |  | 0
16 | DRIVEWAY PAVEMENT REMOVAL HMA | S.Y. | 485 |  | 0
17 | DRIVEWAY/SHOULDER PAVEMENT REMOVAL AGGREGATE | S.Y. | 3276 |  | 0
18 | EX. INLET TO BE ADJUSTED | EACH | 1 |  | 0
19 | REMOVE EX STORM INLETS | EACH | 4 |  | 0
20 | REMOVE EX. INLET SPECIAL & REPLACE 36" RCP THRU REMOVED AREA | EACH | 1 |  | 0
21 | EX. STORM SEWER REMOVAL | FT. | 378 |  | 0
22 | ADJUST EXISTING VALVE & VAULT | EACH | 5 |  | 0
23 | EX. WATER VALVE & VAULT TO BE RECONSTRUCTED | EACH | 2 |  | 0
24 | EX. FIRE HYDRANT & WATER VALVE & VAULT TO BE RELOCARED | EACH | 2 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 6 |  | 0
26 | EX. SANITARY MANHOLE TO BE RECONSTRUCTED | EACH | 2 |  | 0
27 | EX. TELEPHONE MANHOLE TO BE ADJUSTED | EACH | 2 |  | 0
28 | EX. TELEPHONE MANHOLE TO BE RECONSTRUCTED | EACH | 1 |  | 0
29 | EX. SIGN TO BE RELOCATED | EACH | 6 |  | 0
30 | PROPOSED R5-11 SIGN AND POST COMPLETE | EACH | 1 |  | 0
31 | TRAFFIC CONTROL AND PROTECTION | L. SUM | 1 |  | 0
32 | PERIMETER EROSION CONTROL BARRIER | FT. | 1445 |  | 0
33 | INLET PROTECTION | EACH | 27 |  | 0
34 | TEMPORARY EROSION AND SEDIMENT CONTROL MAINT. | L. SUM | 1 |  | 0
35 | 4" TOPSOIL, CLASS 1A SEEDING & EROSION CONTROL BLANKET | S.Y. | 678 |  | 0
36 | 4" TOPSOIL, CLASS 1A SEEDING & MULCH METHOD | S.Y. | 2797 |  | 0
37 | CONSTRUCTION LAYOUT | LSUM | 1 |  | 0
38 | COMPACTED AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | S.Y. | 9531 |  | 0
39 | SUBBASE GRANULAR MATERIAL TYPE B, CA-2, 6" | S.Y. | 9531 |  | 0
40 | AGGREGATE SURFACE COURSE, TYPE A, 6" | S.Y. | 73 |  | 0
41 | *HMA SURFACE COURSE, MIX "D", N50, 2.0" | TON | 1067 |  | 0
42 | *HMA BINDER COURSE, IL-19.0, N50, 4” | TON | 2134 |  | 0
43 | *COMBINATION CONCRETE CURB AND GUTTER, MODIFIED TYPE M 6.18 | FT. | 5000 |  | 0
44 | *PORTLAND CEMENT CONCRETE SIDEWALK, 4" (6" THRU DRIVEWAY) | S.F. | 24356 |  | 0
45 | *DETECTABLE WARNINGS | S.F. | 302 |  | 0
46 | *P.C. CONCRETE DRIVEWAY PAVEMENT, 6" | S.Y. | 810 |  | 0
47 | THERMOPLASTIC PAVEMENT MARKING – LINE 24” WHITE | FT. | 117 |  | 0
48 | THERMOPLASTIC PAVEMENT MARKING – LINE 6” WHITE | FT. | 1044 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | YELLOW CURB PAINT | FT. | 22 |  | 0
50 | RCP STORM SEWER, 12" | FT. | 377 |  | 0
51 | RCP STORM SEWER, 15" | FT. | 956 |  | 0
52 | RCP STORM SEWER, 18" | FT. | 345 |  | 0
53 | RCP STORM SEWER, 24" | FT. | 408 |  | 0
54 | 2' DIA. STORM INLET TYPE A | EACH | 3 |  | 0
55 | 4’ DIA. STORM MANHOLE TYPE A | EACH | 2 |  | 0
56 | 6’ DIA. STORM MANHOLE TYPE A | EACH | 2 |  | 0
57 | 4’X4' INLET SPECIAL | EACH | 8 |  | 0
58 | STORM INLET 700 | EACH | 8 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | 9th Street Reconstruction
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | EARTH EXCAVATION | C.Y. | 3900 | 15 | 58500
2 | UNDERCUT AND BACKFILL UNSUITABLE SUBGRADE | C.Y. | 36 | 25 | 900
3 | EX. TREE REMOVAL | DIA. | 303 | 25 | 7575
4 | EX. BUSH TO BE REMOVED | EACH | 3 | 50 | 150
5 | REMOVE EX. FENCE | FT. | 22 | 5 | 110
6 | REMOVE EX. HANDRAIL | FT. | 33 | 5 | 165
7 | REMOVE & REPLACE EX. FENCE | FT. | 253 | 20 | 5060
8 | REMOVE & REPLACE GUARDRAIL | FT. | 10 | 50 | 500
9 | GUARDRAIL CONSTRUCTED ON CONCRETE BOX CULVERT | FT. | 33 | 50 | 1650
10 | PAVEMENT REMOVAL | S.Y. | 7258 | 6 | 43548
11 | SIDEWALK REMOVAL | S.F. | 616 | 2.5 | 1540
12 | EX. CONCRETE SPILLWAY TO BE REMOVED | EACH | 1 | 50 | 50
13 | COMBINATION CONCRETE CURB & GUTTER REMOVAL | FT. | 397 | 25 | 9925
14 | SAWCUT CURB TO DEPRESS | FT. | 13 | 10 | 130
15 | DRIVEWAY PAVEMENT REMOVAL CONCRETE | S.Y. | 148 | 5 | 740
16 | DRIVEWAY PAVEMENT REMOVAL HMA | S.Y. | 485 | 5 | 2425
17 | DRIVEWAY/SHOULDER PAVEMENT REMOVAL AGGREGATE | S.Y. | 3276 | 5 | 16380
18 | EX. INLET TO BE ADJUSTED | EACH | 1 | 500 | 500
19 | REMOVE EX STORM INLETS | EACH | 4 | 500 | 2000
20 | REMOVE EX. INLET SPECIAL & REPLACE 36" RCP THRU REMOVED AREA | EACH | 1 | 2500 | 2500
21 | EX. STORM SEWER REMOVAL | FT. | 378 | 10 | 3780
22 | ADJUST EXISTING VALVE & VAULT | EACH | 5 | 500 | 2500
23 | EX. WATER VALVE & VAULT TO BE RECONSTRUCTED | EACH | 2 | 2000 | 4000
24 | EX. FIRE HYDRANT & WATER VALVE & VAULT TO BE RELOCARED | EACH | 2 | 2500 | 5000
|  |  |  | Sub Total | 169628
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 9th Street Reconstruction
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 6 | 500 | 3000
26 | EX. SANITARY MANHOLE TO BE RECONSTRUCTED | EACH | 2 | 2000 | 4000
27 | EX. TELEPHONE MANHOLE TO BE ADJUSTED | EACH | 2 | 500 | 1000
28 | EX. TELEPHONE MANHOLE TO BE RECONSTRUCTED | EACH | 1 | 2000 | 2000
29 | EX. SIGN TO BE RELOCATED | EACH | 6 | 250 | 1500
30 | PROPOSED R5-11 SIGN AND POST COMPLETE | EACH | 1 | 400 | 400
31 | TRAFFIC CONTROL AND PROTECTION | L. SUM | 1 | 25000 | 25000
32 | PERIMETER EROSION CONTROL BARRIER | FT. | 1445 | 3 | 4335
33 | INLET PROTECTION | EACH | 27 | 250 | 6750
34 | TEMPORARY EROSION AND SEDIMENT CONTROL MAINT. | L. SUM | 1 | 7500 | 7500
35 | 4" TOPSOIL, CLASS 1A SEEDING & EROSION CONTROL BLANKET | S.Y. | 678 | 3 | 2034
36 | 4" TOPSOIL, CLASS 1A SEEDING & MULCH METHOD | S.Y. | 2797 | 3 | 8391
37 | CONSTRUCTION LAYOUT | LSUM | 1 | 40000 | 40000
38 | COMPACTED AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | S.Y. | 9531 | 8 | 76248
39 | SUBBASE GRANULAR MATERIAL TYPE B, CA-2, 6" | S.Y. | 9531 | 8 | 76248
40 | AGGREGATE SURFACE COURSE, TYPE A, 6" | S.Y. | 73 | 8 | 584
41 | *HMA SURFACE COURSE, MIX "D", N50, 2.0" | TON | 1067 | 80 | 85360
42 | *HMA BINDER COURSE, IL-19.0, N50, 4” | TON | 2134 | 80 | 170720
43 | *COMBINATION CONCRETE CURB AND GUTTER, MODIFIED TYPE M 6.18 | FT. | 5000 | 25 | 125000
44 | *PORTLAND CEMENT CONCRETE SIDEWALK, 4" (6" THRU DRIVEWAY) | S.F. | 24356 | 5 | 121780
45 | *DETECTABLE WARNINGS | S.F. | 302 | 35 | 10570
46 | *P.C. CONCRETE DRIVEWAY PAVEMENT, 6" | S.Y. | 810 | 50 | 40500
47 | THERMOPLASTIC PAVEMENT MARKING – LINE 24” WHITE | FT. | 117 | 5 | 585
48 | THERMOPLASTIC PAVEMENT MARKING – LINE 6” WHITE | FT. | 1044 | 2 | 2088
|  |  |  | Sub Total | 985221
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 9th Street Reconstruction
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | YELLOW CURB PAINT | FT. | 22 | 10 | 220
50 | RCP STORM SEWER, 12" | FT. | 377 | 40 | 15080
51 | RCP STORM SEWER, 15" | FT. | 956 | 45 | 43020
52 | RCP STORM SEWER, 18" | FT. | 345 | 50 | 17250
53 | RCP STORM SEWER, 24" | FT. | 408 | 60 | 24480
54 | 2' DIA. STORM INLET TYPE A | EACH | 3 | 2000 | 6000
55 | 4’ DIA. STORM MANHOLE TYPE A | EACH | 2 | 2500 | 5000
56 | 6’ DIA. STORM MANHOLE TYPE A | EACH | 2 | 4000 | 8000
57 | 4’X4' INLET SPECIAL | EACH | 8 | 3500 | 28000
58 | STORM INLET 700 | EACH | 8 | 2500 | 20000
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1152271
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 9th Street Reconstruction
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1152271
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Stenstrom Excvation | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 9th Street Reconstruction
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | EARTH EXCAVATION | 3900 | C.Y. | 97500 |  | 3900 |  |  | 25
2 | UNDERCUT AND BACKFILL UNSUITABLE SUBGRADE | 36 | C.Y. | 3816 |  | 36 |  |  | 106
3 | EX. TREE REMOVAL | 303 | DIA. | 12953.25 |  | 303 |  |  | 42.75
4 | EX. BUSH TO BE REMOVED | 3 | EACH | 96.15 |  | 3 |  |  | 32.05
5 | REMOVE EX. FENCE | 22 | FT. | 588.5 |  | 22 |  |  | 26.75
6 | REMOVE EX. HANDRAIL | 33 | FT. | 928.95 |  | 33 |  |  | 28.15
7 | REMOVE & REPLACE EX. FENCE | 253 | FT. | 13029.5 |  | 253 |  |  | 51.5
8 | REMOVE & REPLACE GUARDRAIL | 10 | FT. | 852.5 |  | 10 |  |  | 85.25
9 | GUARDRAIL CONSTRUCTED ON CONCRETE BOX CULVERT | 33 | FT. | 8910 |  | 33 |  |  | 270
10 | PAVEMENT REMOVAL | 7258 | S.Y. | 26854.6 |  | 7258 |  |  | 3.7
11 | SIDEWALK REMOVAL | 616 | S.F. | 1601.6 |  | 616 |  |  | 2.6
12 | EX. CONCRETE SPILLWAY TO BE REMOVED | 1 | EACH | 300 |  | 1 |  |  | 300
13 | COMBINATION CONCRETE CURB & GUTTER REMOVAL | 397 | FT. | 5359.5 |  | 397 |  |  | 13.5
14 | SAWCUT CURB TO DEPRESS | 13 | FT. | 614.25 |  | 13 |  |  | 47.25
15 | DRIVEWAY PAVEMENT REMOVAL CONCRETE | 148 | S.Y. | 2849 |  | 148 |  |  | 19.25
16 | DRIVEWAY PAVEMENT REMOVAL HMA | 485 | S.Y. | 4728.75 |  | 485 |  |  | 9.75
17 | DRIVEWAY/SHOULDER PAVEMENT REMOVAL AGGREGATE | 3276 | S.Y. | 26208 |  | 3276 |  |  | 8
18 | EX. INLET TO BE ADJUSTED | 1 | EACH | 1000 |  | 1 |  |  | 1000
19 | REMOVE EX STORM INLETS | 4 | EACH | 2040 |  | 4 |  |  | 510
20 | REMOVE EX. INLET SPECIAL & REPLACE 36" RCP THRU REMOVED AREA | 1 | EACH | 2500 |  | 1 |  |  | 2500
21 | EX. STORM SEWER REMOVAL | 378 | FT. | 8127 |  | 378 |  |  | 21.5
22 | ADJUST EXISTING VALVE & VAULT | 5 | EACH | 3550 |  | 5 |  |  | 710
23 | EX. WATER VALVE & VAULT TO BE RECONSTRUCTED | 2 | EACH | 3940 |  | 2 |  |  | 1970
24 | EX. FIRE HYDRANT & WATER VALVE & VAULT TO BE RELOCARED | 2 | EACH | 5750 |  | 2 |  |  | 2875
Sub Total |  |  |  | 234097.55 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Stenstrom Excvation | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 9th Street Reconstruction
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | EX. SANITARY MANHOLE TO BE ADJUSTED | 6 | EACH | 5010 |  | 6 |  |  | 835
26 | EX. SANITARY MANHOLE TO BE RECONSTRUCTED | 2 | EACH | 4400 |  | 2 |  |  | 2200
27 | EX. TELEPHONE MANHOLE TO BE ADJUSTED | 2 | EACH | 2600 |  | 2 |  |  | 1300
28 | EX. TELEPHONE MANHOLE TO BE RECONSTRUCTED | 1 | EACH | 4225 |  | 1 |  |  | 4225
29 | EX. SIGN TO BE RELOCATED | 6 | EACH | 1764 |  | 6 |  |  | 294
30 | PROPOSED R5-11 SIGN AND POST COMPLETE | 1 | EACH | 455 |  | 1 |  |  | 455
31 | TRAFFIC CONTROL AND PROTECTION | 1 | L. SUM | 24000 |  | 1 |  |  | 24000
32 | PERIMETER EROSION CONTROL BARRIER | 1445 | FT. | 7730.75 |  | 1445 |  |  | 5.35
33 | INLET PROTECTION | 27 | EACH | 2165.4 |  | 27 |  |  | 80.2
34 | TEMPORARY EROSION AND SEDIMENT CONTROL MAINT. | 1 | L. SUM | 3400 |  | 1 |  |  | 3400
35 | 4" TOPSOIL, CLASS 1A SEEDING & EROSION CONTROL BLANKET | 678 | S.Y. | 5152.8 |  | 678 |  |  | 7.6
36 | 4" TOPSOIL, CLASS 1A SEEDING & MULCH METHOD | 2797 | S.Y. | 19019.6 |  | 2797 |  |  | 6.8
37 | CONSTRUCTION LAYOUT | 1 | LSUM | 12820 |  | 1 |  |  | 12820
38 | COMPACTED AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | 9531 | S.Y. | 74341.8 |  | 9531 |  |  | 7.8
39 | SUBBASE GRANULAR MATERIAL TYPE B, CA-2, 6" | 9531 | S.Y. | 61951.5 |  | 9531 |  |  | 6.5
40 | AGGREGATE SURFACE COURSE, TYPE A, 6" | 73 | S.Y. | 2372.5 |  | 73 |  |  | 32.5
41 | *HMA SURFACE COURSE, MIX "D", N50, 2.0" | 1067 | TON | 99764.5 |  | 1067 |  |  | 93.5
42 | *HMA BINDER COURSE, IL-19.0, N50, 4” | 2134 | TON | 170506.6 |  | 2134 |  |  | 79.9
43 | *COMBINATION CONCRETE CURB AND GUTTER, MODIFIED TYPE M 6.18 | 5000 | FT. | 98750 |  | 5000 |  |  | 19.75
44 | *PORTLAND CEMENT CONCRETE SIDEWALK, 4" (6" THRU DRIVEWAY) | 24356 | S.F. | 171709.8 |  | 24356 |  |  | 7.05
45 | *DETECTABLE WARNINGS | 302 | S.F. | 8456 |  | 302 |  |  | 28
46 | *P.C. CONCRETE DRIVEWAY PAVEMENT, 6" | 810 | S.Y. | 61762.5 |  | 810 |  |  | 76.25
47 | THERMOPLASTIC PAVEMENT MARKING – LINE 24” WHITE | 117 | FT. | 1123.2 |  | 117 |  |  | 9.6
48 | THERMOPLASTIC PAVEMENT MARKING – LINE 6” WHITE | 1044 | FT. | 2505.6 |  | 1044 |  |  | 2.4
Sub Total |  |  |  | 1080084.1 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Stenstrom Excvation | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 9th Street Reconstruction
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | YELLOW CURB PAINT | 22 | FT. | 235.4 |  | 22 |  |  | 10.7
50 | RCP STORM SEWER, 12" | 377 | FT. | 46748 |  | 377 |  |  | 124
51 | RCP STORM SEWER, 15" | 956 | FT. | 70744 |  | 956 |  |  | 74
52 | RCP STORM SEWER, 18" | 345 | FT. | 34155 |  | 345 |  |  | 99
53 | RCP STORM SEWER, 24" | 408 | FT. | 48960 |  | 408 |  |  | 120
54 | 2' DIA. STORM INLET TYPE A | 3 | EACH | 5025 |  | 3 |  |  | 1675
55 | 4’ DIA. STORM MANHOLE TYPE A | 2 | EACH | 6900 |  | 2 |  |  | 3450
56 | 6’ DIA. STORM MANHOLE TYPE A | 2 | EACH | 11700 |  | 2 |  |  | 5850
57 | 4’X4' INLET SPECIAL | 8 | EACH | 28800 |  | 8 |  |  | 3600
58 | STORM INLET 700 | 8 | EACH | 23920 |  | 8 |  |  | 2990
Total |  |  |  | 1357271.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Stenstrom Excvation | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 9th Street Reconstruction
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 1357271.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | 9th Street Reconstruction
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Stenstrom Excvation
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.