## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 3472671.1
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | Mobilization | L SUM | 1 | 15000 | 15000
2 | Construction Layout Staking | L SUM | 1 | 7500 | 7500
3 | Inlet and Pipe Protection | EACH | 23 | 125 | 2875
4 | Concrete Truck Washout | EACH | 18 | 450 | 8100
5 | Pavement Removal | SQ YD | 3668 | 7.5 | 27510
6 | Approach Pavement Removal | SQ YD | 682.5 | 7.5 | 5118.75
7 | Sidewalk Removal | SQ FT | 30423 | 2 | 60846
8 | Combination Curb and Gutter Removal | FT | 7361.5 | 5 | 36807.5
9 | Rock Excavation | CU YD | 60 | 50 | 3000
10 | Remove Valve and Valve Vault, Complete | EACH | 22 | 950 | 20900
11 | Remove Fire Hydrant, Complete | EACH | 8 | 1000 | 8000
12 | Ductile Iron Water Main Complete, 6" | FT | 320 | 200 | 64000
13 | Ductile Iron Water Main Complete, 8" | FT | 4420 | 175 | 773500
14 | Ductile Iron Water Main Complete, 12" | FT | 48.5 | 250 | 12125
15 | Ductile Iron Water Main Complete, 16" | FT | 15.5 | 300 | 4650
16 | Gate Valve and Valve Box Complete, 4" | EACH | 4 | 2250 | 9000
17 | Gate Valve and Valve Box Complete, 8" | EACH | 24 | 3000 | 72000
18 | Butterfly Valve and Valve Box Complete, 12" | EACH | 1 | 4000 | 4000
19 | Butterfly Valve and Valve Box Complete, 16" | EACH | 1 | 5500 | 5500
20 | Fire Hydrant with 6" Valve and Valve Box, Complete | EACH | 14 | 6750 | 94500
21 | Water Service (Open-cut), Complete, 1" | EACH | 27 | 3100 | 83700
22 | Water Service (Open-cut), Complete, 2" | EACH | 5 | 4750 | 23750
23 | Water Service (Open-cut), Complete, 4" | EACH | 4 | 7500 | 30000
24 | Water Service (Bored or Pulled), Complete, 1" | EACH | 18 | 5500 | 99000
25 | Exterior Foundation Access Pit | EACH | 7 | 1000 | 7000
26 | Connection To Relocated/Existing Water Meter, Complete | EACH | 7 | 1100 | 7700
27 | Interior Water Meter Relocation, Complete | FT | 110 | 20 | 2200
28 | Reconnection Of Water Service Electrical Jumper Cable | EACH | 7 | 1000 | 7000
29 | Primary Electrical Grounding System Installation | EACH | 7 | 2000 | 14000
30 | Water Main Protection, HDPE, 18" | FT | 913.5 | 125 | 114187.5
31 | Water Service Protection, 2" | FT | 65 | 12 | 780
32 | Water Main Protection, Bore And Jack Steel Casing, 16" | FT | 135 | 1000 | 135000
33 | Connection To Existing 3" Water Main, Complete | EACH | 1 | 2500 | 2500
34 | Connection To Existing 6" Water Main, Complete | EACH | 10 | 2800 | 28000
35 | Connection To Existing 8" Water Main, Complete | EACH | 1 | 3500 | 3500
36 | Connection To Existing 12" Water Main, Complete | EACH | 1 | 3800 | 3800
37 | Connection To Existing 16" Water Main, Complete | EACH | 1 | 5000 | 5000
38 | Water Main Line Stop, 6" | EACH | 9 | 5000 | 45000
39 | Water Main Line Stop, 12" | EACH | 1 | 8000 | 8000
40 | Water Main Line Stop, 16" | EACH | 1 | 10000 | 10000
41 | Insertion Valve, Complete, 6" | EACH | 1 | 6500 | 6500
42 | Insertion Valve, Complete, 12" | EACH | 1 | 12000 | 12000
43 | Insertion Valve, Complete, 16" | EACH | 1 | 16000 | 16000
44 | P.C.C. Approach Pavement, 6" | SQ YD | 162 | 70 | 11340
45 | P.C.C. Approach Pavement, 8" | SQ YD | 358 | 75 | 26850
46 | Hot-Mix Asphalt Approach Pavement, 3" | SQ YD | 68 | 100 | 6800
47 | P.C.C. Sidewalk, 4" | SQ FT | 21848 | 7 | 152936
48 | Detectable Warnings, ADA Ramps | SQ FT | 230 | 20 | 4600
49 | Combination Concrete Curb And Gutter, Type M-6.18 (Modified) | FT | 6987 | 25 | 174675
50 | Combination Concrete Curb And Gutter, Type B-6.24 (Modified) | FT | 22 | 35 | 770
51 | Earth Excavation | CU YD | 30 | 30 | 900
52 | Subbase Granular Material, Type B, 6" (CA-2) | SQ YD | 3609.5 | 10 | 36095
53 | Aggregate Base Repair | SQ YD | 188 | 20 | 3760
54 | Class D Patch, 8" (Special) | SQ YD | 3609.5 | 75 | 270712.5
55 | Bituminous Materials (Prime Coat) | GAL | 1959.6 | 1 | 1959.6
56 | Aggregate (Prime Coat) | TONS | 96.2 | 100 | 9620
57 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | TONS | 2278.4 | 100 | 227840
58 | Hot-Mix Asphalt, Hand Method | TONS | 20 | 300 | 6000
59 | Surface Removal, 2" | SQ YD | 19779.5 | 5.5 | 108787.25
60 | Manholes to be Adjusted | EACH | 25 | 600 | 15000
61 | Manholes to be Adjusted with New Frame and Lid | EACH | 13 | 800 | 10400
62 | Manholes to be Reconstructed | EACH | 1 | 1000 | 1000
63 | Manholes to be Reconstructed with New Frame and Lid | EACH | 2 | 1300 | 2600
64 | Inlets to be Adjusted | EACH | 13 | 1500 | 19500
65 | Inlets to be Adjusted with New Frame and Lid | EACH | 12 | 1600 | 19200
66 | Inlets to be Reconstructed | EACH | 1 | 1500 | 1500
67 | Inlets to be Reconstructed with New Frame and Lid | EACH | 2 | 1900 | 3800
68 | Thermoplastic Pavement Markings, 4" | FT | 10811 | 4 | 43244
69 | Thermoplastic Pavement Markings, 6" | FT | 1621 | 5 | 8105
70 | Thermoplastic Pavement Markings, 12" | FT | 349 | 6 | 2094
71 | Thermoplastic Pavement Markings, 24" | FT | 217 | 12 | 2604
72 | Thermoplastic Pavement Markings, Letters and Symbols | SQ FT | 1217 | 12 | 14604
73 | Parkway Restoration | L SUM | 1 | 80000 | 80000
74 | Traffic Control And Protection, Special | L SUM | 1 | 35000 | 35000
75 | Railroad Protective Liability Insurance (Idot Pay Item Z0048665) | L SUM | 1 | 6500 | 6500
76 | Railroad Flagging | CL DAY | 5 | 1500 | 7500
77 | Non-Special Waste Disposal (Idot Pay Item 66900200) | CU YD | 25 | 100 | 2500
78 | Special Waste Disposal (Idot Pay Item 66900205) | CU YD | 25 | 100 | 2500
79 | Special Waste Plans And Reports (Idot Pay Item 66900450) | L SUM | 1 | 2000 | 2000
80 | Soil Disposal Analysis ( Idot Pay Item 66900530) | EACH | 25 | 2000 | 50000
81 | Sanitary Riser / Valve Boxes to be Adjusted | EACH | 3 | 300 | 900
82 | Detector Loops | FT | 800 | 30 | 24000
83 | Sanitary Manholes to be Reconstructed with New Type 1 Frame, Closed Lid | EACH | 1 | 3750 | 3750
84 | Sanitary Manholes to be Removed | EACH | 1 | 1750 | 1750
85 | Sanitary Manholes to be Removed and Replace, 4' Dia | EACH | 9 | 8500 | 76500
86 | Sanitary Manholes, 4" Dia | EACH | 2 | 7000 | 14000
87 | Sanitary Sewer Mainline Repair, 10" Dia | FT | 5 | 450 | 2250
88 | Sanitary Sewer Mainline Repair, 12" Dia | FT | 10 | 500 | 5000
89 | Sanitary Sewer Mainline Repair, 15" Dia | FT | 10 | 550 | 5500
90 | Sanitary Sewer Service Reconnection, 6" Dia | FT | 20 | 250 | 5000
91 | Sanitary Sewer Service Replacement, 6" Dia | FT | 238 | 95 | 22610
92 | Sanitary Sewer Service Replacement, 8" Dia | FT | 135 | 115 | 15525
93 | Sanitary Sewer Service Replacement, 10" Dia | FT | 77 | 120 | 9240
94 | Sanitary Sewer, PVC SDR 26 WMQ, 8" Dia | FT | 82.5 | 120 | 9900
95 | Sanitary Sewer Service Riser to be Lowered and Capped | EACH | 3 | 1300 | 3900
96
Note on E27: Marting, Dale: using $3,500 for the public side based on older bid tabs. Plus $2,00 for the private side assuming 25 ft average and $80/ft. Also based on older bid tabs.

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Northern Illinois Service |  | N-Trak Group |  | Fischer Excavating
City of Rockford | [5 empty] | Rockford, IL |  | Loves Park, IL |  | Freeport, IL
15th Avenue Improvements | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond
Bid No.: 522-W-052 Vendor Notified: 112
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Mobilization | L SUM | 1 | 15000 | 15000 | 116040 | 116040 | 50000 | 50000 | 31500 | 31500 |  | 0 |  | 0 |  | 0
2 | Construction Layout Staking | L SUM | 1 | 7500 | 7500 | 20000 | 20000 | 20000 | 20000 | 7025 | 7025 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | EACH | 23 | 125 | 2875 | 200 | 4600 | 100 | 2300 | 260 | 5980 |  | 0 |  | 0 |  | 0
4 | Concrete Truck Washout | EACH | 18 | 450 | 8100 | 50.25 | 904.5 | 0.01 | 0.18 | 250 | 4500 |  | 0 |  | 0 |  | 0
5 | Pavement Removal | SQ YD | 3668 | 7.5 | 27510 | 29 | 106372 | 20 | 73360 | 16 | 58688 |  | 0 |  | 0 |  | 0
6 | Approach Pavement Removal | SQ YD | 682.5 | 7.5 | 5118.75 | 25 | 17062.5 | 15 | 10237.5 | 10 | 6825 |  | 0 |  | 0 |  | 0
7 | Sidewalk Removal | SQ FT | 30423 | 2 | 60846 | 1.5 | 45634.5 | 2 | 60846 | 2.6 | 79099.8 |  | 0 |  | 0 |  | 0
8 | Combination Curb and Gutter Removal | FT | 7361.5 | 5 | 36807.5 | 15.4 | 113367.1 | 6 | 44169 | 5.6 | 41224.4 |  | 0 |  | 0 |  | 0
9 | Rock Excavation | CU YD | 60 | 50 | 3000 | 200 | 12000 | 200 | 12000 | 97 | 5820 |  | 0 |  | 0 |  | 0
10 | Remove Valve and Valve Vault, Complete | EACH | 22 | 950 | 20900 | 1000 | 22000 | 3000 | 66000 | 1169 | 25718 |  | 0 |  | 0 |  | 0
11 | Remove Fire Hydrant, Complete | EACH | 8 | 1000 | 8000 | 1000 | 8000 | 2000 | 16000 | 795 | 6360 |  | 0 |  | 0 |  | 0
12 | Ductile Iron Water Main Complete, 6" | FT | 320 | 200 | 64000 | 180 | 57600 | 200 | 64000 | 166 | 53120 |  | 0 |  | 0 |  | 0
13 | Ductile Iron Water Main Complete, 8" | FT | 4420 | 175 | 773500 | 202 | 892840 | 220 | 972400 | 160 | 707200 |  | 0 |  | 0 |  | 0
14 | Ductile Iron Water Main Complete, 12" | FT | 48.5 | 250 | 12125 | 270 | 13095 | 300 | 14550 | 394 | 19109 |  | 0 |  | 0 |  | 0
15 | Ductile Iron Water Main Complete, 16" | FT | 15.5 | 300 | 4650 | 380 | 5890 | 575 | 8912.5 | 615 | 9532.5 |  | 0 |  | 0 |  | 0
16 | Gate Valve and Valve Box Complete, 4" | EACH | 4 | 2250 | 9000 | 2600 | 10400 | 2500 | 10000 | 2014 | 8056 |  | 0 |  | 0 |  | 0
17 | Gate Valve and Valve Box Complete, 8" | EACH | 24 | 3000 | 72000 | 3350 | 80400 | 3500 | 84000 | 2946 | 70704 |  | 0 |  | 0 |  | 0
18 | Butterfly Valve and Valve Box Complete, 12" | EACH | 1 | 4000 | 4000 | 4800 | 4800 | 4700 | 4700 | 4350 | 4350 |  | 0 |  | 0 |  | 0
19 | Butterfly Valve and Valve Box Complete, 16" | EACH | 1 | 5500 | 5500 | 7200 | 7200 | 7500 | 7500 | 7262 | 7262 |  | 0 |  | 0 |  | 0
20 | Fire Hydrant with 6" Valve and Valve Box, Complete | EACH | 14 | 6750 | 94500 | 7000 | 98000 | 7200 | 100800 | 8113 | 113582 |  | 0 |  | 0 |  | 0
21 | Water Service (Open-cut), Complete, 1" | EACH | 27 | 3100 | 83700 | 4500 | 121500 | 4200 | 113400 | 3110 | 83970 |  | 0 |  | 0 |  | 0
22 | Water Service (Open-cut), Complete, 2" | EACH | 5 | 4750 | 23750 | 6300 | 31500 | 5300 | 26500 | 4362 | 21810 |  | 0 |  | 0 |  | 0
23 | Water Service (Open-cut), Complete, 4" | EACH | 4 | 7500 | 30000 | 7500 | 30000 | 5500 | 22000 | 7925 | 31700 |  | 0 |  | 0 |  | 0
24 | Water Service (Bored or Pulled), Complete, 1" | EACH | 18 | 5500 | 99000 | 4500 | 81000 | 4500 | 81000 | 3296 | 59328 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 1471382.25 |  | 1900205.6 |  | 1864675.18 |  | 1462463.7
| Award to Northern Illinois Service | Total |  | As corrected | 1471382.25 |  | 1900205.6 |  | 1864675.18 |  | 1462463.7
25 | Exterior Foundation Access Pit | EACH | 7 | 1000 | 7000 | 1500 | 10500 | 500 | 3500 | 955 | 6685 |  | 0 |  | 0 |  | 0
26 | Connection To Relocated/Existing Water Meter, Complete | EACH | 7 | 1100 | 7700 | 2200 | 15400 | 1000 | 7000 | 2321 | 16247 |  | 0 |  | 0 |  | 0
27 | Interior Water Meter Relocation, Complete | FT | 110 | 20 | 2200 | 25 | 2750 | 50 | 5500 | 62 | 6820 |  | 0 |  | 0 |  | 0
28 | Reconnection Of Water Service Electrical Jumper Cable | EACH | 7 | 1000 | 7000 | 200 | 1400 | 550 | 3850 | 750 | 5250 |  | 0 |  | 0 |  | 0
29 | Primary Electrical Grounding System Installation | EACH | 7 | 2000 | 14000 | 1600 | 11200 | 1100 | 7700 | 2125 | 14875 |  | 0 |  | 0 |  | 0
30 | Water Main Protection, HDPE, 18" | FT | 913.5 | 125 | 114187.5 | 200 | 182700 | 175 | 159862.5 | 190 | 173565 |  | 0 |  | 0 |  | 0
31 | Water Service Protection, 2" | FT | 65 | 12 | 780 | 35 | 2275 | 25 | 1625 | 18 | 1170 |  | 0 |  | 0 |  | 0
32 | Water Main Protection, Bore And Jack Steel Casing, 16" | FT | 135 | 1000 | 135000 | 643 | 86805 | 700 | 94500 | 595 | 80325 |  | 0 |  | 0 |  | 0
33 | Connection To Existing 3" Water Main, Complete | EACH | 1 | 2500 | 2500 | 4200 | 4200 | 5000 | 5000 | 3563 | 3563 |  | 0 |  | 0 |  | 0
34 | Connection To Existing 6" Water Main, Complete | EACH | 10 | 2800 | 28000 | 4400 | 44000 | 5500 | 55000 | 4200 | 42000 |  | 0 |  | 0 |  | 0
35 | Connection To Existing 8" Water Main, Complete | EACH | 1 | 3500 | 3500 | 4500 | 4500 | 5500 | 5500 | 4850 | 4850 |  | 0 |  | 0 |  | 0
36 | Connection To Existing 12" Water Main, Complete | EACH | 1 | 3800 | 3800 | 6000 | 6000 | 6500 | 6500 | 7461 | 7461 |  | 0 |  | 0 |  | 0
37 | Connection To Existing 16" Water Main, Complete | EACH | 1 | 5000 | 5000 | 9000 | 9000 | 12000 | 12000 | 10610 | 10610 |  | 0 |  | 0 |  | 0
38 | Water Main Line Stop, 6" | EACH | 9 | 5000 | 45000 | 5000 | 45000 | 6500 | 58500 | 5788 | 52092 |  | 0 |  | 0 |  | 0
39 | Water Main Line Stop, 12" | EACH | 1 | 8000 | 8000 | 8500 | 8500 | 8750 | 8750 | 9384 | 9384 |  | 0 |  | 0 |  | 0
40 | Water Main Line Stop, 16" | EACH | 1 | 10000 | 10000 | 12500 | 12500 | 40000 | 40000 | 9348 | 9348 |  | 0 |  | 0 |  | 0
41 | Insertion Valve, Complete, 6" | EACH | 1 | 6500 | 6500 | 6000 | 6000 | 7000 | 7000 | 6196 | 6196 |  | 0 |  | 0 |  | 0
42 | Insertion Valve, Complete, 12" | EACH | 1 | 12000 | 12000 | 12000 | 12000 | 14000 | 14000 | 15122 | 15122 |  | 0 |  | 0 |  | 0
43 | Insertion Valve, Complete, 16" | EACH | 1 | 16000 | 16000 | 45000 | 45000 | 45000 | 45000 | 33670 | 33670 |  | 0 |  | 0 |  | 0
44 | P.C.C. Approach Pavement, 6" | SQ YD | 162 | 70 | 11340 | 69 | 11178 | 68.25 | 11056.5 | 119 | 19278 |  | 0 |  | 0 |  | 0
45 | P.C.C. Approach Pavement, 8" | SQ YD | 358 | 75 | 26850 | 85 | 30430 | 78.75 | 28192.5 | 131 | 46898 |  | 0 |  | 0 |  | 0
46 | Hot-Mix Asphalt Approach Pavement, 3" | SQ YD | 68 | 100 | 6800 | 35 | 2380 | 47.25 | 3213 | 49 | 3332 |  | 0 |  | 0 |  | 0
47 | P.C.C. Sidewalk, 4" | SQ FT | 21848 | 7 | 152936 | 8 | 174784 | 6.3 | 137642.4 | 10 | 218480 |  | 0 |  | 0 |  | 0
48 | Detectable Warnings, ADA Ramps | SQ FT | 230 | 20 | 4600 | 30 | 6900 | 30.45 | 7003.5 | 32 | 7360 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 2102075.75 |  | 2635607.6 |  | 2592570.58 |  | 2257044.7
| Award to Northern Illinois Service | Total |  | As corrected | 2102075.75 |  | 2635607.6 |  | 2592570.58 |  | 2257044.7
49 | Combination Concrete Curb And Gutter, Type M-6.18 (Modified) | FT | 6987 | 25 | 174675 | 29.5 | 206116.5 | 28 | 195636 | 35 | 244545 |  | 0 |  | 0 |  | 0
50 | Combination Concrete Curb And Gutter, Type B-6.24 (Modified) | FT | 22 | 35 | 770 | 60 | 1320 | 94.5 | 2079 | 93 | 2046 |  | 0 |  | 0 |  | 0
51 | Earth Excavation | CU YD | 30 | 30 | 900 | 100 | 3000 | 125 | 3750 | 31 | 930 |  | 0 |  | 0 |  | 0
52 | Subbase Granular Material, Type B, 6" (CA-2) | SQ YD | 3609.5 | 10 | 36095 | 14 | 50533 | 10 | 36095 | 31 | 111894.5 |  | 0 |  | 0 |  | 0
53 | Aggregate Base Repair | SQ YD | 188 | 20 | 3760 | 30 | 5640 | 28 | 5264 | 28 | 5264 |  | 0 |  | 0 |  | 0
54 | Class D Patch, 8" (Special) | SQ YD | 3609.5 | 75 | 270712.5 | 43.83 | 158204.385 | 70 | 252665 | 85 | 306807.5 |  | 0 |  | 0 |  | 0
55 | Bituminous Materials (Prime Coat) | GAL | 1959.6 | 1 | 1959.6 | 0.01 | 19.596 | 4 | 7838.4 | 0.02 | 39.192 |  | 0 |  | 0 |  | 0
56 | Aggregate (Prime Coat) | TONS | 96.2 | 100 | 9620 | 0.01 | 0.962 | 0.01 | 0.962 | 0.01 | 0.962 |  | 0 |  | 0 |  | 0
57 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | TONS | 2278.4 | 100 | 227840 | 82.66 | 188332.544 | 95 | 216448 | 82.7 | 188423.68 |  | 0 |  | 0 |  | 0
58 | Hot-Mix Asphalt, Hand Method | TONS | 20 | 300 | 6000 | 200 | 4000 | 375 | 7500 | 200 | 4000 |  | 0 |  | 0 |  | 0
59 | Surface Removal, 2" | SQ YD | 19779.5 | 5.5 | 108787.25 | 2.7 | 53404.65 | 3.25 | 64283.375 | 4.65 | 91974.675 |  | 0 |  | 0 |  | 0
60 | Manholes to be Adjusted | EACH | 25 | 600 | 15000 | 1350 | 33750 | 1800 | 45000 | 757 | 18925 |  | 0 |  | 0 |  | 0
61 | Manholes to be Adjusted with New Frame and Lid | EACH | 13 | 800 | 10400 | 1700 | 22100 | 2200 | 28600 | 1185 | 15405 |  | 0 |  | 0 |  | 0
62 | Manholes to be Reconstructed | EACH | 1 | 1000 | 1000 | 2800 | 2800 | 2800 | 2800 | 13940 | 13940 |  | 0 |  | 0 |  | 0
63 | Manholes to be Reconstructed with New Frame and Lid | EACH | 2 | 1300 | 2600 | 3200 | 6400 | 3200 | 6400 | 1521 | 3042 |  | 0 |  | 0 |  | 0
64 | Inlets to be Adjusted | EACH | 13 | 1500 | 19500 | 1500 | 19500 | 2000 | 26000 | 954 | 12402 |  | 0 |  | 0 |  | 0
65 | Inlets to be Adjusted with New Frame and Lid | EACH | 12 | 1600 | 19200 | 2200 | 26400 | 2650 | 31800 | 1755 | 21060 |  | 0 |  | 0 |  | 0
66 | Inlets to be Reconstructed | EACH | 1 | 1500 | 1500 | 2800 | 2800 | 3400 | 3400 | 1181 | 1181 |  | 0 |  | 0 |  | 0
67 | Inlets to be Reconstructed with New Frame and Lid | EACH | 2 | 1900 | 3800 | 3400 | 6800 | 4000 | 8000 | 1905 | 3810 |  | 0 |  | 0 |  | 0
68 | Thermoplastic Pavement Markings, 4" | FT | 10811 | 4 | 43244 | 0.9 | 9729.9 | 1 | 10811 | 1.5 | 16216.5 |  | 0 |  | 0 |  | 0
69 | Thermoplastic Pavement Markings, 6" | FT | 1621 | 5 | 8105 | 1.35 | 2188.35 | 1.35 | 2188.35 | 2.31 | 3744.51 |  | 0 |  | 0 |  | 0
70 | Thermoplastic Pavement Markings, 12" | FT | 349 | 6 | 2094 | 2.7 | 942.3 | 2.7 | 942.3 | 4.62 | 1612.38 |  | 0 |  | 0 |  | 0
71 | Thermoplastic Pavement Markings, 24" | FT | 217 | 12 | 2604 | 5.4 | 1171.8 | 5.4 | 1171.8 | 9.24 | 2005.08 |  | 0 |  | 0 |  | 0
72 | Thermoplastic Pavement Markings, Letters and Symbols | SQ FT | 1217 | 12 | 14604 | 9 | 10953 | 9 | 10953 | 5 | 6085 |  | 0 |  | 0 |  | 0
| Page 3 | Sub |  | As read | 3086846.1 |  | 3451714.587 |  | 3562196.767 |  | 3332398.679
| Award to Northern Illinois Service | Total |  | As corrected | 3086846.1 |  | 3451714.587 |  | 3562196.767 |  | 3332398.679
73 | Parkway Restoration | L SUM | 1 | 80000 | 80000 | 60000 | 60000 | 70000 | 70000 | 53984 | 53984 |  | 0 |  | 0 |  | 0
74 | Traffic Control And Protection, Special | L SUM | 1 | 35000 | 35000 | 55000 | 55000 | 20000 | 20000 | 266781 | 266781 |  | 0 |  | 0 |  | 0
75 | Railroad Protective Liability Insurance (Idot Pay Item Z0048665) | L SUM | 1 | 6500 | 6500 | 5000 | 5000 | 10200 | 10200 | 7500 | 7500 |  | 0 |  | 0 |  | 0
76 | Railroad Flagging | CL DAY | 5 | 1500 | 7500 | 1750 | 8750 | 1500 | 7500 | 1500 | 7500 |  | 0 |  | 0 |  | 0
77 | Non-Special Waste Disposal (Idot Pay Item 66900200) | CU YD | 25 | 100 | 2500 | 200 | 5000 | 75 | 1875 | 95 | 2375 |  | 0 |  | 0 |  | 0
78 | Special Waste Disposal (Idot Pay Item 66900205) | CU YD | 25 | 100 | 2500 | 300 | 7500 | 85 | 2125 | 120 | 3000 |  | 0 |  | 0 |  | 0
79 | Special Waste Plans And Reports (Idot Pay Item 66900450) | L SUM | 1 | 2000 | 2000 | 3500 | 3500 | 2300 | 2300 | 2300 | 2300 |  | 0 |  | 0 |  | 0
80 | Soil Disposal Analysis ( Idot Pay Item 66900530) | EACH | 25 | 2000 | 50000 | 500 | 12500 | 950 | 23750 | 950 | 23750 |  | 0 |  | 0 |  | 0
81 | Sanitary Riser / Valve Boxes to be Adjusted | EACH | 3 | 300 | 900 | 1200 | 3600 | 1000 | 3000 | 1019 | 3057 |  | 0 |  | 0 |  | 0
82 | Detector Loops | FT | 800 | 30 | 24000 | 32.75 | 26200 | 34.5 | 27600 | 32.75 | 26200 |  | 0 |  | 0 |  | 0
83 | Sanitary Manholes to be Reconstructed with New Type 1 Frame, Closed Lid | EACH | 1 | 3750 | 3750 | 10000 | 10000 | 11000 | 11000 | 14170 | 14170 |  | 0 |  | 0 |  | 0
84 | Sanitary Manholes to be Removed | EACH | 1 | 1750 | 1750 | 3000 | 3000 | 2500 | 2500 | 4962 | 4962 |  | 0 |  | 0 |  | 0
85 | Sanitary Manholes to be Removed and Replace, 4' Dia | EACH | 9 | 8500 | 76500 | 19350 | 174150 | 16500 | 148500 | 29000 | 261000 |  | 0 |  | 0 |  | 0
86 | Sanitary Manholes, 4" Dia | EACH | 2 | 7000 | 14000 | 8000 | 16000 | 10000 | 20000 | 23153 | 46306 |  | 0 |  | 0 |  | 0
87 | Sanitary Sewer Mainline Repair, 10" Dia | FT | 5 | 450 | 2250 | 1000 | 5000 | 850 | 4250 | 2153 | 10765 |  | 0 |  | 0 |  | 0
88 | Sanitary Sewer Mainline Repair, 12" Dia | FT | 10 | 500 | 5000 | 1000 | 10000 | 725 | 7250 | 1504 | 15040 |  | 0 |  | 0 |  | 0
89 | Sanitary Sewer Mainline Repair, 15" Dia | FT | 10 | 550 | 5500 | 1200 | 12000 | 1050 | 10500 | 1390 | 13900 |  | 0 |  | 0 |  | 0
90 | Sanitary Sewer Service Reconnection, 6" Dia | FT | 20 | 250 | 5000 | 150 | 3000 | 500 | 10000 | 204 | 4080 |  | 0 |  | 0 |  | 0
91 | Sanitary Sewer Service Replacement, 6" Dia | FT | 238 | 95 | 22610 | 150 | 35700 | 225 | 53550 | 218 | 51884 |  | 0 |  | 0 |  | 0
92 | Sanitary Sewer Service Replacement, 8" Dia | FT | 135 | 115 | 15525 | 160 | 21600 | 300 | 40500 | 229 | 30915 |  | 0 |  | 0 |  | 0
93 | Sanitary Sewer Service Replacement, 10" Dia | FT | 77 | 120 | 9240 | 170 | 13090 | 310 | 23870 | 325 | 25025 |  | 0 |  | 0 |  | 0
94 | Sanitary Sewer, PVC SDR 26 WMQ, 8" Dia | FT | 82.5 | 120 | 9900 | 160 | 13200 | 302 | 24915 | 233 | 19222.5 |  | 0 |  | 0 |  | 0
95 | Sanitary Sewer Service Riser to be Lowered and Capped | EACH | 3 | 1300 | 3900 | 1350 | 4050 | 1200 | 3600 | 540 | 1620 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | 3472671.1 |  | 3959554.587 |  | 4090981.767 |  | 4227735.179
| Award to Northern Illinois Service | Bid |  | As corrected | 3472671.1 |  | 3959554.587 |  | 4090981.767 |  | 4227735.179

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
15th Avenue Improvements
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Mobilization | L SUM | 1 |  | 0
2 | Construction Layout Staking | L SUM | 1 |  | 0
3 | Inlet and Pipe Protection | EACH | 23 |  | 0
4 | Concrete Truck Washout | EACH | 18 |  | 0
5 | Pavement Removal | SQ YD | 3668 |  | 0
6 | Approach Pavement Removal | SQ YD | 682.5 |  | 0
7 | Sidewalk Removal | SQ FT | 30423 |  | 0
8 | Combination Curb and Gutter Removal | FT | 7361.5 |  | 0
9 | Rock Excavation | CU YD | 60 |  | 0
10 | Remove Valve and Valve Vault, Complete | EACH | 22 |  | 0
11 | Remove Fire Hydrant, Complete | EACH | 8 |  | 0
12 | Ductile Iron Water Main Complete, 6" | FT | 320 |  | 0
13 | Ductile Iron Water Main Complete, 8" | FT | 4420 |  | 0
14 | Ductile Iron Water Main Complete, 12" | FT | 48.5 |  | 0
15 | Ductile Iron Water Main Complete, 16" | FT | 15.5 |  | 0
16 | Gate Valve and Valve Box Complete, 4" | EACH | 4 |  | 0
17 | Gate Valve and Valve Box Complete, 8" | EACH | 24 |  | 0
18 | Butterfly Valve and Valve Box Complete, 12" | EACH | 1 |  | 0
19 | Butterfly Valve and Valve Box Complete, 16" | EACH | 1 |  | 0
20 | Fire Hydrant with 6" Valve and Valve Box, Complete | EACH | 14 |  | 0
21 | Water Service (Open-cut), Complete, 1" | EACH | 27 |  | 0
22 | Water Service (Open-cut), Complete, 2" | EACH | 5 |  | 0
23 | Water Service (Open-cut), Complete, 4" | EACH | 4 |  | 0
24 | Water Service (Bored or Pulled), Complete, 1" | EACH | 18 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Exterior Foundation Access Pit | EACH | 7 |  | 0
26 | Connection To Relocated/Existing Water Meter, Complete | EACH | 7 |  | 0
27 | Interior Water Meter Relocation, Complete | FT | 110 |  | 0
28 | Reconnection Of Water Service Electrical Jumper Cable | EACH | 7 |  | 0
29 | Primary Electrical Grounding System Installation | EACH | 7 |  | 0
30 | Water Main Protection, HDPE, 18" | FT | 913.5 |  | 0
31 | Water Service Protection, 2" | FT | 65 |  | 0
32 | Water Main Protection, Bore And Jack Steel Casing, 16" | FT | 135 |  | 0
33 | Connection To Existing 3" Water Main, Complete | EACH | 1 |  | 0
34 | Connection To Existing 6" Water Main, Complete | EACH | 10 |  | 0
35 | Connection To Existing 8" Water Main, Complete | EACH | 1 |  | 0
36 | Connection To Existing 12" Water Main, Complete | EACH | 1 |  | 0
37 | Connection To Existing 16" Water Main, Complete | EACH | 1 |  | 0
38 | Water Main Line Stop, 6" | EACH | 9 |  | 0
39 | Water Main Line Stop, 12" | EACH | 1 |  | 0
40 | Water Main Line Stop, 16" | EACH | 1 |  | 0
41 | Insertion Valve, Complete, 6" | EACH | 1 |  | 0
42 | Insertion Valve, Complete, 12" | EACH | 1 |  | 0
43 | Insertion Valve, Complete, 16" | EACH | 1 |  | 0
44 | P.C.C. Approach Pavement, 6" | SQ YD | 162 |  | 0
45 | P.C.C. Approach Pavement, 8" | SQ YD | 358 |  | 0
46 | Hot-Mix Asphalt Approach Pavement, 3" | SQ YD | 68 |  | 0
47 | P.C.C. Sidewalk, 4" | SQ FT | 21848 |  | 0
48 | Detectable Warnings, ADA Ramps | SQ FT | 230 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | Combination Concrete Curb And Gutter, Type M-6.18 (Modified) | FT | 6987 |  | 0
50 | Combination Concrete Curb And Gutter, Type B-6.24 (Modified) | FT | 22 |  | 0
51 | Earth Excavation | CU YD | 30 |  | 0
52 | Subbase Granular Material, Type B, 6" (CA-2) | SQ YD | 3609.5 |  | 0
53 | Aggregate Base Repair | SQ YD | 188 |  | 0
54 | Class D Patch, 8" (Special) | SQ YD | 3609.5 |  | 0
55 | Bituminous Materials (Prime Coat) | GAL | 1959.6 |  | 0
56 | Aggregate (Prime Coat) | TONS | 96.2 |  | 0
57 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | TONS | 2278.4 |  | 0
58 | Hot-Mix Asphalt, Hand Method | TONS | 20 |  | 0
59 | Surface Removal, 2" | SQ YD | 19779.5 |  | 0
60 | Manholes to be Adjusted | EACH | 25 |  | 0
61 | Manholes to be Adjusted with New Frame and Lid | EACH | 13 |  | 0
62 | Manholes to be Reconstructed | EACH | 1 |  | 0
63 | Manholes to be Reconstructed with New Frame and Lid | EACH | 2 |  | 0
64 | Inlets to be Adjusted | EACH | 13 |  | 0
65 | Inlets to be Adjusted with New Frame and Lid | EACH | 12 |  | 0
66 | Inlets to be Reconstructed | EACH | 1 |  | 0
67 | Inlets to be Reconstructed with New Frame and Lid | EACH | 2 |  | 0
68 | Thermoplastic Pavement Markings, 4" | FT | 10811 |  | 0
69 | Thermoplastic Pavement Markings, 6" | FT | 1621 |  | 0
70 | Thermoplastic Pavement Markings, 12" | FT | 349 |  | 0
71 | Thermoplastic Pavement Markings, 24" | FT | 217 |  | 0
72 | Thermoplastic Pavement Markings, Letters and Symbols | SQ FT | 1217 |  | 0
| Page 3 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
73 | Parkway Restoration | L SUM | 1 |  | 0
74 | Traffic Control And Protection, Special | L SUM | 1 |  | 0
75 | Railroad Protective Liability Insurance (Idot Pay Item Z0048665) | L SUM | 1 |  | 0
76 | Railroad Flagging | CL DAY | 5 |  | 0
77 | Non-Special Waste Disposal (Idot Pay Item 66900200) | CU YD | 25 |  | 0
78 | Special Waste Disposal (Idot Pay Item 66900205) | CU YD | 25 |  | 0
79 | Special Waste Plans And Reports (Idot Pay Item 66900450) | L SUM | 1 |  | 0
80 | Soil Disposal Analysis ( Idot Pay Item 66900530) | EACH | 25 |  | 0
81 | Sanitary Riser / Valve Boxes to be Adjusted | EACH | 3 |  | 0
82 | Detector Loops | FT | 800 |  | 0
83 | Sanitary Manholes to be Reconstructed with New Type 1 Frame, Closed Lid | EACH | 1 |  | 0
84 | Sanitary Manholes to be Removed | EACH | 1 |  | 0
85 | Sanitary Manholes to be Removed and Replace, 4' Dia | EACH | 9 |  | 0
86 | Sanitary Manholes, 4" Dia | EACH | 2 |  | 0
87 | Sanitary Sewer Mainline Repair, 10" Dia | FT | 5 |  | 0
88 | Sanitary Sewer Mainline Repair, 12" Dia | FT | 10 |  | 0
89 | Sanitary Sewer Mainline Repair, 15" Dia | FT | 10 |  | 0
90 | Sanitary Sewer Service Reconnection, 6" Dia | FT | 20 |  | 0
91 | Sanitary Sewer Service Replacement, 6" Dia | FT | 238 |  | 0
92 | Sanitary Sewer Service Replacement, 8" Dia | FT | 135 |  | 0
93 | Sanitary Sewer Service Replacement, 10" Dia | FT | 77 |  | 0
94 | Sanitary Sewer, PVC SDR 26 WMQ, 8" Dia | FT | 82.5 |  | 0
95 | Sanitary Sewer Service Riser to be Lowered and Capped | EACH | 3 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | 15th Avenue Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Mobilization | L SUM | 1 | 15000 | 15000
2 | Construction Layout Staking | L SUM | 1 | 7500 | 7500
3 | Inlet and Pipe Protection | EACH | 23 | 125 | 2875
4 | Concrete Truck Washout | EACH | 18 | 450 | 8100
5 | Pavement Removal | SQ YD | 3668 | 7.5 | 27510
6 | Approach Pavement Removal | SQ YD | 682.5 | 7.5 | 5118.75
7 | Sidewalk Removal | SQ FT | 30423 | 2 | 60846
8 | Combination Curb and Gutter Removal | FT | 7361.5 | 5 | 36807.5
9 | Rock Excavation | CU YD | 60 | 50 | 3000
10 | Remove Valve and Valve Vault, Complete | EACH | 22 | 950 | 20900
11 | Remove Fire Hydrant, Complete | EACH | 8 | 1000 | 8000
12 | Ductile Iron Water Main Complete, 6" | FT | 320 | 200 | 64000
13 | Ductile Iron Water Main Complete, 8" | FT | 4420 | 175 | 773500
14 | Ductile Iron Water Main Complete, 12" | FT | 48.5 | 250 | 12125
15 | Ductile Iron Water Main Complete, 16" | FT | 15.5 | 300 | 4650
16 | Gate Valve and Valve Box Complete, 4" | EACH | 4 | 2250 | 9000
17 | Gate Valve and Valve Box Complete, 8" | EACH | 24 | 3000 | 72000
18 | Butterfly Valve and Valve Box Complete, 12" | EACH | 1 | 4000 | 4000
19 | Butterfly Valve and Valve Box Complete, 16" | EACH | 1 | 5500 | 5500
20 | Fire Hydrant with 6" Valve and Valve Box, Complete | EACH | 14 | 6750 | 94500
21 | Water Service (Open-cut), Complete, 1" | EACH | 27 | 3100 | 83700
22 | Water Service (Open-cut), Complete, 2" | EACH | 5 | 4750 | 23750
23 | Water Service (Open-cut), Complete, 4" | EACH | 4 | 7500 | 30000
24 | Water Service (Bored or Pulled), Complete, 1" | EACH | 18 | 5500 | 99000
|  |  |  | Sub Total | 1471382.25
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 15th Avenue Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Exterior Foundation Access Pit | EACH | 7 | 1000 | 7000
26 | Connection To Relocated/Existing Water Meter, Complete | EACH | 7 | 1100 | 7700
27 | Interior Water Meter Relocation, Complete | FT | 110 | 20 | 2200
28 | Reconnection Of Water Service Electrical Jumper Cable | EACH | 7 | 1000 | 7000
29 | Primary Electrical Grounding System Installation | EACH | 7 | 2000 | 14000
30 | Water Main Protection, HDPE, 18" | FT | 913.5 | 125 | 114187.5
31 | Water Service Protection, 2" | FT | 65 | 12 | 780
32 | Water Main Protection, Bore And Jack Steel Casing, 16" | FT | 135 | 1000 | 135000
33 | Connection To Existing 3" Water Main, Complete | EACH | 1 | 2500 | 2500
34 | Connection To Existing 6" Water Main, Complete | EACH | 10 | 2800 | 28000
35 | Connection To Existing 8" Water Main, Complete | EACH | 1 | 3500 | 3500
36 | Connection To Existing 12" Water Main, Complete | EACH | 1 | 3800 | 3800
37 | Connection To Existing 16" Water Main, Complete | EACH | 1 | 5000 | 5000
38 | Water Main Line Stop, 6" | EACH | 9 | 5000 | 45000
39 | Water Main Line Stop, 12" | EACH | 1 | 8000 | 8000
40 | Water Main Line Stop, 16" | EACH | 1 | 10000 | 10000
41 | Insertion Valve, Complete, 6" | EACH | 1 | 6500 | 6500
42 | Insertion Valve, Complete, 12" | EACH | 1 | 12000 | 12000
43 | Insertion Valve, Complete, 16" | EACH | 1 | 16000 | 16000
44 | P.C.C. Approach Pavement, 6" | SQ YD | 162 | 70 | 11340
45 | P.C.C. Approach Pavement, 8" | SQ YD | 358 | 75 | 26850
46 | Hot-Mix Asphalt Approach Pavement, 3" | SQ YD | 68 | 100 | 6800
47 | P.C.C. Sidewalk, 4" | SQ FT | 21848 | 7 | 152936
48 | Detectable Warnings, ADA Ramps | SQ FT | 230 | 20 | 4600
|  |  |  | Sub Total | 2102075.75
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 15th Avenue Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | Combination Concrete Curb And Gutter, Type M-6.18 (Modified) | FT | 6987 | 25 | 174675
50 | Combination Concrete Curb And Gutter, Type B-6.24 (Modified) | FT | 22 | 35 | 770
51 | Earth Excavation | CU YD | 30 | 30 | 900
52 | Subbase Granular Material, Type B, 6" (CA-2) | SQ YD | 3609.5 | 10 | 36095
53 | Aggregate Base Repair | SQ YD | 188 | 20 | 3760
54 | Class D Patch, 8" (Special) | SQ YD | 3609.5 | 75 | 270712.5
55 | Bituminous Materials (Prime Coat) | GAL | 1959.6 | 1 | 1959.6
56 | Aggregate (Prime Coat) | TONS | 96.2 | 100 | 9620
57 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | TONS | 2278.4 | 100 | 227840
58 | Hot-Mix Asphalt, Hand Method | TONS | 20 | 300 | 6000
59 | Surface Removal, 2" | SQ YD | 19779.5 | 5.5 | 108787.25
60 | Manholes to be Adjusted | EACH | 25 | 600 | 15000
61 | Manholes to be Adjusted with New Frame and Lid | EACH | 13 | 800 | 10400
62 | Manholes to be Reconstructed | EACH | 1 | 1000 | 1000
63 | Manholes to be Reconstructed with New Frame and Lid | EACH | 2 | 1300 | 2600
64 | Inlets to be Adjusted | EACH | 13 | 1500 | 19500
65 | Inlets to be Adjusted with New Frame and Lid | EACH | 12 | 1600 | 19200
66 | Inlets to be Reconstructed | EACH | 1 | 1500 | 1500
67 | Inlets to be Reconstructed with New Frame and Lid | EACH | 2 | 1900 | 3800
68 | Thermoplastic Pavement Markings, 4" | FT | 10811 | 4 | 43244
69 | Thermoplastic Pavement Markings, 6" | FT | 1621 | 5 | 8105
70 | Thermoplastic Pavement Markings, 12" | FT | 349 | 6 | 2094
71 | Thermoplastic Pavement Markings, 24" | FT | 217 | 12 | 2604
72 | Thermoplastic Pavement Markings, Letters and Symbols | SQ FT | 1217 | 12 | 14604
|  |  |  | Sub Total | 3086846.1
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 15th Avenue Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
73 | Parkway Restoration | L SUM | 1 | 80000 | 80000
74 | Traffic Control And Protection, Special | L SUM | 1 | 35000 | 35000
75 | Railroad Protective Liability Insurance (Idot Pay Item Z0048665) | L SUM | 1 | 6500 | 6500
76 | Railroad Flagging | CL DAY | 5 | 1500 | 7500
77 | Non-Special Waste Disposal (Idot Pay Item 66900200) | CU YD | 25 | 100 | 2500
78 | Special Waste Disposal (Idot Pay Item 66900205) | CU YD | 25 | 100 | 2500
79 | Special Waste Plans And Reports (Idot Pay Item 66900450) | L SUM | 1 | 2000 | 2000
80 | Soil Disposal Analysis ( Idot Pay Item 66900530) | EACH | 25 | 2000 | 50000
81 | Sanitary Riser / Valve Boxes to be Adjusted | EACH | 3 | 300 | 900
82 | Detector Loops | FT | 800 | 30 | 24000
83 | Sanitary Manholes to be Reconstructed with New Type 1 Frame, Closed Lid | EACH | 1 | 3750 | 3750
84 | Sanitary Manholes to be Removed | EACH | 1 | 1750 | 1750
85 | Sanitary Manholes to be Removed and Replace, 4' Dia | EACH | 9 | 8500 | 76500
86 | Sanitary Manholes, 4" Dia | EACH | 2 | 7000 | 14000
87 | Sanitary Sewer Mainline Repair, 10" Dia | FT | 5 | 450 | 2250
88 | Sanitary Sewer Mainline Repair, 12" Dia | FT | 10 | 500 | 5000
89 | Sanitary Sewer Mainline Repair, 15" Dia | FT | 10 | 550 | 5500
90 | Sanitary Sewer Service Reconnection, 6" Dia | FT | 20 | 250 | 5000
91 | Sanitary Sewer Service Replacement, 6" Dia | FT | 238 | 95 | 22610
92 | Sanitary Sewer Service Replacement, 8" Dia | FT | 135 | 115 | 15525
93 | Sanitary Sewer Service Replacement, 10" Dia | FT | 77 | 120 | 9240
94 | Sanitary Sewer, PVC SDR 26 WMQ, 8" Dia | FT | 82.5 | 120 | 9900
95 | Sanitary Sewer Service Riser to be Lowered and Capped | EACH | 3 | 1300 | 3900
|  |  | 0 | 0 | 0
|  |  |  | Total | 3472671.1
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 15th Avenue Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Mobilization | 1 | L SUM | 116040 |  | 1 |  |  | 116040
2 | Construction Layout Staking | 1 | L SUM | 20000 |  | 1 |  |  | 20000
3 | Inlet and Pipe Protection | 23 | EACH | 4600 |  | 23 |  |  | 200
4 | Concrete Truck Washout | 18 | EACH | 904.5 |  | 18 |  |  | 50.25
5 | Pavement Removal | 3668 | SQ YD | 106372 |  | 3668 |  |  | 29
6 | Approach Pavement Removal | 682.5 | SQ YD | 17062.5 |  | 682.5 |  |  | 25
7 | Sidewalk Removal | 30423 | SQ FT | 45634.5 |  | 30423 |  |  | 1.5
8 | Combination Curb and Gutter Removal | 7361.5 | FT | 113367.1 |  | 7361.5 |  |  | 15.4
9 | Rock Excavation | 60 | CU YD | 12000 |  | 60 |  |  | 200
10 | Remove Valve and Valve Vault, Complete | 22 | EACH | 22000 |  | 22 |  |  | 1000
11 | Remove Fire Hydrant, Complete | 8 | EACH | 8000 |  | 8 |  |  | 1000
12 | Ductile Iron Water Main Complete, 6" | 320 | FT | 57600 |  | 320 |  |  | 180
13 | Ductile Iron Water Main Complete, 8" | 4420 | FT | 892840 |  | 4420 |  |  | 202
14 | Ductile Iron Water Main Complete, 12" | 48.5 | FT | 13095 |  | 48.5 |  |  | 270
15 | Ductile Iron Water Main Complete, 16" | 15.5 | FT | 5890 |  | 15.5 |  |  | 380
16 | Gate Valve and Valve Box Complete, 4" | 4 | EACH | 10400 |  | 4 |  |  | 2600
17 | Gate Valve and Valve Box Complete, 8" | 24 | EACH | 80400 |  | 24 |  |  | 3350
18 | Butterfly Valve and Valve Box Complete, 12" | 1 | EACH | 4800 |  | 1 |  |  | 4800
19 | Butterfly Valve and Valve Box Complete, 16" | 1 | EACH | 7200 |  | 1 |  |  | 7200
20 | Fire Hydrant with 6" Valve and Valve Box, Complete | 14 | EACH | 98000 |  | 14 |  |  | 7000
21 | Water Service (Open-cut), Complete, 1" | 27 | EACH | 121500 |  | 27 |  |  | 4500
22 | Water Service (Open-cut), Complete, 2" | 5 | EACH | 31500 |  | 5 |  |  | 6300
23 | Water Service (Open-cut), Complete, 4" | 4 | EACH | 30000 |  | 4 |  |  | 7500
24 | Water Service (Bored or Pulled), Complete, 1" | 18 | EACH | 81000 |  | 18 |  |  | 4500
Sub Total |  |  |  | 1900205.6 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 15th Avenue Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Exterior Foundation Access Pit | 7 | EACH | 10500 |  | 7 |  |  | 1500
26 | Connection To Relocated/Existing Water Meter, Complete | 7 | EACH | 15400 |  | 7 |  |  | 2200
27 | Interior Water Meter Relocation, Complete | 110 | FT | 2750 |  | 110 |  |  | 25
28 | Reconnection Of Water Service Electrical Jumper Cable | 7 | EACH | 1400 |  | 7 |  |  | 200
29 | Primary Electrical Grounding System Installation | 7 | EACH | 11200 |  | 7 |  |  | 1600
30 | Water Main Protection, HDPE, 18" | 913.5 | FT | 182700 |  | 913.5 |  |  | 200
31 | Water Service Protection, 2" | 65 | FT | 2275 |  | 65 |  |  | 35
32 | Water Main Protection, Bore And Jack Steel Casing, 16" | 135 | FT | 86805 |  | 135 |  |  | 643
33 | Connection To Existing 3" Water Main, Complete | 1 | EACH | 4200 |  | 1 |  |  | 4200
34 | Connection To Existing 6" Water Main, Complete | 10 | EACH | 44000 |  | 10 |  |  | 4400
35 | Connection To Existing 8" Water Main, Complete | 1 | EACH | 4500 |  | 1 |  |  | 4500
36 | Connection To Existing 12" Water Main, Complete | 1 | EACH | 6000 |  | 1 |  |  | 6000
37 | Connection To Existing 16" Water Main, Complete | 1 | EACH | 9000 |  | 1 |  |  | 9000
38 | Water Main Line Stop, 6" | 9 | EACH | 45000 |  | 9 |  |  | 5000
39 | Water Main Line Stop, 12" | 1 | EACH | 8500 |  | 1 |  |  | 8500
40 | Water Main Line Stop, 16" | 1 | EACH | 12500 |  | 1 |  |  | 12500
41 | Insertion Valve, Complete, 6" | 1 | EACH | 6000 |  | 1 |  |  | 6000
42 | Insertion Valve, Complete, 12" | 1 | EACH | 12000 |  | 1 |  |  | 12000
43 | Insertion Valve, Complete, 16" | 1 | EACH | 45000 |  | 1 |  |  | 45000
44 | P.C.C. Approach Pavement, 6" | 162 | SQ YD | 11178 |  | 162 |  |  | 69
45 | P.C.C. Approach Pavement, 8" | 358 | SQ YD | 30430 |  | 358 |  |  | 85
46 | Hot-Mix Asphalt Approach Pavement, 3" | 68 | SQ YD | 2380 |  | 68 |  |  | 35
47 | P.C.C. Sidewalk, 4" | 21848 | SQ FT | 174784 |  | 21848 |  |  | 8
48 | Detectable Warnings, ADA Ramps | 230 | SQ FT | 6900 |  | 230 |  |  | 30
Sub Total |  |  |  | 2635607.6 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 15th Avenue Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | Combination Concrete Curb And Gutter, Type M-6.18 (Modified) | 6987 | FT | 206116.5 |  | 6987 |  |  | 29.5
50 | Combination Concrete Curb And Gutter, Type B-6.24 (Modified) | 22 | FT | 1320 |  | 22 |  |  | 60
51 | Earth Excavation | 30 | CU YD | 3000 |  | 30 |  |  | 100
52 | Subbase Granular Material, Type B, 6" (CA-2) | 3609.5 | SQ YD | 50533 |  | 3609.5 |  |  | 14
53 | Aggregate Base Repair | 188 | SQ YD | 5640 |  | 188 |  |  | 30
54 | Class D Patch, 8" (Special) | 3609.5 | SQ YD | 158204.385 |  | 3609.5 |  |  | 43.83
55 | Bituminous Materials (Prime Coat) | 1959.6 | GAL | 19.596 |  | 1959.6 |  |  | 0.01
56 | Aggregate (Prime Coat) | 96.2 | TONS | 0.962 |  | 96.2 |  |  | 0.01
57 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | 2278.4 | TONS | 188332.544 |  | 2278.4 |  |  | 82.66
58 | Hot-Mix Asphalt, Hand Method | 20 | TONS | 4000 |  | 20 |  |  | 200
59 | Surface Removal, 2" | 19779.5 | SQ YD | 53404.65 |  | 19779.5 |  |  | 2.7
60 | Manholes to be Adjusted | 25 | EACH | 33750 |  | 25 |  |  | 1350
61 | Manholes to be Adjusted with New Frame and Lid | 13 | EACH | 22100 |  | 13 |  |  | 1700
62 | Manholes to be Reconstructed | 1 | EACH | 2800 |  | 1 |  |  | 2800
63 | Manholes to be Reconstructed with New Frame and Lid | 2 | EACH | 6400 |  | 2 |  |  | 3200
64 | Inlets to be Adjusted | 13 | EACH | 19500 |  | 13 |  |  | 1500
65 | Inlets to be Adjusted with New Frame and Lid | 12 | EACH | 26400 |  | 12 |  |  | 2200
66 | Inlets to be Reconstructed | 1 | EACH | 2800 |  | 1 |  |  | 2800
67 | Inlets to be Reconstructed with New Frame and Lid | 2 | EACH | 6800 |  | 2 |  |  | 3400
68 | Thermoplastic Pavement Markings, 4" | 10811 | FT | 9729.9 |  | 10811 |  |  | 0.9
69 | Thermoplastic Pavement Markings, 6" | 1621 | FT | 2188.35 |  | 1621 |  |  | 1.35
70 | Thermoplastic Pavement Markings, 12" | 349 | FT | 942.3 |  | 349 |  |  | 2.7
71 | Thermoplastic Pavement Markings, 24" | 217 | FT | 1171.8 |  | 217 |  |  | 5.4
72 | Thermoplastic Pavement Markings, Letters and Symbols | 1217 | SQ FT | 10953 |  | 1217 |  |  | 9
Sub Total |  |  |  | 3451714.587 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 15th Avenue Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
73 | Parkway Restoration | 1 | L SUM | 60000 |  | 1 |  |  | 60000
74 | Traffic Control And Protection, Special | 1 | L SUM | 55000 |  | 1 |  |  | 55000
75 | Railroad Protective Liability Insurance (Idot Pay Item Z0048665) | 1 | L SUM | 5000 |  | 1 |  |  | 5000
76 | Railroad Flagging | 5 | CL DAY | 8750 |  | 5 |  |  | 1750
77 | Non-Special Waste Disposal (Idot Pay Item 66900200) | 25 | CU YD | 5000 |  | 25 |  |  | 200
78 | Special Waste Disposal (Idot Pay Item 66900205) | 25 | CU YD | 7500 |  | 25 |  |  | 300
79 | Special Waste Plans And Reports (Idot Pay Item 66900450) | 1 | L SUM | 3500 |  | 1 |  |  | 3500
80 | Soil Disposal Analysis ( Idot Pay Item 66900530) | 25 | EACH | 12500 |  | 25 |  |  | 500
81 | Sanitary Riser / Valve Boxes to be Adjusted | 3 | EACH | 3600 |  | 3 |  |  | 1200
82 | Detector Loops | 800 | FT | 26200 |  | 800 |  |  | 32.75
83 | Sanitary Manholes to be Reconstructed with New Type 1 Frame, Closed Lid | 1 | EACH | 10000 |  | 1 |  |  | 10000
84 | Sanitary Manholes to be Removed | 1 | EACH | 3000 |  | 1 |  |  | 3000
85 | Sanitary Manholes to be Removed and Replace, 4' Dia | 9 | EACH | 174150 |  | 9 |  |  | 19350
86 | Sanitary Manholes, 4" Dia | 2 | EACH | 16000 |  | 2 |  |  | 8000
87 | Sanitary Sewer Mainline Repair, 10" Dia | 5 | FT | 5000 |  | 5 |  |  | 1000
88 | Sanitary Sewer Mainline Repair, 12" Dia | 10 | FT | 10000 |  | 10 |  |  | 1000
89 | Sanitary Sewer Mainline Repair, 15" Dia | 10 | FT | 12000 |  | 10 |  |  | 1200
90 | Sanitary Sewer Service Reconnection, 6" Dia | 20 | FT | 3000 |  | 20 |  |  | 150
91 | Sanitary Sewer Service Replacement, 6" Dia | 238 | FT | 35700 |  | 238 |  |  | 150
92 | Sanitary Sewer Service Replacement, 8" Dia | 135 | FT | 21600 |  | 135 |  |  | 160
93 | Sanitary Sewer Service Replacement, 10" Dia | 77 | FT | 13090 |  | 77 |  |  | 170
94 | Sanitary Sewer, PVC SDR 26 WMQ, 8" Dia | 82.5 | FT | 13200 |  | 82.5 |  |  | 160
95 | Sanitary Sewer Service Riser to be Lowered and Capped | 3 | EACH | 4050 |  | 3 |  |  | 1350
Total |  |  |  | 3959554.587 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | 15th Avenue Improvements
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Northern Illinois Service
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.