## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 392757.45
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | PERIMETER EROSION BARRIER | FOOT | 256 | 3.2 | 819.2
2 | INLET AND PIPE PROTECTION | EACH | 1 | 165 | 165
3 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 380 | 9.5 | 3610
4 | DETECTABLE WARNINGS | SQ FT | 144 | 30 | 4320
5 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 114 | 12 | 1368
6 | COMBINATION CONCRETE CURB AND GUTTER, TYPE B-6.24 (ABUTTING EXISTING PAVEMENT) | FOOT | 114 | 55 | 6270
7 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.06 (ABUTTING EXISTING PAVEMENT) | FOOT | 118 | 55 | 6490
8 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.24 (ABUTTING EXISTING PAVEMENT) | FOOT | 99 | 55 | 5445
9 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.24 (VARIABLE WIDTH GUTTER FLAG) | FOOT | 92 | 55 | 5060
10 | ISLAND PAVEMENT (6") | SQ YD | 128 | 80 | 10240
11 | NON-SPECIAL WASTE DISPOSAL | CU YD | 25 | 65 | 1625
12 | SPECIAL WASTE DISPOSAL | CU YD | 25 | 75 | 1875
13 | SOIL DISPOSAL ANALYSIS | EACH | 1 | 1000 | 1000
14 | MOBILIZATION | L SUM | 1 | 15000 | 15000
15 | CHANGEABLE MESSAGE SIGN | CAL DA | 56 | 60 | 3360
16 | SIGN PANEL - TYPE 1 | SQ FT | 25 | 40 | 1000
17 | EPOXY PAVEMENT MARKING - LETTERS AND SYMBOLS | SQ FT | 46.8 | 10 | 468
18 | EPOXY PAVEMENT MARKING - LINE 4" | FOOT | 114 | 3.25 | 370.5
19 | EPOXY PAVEMENT MARKING - LINE 6" | FOOT | 484 | 5 | 2420
20 | EPOXY PAVEMENT MARKING - LINE 8" | FOOT | 432 | 5 | 2160
21 | EPOXY PAVEMENT MARKING - LINE 24" | FOOT | 116 | 18.5 | 2146
22 | PAVEMENT MARKING REMOVAL - WATER BLASTING | SQ FT | 385 | 6 | 2310
23 | SERVICE INSTALLATION, TYPE B | EACH | 1 | 3500 | 3500
24 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 5" DIA. | FOOT | 269 | 90 | 24210
25 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 6" DIA. | FOOT | 90 | 100 | 9000
26 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 1 1/2" DIA. | FOOT | 7 | 18 | 126
27 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 2 1/2" DIA. | FOOT | 35 | 28 | 980
28 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 3" DIA. | FOOT | 28 | 28 | 784
29 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 4" DIA. | FOOT | 269 | 30 | 8070
30 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 5" DIA. | FOOT | 112 | 45 | 5040
31 | HANDHOLE | EACH | 3 | 2000 | 6000
32 | DOUBLE HANDHOLE | EACH | 1 | 3500 | 3500
33 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 10 | FOOT | 1142 | 1.5 | 1713
34 | FULL-ACTUATED CONTROLLER AND TYPE IV CABINET | EACH | 1 | 17000 | 17000
35 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 2C | FOOT | 2336 | 1.5 | 3504
36 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 3C | FOOT | 2939 | 1.75 | 5143.25
37 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 5C | FOOT | 1077 | 2 | 2154
38 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 7C | FOOT | 2404 | 2.25 | 5409
39 | ELECTRIC CABLE IN CONDUIT, SERVICE, NO. 6 3 C | FOOT | 23 | 6.5 | 149.5
40 | ELECTRIC CABLE IN CONDUIT, EQUIPMENT GROUNDING CONDUCTOR, NO. 6 1C | FOOT | 1074 | 3.25 | 3490.5
41 | TRAFFIC SIGNAL POST, GALVANIZED STEEL 16 FT. | EACH | 4 | 1400 | 5600
42 | STEEL MAST ARM ASSEMBLY AND POLE, 44 FT. | EACH | 1 | 14000 | 14000
43 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE, 26 FT. | EACH | 1 | 10000 | 10000
44 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE, 28 FT. | EACH | 1 | 11000 | 11000
45 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE 46 FT. | EACH | 1 | 18000 | 18000
46 | CONCRETE FOUNDATION, TYPE A | FOOT | 12.3 | 275 | 3382.5
47 | CONCRETE FOUNDATION, TYPE D | FOOT | 3.1 | 800 | 2480
48 | CONCRETE FOUNDATION, TYPE E 30-INCH DIAMETER | FOOT | 20 | 275 | 5500
49 | CONCRETE FOUNDATION, TYPE E 36-INCH DIAMETER | FOOT | 26 | 315 | 8190
50 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, BRACKET MOUNTED | EACH | 1 | 800 | 800
51 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, MAST ARM MOUNTED | EACH | 6 | 850 | 5100
52 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 4-SECTION, BRACKET MOUNTED | EACH | 4 | 900 | 3600
53 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 4-SECTION, MAST ARM MOUNTED | EACH | 4 | 950 | 3800
54 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 5-SECTION, BRACKET MOUNTED | EACH | 6 | 1000 | 6000
55 | PEDESTRIAN SIGNAL HEAD, LED, 1-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 3 | 685 | 2055
56 | PEDESTRIAN SIGNAL HEAD, LED, 2-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 1 | 1200 | 1200
57 | PEDESTRIAN SIGNAL HEAD, LED, 3-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 3 | 1800 | 5400
58 | TRAFFIC SIGNAL BACKPLATE, LOUVERED, PLASTIC | EACH | 10 | 160 | 1600
59 | PEDESTRIAN PUSH-BUTTON | EACH | 11 | 425 | 4675
60 | REMOVE EXISTING TRAFFIC SIGNAL EQUIPMENT | EACH | 4 | 4000 | 16000
61 | REMOVE EXISTING HANDHOLE | EACH | 4 | 500 | 2000
62 | REMOVE EXISTING CONCRETE FOUNDATION | EACH | 5 | 650 | 3250
63 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 | 6200 | 6200
64 | INSTALL STREET SIGN | SQ FT | 27 | 50 | 1350
65 | ABANDON CONDUIT IN PLACE | EACH | 7 | 350 | 2450
66 | ISLAND REMOVAL | SQ FT | 1866 | 5 | 9330
67 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 | 15000 | 15000
68 | EMERGENCY VEHICLE PRIORITY SYSTEM | EACH | 1 | 9500 | 9500
69 | REMOVE EXISTING TRAFFIC CONTROLLER AND CABINET | EACH | 1 | 800 | 800
70 | PARKWAY RESTORATION | L SUM | 1 | 3000 | 3000
71 | CONCRETE TRUCK WASHOUT | L SUM | 1 | 1500 | 1500
72 | LUMINAIRE, LED, HORIZONTAL MOUNT, SPECIAL | EACH | 3 | 900 | 2700
73 | CONSTRUCTION LAYOUT | L SUM | 1 | 5000 | 5000
74 | VIDEO VEHICLE DETECTION SYSTEM | EACH | 1 | 20000 | 20000
75 | REMOVE AND REINSTALL ALPR SYSTEM | L SUM | 1 | 5000 | 5000
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | William Charles Electric |  | Engel Electric
City of Rockford | [5 empty] | Rockford, IL |  | Rockford, IL
[6 empty] | Bid Bond |  | Bid Bond
Bid No.:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | PERIMETER EROSION BARRIER | FOOT | 256 | 3.2 | 819.2 | 9.75 | 2496 | 6.67 | 1707.52 |  | 0 |  | 0 |  | 0 |  | 0
2 | INLET AND PIPE PROTECTION | EACH | 1 | 165 | 165 | 200 | 200 | 416.63 | 416.63 |  | 0 |  | 0 |  | 0 |  | 0
3 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 380 | 9.5 | 3610 | 9 | 3420 | 34.98 | 13292.4 |  | 0 |  | 0 |  | 0 |  | 0
4 | DETECTABLE WARNINGS | SQ FT | 144 | 30 | 4320 | 35.4 | 5097.6 | 47.77 | 6878.88 |  | 0 |  | 0 |  | 0 |  | 0
5 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 114 | 12 | 1368 | 5 | 570 | 38.89 | 4433.46 |  | 0 |  | 0 |  | 0 |  | 0
6 | COMBINATION CONCRETE CURB AND GUTTER, TYPE B-6.24 (ABUTTING EXISTING PAVEMENT) | FOOT | 114 | 55 | 6270 | 52 | 5928 | 88.88 | 10132.32 |  | 0 |  | 0 |  | 0 |  | 0
7 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.06 (ABUTTING EXISTING PAVEMENT) | FOOT | 118 | 55 | 6490 | 49 | 5782 | 88.88 | 10487.84 |  | 0 |  | 0 |  | 0 |  | 0
8 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.24 (ABUTTING EXISTING PAVEMENT) | FOOT | 99 | 55 | 5445 | 52 | 5148 | 88.88 | 8799.12 |  | 0 |  | 0 |  | 0 |  | 0
9 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.24 (VARIABLE WIDTH GUTTER FLAG) | FOOT | 92 | 55 | 5060 | 57 | 5244 | 88.88 | 8176.96 |  | 0 |  | 0 |  | 0 |  | 0
10 | ISLAND PAVEMENT (6") | SQ YD | 128 | 80 | 10240 | 79 | 10112 | 253.31 | 32423.68 |  | 0 |  | 0 |  | 0 |  | 0
11 | NON-SPECIAL WASTE DISPOSAL | CU YD | 25 | 65 | 1625 | 32 | 800 | 20.4 | 510 | 20.4 | 2611.2 | Calculation Error |  |  | 0 |  | 0
12 | SPECIAL WASTE DISPOSAL | CU YD | 25 | 75 | 1875 | 32 | 800 | 125.54 | 3138.5 |  | 0 |  | 0 |  | 0 |  | 0
13 | SOIL DISPOSAL ANALYSIS | EACH | 1 | 1000 | 1000 | 1250 | 1250 | 1444.3 | 1444.3 |  | 0 |  | 0 |  | 0 |  | 0
14 | MOBILIZATION | L SUM | 1 | 15000 | 15000 | 29900 | 29900 | 15790 | 15790 |  | 0 |  | 0 |  | 0 |  | 0
15 | CHANGEABLE MESSAGE SIGN | CAL DA | 56 | 60 | 3360 | 48 | 2688 | 140 | 7840 |  | 0 |  | 0 |  | 0 |  | 0
16 | SIGN PANEL - TYPE 1 | SQ FT | 25 | 40 | 1000 | 68.71 | 1717.75 | 61.61 | 1540.25 |  | 0 |  | 0 |  | 0 |  | 0
17 | EPOXY PAVEMENT MARKING - LETTERS AND SYMBOLS | SQ FT | 46.8 | 10 | 468 | 12 | 561.6 | 13.33 | 623.844 |  | 0 |  | 0 |  | 0 |  | 0
18 | EPOXY PAVEMENT MARKING - LINE 4" | FOOT | 114 | 3.25 | 370.5 | 2 | 228 | 2.22 | 253.08 |  | 0 |  | 0 |  | 0 |  | 0
19 | EPOXY PAVEMENT MARKING - LINE 6" | FOOT | 484 | 5 | 2420 | 3 | 1452 | 3.33 | 1611.72 |  | 0 |  | 0 |  | 0 |  | 0
20 | EPOXY PAVEMENT MARKING - LINE 8" | FOOT | 432 | 5 | 2160 | 4 | 1728 | 4.44 | 1918.08 |  | 0 |  | 0 |  | 0 |  | 0
21 | EPOXY PAVEMENT MARKING - LINE 24" | FOOT | 116 | 18.5 | 2146 | 12 | 1392 | 13.33 | 1546.28 |  | 0 |  | 0 |  | 0 |  | 0
22 | PAVEMENT MARKING REMOVAL - WATER BLASTING | SQ FT | 385 | 6 | 2310 | 9 | 3465 | 11.11 | 4277.35 |  | 0 |  | 0 |  | 0 |  | 0
23 | SERVICE INSTALLATION, TYPE B | EACH | 1 | 3500 | 3500 | 4312.13 | 4312.13 | 3057 | 3057 |  | 0 |  | 0 |  | 0 |  | 0
24 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 5" DIA. | FOOT | 269 | 90 | 24210 | 161.9 | 43551.1 | 105.52 | 28384.88 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 105231.7 |  | 137843.18 |  | 168684.09
| Award to William Charles Electric | Total |  | As corrected | 105231.7 |  | 137843.18 |  | 168684.094
25 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 6" DIA. | FOOT | 90 | 100 | 9000 | 198.47 | 17862.3 | 170.42 | 15337.8 |  | 0 |  | 0 |  | 0 |  | 0
26 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 1 1/2" DIA. | FOOT | 7 | 18 | 126 | 38.04 | 266.28 | 45.6 | 319.2 |  | 0 |  | 0 |  | 0 |  | 0
27 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 2 1/2" DIA. | FOOT | 35 | 28 | 980 | 40.25 | 1408.75 | 48.72 | 1705.2 |  | 0 |  | 0 |  | 0 |  | 0
28 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 3" DIA. | FOOT | 28 | 28 | 784 | 41.73 | 1168.44 | 52.34 | 1465.52 |  | 0 |  | 0 |  | 0 |  | 0
29 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 4" DIA. | FOOT | 269 | 30 | 8070 | 30.54 | 8215.26 | 45 | 12105 |  | 0 |  | 0 |  | 0 |  | 0
30 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 5" DIA. | FOOT | 112 | 45 | 5040 | 35.03 | 3923.36 | 56 | 6272 |  | 0 |  | 0 |  | 0 |  | 0
31 | HANDHOLE | EACH | 3 | 2000 | 6000 | 2747.68 | 8243.04 | 2508 | 7524 |  | 0 |  | 0 |  | 0 |  | 0
32 | DOUBLE HANDHOLE | EACH | 1 | 3500 | 3500 | 4674.18 | 4674.18 | 4205 | 4205 |  | 0 |  | 0 |  | 0 |  | 0
33 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 10 | FOOT | 1142 | 1.5 | 1713 | 1.93 | 2204.06 | 2.04 | 2329.68 |  | 0 |  | 0 |  | 0 |  | 0
34 | FULL-ACTUATED CONTROLLER AND TYPE IV CABINET | EACH | 1 | 17000 | 17000 | 20089.52 | 20089.52 | 18275 | 18275 |  | 0 |  | 0 |  | 0 |  | 0
35 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 2C | FOOT | 2336 | 1.5 | 3504 | 2.39 | 5583.04 | 2.39 | 5583.04 |  | 0 |  | 0 |  | 0 |  | 0
36 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 3C | FOOT | 2939 | 1.75 | 5143.25 | 2.46 | 7229.94 | 2.81 | 8258.59 |  | 0 |  | 0 |  | 0 |  | 0
37 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 5C | FOOT | 1077 | 2 | 2154 | 3.53 | 3801.81 | 3.58 | 3855.66 |  | 0 |  | 0 |  | 0 |  | 0
38 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 7C | FOOT | 2404 | 2.25 | 5409 | 4.2 | 10096.8 | 4.1 | 9856.4 |  | 0 |  | 0 |  | 0 |  | 0
39 | ELECTRIC CABLE IN CONDUIT, SERVICE, NO. 6 3 C | FOOT | 23 | 6.5 | 149.5 | 17.93 | 412.39 | 17.81 | 409.63 |  | 0 |  | 0 |  | 0 |  | 0
40 | ELECTRIC CABLE IN CONDUIT, EQUIPMENT GROUNDING CONDUCTOR, NO. 6 1C | FOOT | 1074 | 3.25 | 3490.5 | 3.2 | 3436.8 | 3.65 | 3920.1 |  | 0 |  | 0 |  | 0 |  | 0
41 | TRAFFIC SIGNAL POST, GALVANIZED STEEL 16 FT. | EACH | 4 | 1400 | 5600 | 1617.45 | 6469.8 | 1412 | 5648 |  | 0 |  | 0 |  | 0 |  | 0
42 | STEEL MAST ARM ASSEMBLY AND POLE, 44 FT. | EACH | 1 | 14000 | 14000 | 18363.13 | 18363.13 | 20523 | 20523 |  | 0 |  | 0 |  | 0 |  | 0
43 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE, 26 FT. | EACH | 1 | 10000 | 10000 | 18823.01 | 18823.01 | 19827 | 19827 |  | 0 |  | 0 |  | 0 |  | 0
44 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE, 28 FT. | EACH | 1 | 11000 | 11000 | 18849.73 | 18849.73 | 19857 | 19857 |  | 0 |  | 0 |  | 0 |  | 0
45 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE 46 FT. | EACH | 1 | 18000 | 18000 | 22514.28 | 22514.28 | 25070 | 25070 |  | 0 |  | 0 |  | 0 |  | 0
46 | CONCRETE FOUNDATION, TYPE A | FOOT | 12.3 | 275 | 3382.5 | 342.5 | 4212.75 | 370 | 4551 |  | 0 |  | 0 |  | 0 |  | 0
47 | CONCRETE FOUNDATION, TYPE D | FOOT | 3.1 | 800 | 2480 | 1482.66 | 4596.246 | 898 | 2783.8 |  | 0 |  | 0 |  | 0 |  | 0
48 | CONCRETE FOUNDATION, TYPE E 30-INCH DIAMETER | FOOT | 20 | 275 | 5500 | 333.24 | 6664.8 | 395 | 7900 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 247257.45 |  | 336952.896 |  | 376265.71
| Award to William Charles Electric | Total |  | As corrected | 247257.45 |  | 336952.896 |  | 376265.714
49 | CONCRETE FOUNDATION, TYPE E 36-INCH DIAMETER | FOOT | 26 | 315 | 8190 | 729.42 | 18964.92 | 458 | 11908 |  | 0 |  | 0 |  | 0 |  | 0
50 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, BRACKET MOUNTED | EACH | 1 | 800 | 800 | 815.87 | 815.87 | 989 | 989 |  | 0 |  | 0 |  | 0 |  | 0
51 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, MAST ARM MOUNTED | EACH | 6 | 850 | 5100 | 961.8 | 5770.8 | 980 | 5880 |  | 0 |  | 0 |  | 0 |  | 0
52 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 4-SECTION, BRACKET MOUNTED | EACH | 4 | 900 | 3600 | 1083.83 | 4335.32 | 1168 | 4672 |  | 0 |  | 0 |  | 0 |  | 0
53 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 4-SECTION, MAST ARM MOUNTED | EACH | 4 | 950 | 3800 | 1236.43 | 4945.72 | 1127 | 4508 |  | 0 |  | 0 |  | 0 |  | 0
54 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 5-SECTION, BRACKET MOUNTED | EACH | 6 | 1000 | 6000 | 1145.07 | 6870.42 | 1322 | 7932 |  | 0 |  | 0 |  | 0 |  | 0
55 | PEDESTRIAN SIGNAL HEAD, LED, 1-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 3 | 685 | 2055 | 808.02 | 2424.06 | 995 | 2985 |  | 0 |  | 0 |  | 0 |  | 0
56 | PEDESTRIAN SIGNAL HEAD, LED, 2-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 1 | 1200 | 1200 | 1363.06 | 1363.06 | 1690 | 1690 |  | 0 |  | 0 |  | 0 |  | 0
57 | PEDESTRIAN SIGNAL HEAD, LED, 3-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 3 | 1800 | 5400 | 1755.93 | 5267.79 | 2315 | 6945 |  | 0 |  | 0 |  | 0 |  | 0
58 | TRAFFIC SIGNAL BACKPLATE, LOUVERED, PLASTIC | EACH | 10 | 160 | 1600 | 185.35 | 1853.5 | 256 | 2560 |  | 0 |  | 0 |  | 0 |  | 0
59 | PEDESTRIAN PUSH-BUTTON | EACH | 11 | 425 | 4675 | 423.98 | 4663.78 | 502 | 5522 |  | 0 |  | 0 |  | 0 |  | 0
60 | REMOVE EXISTING TRAFFIC SIGNAL EQUIPMENT | EACH | 4 | 4000 | 16000 | 1439.31 | 5757.24 | 2000 | 8000 |  | 0 |  | 0 |  | 0 |  | 0
61 | REMOVE EXISTING HANDHOLE | EACH | 4 | 500 | 2000 | 695.96 | 2783.84 | 500 | 2000 |  | 0 |  | 0 |  | 0 |  | 0
62 | REMOVE EXISTING CONCRETE FOUNDATION | EACH | 5 | 650 | 3250 | 695.96 | 3479.8 | 1082 | 5410 |  | 0 |  | 0 |  | 0 |  | 0
63 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 | 6200 | 6200 | 2400 | 2400 | 2778 | 2778 |  | 0 |  | 0 |  | 0 |  | 0
64 | INSTALL STREET SIGN | SQ FT | 27 | 50 | 1350 | 53.48 | 1443.96 | 61.11 | 1649.97 |  | 0 |  | 0 |  | 0 |  | 0
65 | ABANDON CONDUIT IN PLACE | EACH | 7 | 350 | 2450 | 162.11 | 1134.77 | 200 | 1400 |  | 0 |  | 0 |  | 0 |  | 0
66 | ISLAND REMOVAL | SQ FT | 1866 | 5 | 9330 | 15 | 27990 | 6.33 | 11811.78 |  | 0 |  | 0 |  | 0 |  | 0
67 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 | 15000 | 15000 | 4730 | 4730 | 22631 | 22631 |  | 0 |  | 0 |  | 0 |  | 0
68 | EMERGENCY VEHICLE PRIORITY SYSTEM | EACH | 1 | 9500 | 9500 | 11684.58 | 11684.58 | 11500 | 11500 |  | 0 |  | 0 |  | 0 |  | 0
69 | REMOVE EXISTING TRAFFIC CONTROLLER AND CABINET | EACH | 1 | 800 | 800 | 298.05 | 298.05 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0
70 | PARKWAY RESTORATION | L SUM | 1 | 3000 | 3000 | 5115 | 5115 | 17910 | 17910 |  | 0 |  | 0 |  | 0 |  | 0
71 | CONCRETE TRUCK WASHOUT | L SUM | 1 | 1500 | 1500 | 500 | 500 | 2311 | 2311 |  | 0 |  | 0 |  | 0 |  | 0
72 | LUMINAIRE, LED, HORIZONTAL MOUNT, SPECIAL | EACH | 3 | 900 | 2700 | 936.2 | 2808.6 | 1560 | 4680 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Sub |  | As read | 362757.45 |  | 464353.976 |  | 525438.46
| Award to William Charles Electric | Total |  | As corrected | 362757.45 |  | 464353.976 |  | 525438.464
73 | CONSTRUCTION LAYOUT | L SUM | 1 | 5000 | 5000 | 5800 | 5800 | 2395 | 2395 |  | 0 |  | 0 |  | 0 |  | 0
74 | VIDEO VEHICLE DETECTION SYSTEM | EACH | 1 | 20000 | 20000 | 19573.96 | 19573.96 | 22491 | 22491 |  | 0 |  | 0 |  | 0 |  | 0
75 | REMOVE AND REINSTALL ALPR SYSTEM | L SUM | 1 | 5000 | 5000 | 8858.43 | 8858.43 | 10360 | 10360 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
#VALUE! | As Read |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
#VALUE! | As Corrected |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
#VALUE! | Calculation error |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | 392757.45 |  | 498586.366 |  | 562965.66
| Award to William Charles Electric | Bid |  | As corrected | 392757.45 |  | 498586.366 |  | 560684.464

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
0
Item No. | Items | Units | Quantity | Unit Price | Total
1 | PERIMETER EROSION BARRIER | FOOT | 256 |  | 0
2 | INLET AND PIPE PROTECTION | EACH | 1 |  | 0
3 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 380 |  | 0
4 | DETECTABLE WARNINGS | SQ FT | 144 |  | 0
5 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 114 |  | 0
6 | COMBINATION CONCRETE CURB AND GUTTER, TYPE B-6.24 (ABUTTING EXISTING PAVEMENT) | FOOT | 114 |  | 0
7 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.06 (ABUTTING EXISTING PAVEMENT) | FOOT | 118 |  | 0
8 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.24 (ABUTTING EXISTING PAVEMENT) | FOOT | 99 |  | 0
9 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.24 (VARIABLE WIDTH GUTTER FLAG) | FOOT | 92 |  | 0
10 | ISLAND PAVEMENT (6") | SQ YD | 128 |  | 0
11 | NON-SPECIAL WASTE DISPOSAL | CU YD | 25 |  | 0
12 | SPECIAL WASTE DISPOSAL | CU YD | 25 |  | 0
13 | SOIL DISPOSAL ANALYSIS | EACH | 1 |  | 0
14 | MOBILIZATION | L SUM | 1 |  | 0
15 | CHANGEABLE MESSAGE SIGN | CAL DA | 56 |  | 0
16 | SIGN PANEL - TYPE 1 | SQ FT | 25 |  | 0
17 | EPOXY PAVEMENT MARKING - LETTERS AND SYMBOLS | SQ FT | 46.8 |  | 0
18 | EPOXY PAVEMENT MARKING - LINE 4" | FOOT | 114 |  | 0
19 | EPOXY PAVEMENT MARKING - LINE 6" | FOOT | 484 |  | 0
20 | EPOXY PAVEMENT MARKING - LINE 8" | FOOT | 432 |  | 0
21 | EPOXY PAVEMENT MARKING - LINE 24" | FOOT | 116 |  | 0
22 | PAVEMENT MARKING REMOVAL - WATER BLASTING | SQ FT | 385 |  | 0
23 | SERVICE INSTALLATION, TYPE B | EACH | 1 |  | 0
24 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 5" DIA. | FOOT | 269 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 6" DIA. | FOOT | 90 |  | 0
26 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 1 1/2" DIA. | FOOT | 7 |  | 0
27 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 2 1/2" DIA. | FOOT | 35 |  | 0
28 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 3" DIA. | FOOT | 28 |  | 0
29 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 4" DIA. | FOOT | 269 |  | 0
30 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 5" DIA. | FOOT | 112 |  | 0
31 | HANDHOLE | EACH | 3 |  | 0
32 | DOUBLE HANDHOLE | EACH | 1 |  | 0
33 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 10 | FOOT | 1142 |  | 0
34 | FULL-ACTUATED CONTROLLER AND TYPE IV CABINET | EACH | 1 |  | 0
35 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 2C | FOOT | 2336 |  | 0
36 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 3C | FOOT | 2939 |  | 0
37 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 5C | FOOT | 1077 |  | 0
38 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 7C | FOOT | 2404 |  | 0
39 | ELECTRIC CABLE IN CONDUIT, SERVICE, NO. 6 3 C | FOOT | 23 |  | 0
40 | ELECTRIC CABLE IN CONDUIT, EQUIPMENT GROUNDING CONDUCTOR, NO. 6 1C | FOOT | 1074 |  | 0
41 | TRAFFIC SIGNAL POST, GALVANIZED STEEL 16 FT. | EACH | 4 |  | 0
42 | STEEL MAST ARM ASSEMBLY AND POLE, 44 FT. | EACH | 1 |  | 0
43 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE, 26 FT. | EACH | 1 |  | 0
44 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE, 28 FT. | EACH | 1 |  | 0
45 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE 46 FT. | EACH | 1 |  | 0
46 | CONCRETE FOUNDATION, TYPE A | FOOT | 12.3 |  | 0
47 | CONCRETE FOUNDATION, TYPE D | FOOT | 3.1 |  | 0
48 | CONCRETE FOUNDATION, TYPE E 30-INCH DIAMETER | FOOT | 20 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | CONCRETE FOUNDATION, TYPE E 36-INCH DIAMETER | FOOT | 26 |  | 0
50 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, BRACKET MOUNTED | EACH | 1 |  | 0
51 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, MAST ARM MOUNTED | EACH | 6 |  | 0
52 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 4-SECTION, BRACKET MOUNTED | EACH | 4 |  | 0
53 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 4-SECTION, MAST ARM MOUNTED | EACH | 4 |  | 0
54 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 5-SECTION, BRACKET MOUNTED | EACH | 6 |  | 0
55 | PEDESTRIAN SIGNAL HEAD, LED, 1-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 3 |  | 0
56 | PEDESTRIAN SIGNAL HEAD, LED, 2-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 1 |  | 0
57 | PEDESTRIAN SIGNAL HEAD, LED, 3-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 3 |  | 0
58 | TRAFFIC SIGNAL BACKPLATE, LOUVERED, PLASTIC | EACH | 10 |  | 0
59 | PEDESTRIAN PUSH-BUTTON | EACH | 11 |  | 0
60 | REMOVE EXISTING TRAFFIC SIGNAL EQUIPMENT | EACH | 4 |  | 0
61 | REMOVE EXISTING HANDHOLE | EACH | 4 |  | 0
62 | REMOVE EXISTING CONCRETE FOUNDATION | EACH | 5 |  | 0
63 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 |  | 0
64 | INSTALL STREET SIGN | SQ FT | 27 |  | 0
65 | ABANDON CONDUIT IN PLACE | EACH | 7 |  | 0
66 | ISLAND REMOVAL | SQ FT | 1866 |  | 0
67 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 |  | 0
68 | EMERGENCY VEHICLE PRIORITY SYSTEM | EACH | 1 |  | 0
69 | REMOVE EXISTING TRAFFIC CONTROLLER AND CABINET | EACH | 1 |  | 0
70 | PARKWAY RESTORATION | L SUM | 1 |  | 0
71 | CONCRETE TRUCK WASHOUT | L SUM | 1 |  | 0
72 | LUMINAIRE, LED, HORIZONTAL MOUNT, SPECIAL | EACH | 3 |  | 0
| Page 3 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
73 | CONSTRUCTION LAYOUT | L SUM | 1 |  | 0
74 | VIDEO VEHICLE DETECTION SYSTEM | EACH | 1 |  | 0
75 | REMOVE AND REINSTALL ALPR SYSTEM | L SUM | 1 |  | 0
|  |  | 0 |  | 0
#VALUE! | As Read |  | 0 |  | 0
#VALUE! | As Corrected |  | 0 |  | 0
|  |  | 0 |  | 0
#VALUE! | Calculation error |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | PERIMETER EROSION BARRIER | FOOT | 256 | 3.2 | 819.2
2 | INLET AND PIPE PROTECTION | EACH | 1 | 165 | 165
3 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 380 | 9.5 | 3610
4 | DETECTABLE WARNINGS | SQ FT | 144 | 30 | 4320
5 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 114 | 12 | 1368
6 | COMBINATION CONCRETE CURB AND GUTTER, TYPE B-6.24 (ABUTTING EXISTING PAVEMENT) | FOOT | 114 | 55 | 6270
7 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.06 (ABUTTING EXISTING PAVEMENT) | FOOT | 118 | 55 | 6490
8 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.24 (ABUTTING EXISTING PAVEMENT) | FOOT | 99 | 55 | 5445
9 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.24 (VARIABLE WIDTH GUTTER FLAG) | FOOT | 92 | 55 | 5060
10 | ISLAND PAVEMENT (6") | SQ YD | 128 | 80 | 10240
11 | NON-SPECIAL WASTE DISPOSAL | CU YD | 25 | 65 | 1625
12 | SPECIAL WASTE DISPOSAL | CU YD | 25 | 75 | 1875
13 | SOIL DISPOSAL ANALYSIS | EACH | 1 | 1000 | 1000
14 | MOBILIZATION | L SUM | 1 | 15000 | 15000
15 | CHANGEABLE MESSAGE SIGN | CAL DA | 56 | 60 | 3360
16 | SIGN PANEL - TYPE 1 | SQ FT | 25 | 40 | 1000
17 | EPOXY PAVEMENT MARKING - LETTERS AND SYMBOLS | SQ FT | 46.8 | 10 | 468
18 | EPOXY PAVEMENT MARKING - LINE 4" | FOOT | 114 | 3.25 | 370.5
19 | EPOXY PAVEMENT MARKING - LINE 6" | FOOT | 484 | 5 | 2420
20 | EPOXY PAVEMENT MARKING - LINE 8" | FOOT | 432 | 5 | 2160
21 | EPOXY PAVEMENT MARKING - LINE 24" | FOOT | 116 | 18.5 | 2146
22 | PAVEMENT MARKING REMOVAL - WATER BLASTING | SQ FT | 385 | 6 | 2310
23 | SERVICE INSTALLATION, TYPE B | EACH | 1 | 3500 | 3500
24 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 5" DIA. | FOOT | 269 | 90 | 24210
|  |  |  | Sub Total | 105231.7
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 6" DIA. | FOOT | 90 | 100 | 9000
26 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 1 1/2" DIA. | FOOT | 7 | 18 | 126
27 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 2 1/2" DIA. | FOOT | 35 | 28 | 980
28 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 3" DIA. | FOOT | 28 | 28 | 784
29 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 4" DIA. | FOOT | 269 | 30 | 8070
30 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 5" DIA. | FOOT | 112 | 45 | 5040
31 | HANDHOLE | EACH | 3 | 2000 | 6000
32 | DOUBLE HANDHOLE | EACH | 1 | 3500 | 3500
33 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 10 | FOOT | 1142 | 1.5 | 1713
34 | FULL-ACTUATED CONTROLLER AND TYPE IV CABINET | EACH | 1 | 17000 | 17000
35 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 2C | FOOT | 2336 | 1.5 | 3504
36 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 3C | FOOT | 2939 | 1.75 | 5143.25
37 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 5C | FOOT | 1077 | 2 | 2154
38 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 7C | FOOT | 2404 | 2.25 | 5409
39 | ELECTRIC CABLE IN CONDUIT, SERVICE, NO. 6 3 C | FOOT | 23 | 6.5 | 149.5
40 | ELECTRIC CABLE IN CONDUIT, EQUIPMENT GROUNDING CONDUCTOR, NO. 6 1C | FOOT | 1074 | 3.25 | 3490.5
41 | TRAFFIC SIGNAL POST, GALVANIZED STEEL 16 FT. | EACH | 4 | 1400 | 5600
42 | STEEL MAST ARM ASSEMBLY AND POLE, 44 FT. | EACH | 1 | 14000 | 14000
43 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE, 26 FT. | EACH | 1 | 10000 | 10000
44 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE, 28 FT. | EACH | 1 | 11000 | 11000
45 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE 46 FT. | EACH | 1 | 18000 | 18000
46 | CONCRETE FOUNDATION, TYPE A | FOOT | 12.3 | 275 | 3382.5
47 | CONCRETE FOUNDATION, TYPE D | FOOT | 3.1 | 800 | 2480
48 | CONCRETE FOUNDATION, TYPE E 30-INCH DIAMETER | FOOT | 20 | 275 | 5500
|  |  |  | Sub Total | 247257.45
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | CONCRETE FOUNDATION, TYPE E 36-INCH DIAMETER | FOOT | 26 | 315 | 8190
50 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, BRACKET MOUNTED | EACH | 1 | 800 | 800
51 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, MAST ARM MOUNTED | EACH | 6 | 850 | 5100
52 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 4-SECTION, BRACKET MOUNTED | EACH | 4 | 900 | 3600
53 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 4-SECTION, MAST ARM MOUNTED | EACH | 4 | 950 | 3800
54 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 5-SECTION, BRACKET MOUNTED | EACH | 6 | 1000 | 6000
55 | PEDESTRIAN SIGNAL HEAD, LED, 1-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 3 | 685 | 2055
56 | PEDESTRIAN SIGNAL HEAD, LED, 2-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 1 | 1200 | 1200
57 | PEDESTRIAN SIGNAL HEAD, LED, 3-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | EACH | 3 | 1800 | 5400
58 | TRAFFIC SIGNAL BACKPLATE, LOUVERED, PLASTIC | EACH | 10 | 160 | 1600
59 | PEDESTRIAN PUSH-BUTTON | EACH | 11 | 425 | 4675
60 | REMOVE EXISTING TRAFFIC SIGNAL EQUIPMENT | EACH | 4 | 4000 | 16000
61 | REMOVE EXISTING HANDHOLE | EACH | 4 | 500 | 2000
62 | REMOVE EXISTING CONCRETE FOUNDATION | EACH | 5 | 650 | 3250
63 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 | 6200 | 6200
64 | INSTALL STREET SIGN | SQ FT | 27 | 50 | 1350
65 | ABANDON CONDUIT IN PLACE | EACH | 7 | 350 | 2450
66 | ISLAND REMOVAL | SQ FT | 1866 | 5 | 9330
67 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 | 15000 | 15000
68 | EMERGENCY VEHICLE PRIORITY SYSTEM | EACH | 1 | 9500 | 9500
69 | REMOVE EXISTING TRAFFIC CONTROLLER AND CABINET | EACH | 1 | 800 | 800
70 | PARKWAY RESTORATION | L SUM | 1 | 3000 | 3000
71 | CONCRETE TRUCK WASHOUT | L SUM | 1 | 1500 | 1500
72 | LUMINAIRE, LED, HORIZONTAL MOUNT, SPECIAL | EACH | 3 | 900 | 2700
|  |  |  | Sub Total | 362757.45
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
73 | CONSTRUCTION LAYOUT | L SUM | 1 | 5000 | 5000
74 | VIDEO VEHICLE DETECTION SYSTEM | EACH | 1 | 20000 | 20000
75 | REMOVE AND REINSTALL ALPR SYSTEM | L SUM | 1 | 5000 | 5000
|  |  | 0 | 0 | 0
#VALUE! | As Read |  | 0 | 0 | 0
#VALUE! | As Corrected |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
#VALUE! | Calculation error |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 392757.45
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: William Charles Electric | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | PERIMETER EROSION BARRIER | 256 | FOOT | 2496 |  | 256 |  |  | 9.75
2 | INLET AND PIPE PROTECTION | 1 | EACH | 200 |  | 1 |  |  | 200
3 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | 380 | SQ FT | 3420 |  | 380 |  |  | 9
4 | DETECTABLE WARNINGS | 144 | SQ FT | 5097.6 |  | 144 |  |  | 35.4
5 | COMBINATION CURB AND GUTTER REMOVAL | 114 | FOOT | 570 |  | 114 |  |  | 5
6 | COMBINATION CONCRETE CURB AND GUTTER, TYPE B-6.24 (ABUTTING EXISTING PAVEMENT) | 114 | FOOT | 5928 |  | 114 |  |  | 52
7 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.06 (ABUTTING EXISTING PAVEMENT) | 118 | FOOT | 5782 |  | 118 |  |  | 49
8 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.24 (ABUTTING EXISTING PAVEMENT) | 99 | FOOT | 5148 |  | 99 |  |  | 52
9 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.24 (VARIABLE WIDTH GUTTER FLAG) | 92 | FOOT | 5244 |  | 92 |  |  | 57
10 | ISLAND PAVEMENT (6") | 128 | SQ YD | 10112 |  | 128 |  |  | 79
11 | NON-SPECIAL WASTE DISPOSAL | 25 | CU YD | 800 |  | 25 |  |  | 32
12 | SPECIAL WASTE DISPOSAL | 25 | CU YD | 800 |  | 25 |  |  | 32
13 | SOIL DISPOSAL ANALYSIS | 1 | EACH | 1250 |  | 1 |  |  | 1250
14 | MOBILIZATION | 1 | L SUM | 29900 |  | 1 |  |  | 29900
15 | CHANGEABLE MESSAGE SIGN | 56 | CAL DA | 2688 |  | 56 |  |  | 48
16 | SIGN PANEL - TYPE 1 | 25 | SQ FT | 1717.75 |  | 25 |  |  | 68.71
17 | EPOXY PAVEMENT MARKING - LETTERS AND SYMBOLS | 46.8 | SQ FT | 561.6 |  | 46.8 |  |  | 12
18 | EPOXY PAVEMENT MARKING - LINE 4" | 114 | FOOT | 228 |  | 114 |  |  | 2
19 | EPOXY PAVEMENT MARKING - LINE 6" | 484 | FOOT | 1452 |  | 484 |  |  | 3
20 | EPOXY PAVEMENT MARKING - LINE 8" | 432 | FOOT | 1728 |  | 432 |  |  | 4
21 | EPOXY PAVEMENT MARKING - LINE 24" | 116 | FOOT | 1392 |  | 116 |  |  | 12
22 | PAVEMENT MARKING REMOVAL - WATER BLASTING | 385 | SQ FT | 3465 |  | 385 |  |  | 9
23 | SERVICE INSTALLATION, TYPE B | 1 | EACH | 4312.13 |  | 1 |  |  | 4312.13
24 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 5" DIA. | 269 | FOOT | 43551.1 |  | 269 |  |  | 161.9
Sub Total |  |  |  | 137843.18 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: William Charles Electric | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 6" DIA. | 90 | FOOT | 17862.3 |  | 90 |  |  | 198.47
26 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 1 1/2" DIA. | 7 | FOOT | 266.28 |  | 7 |  |  | 38.04
27 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 2 1/2" DIA. | 35 | FOOT | 1408.75 |  | 35 |  |  | 40.25
28 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 3" DIA. | 28 | FOOT | 1168.44 |  | 28 |  |  | 41.73
29 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 4" DIA. | 269 | FOOT | 8215.26 |  | 269 |  |  | 30.54
30 | UNDERGROUND CONDUIT, COILABLE NONMETALLIC CONDUIT, 5" DIA. | 112 | FOOT | 3923.36 |  | 112 |  |  | 35.03
31 | HANDHOLE | 3 | EACH | 8243.04 |  | 3 |  |  | 2747.68
32 | DOUBLE HANDHOLE | 1 | EACH | 4674.18 |  | 1 |  |  | 4674.18
33 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 10 | 1142 | FOOT | 2204.06 |  | 1142 |  |  | 1.93
34 | FULL-ACTUATED CONTROLLER AND TYPE IV CABINET | 1 | EACH | 20089.52 |  | 1 |  |  | 20089.52
35 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 2C | 2336 | FOOT | 5583.04 |  | 2336 |  |  | 2.39
36 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 3C | 2939 | FOOT | 7229.94 |  | 2939 |  |  | 2.46
37 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 5C | 1077 | FOOT | 3801.81 |  | 1077 |  |  | 3.53
38 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 7C | 2404 | FOOT | 10096.8 |  | 2404 |  |  | 4.2
39 | ELECTRIC CABLE IN CONDUIT, SERVICE, NO. 6 3 C | 23 | FOOT | 412.39 |  | 23 |  |  | 17.93
40 | ELECTRIC CABLE IN CONDUIT, EQUIPMENT GROUNDING CONDUCTOR, NO. 6 1C | 1074 | FOOT | 3436.8 |  | 1074 |  |  | 3.2
41 | TRAFFIC SIGNAL POST, GALVANIZED STEEL 16 FT. | 4 | EACH | 6469.8 |  | 4 |  |  | 1617.45
42 | STEEL MAST ARM ASSEMBLY AND POLE, 44 FT. | 1 | EACH | 18363.13 |  | 1 |  |  | 18363.13
43 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE, 26 FT. | 1 | EACH | 18823.01 |  | 1 |  |  | 18823.01
44 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE, 28 FT. | 1 | EACH | 18849.73 |  | 1 |  |  | 18849.73
45 | STEEL COMBINATION MAST ARM ASSEMBLY AND POLE 46 FT. | 1 | EACH | 22514.28 |  | 1 |  |  | 22514.28
46 | CONCRETE FOUNDATION, TYPE A | 12.3 | FOOT | 4212.75 |  | 12.3 |  |  | 342.5
47 | CONCRETE FOUNDATION, TYPE D | 3.1 | FOOT | 4596.246 |  | 3.1 |  |  | 1482.66
48 | CONCRETE FOUNDATION, TYPE E 30-INCH DIAMETER | 20 | FOOT | 6664.8 |  | 20 |  |  | 333.24
Sub Total |  |  |  | 336952.896 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: William Charles Electric | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | CONCRETE FOUNDATION, TYPE E 36-INCH DIAMETER | 26 | FOOT | 18964.92 |  | 26 |  |  | 729.42
50 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, BRACKET MOUNTED | 1 | EACH | 815.87 |  | 1 |  |  | 815.87
51 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, MAST ARM MOUNTED | 6 | EACH | 5770.8 |  | 6 |  |  | 961.8
52 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 4-SECTION, BRACKET MOUNTED | 4 | EACH | 4335.32 |  | 4 |  |  | 1083.83
53 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 4-SECTION, MAST ARM MOUNTED | 4 | EACH | 4945.72 |  | 4 |  |  | 1236.43
54 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 5-SECTION, BRACKET MOUNTED | 6 | EACH | 6870.42 |  | 6 |  |  | 1145.07
55 | PEDESTRIAN SIGNAL HEAD, LED, 1-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | 3 | EACH | 2424.06 |  | 3 |  |  | 808.02
56 | PEDESTRIAN SIGNAL HEAD, LED, 2-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | 1 | EACH | 1363.06 |  | 1 |  |  | 1363.06
57 | PEDESTRIAN SIGNAL HEAD, LED, 3-FACE, BRACKET MOUNTED WITH COUNTDOWN TIMER | 3 | EACH | 5267.79 |  | 3 |  |  | 1755.93
58 | TRAFFIC SIGNAL BACKPLATE, LOUVERED, PLASTIC | 10 | EACH | 1853.5 |  | 10 |  |  | 185.35
59 | PEDESTRIAN PUSH-BUTTON | 11 | EACH | 4663.78 |  | 11 |  |  | 423.98
60 | REMOVE EXISTING TRAFFIC SIGNAL EQUIPMENT | 4 | EACH | 5757.24 |  | 4 |  |  | 1439.31
61 | REMOVE EXISTING HANDHOLE | 4 | EACH | 2783.84 |  | 4 |  |  | 695.96
62 | REMOVE EXISTING CONCRETE FOUNDATION | 5 | EACH | 3479.8 |  | 5 |  |  | 695.96
63 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | 1 | L SUM | 2400 |  | 1 |  |  | 2400
64 | INSTALL STREET SIGN | 27 | SQ FT | 1443.96 |  | 27 |  |  | 53.48
65 | ABANDON CONDUIT IN PLACE | 7 | EACH | 1134.77 |  | 7 |  |  | 162.11
66 | ISLAND REMOVAL | 1866 | SQ FT | 27990 |  | 1866 |  |  | 15
67 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | 1 | L SUM | 4730 |  | 1 |  |  | 4730
68 | EMERGENCY VEHICLE PRIORITY SYSTEM | 1 | EACH | 11684.58 |  | 1 |  |  | 11684.58
69 | REMOVE EXISTING TRAFFIC CONTROLLER AND CABINET | 1 | EACH | 298.05 |  | 1 |  |  | 298.05
70 | PARKWAY RESTORATION | 1 | L SUM | 5115 |  | 1 |  |  | 5115
71 | CONCRETE TRUCK WASHOUT | 1 | L SUM | 500 |  | 1 |  |  | 500
72 | LUMINAIRE, LED, HORIZONTAL MOUNT, SPECIAL | 3 | EACH | 2808.6 |  | 3 |  |  | 936.2
Sub Total |  |  |  | 464353.976 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: William Charles Electric | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
73 | CONSTRUCTION LAYOUT | 1 | L SUM | 5800 |  | 1 |  |  | 5800
74 | VIDEO VEHICLE DETECTION SYSTEM | 1 | EACH | 19573.96 |  | 1 |  |  | 19573.96
75 | REMOVE AND REINSTALL ALPR SYSTEM | 1 | L SUM | 8858.43 |  | 1 |  |  | 8858.43
#VALUE! | As Read
#VALUE! | As Corrected
#VALUE! | Calculation error
Total |  |  |  | 498586.366 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | 0
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | William Charles Electric
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.