## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 627634
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | Tree Removal, Acres | Acres | 1.1 | 23000 | 25300
2 | Earth Excavation, Special | Cu. Yd. | 2632 | 40 | 105280
3 | Topsoil Furnish and Place, 4" | Sq. Yd. | 1943 | 6 | 11658
4 | Parkway Restoration | L. Sum | 1 | 5898 | 5898
5 | Erosion Control Blanket | Sq. Yd. | 68 | 4 | 272
6 | Turf Reinforcement Mat | Sq. Yd. | 2881 | 8 | 23048
7 | Temporary Erosion Control Seeding | Pound | 62 | 6 | 372
8 | Inlet and Pipe Protection | Each | 2 | 200 | 400
9 | Stabilized Construction Entrance | L. Sum | 1 | 10000 | 10000
10 | Stone Riprap, Class B5 | Sq. Yd. | 2831 | 73 | 206663
11 | Filter Fabric | Sq. Yd. | 2831 | 4 | 11324
12 | Portland Cement Concrete Sidewalk, 4-Inch, Remove and Replace | Sq. Ft. | 116 | 24 | 2784
13 | Pipe Culvert Removal | Foot | 40 | 20 | 800
14 | Pipe Culverts, Class C, Type 1, 18" | Foot | 17 | 125 | 2125
15 | Pipe Culverts, Class C, Type 1, 24" | Foot | 8 | 135 | 1080
16 | Sanitary Manholes to be Removed | Each | 1 | 3500 | 3500
17 | Sanitary Manholes to be Removed and Replaced, 4' Dia. | Each | 1 | 27000 | 27000
18 | Sanitary Sewer Main Line Repair, 12" | Foot | 14 | 1500 | 21000
19 | Concrete Encasement for Sanitary Sewers | Foot | 200 | 180 | 36000
20 | Sump Pump Discharge Removal | Foot | 41 | 20 | 820
21 | Sump Pump Discharge Extension, 2" | Foot | 12 | 23 | 276
22 | Sump Pump Discharge Extension, 3" | Foot | 10 | 27 | 270
23 | Fence Removal | Foot | 617 | 10 | 6170
24 | Chain Link Fence, 4', Special | Foot | 588 | 38 | 22344
25 | Relocate Existing Shed | L. Sum | 1 | 1750 | 1750
26 | By-Pass Pumping | L. Sum | 1 | 25000 | 25000
27 | Traffic Control and Protection, Special | L. Sum | 1 | 3500 | 3500
28 | Construction Layout Stakes | L. Sum | 1 | 8000 | 8000
29 | Non-Special Waste Disposal | Cu. Yd. | 100 | 100 | 10000
30 | Special Waste Disposal | Cu. Yd. | 100 | 250 | 25000
31 | Special Waste Plans and Reports | L. Sum | 1 | 6000 | 6000
32 | Soil Disposal Analysis | Each | 10 | 900 | 9000
33 | Mobilization | L.Sum | 1 | 15000 | 15000
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Fischer Excavating |  | Northern Illinois Service |  | DPI Construction |  | N-Trak Group |  | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | V3 Construction Group |  | Stenstrom Excavation | [5 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Freeport, IL |  | Rockford, IL |  | Pecatonica, IL |  | Loves Park, IL |  | City of Rockford | [5 empty] | Woodridge, IL |  | Rockford, IL | [5 empty] | City of Rockford
Buckbee Drainageway Improvements | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond |  | Buckbee Drainageway Improvements | [5 empty] | Bid Bond |  | Bid Bond | [5 empty] | Buckbee Drainageway Improvements
Bid No. 622-PW-055 Vendors Notified: 102
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Tree Removal, Acres | Acres | 1.1 | 23000 | 25300 | 37000 | 40700 | 42000 | 46200 | 37740 | 41514 | 56000 | 61600 | 1 | Tree Removal, Acres | Acres | 1.1 | 23000 | 25300 | 38000 | 41800 | 50000 | 55000 |  | 0 |  | 0 | 1 | Tree Removal, Acres | Acres | 1.1 | 23000 | 25300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Earth Excavation, Special | Cu. Yd. | 2632 | 40 | 105280 | 34.5 | 90804 | 48 | 126336 | 57 | 150024 | 80 | 210560 | 2 | Earth Excavation, Special | Cu. Yd. | 2632 | 40 | 105280 | 60 | 157920 | 95 | 250040 |  | 0 |  | 0 | 2 | Earth Excavation, Special | Cu. Yd. | 2632 | 40 | 105280 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Topsoil Furnish and Place, 4" | Sq. Yd. | 1943 | 6 | 11658 | 3.9 | 7577.7 | 6 | 11658 | 5 | 9715 | 19 | 36917 | 3 | Topsoil Furnish and Place, 4" | Sq. Yd. | 1943 | 6 | 11658 | 32 | 62176 | 4.35 | 8452.05 |  | 0 |  | 0 | 3 | Topsoil Furnish and Place, 4" | Sq. Yd. | 1943 | 6 | 11658 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Parkway Restoration | L. Sum | 1 | 5898 | 5898 | 5500 | 5500 | 8000 | 8000 | 11796 | 11796 | 15000 | 15000 | 4 | Parkway Restoration | L. Sum | 1 | 5898 | 5898 | 5491 | 5491 | 6100 | 6100 |  | 0 |  | 0 | 4 | Parkway Restoration | L. Sum | 1 | 5898 | 5898 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Erosion Control Blanket | Sq. Yd. | 68 | 4 | 272 | 3.8 | 258.4 | 3.5 | 238 | 4 | 272 | 3.5 | 238 | 5 | Erosion Control Blanket | Sq. Yd. | 68 | 4 | 272 | 16 | 1088 | 4.25 | 289 |  | 0 |  | 0 | 5 | Erosion Control Blanket | Sq. Yd. | 68 | 4 | 272 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Turf Reinforcement Mat | Sq. Yd. | 2881 | 8 | 23048 | 11.5 | 33131.5 | 8.25 | 23768.25 | 9 | 25929 | 6.5 | 18726.5 | 6 | Turf Reinforcement Mat | Sq. Yd. | 2881 | 8 | 23048 | 9 | 25929 | 12.75 | 36732.75 |  | 0 |  | 0 | 6 | Turf Reinforcement Mat | Sq. Yd. | 2881 | 8 | 23048 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Temporary Erosion Control Seeding | Pound | 62 | 6 | 372 | 3 | 186 | 20 | 1240 | 21 | 1302 | 5.5 | 341 | 7 | Temporary Erosion Control Seeding | Pound | 62 | 6 | 372 | 115 | 7130 | 3.35 | 207.7 |  | 0 |  | 0 | 7 | Temporary Erosion Control Seeding | Pound | 62 | 6 | 372 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Inlet and Pipe Protection | Each | 2 | 200 | 400 | 220 | 440 | 200 | 400 | 126 | 252 | 275 | 550 | 8 | Inlet and Pipe Protection | Each | 2 | 200 | 400 | 500 | 1000 | 245 | 490 |  | 0 |  | 0 | 8 | Inlet and Pipe Protection | Each | 2 | 200 | 400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Stabilized Construction Entrance | L. Sum | 1 | 10000 | 10000 | 2388 | 2388 | 14900 | 14900 | 15290 | 15290 | 7500 | 7500 | 9 | Stabilized Construction Entrance | L. Sum | 1 | 10000 | 10000 | 4500 | 4500 | 20000 | 20000 |  | 0 |  | 0 | 9 | Stabilized Construction Entrance | L. Sum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Stone Riprap, Class B5 | Sq. Yd. | 2831 | 73 | 206663 | 66 | 186846 | 95 | 268945 | 95 | 268945 | 70 | 198170 | 10 | Stone Riprap, Class B5 | Sq. Yd. | 2831 | 73 | 206663 | 118 | 334058 | 145 | 410495 |  | 0 |  | 0 | 10 | Stone Riprap, Class B5 | Sq. Yd. | 2831 | 73 | 206663 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Filter Fabric | Sq. Yd. | 2831 | 4 | 11324 | 2.7 | 7643.7 | 5 | 14155 | 4 | 11324 | 8.5 | 24063.5 | 11 | Filter Fabric | Sq. Yd. | 2831 | 4 | 11324 | 2 | 5662 | 5.25 | 14862.75 |  | 0 |  | 0 | 11 | Filter Fabric | Sq. Yd. | 2831 | 4 | 11324 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | Portland Cement Concrete Sidewalk, 4-Inch, Remove and Replace | Sq. Ft. | 116 | 24 | 2784 | 12.5 | 1450 | 30 | 3480 | 26 | 3016 | 20 | 2320 | 12 | Portland Cement Concrete Sidewalk, 4-Inch, Remove and Replace | Sq. Ft. | 116 | 24 | 2784 | 65 | 7540 | 15.25 | 1769 |  | 0 |  | 0 | 12 | Portland Cement Concrete Sidewalk, 4-Inch, Remove and Replace | Sq. Ft. | 116 | 24 | 2784 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | Pipe Culvert Removal | Foot | 40 | 20 | 800 | 3.8 | 152 | 15 | 600 | 13 | 520 | 50 | 2000 | 13 | Pipe Culvert Removal | Foot | 40 | 20 | 800 | 30 | 1200 | 55 | 2200 |  | 0 |  | 0 | 13 | Pipe Culvert Removal | Foot | 40 | 20 | 800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | Pipe Culverts, Class C, Type 1, 18" | Foot | 17 | 125 | 2125 | 117 | 1989 | 100 | 1700 | 123 | 2091 | 200 | 3400 | 14 | Pipe Culverts, Class C, Type 1, 18" | Foot | 17 | 125 | 2125 | 150 | 2550 | 136 | 2312 |  | 0 |  | 0 | 14 | Pipe Culverts, Class C, Type 1, 18" | Foot | 17 | 125 | 2125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Pipe Culverts, Class C, Type 1, 24" | Foot | 8 | 135 | 1080 | 231.5 | 1852 | 120 | 960 | 148 | 1184 | 450 | 3600 | 15 | Pipe Culverts, Class C, Type 1, 24" | Foot | 8 | 135 | 1080 | 340 | 2720 | 260 | 2080 |  | 0 |  | 0 | 15 | Pipe Culverts, Class C, Type 1, 24" | Foot | 8 | 135 | 1080 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Sanitary Manholes to be Removed | Each | 1 | 3500 | 3500 | 1437 | 1437 | 1200 | 1200 | 9508 | 9508 | 5000 | 5000 | 16 | Sanitary Manholes to be Removed | Each | 1 | 3500 | 3500 | 1200 | 1200 | 10500 | 10500 |  | 0 |  | 0 | 16 | Sanitary Manholes to be Removed | Each | 1 | 3500 | 3500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Sanitary Manholes to be Removed and Replaced, 4' Dia. | Each | 1 | 27000 | 27000 | 16858 | 16858 | 8500 | 8500 | 17389 | 17389 | 15000 | 15000 | 17 | Sanitary Manholes to be Removed and Replaced, 4' Dia. | Each | 1 | 27000 | 27000 | 15000 | 15000 | 18500 | 18500 |  | 0 |  | 0 | 17 | Sanitary Manholes to be Removed and Replaced, 4' Dia. | Each | 1 | 27000 | 27000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Sanitary Sewer Main Line Repair, 12" | Foot | 14 | 1500 | 21000 | 626 | 8764 | 1500 | 21000 | 526 | 7364 | 500 | 7000 | 18 | Sanitary Sewer Main Line Repair, 12" | Foot | 14 | 1500 | 21000 | 870 | 12180 | 1000 | 14000 |  | 0 |  | 0 | 18 | Sanitary Sewer Main Line Repair, 12" | Foot | 14 | 1500 | 21000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Concrete Encasement for Sanitary Sewers | Foot | 200 | 180 | 36000 | 318 | 63600 | 160 | 32000 | 148 | 29600 | 215 | 43000 | 19 | Concrete Encasement for Sanitary Sewers | Foot | 200 | 180 | 36000 | 56 | 11200 | 375 | 75000 |  | 0 |  | 0 | 19 | Concrete Encasement for Sanitary Sewers | Foot | 200 | 180 | 36000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Sump Pump Discharge Removal | Foot | 41 | 20 | 820 | 7.25 | 297.25 | 10 | 410 | 17 | 697 | 68 | 2788 | 20 | Sump Pump Discharge Removal | Foot | 41 | 20 | 820 | 19 | 779 | 20 | 820 |  | 0 |  | 0 | 20 | Sump Pump Discharge Removal | Foot | 41 | 20 | 820 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Sump Pump Discharge Extension, 2" | Foot | 12 | 23 | 276 | 19.4 | 232.8 | 20 | 240 | 27 | 324 | 128 | 1536 | 21 | Sump Pump Discharge Extension, 2" | Foot | 12 | 23 | 276 | 77 | 924 | 50 | 600 |  | 0 |  | 0 | 21 | Sump Pump Discharge Extension, 2" | Foot | 12 | 23 | 276 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Sump Pump Discharge Extension, 3" | Foot | 10 | 27 | 270 | 54 | 540 | 20 | 200 | 27 | 270 | 157 | 1570 | 22 | Sump Pump Discharge Extension, 3" | Foot | 10 | 27 | 270 | 96 | 960 | 65 | 650 |  | 0 |  | 0 | 22 | Sump Pump Discharge Extension, 3" | Foot | 10 | 27 | 270 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Fence Removal | Foot | 617 | 10 | 6170 | 4.2 | 2591.4 | 10 | 6170 | 11 | 6787 | 15 | 9255 | 23 | Fence Removal | Foot | 617 | 10 | 6170 | 14 | 8638 | 11 | 6787 |  | 0 |  | 0 | 23 | Fence Removal | Foot | 617 | 10 | 6170 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Chain Link Fence, 4', Special | Foot | 588 | 38 | 22344 | 34 | 19992 | 34 | 19992 | 36 | 21168 | 35.5 | 20874 | 24 | Chain Link Fence, 4', Special | Foot | 588 | 38 | 22344 | 33 | 19404 | 37 | 21756 |  | 0 |  | 0 | 24 | Chain Link Fence, 4', Special | Foot | 588 | 38 | 22344 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 524384 |  | 495230.75 |  | 612292.25 |  | 636281 |  | 691009 |  | Page 1 | Sub |  | As read | 524384 |  | 731049 |  | 959643.25 | [5 empty] | Page 1 | Sub |  | As read | 524384
| Award to Fischer Excavating | Total |  | As corrected | 524384 |  | 495230.75 |  | 612292.25 |  | 636281 |  | 691009 |  | Award to Fischer Excavating | Total |  | As corrected | 524384 |  | 731049 |  | 959643.25 | [5 empty] | Award to Fischer Excavating | Total |  | As corrected | 524384
25 | Relocate Existing Shed | L. Sum | 1 | 1750 | 1750 | 945 | 945 | 3500 | 3500 | 1934 | 1934 | 2000 | 2000 | 25 | Relocate Existing Shed | L. Sum | 1 | 1750 | 1750 | 1500 | 1500 | 2250 | 2250 |  | 0 |  | 0 | 25 | Relocate Existing Shed | L. Sum | 1 | 1750 | 1750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | By-Pass Pumping | L. Sum | 1 | 25000 | 25000 | 7315 | 7315 | 1 | 1 | 0.1 | 0.1 | 10000 | 10000 | 26 | By-Pass Pumping | L. Sum | 1 | 25000 | 25000 | 1 | 1 | 50000 | 50000 |  | 0 |  | 0 | 26 | By-Pass Pumping | L. Sum | 1 | 25000 | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Traffic Control and Protection, Special | L. Sum | 1 | 3500 | 3500 | 2300 | 2300 | 5000 | 5000 | 11530 | 11530 | 30000 | 30000 | 27 | Traffic Control and Protection, Special | L. Sum | 1 | 3500 | 3500 | 6000 | 6000 | 2650 | 2650 |  | 0 |  | 0 | 27 | Traffic Control and Protection, Special | L. Sum | 1 | 3500 | 3500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Construction Layout Stakes | L. Sum | 1 | 8000 | 8000 | 1350 | 1350 | 10000 | 10000 | 13570 | 13570 | 4000 | 4000 | 28 | Construction Layout Stakes | L. Sum | 1 | 8000 | 8000 | 6000 | 6000 | 5500 | 5500 |  | 0 |  | 0 | 28 | Construction Layout Stakes | L. Sum | 1 | 8000 | 8000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Non-Special Waste Disposal | Cu. Yd. | 100 | 100 | 10000 | 75 | 7500 | 0.01 | 1 | 0.1 | 10 | 0.01 | 1 | 29 | Non-Special Waste Disposal | Cu. Yd. | 100 | 100 | 10000 | 31 | 3100 | 75 | 7500 |  | 0 |  | 0 | 29 | Non-Special Waste Disposal | Cu. Yd. | 100 | 100 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Special Waste Disposal | Cu. Yd. | 100 | 250 | 25000 | 94 | 9400 | 0.01 | 1 | 0.1 | 10 | 0.01 | 1 | 30 | Special Waste Disposal | Cu. Yd. | 100 | 250 | 25000 | 92 | 9200 | 85 | 8500 |  | 0 |  | 0 | 30 | Special Waste Disposal | Cu. Yd. | 100 | 250 | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Special Waste Plans and Reports | L. Sum | 1 | 6000 | 6000 | 2600 | 2600 | 0.01 | 0.01 | 2652 | 2652 | 0.01 | 0.01 | 31 | Special Waste Plans and Reports | L. Sum | 1 | 6000 | 6000 | 1550 | 1550 | 4950 | 4950 |  | 0 |  | 0 | 31 | Special Waste Plans and Reports | L. Sum | 1 | 6000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Soil Disposal Analysis | Each | 10 | 900 | 9000 | 1100 | 11000 | 0.01 | 0.1 | 1122 | 11220 | 0.01 | 0.1 | 32 | Soil Disposal Analysis | Each | 10 | 900 | 9000 | 1550 | 15500 | 1350 | 13500 |  | 0 |  | 0 | 32 | Soil Disposal Analysis | Each | 10 | 900 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Mobilization | L.Sum | 1 | 15000 | 15000 | 15575 | 15575 | 35000 | 35000 | 35000 | 35000 | 55000 | 55000 | 33 | Mobilization | L.Sum | 1 | 15000 | 15000 | 23600 | 23600 | 22500 | 22500 |  | 0 |  | 0 | 33 | Mobilization | L.Sum | 1 | 15000 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 627634 |  | 553215.75 |  | 665795.36 |  | 712207.1 |  | 792011.11 |  | Page 2 | Total |  | As read | 627634 |  | 797500 |  | 1076993.25 | [5 empty] | Page 2 | Total |  | As read | 627634
| Award to Fischer Excavating | Bid |  | As corrected | 627634 |  | 553215.75 |  | 665795.36 |  | 712207.1 |  | 792011.11 |  | Award to Fischer Excavating | Bid |  | As corrected | 627634 |  | 797500 |  | 1076993.25 | [5 empty] | Award to Fischer Excavating | Bid |  | As corrected | 627634
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Fischer Excavating | Bid |  | As corrected | [10 empty] | Award to Fischer Excavating | Bid |  | As corrected | [10 empty] | Award to Fischer Excavating | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Fischer Excavating | Bid |  | As corrected | [10 empty] | Award to Fischer Excavating | Bid |  | As corrected | [10 empty] | Award to Fischer Excavating | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Buckbee Drainageway Improvements
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Tree Removal, Acres | Acres | 1.1 |  | 0
2 | Earth Excavation, Special | Cu. Yd. | 2632 |  | 0
3 | Topsoil Furnish and Place, 4" | Sq. Yd. | 1943 |  | 0
4 | Parkway Restoration | L. Sum | 1 |  | 0
5 | Erosion Control Blanket | Sq. Yd. | 68 |  | 0
6 | Turf Reinforcement Mat | Sq. Yd. | 2881 |  | 0
7 | Temporary Erosion Control Seeding | Pound | 62 |  | 0
8 | Inlet and Pipe Protection | Each | 2 |  | 0
9 | Stabilized Construction Entrance | L. Sum | 1 |  | 0
10 | Stone Riprap, Class B5 | Sq. Yd. | 2831 |  | 0
11 | Filter Fabric | Sq. Yd. | 2831 |  | 0
12 | Portland Cement Concrete Sidewalk, 4-Inch, Remove and Replace | Sq. Ft. | 116 |  | 0
13 | Pipe Culvert Removal | Foot | 40 |  | 0
14 | Pipe Culverts, Class C, Type 1, 18" | Foot | 17 |  | 0
15 | Pipe Culverts, Class C, Type 1, 24" | Foot | 8 |  | 0
16 | Sanitary Manholes to be Removed | Each | 1 |  | 0
17 | Sanitary Manholes to be Removed and Replaced, 4' Dia. | Each | 1 |  | 0
18 | Sanitary Sewer Main Line Repair, 12" | Foot | 14 |  | 0
19 | Concrete Encasement for Sanitary Sewers | Foot | 200 |  | 0
20 | Sump Pump Discharge Removal | Foot | 41 |  | 0
21 | Sump Pump Discharge Extension, 2" | Foot | 12 |  | 0
22 | Sump Pump Discharge Extension, 3" | Foot | 10 |  | 0
23 | Fence Removal | Foot | 617 |  | 0
24 | Chain Link Fence, 4', Special | Foot | 588 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Relocate Existing Shed | L. Sum | 1 |  | 0
26 | By-Pass Pumping | L. Sum | 1 |  | 0
27 | Traffic Control and Protection, Special | L. Sum | 1 |  | 0
28 | Construction Layout Stakes | L. Sum | 1 |  | 0
29 | Non-Special Waste Disposal | Cu. Yd. | 100 |  | 0
30 | Special Waste Disposal | Cu. Yd. | 100 |  | 0
31 | Special Waste Plans and Reports | L. Sum | 1 |  | 0
32 | Soil Disposal Analysis | Each | 10 |  | 0
33 | Mobilization | L.Sum | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Buckbee Drainageway Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Tree Removal, Acres | Acres | 1.1 | 23000 | 25300
2 | Earth Excavation, Special | Cu. Yd. | 2632 | 40 | 105280
3 | Topsoil Furnish and Place, 4" | Sq. Yd. | 1943 | 6 | 11658
4 | Parkway Restoration | L. Sum | 1 | 5898 | 5898
5 | Erosion Control Blanket | Sq. Yd. | 68 | 4 | 272
6 | Turf Reinforcement Mat | Sq. Yd. | 2881 | 8 | 23048
7 | Temporary Erosion Control Seeding | Pound | 62 | 6 | 372
8 | Inlet and Pipe Protection | Each | 2 | 200 | 400
9 | Stabilized Construction Entrance | L. Sum | 1 | 10000 | 10000
10 | Stone Riprap, Class B5 | Sq. Yd. | 2831 | 73 | 206663
11 | Filter Fabric | Sq. Yd. | 2831 | 4 | 11324
12 | Portland Cement Concrete Sidewalk, 4-Inch, Remove and Replace | Sq. Ft. | 116 | 24 | 2784
13 | Pipe Culvert Removal | Foot | 40 | 20 | 800
14 | Pipe Culverts, Class C, Type 1, 18" | Foot | 17 | 125 | 2125
15 | Pipe Culverts, Class C, Type 1, 24" | Foot | 8 | 135 | 1080
16 | Sanitary Manholes to be Removed | Each | 1 | 3500 | 3500
17 | Sanitary Manholes to be Removed and Replaced, 4' Dia. | Each | 1 | 27000 | 27000
18 | Sanitary Sewer Main Line Repair, 12" | Foot | 14 | 1500 | 21000
19 | Concrete Encasement for Sanitary Sewers | Foot | 200 | 180 | 36000
20 | Sump Pump Discharge Removal | Foot | 41 | 20 | 820
21 | Sump Pump Discharge Extension, 2" | Foot | 12 | 23 | 276
22 | Sump Pump Discharge Extension, 3" | Foot | 10 | 27 | 270
23 | Fence Removal | Foot | 617 | 10 | 6170
24 | Chain Link Fence, 4', Special | Foot | 588 | 38 | 22344
|  |  |  | Sub Total | 524384
Made by: Dale K. Hamilton, P.E. |  |  | Date: April 19, 2022
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Buckbee Drainageway Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Relocate Existing Shed | L. Sum | 1 | 1750 | 1750
26 | By-Pass Pumping | L. Sum | 1 | 25000 | 25000
27 | Traffic Control and Protection, Special | L. Sum | 1 | 3500 | 3500
28 | Construction Layout Stakes | L. Sum | 1 | 8000 | 8000
29 | Non-Special Waste Disposal | Cu. Yd. | 100 | 100 | 10000
30 | Special Waste Disposal | Cu. Yd. | 100 | 250 | 25000
31 | Special Waste Plans and Reports | L. Sum | 1 | 6000 | 6000
32 | Soil Disposal Analysis | Each | 10 | 900 | 9000
33 | Mobilization | L.Sum | 1 | 15000 | 15000
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 627634
Made by: Dale K. Hamilton, P.E. |  |  | Date: Arpil 19, 2022
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Buckbee Drainageway Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 627634
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Buckbee Drainageway Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 627634
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Fischer Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Freeport, IL Bid Bond | [5 empty] | SECTION | Buckbee Drainageway Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Tree Removal, Acres | 1.1 | Acres | 40700 |  | 1.1 |  |  | 37000
2 | Earth Excavation, Special | 2632 | Cu. Yd. | 90804 |  | 2632 |  |  | 34.5
3 | Topsoil Furnish and Place, 4" | 1943 | Sq. Yd. | 7577.7 |  | 1943 |  |  | 3.9
4 | Parkway Restoration | 1 | L. Sum | 5500 |  | 1 |  |  | 5500
5 | Erosion Control Blanket | 68 | Sq. Yd. | 258.4 |  | 68 |  |  | 3.8
6 | Turf Reinforcement Mat | 2881 | Sq. Yd. | 33131.5 |  | 2881 |  |  | 11.5
7 | Temporary Erosion Control Seeding | 62 | Pound | 186 |  | 62 |  |  | 3
8 | Inlet and Pipe Protection | 2 | Each | 440 |  | 2 |  |  | 220
9 | Stabilized Construction Entrance | 1 | L. Sum | 2388 |  | 1 |  |  | 2388
10 | Stone Riprap, Class B5 | 2831 | Sq. Yd. | 186846 |  | 2831 |  |  | 66
11 | Filter Fabric | 2831 | Sq. Yd. | 7643.7 |  | 2831 |  |  | 2.7
12 | Portland Cement Concrete Sidewalk, 4-Inch, Remove and Replace | 116 | Sq. Ft. | 1450 |  | 116 |  |  | 12.5
13 | Pipe Culvert Removal | 40 | Foot | 152 |  | 40 |  |  | 3.8
14 | Pipe Culverts, Class C, Type 1, 18" | 17 | Foot | 1989 |  | 17 |  |  | 117
15 | Pipe Culverts, Class C, Type 1, 24" | 8 | Foot | 1852 |  | 8 |  |  | 231.5
16 | Sanitary Manholes to be Removed | 1 | Each | 1437 |  | 1 |  |  | 1437
17 | Sanitary Manholes to be Removed and Replaced, 4' Dia. | 1 | Each | 16858 |  | 1 |  |  | 16858
18 | Sanitary Sewer Main Line Repair, 12" | 14 | Foot | 8764 |  | 14 |  |  | 626
19 | Concrete Encasement for Sanitary Sewers | 200 | Foot | 63600 |  | 200 |  |  | 318
20 | Sump Pump Discharge Removal | 41 | Foot | 297.25 |  | 41 |  |  | 7.25
21 | Sump Pump Discharge Extension, 2" | 12 | Foot | 232.8 |  | 12 |  |  | 19.4
22 | Sump Pump Discharge Extension, 3" | 10 | Foot | 540 |  | 10 |  |  | 54
23 | Fence Removal | 617 | Foot | 2591.4 |  | 617 |  |  | 4.2
24 | Chain Link Fence, 4', Special | 588 | Foot | 19992 |  | 588 |  |  | 34
Sub Total |  |  |  | 495230.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Fischer Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Freeport, IL Bid Bond | [5 empty] | SECTION | Buckbee Drainageway Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Relocate Existing Shed | 1 | L. Sum | 945 |  | 1 |  |  | 945
26 | By-Pass Pumping | 1 | L. Sum | 7315 |  | 1 |  |  | 7315
27 | Traffic Control and Protection, Special | 1 | L. Sum | 2300 |  | 1 |  |  | 2300
28 | Construction Layout Stakes | 1 | L. Sum | 1350 |  | 1 |  |  | 1350
29 | Non-Special Waste Disposal | 100 | Cu. Yd. | 7500 |  | 100 |  |  | 75
30 | Special Waste Disposal | 100 | Cu. Yd. | 9400 |  | 100 |  |  | 94
31 | Special Waste Plans and Reports | 1 | L. Sum | 2600 |  | 1 |  |  | 2600
32 | Soil Disposal Analysis | 10 | Each | 11000 |  | 10 |  |  | 1100
33 | Mobilization | 1 | L.Sum | 15575 |  | 1 |  |  | 15575
Total |  |  |  | 553215.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Fischer Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Freeport, IL Bid Bond | [5 empty] | SECTION | Buckbee Drainageway Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 553215.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Fischer Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Freeport, IL Bid Bond | [5 empty] | SECTION | Buckbee Drainageway Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 553215.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Buckbee Drainageway Improvements
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Fischer Excavating
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.