## Item List
| City -Wide Street Repairs Group No. 2 - 2022 (Alleys) | [19 empty] | 347931
Summary Of Quantities |  |  | 2nd Ward - 9403002 |  |  | 9403003 | 9403006 | 9403007 | 9403007 | 11th Ward - 9403011 |  |  |  | 11th Ward - 9403011
No. | Item | Units | Alley 105 | Alley 323 | Alley 330 | Alley 727 | Alley 26 | Alleys 1024 and 1029 | Alley 1032 | Alleys 227 and 231 | Alley 239 | Alley 246 | Alleys 263 and 264 | Alley 274 | Alley 398 | Alley 472 | Alley 486 | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. |  |  |  |  | 65 |  | 210 |  | 230 | [7 empty] | 505 | 30 | 15150
2 | Parkway Restoration | Lsum | 0.04 | 0.03 | 0.04 | 0.06 | 0.03 | 0.13 | 0.1 | 0.07 | 0.13 | 0.06 | 0.11 | 0.06 | 0.03 | 0.05 | 0.06 |  | 1 | 10000 | 10000
3 | Inlet and Pipe Protection | Each | [5 empty] | 2 | [10 empty] | 2 | 100 | 200
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons |  |  |  |  | 85 |  | 325 |  | 350 | [7 empty] | 760 | 25 | 19000
5 | Aggregate Base Repair, 10" | S.Y. | 35 | 40 | 25 | 45 |  | 137 |  | 77 |  | 75 | 80 | 47 | 22 | 60 | 85 |  | 728 | 25 | 18200
6 | Bituminous Materials (Prime Coat) | Gal | 35 | 40 | 25 | 45 | 15 | 137 | 57 | 77 | 62 | 75 | 80 | 47 | 22 | 60 | 85 |  | 862 | 3 | 2586
7 | Aggregate (Prime Coat) | Tons | 3 | 4 | 2 | 4 | 1 | 13 | 5 | 7 | 6 | 7 | 8 | 4 | 2 | 6 | 8 |  | 80 | 10 | 800
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons |  |  |  |  | 20 |  | 60 |  | 65 | [6 empty] | 50 | 195 | 100 | 19500
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons |  |  |  |  | 20 |  | 60 |  | 65 | [6 empty] | 50 | 195 | 100 | 19500
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 50 | 60 | 35 | 65 |  | 170 |  | 100 |  | 100 | 100 | 65 | 30 | 75 | 105 | 100 | 1055 | 100 | 105500
11 | Hot-Mix Asphalt, Hand Method | Tons | [15 empty] | 10 | 10 | 300 | 3000
12 | P.C.C. Approach Pavement, 6" | S.Y. | [14 empty] | 26 | 50 | 76 | 60 | 4560
13 | P.C.C. Approach Pavement, 8" | S.Y. | 9 |  | 14 | 32 |  | 55 | 18 | 29 | 37 | 18 | 15 |  | 21 | 27 | 26 | 50 | 351 | 75 | 26325
14 | P.C.C. Sidewalk, 4" | S.F. | 175 |  | 125 | 200 |  | 600 | 200 | 225 | 325 | 125 | 200 |  | 100 | 175 | 275 | 500 | 3225 | 6 | 19350
15 | Combination Curb and Gutter Removal | L.F. | 30 |  | 90 | 45 |  | 65 |  | 40 | 60 | 35 | 30 |  | 25 | 35 | 55 | 50 | 560 | 20 | 11200
16 | Sidewalk Removal | S.F. | 175 |  | 125 | 200 |  | 600 | 200 | 225 | 325 | 125 | 200 |  | 100 | 175 | 275 | 500 | 3225 | 2 | 6450
17 | Approach Pavement Removal | S.Y. | 9 |  | 14 | 32 |  | 55 | 18 | 29 | 37 | 18 | 15 |  | 21 | 27 | 52 | 50 | 377 | 30 | 11310
18 | Surface Removal, 2" | S.Y. | 350 | 400 | 250 | 450 |  | 1375 |  | 775 |  | 750 | 800 | 475 | 225 | 600 | 850 | 500 | 7800 | 4 | 31200
19 | Aggregate Shoulder | Tons | [15 empty] | 50 | 50 | 40 | 2000
20 | Manholes to be Adjusted | Each | [7 empty] | 1 | [8 empty] | 1 | 800 | 800
21 | Manholes to be Adjusted with Casting | Each |  |  |  | 2 |  | 1 | [10 empty] | 3 | 1000 | 3000
22 | Inlets to be Adjusted | Each | [5 empty] | 1 | [10 empty] | 1 | 1500 | 1500
23 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 30 |  | 90 | 45 |  | 65 |  | 40 | 60 | 35 | 30 |  | 25 | 35 | 55 | 50 | 560 | 30 | 16800
24 | Traffic Control and Protection | Lsum | 0.04 | 0.03 | 0.04 | 0.06 | 0.03 | 0.13 | 0.1 | 0.07 | 0.13 | 0.06 | 0.11 | 0.06 | 0.03 | 0.05 | 0.06 |  | 1
25
26
27 | [19 empty] | 10000
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 11655 | 9060 | 12590 | 19410 | 8430 | 44291 | 31136 | 23671 | 39681 | 20410 | 21295 | 10356 | 9091 | 18125 | 26980 | 41750 | #VALUE!
|  |  | 1547.2759 | 1256.3351 | 1679.5217 | 2360.5876 | 1256.3351 | 5633.6712 | 4073.1707 | 3044.9596 | 5544.4053 | 2466.3842 | 4585.6232 | 2334.1384 | 1302.6212 | 2307.6893 | 2357.2814 |  | 347931
|  |  | 13202.2759 | 10316.3351 | 14269.5217 | 21770.5876 | 9686.3351 | 49924.6712 | 35209.1707 | 26715.9596 | 45225.4053 | 22876.3842 | 25880.6232 | 12690.1384 | 10393.6212 | 20432.6893 | 29337.2814 |  | 347931
|  |  | 11700 | 9500 | 12700 | 17850 | 9500 | 42600 | 30800 | 23025 | 41925 | 18650 | 34675 | 17650 | 9850 | 17450 | 17825 | 0 | 315700
#REF!
|  |  | 0.037061 | 0.030092 | 0.040228 | 0.056541 | 0.030092 | 0.13494 | 0.097561 | 0.072933 | 0.1328 | 0.059075 | 0.10984 | 0.055908 | 0.031201 | 0.055274 | 0.056462 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Norwest Construction |  | Stenstrom Excavation |  | William Charles |  | Curran Contracting |  |  |  | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | S.Beloit, IL |  | Rockford, IL |  | Rockford, IL |  | Crystal Lake, IL |  |  |  | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 2 - 2022 (Alleys) | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond | [5 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 505 | 30 | 15150 | 35.64 | 17998.2 | 43.75 | 22093.75 | 37.35 | 18861.75 | 35 | 17675 |  | 0 | 1 | Earth Excavation | C.Y. | 505 | 30 | 15150 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 505 | 30 | 15150 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 | 9000 | 9000 | 29200 | 29200 | 12929.02 | 12929.02 | 30000 | 30000 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 2 | 100 | 200 | 50 | 100 | 190 | 380 | 372.64 | 745.28 | 350 | 700 |  | 0 | 3 | Inlet and Pipe Protection | Each | 2 | 100 | 200 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 2 | 100 | 200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 760 | 25 | 19000 | 14.47 | 10997.2 | 33 | 25080 | 30.49 | 23172.4 | 25 | 19000 |  | 0 | 4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 760 | 25 | 19000 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 760 | 25 | 19000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Aggregate Base Repair, 10" | S.Y. | 728 | 25 | 18200 | 0.01 | 7.28 | 0.01 | 7.28 | 0.01 | 7.28 | 0.01 | 7.28 |  | 0 | 5 | Aggregate Base Repair, 10" | S.Y. | 728 | 25 | 18200 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Aggregate Base Repair, 10" | S.Y. | 728 | 25 | 18200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Bituminous Materials (Prime Coat) | Gal | 862 | 3 | 2586 | 0.01 | 8.62 | 6 | 5172 | 7.74 | 6671.88 | 5 | 4310 |  | 0 | 6 | Bituminous Materials (Prime Coat) | Gal | 862 | 3 | 2586 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Bituminous Materials (Prime Coat) | Gal | 862 | 3 | 2586 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Aggregate (Prime Coat) | Tons | 80 | 10 | 800 | 0.01 | 0.8 | 0.01 | 0.8 | 0.01 | 0.8 | 0.01 | 0.8 |  | 0 | 7 | Aggregate (Prime Coat) | Tons | 80 | 10 | 800 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Aggregate (Prime Coat) | Tons | 80 | 10 | 800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 195 | 100 | 19500 | 113 | 22035 | 113 | 22035 | 120.66 | 23528.7 | 98 | 19110 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 195 | 100 | 19500 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 195 | 100 | 19500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 195 | 100 | 19500 | 113 | 22035 | 132 | 25740 | 127.27 | 24817.65 | 98 | 19110 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 195 | 100 | 19500 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 195 | 100 | 19500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1055 | 100 | 105500 | 113 | 119215 | 116 | 122380 | 116.84 | 123266.2 | 98 | 103390 |  | 0 | 10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1055 | 100 | 105500 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1055 | 100 | 105500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 | 300 | 3000 | 400 | 4000 | 371.6 | 3716 | 450 | 4500 |  | 0 | 11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 76 | 60 | 4560 | 80 | 6080 | 72.5 | 5510 | 88.45 | 6722.2 | 75 | 5700 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 76 | 60 | 4560 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 76 | 60 | 4560 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 351 | 75 | 26325 | 82.51 | 28961.01 | 81 | 28431 | 90.88 | 31898.88 | 80 | 28080 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 351 | 75 | 26325 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 351 | 75 | 26325 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 3225 | 6 | 19350 | 8.5 | 27412.5 | 8.75 | 28218.75 | 8.41 | 27122.25 | 8 | 25800 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 3225 | 6 | 19350 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 3225 | 6 | 19350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Combination Curb and Gutter Removal | L.F. | 560 | 20 | 11200 | 8.8 | 4928 | 22 | 12320 | 29.28 | 16396.8 | 20 | 11200 |  | 0 | 15 | Combination Curb and Gutter Removal | L.F. | 560 | 20 | 11200 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Combination Curb and Gutter Removal | L.F. | 560 | 20 | 11200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Sidewalk Removal | S.F. | 3225 | 2 | 6450 | 2 | 6450 | 3 | 9675 | 2.13 | 6869.25 | 4 | 12900 |  | 0 | 16 | Sidewalk Removal | S.F. | 3225 | 2 | 6450 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Sidewalk Removal | S.F. | 3225 | 2 | 6450 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Approach Pavement Removal | S.Y. | 377 | 30 | 11310 | 18 | 6786 | 32.75 | 12346.75 | 39.23 | 14789.71 | 30 | 11310 |  | 0 | 17 | Approach Pavement Removal | S.Y. | 377 | 30 | 11310 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Approach Pavement Removal | S.Y. | 377 | 30 | 11310 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Surface Removal, 2" | S.Y. | 7800 | 4 | 31200 | 8.97 | 69966 | 7.3 | 56940 | 4.18 | 32604 | 6 | 46800 |  | 0 | 18 | Surface Removal, 2" | S.Y. | 7800 | 4 | 31200 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Surface Removal, 2" | S.Y. | 7800 | 4 | 31200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Aggregate Shoulder | Tons | 50 | 40 | 2000 | 1 | 50 | 0.01 | 0.5 | 58.69 | 2934.5 | 0.01 | 0.5 |  | 0 | 19 | Aggregate Shoulder | Tons | 50 | 40 | 2000 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Aggregate Shoulder | Tons | 50 | 40 | 2000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Manholes to be Adjusted | Each | 1 | 800 | 800 | 1300 | 1300 | 975 | 975 | 1189.25 | 1189.25 | 1000 | 1000 |  | 0 | 20 | Manholes to be Adjusted | Each | 1 | 800 | 800 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Manholes to be Adjusted | Each | 1 | 800 | 800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Manholes to be Adjusted with Casting | Each | 3 | 1000 | 3000 | 1833.33 | 5499.99 | 1300 | 3900 | 1526.37 | 4579.11 | 1400 | 4200 |  | 0 | 21 | Manholes to be Adjusted with Casting | Each | 3 | 1000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Manholes to be Adjusted with Casting | Each | 3 | 1000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Inlets to be Adjusted | Each | 1 | 1500 | 1500 | 1700 | 1700 | 975 | 975 | 1565.24 | 1565.24 | 1400 | 1400 |  | 0 | 22 | Inlets to be Adjusted | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Inlets to be Adjusted | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 560 | 30 | 16800 | 31.8 | 17808 | 42 | 23520 | 38.4 | 21504 | 45 | 25200 |  | 0 | 23 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 560 | 30 | 16800 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 560 | 30 | 16800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Traffic Control and Protection | Lsum | 1 | 0 | 0 | 12000 | 12000 | 14700 | 14700 | 19331.29 | 19331.29 | 26500 | 26500 |  | 0 | 24 | Traffic Control and Protection | Lsum | 1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Traffic Control and Protection | Lsum | 1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Total |  | As read | 347931 |  | 393377 |  | 453600.83 |  | 425223.44 |  | 417893.58 |  |  |  | Page 3 | Total |  | As read | 347931 | [9 empty] | Page 1 | Total |  | As read | 347931
| Award to Norwest Construction | Bid |  | As corrected | 347931 |  | 393338.6 |  | 453600.83 |  | 425223.44 |  | 417893.58 |  |  |  | Award to Norwest Construction | Bid |  | As corrected | 347931 | [9 empty] | Award to Norwest Construction | Bid |  | As corrected | 347931
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 10000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 10000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 10000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 2 | Total |  | As read
| Award to Norwest Construction | Bid |  | As corrected |  |  |  | 0 |  | 0 |  |  | 715415 |  |  |  | Award to Norwest Construction | Bid |  | As corrected | [10 empty] | Award to Norwest Construction | Bid |  | As corrected
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Norwest Construction | Bid |  | As corrected | [12 empty] | Award to Norwest Construction | Bid |  | As corrected | [10 empty] | Award to Norwest Construction | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Norwest Construction | Bid |  | As corrected | [12 empty] | Award to Norwest Construction | Bid |  | As corrected | [10 empty] | Award to Norwest Construction | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 2 - 2022 (Alleys)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 505 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 2 |  | 0
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 760 |  | 0
5 | Aggregate Base Repair, 10" | S.Y. | 728 |  | 0
6 | Bituminous Materials (Prime Coat) | Gal | 862 |  | 0
7 | Aggregate (Prime Coat) | Tons | 80 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 195 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 195 |  | 0
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1055 |  | 0
11 | Hot-Mix Asphalt, Hand Method | Tons | 10 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 76 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 351 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 3225 |  | 0
15 | Combination Curb and Gutter Removal | L.F. | 560 |  | 0
16 | Sidewalk Removal | S.F. | 3225 |  | 0
17 | Approach Pavement Removal | S.Y. | 377 |  | 0
18 | Surface Removal, 2" | S.Y. | 7800 |  | 0
19 | Aggregate Shoulder | Tons | 50 |  | 0
20 | Manholes to be Adjusted | Each | 1 |  | 0
21 | Manholes to be Adjusted with Casting | Each | 3 |  | 0
22 | Inlets to be Adjusted | Each | 1 |  | 0
23 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 560 |  | 0
24 | Traffic Control and Protection | Lsum | 1 |  | 0
| Page 1 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
#VALUE!
| Page 2 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2022 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 505 | 30 | 15150
2 | Parkway Restoration | Lsum | 1 | 10000 | 10000
3 | Inlet and Pipe Protection | Each | 2 | 100 | 200
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 760 | 25 | 19000
5 | Aggregate Base Repair, 10" | S.Y. | 728 | 25 | 18200
6 | Bituminous Materials (Prime Coat) | Gal | 862 | 3 | 2586
7 | Aggregate (Prime Coat) | Tons | 80 | 10 | 800
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 195 | 100 | 19500
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 195 | 100 | 19500
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1055 | 100 | 105500
11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000
12 | P.C.C. Approach Pavement, 6" | S.Y. | 76 | 60 | 4560
13 | P.C.C. Approach Pavement, 8" | S.Y. | 351 | 75 | 26325
14 | P.C.C. Sidewalk, 4" | S.F. | 3225 | 6 | 19350
15 | Combination Curb and Gutter Removal | L.F. | 560 | 20 | 11200
16 | Sidewalk Removal | S.F. | 3225 | 2 | 6450
17 | Approach Pavement Removal | S.Y. | 377 | 30 | 11310
18 | Surface Removal, 2" | S.Y. | 7800 | 4 | 31200
19 | Aggregate Shoulder | Tons | 50 | 40 | 2000
20 | Manholes to be Adjusted | Each | 1 | 800 | 800
21 | Manholes to be Adjusted with Casting | Each | 3 | 1000 | 3000
22 | Inlets to be Adjusted | Each | 1 | 1500 | 1500
23 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 560 | 30 | 16800
24 | Traffic Control and Protection | Lsum | 1 | 0 | 0
|  |  |  | Total | 347931
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2022 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 10000 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2022 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2022 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | P.O. #18305125 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: S.Beloit, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2022 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 505 | C.Y. | 17998.2 |  | 505 |  |  | 35.64
2 | Parkway Restoration | 1 | Lsum | 9000 |  | 1 |  |  | 9000
3 | Inlet and Pipe Protection | 2 | Each | 100 |  | 2 |  |  | 50
4 | Aggregate Base Course, Type B, CA-6, 10" | 760 | Tons | 10997.2 |  | 760 |  |  | 14.47
5 | Aggregate Base Repair, 10" | 728 | S.Y. | 7.28 |  | 728 |  |  | 0.01
6 | Bituminous Materials (Prime Coat) | 862 | Gal | 8.62 |  | 862 |  |  | 0.01
7 | Aggregate (Prime Coat) | 80 | Tons | 0.8 |  | 80 |  |  | 0.01
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | 195 | Tons | 22035 |  | 195 |  |  | 113
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | 195 | Tons | 22035 |  | 195 |  |  | 113
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 1055 | Tons | 119215 |  | 1055 |  |  | 113
11 | Hot-Mix Asphalt, Hand Method | 10 | Tons | 3000 |  | 10 |  |  | 300
12 | P.C.C. Approach Pavement, 6" | 76 | S.Y. | 6080 |  | 76 |  |  | 80
13 | P.C.C. Approach Pavement, 8" | 351 | S.Y. | 28961.01 |  | 351 |  |  | 82.51
14 | P.C.C. Sidewalk, 4" | 3225 | S.F. | 27412.5 |  | 3225 |  |  | 8.5
15 | Combination Curb and Gutter Removal | 560 | L.F. | 4928 |  | 560 |  |  | 8.8
16 | Sidewalk Removal | 3225 | S.F. | 6450 |  | 3225 |  |  | 2
17 | Approach Pavement Removal | 377 | S.Y. | 6786 |  | 377 |  |  | 18
18 | Surface Removal, 2" | 7800 | S.Y. | 69966 |  | 7800 |  |  | 8.97
19 | Aggregate Shoulder | 50 | Tons | 50 |  | 50 |  |  | 1
20 | Manholes to be Adjusted | 1 | Each | 1300 |  | 1 |  |  | 1300
21 | Manholes to be Adjusted with Casting | 3 | Each | 5499.99 |  | 3 |  |  | 1833.33
22 | Inlets to be Adjusted | 1 | Each | 1700 |  | 1 |  |  | 1700
23 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 560 | L.F. | 17808 |  | 560 |  |  | 31.8
24 | Traffic Control and Protection | 1 | Lsum | 12000 |  | 1 |  |  | 12000
Total |  |  |  | 393338.6 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: S.Beloit, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2022 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 393338.6 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
[8 empty] | DEDUCT RETAINAGE | 10% | 0
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: S.Beloit, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2022 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 393338.6 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: S.Beloit, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2022 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 393338.6 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Norwest Construction
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.