## Item List
| City -Wide Street Repairs Group No. 3 - 2022 (Residential) | [42 empty] | 2015009
Summary Of Quantities |  |  | 3rd Ward - 9403003 |  |  |  |  | 9403003 | 5th Ward - 9403005 |  |  |  | 9403005 | 6th Ward - 9403006 |  |  |  | 9403006 | 7th Ward - 9403007 |  |  | 9403007/9403013 | 9403008 | 10th Ward - 9403010 |  |  |  | 10th Ward - 9403010 |  |  |  |  | 10th Ward - 9403010 |  |  |  |  | 9403013 | W2244 | W2244
No. | Item | Units | 1400/1500 Arden Avenue | 1000 B Street Patching | 2700 Green Apple Lane | 1300/1400 Irvington Place | 0700 Joslyn Street | 1400/1600 Oakes Avenue | 1200 Banks Street | 1300/1700 Banks Street | 2400/2500 Clover Avenue | 0100 Parkview Terrace | 1300 South Johnston Avenue | 2500/2900 Bluffside Drive | 3700/3800 Golden Prairie Avenue | 060 Kennon Road | Senate Drive/ Congress Drive | 4200 Tesa Road | 2000/2200 Belden Street | 1500/1600 Evergreen Street | 1400/1600 Sherman Avenue | 0700 Maple Street | 2400/2500 17th Avenue | 2600 9th Avenue | 2700 10th Avenue | 12th Avenue/ 26th Street Patching | 4800 Alpine Park Drive | 3600 Cardinal Lane Patching | Crosby Street/ Hemlock Lane | 4500 Forest View Avenue | 2800 Greenwood Avenue | 3700 Keith View Drive | 5100 Norwich Drive Patching | 0500 Skylark Drive Patching | Skyline Drive/ Bluecrest Drive | 3700 Thornwood Drive | 0400 Wood Road | 1100 Fairview Avenue | 7500/7700 Rote Road Reconstruction | East State Street/ New Towne Drive Circulation Easement | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. | 30 | [35 empty] | 2200 |  | 100 | 2330 | 30 | 69900
2 | Geotechnical Fabric for Ground Stabilization | S.Y. | [36 empty] | 3800 |  |  | 3800 | 5 | 19000
3 | Parkway Restoration | Lsum | 0.09 | 0 | 0 | 0.09 | 0.06 | 0.09 | 0 | 0 | 0 | 0 | 0.03 | 0.03 | 0.03 | 0 | 0 | 0.03 | 0.03 | 0.12 | 0.15 | 0 | 0.06 | 0 | 0 | 0 | 0.06 | 0.02 | 0 | 0.03 | 0.04 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 50000 | 50000
4 | Inlet and Pipe Protection | Each | 3 |  | 3 | 3 | 4 | [5 empty] | 3 | 1 |  |  | 1 | 1 | 2 | 2 | 12 |  | 2 |  |  |  | 1 | 2 |  |  | 1 | 4 |  |  |  | 4 | 1 |  |  |  |  | 50 | 60 | 3000
5 | Aggregate Subbase Improvement, CS-01, 9" | Tons | [36 empty] | 1900 |  |  | 1900 | 25 | 47500
6 | Aggregate Base Course, Type B, CA-6, 3" | Tons | [36 empty] | 640 |  |  | 640 | 25 | 16000
7 | Aggregate Base Repair, 10" | S.Y. | 17 | 5 | 23 | 24 | 26 | 43 | 18 | 51 | 16 | 7 | 8 | 67 | 26 | 19 | 91 | 15 | 32 | 27 | 37 | 12 | 11 | 10 | 8 | 5 | 13 | 8 |  | 13 | 9 | 28 | 15 |  |  | 18 | 9 | 23 |  | 20 |  | 754 | 20 | 15080
8 | Bituminous Materials (Prime Coat) | Gal | 177 | 52 | 230 | 237 | 265 | 430 | 180 | 510 | 162 | 70 | 87 | 675 | 260 | 190 | 910 | 155 | 325 | 270 | 377 | 125 | 115 | 105 | 80 | 50 | 135 | 85 | 12 | 130 | 90 | 280 | 150 | 25 | 45 | 185 | 95 | 235 |  | 205 |  | 7709 | 3 | 23127
9 | Aggregate (Prime Coat) | Tons | 9 | 2 | 12 | 12 | 13 | 22 | 9 | 26 | 8 | 3 | 4 | 34 | 3 | 10 | 46 | 8 | 16 | 14 | 19 | 6 | 6 | 5 | 4 | 2 | 7 | 4 |  | 7 | 5 | 14 | 8 |  |  | 9 | 5 | 12 |  | 10 |  | 374 | 10 | 3740
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | [37 empty] | 225 |  | 225 | 75 | 16875
11 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | [36 empty] | 950 |  |  | 950 | 75 | 71250
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 225 | 75 | 275 | 300 | 325 | 525 | 225 | 600 | 200 | 100 | 125 | 800 | 325 | 225 | 1075 | 200 | 400 | 325 | 450 | 175 | 150 | 125 | 100 | 75 | 175 | 100 | 25 | 175 | 125 | 350 | 200 | 50 | 75 | 225 | 125 | 300 | 450 | 250 | 500 | 10525 | 75 | 789375
13 | Hot-Mix Asphalt, Hand Method | Tons | [38 empty] | 10 | 10 | 300 | 3000
14 | P.C.C. Approach Pavement, 6" | S.Y. |  |  |  | 79 | 14 | 77 | [11 empty] | 44 |  |  | 37 |  |  |  | 37 | [13 empty] | 25 | 313 | 60 | 18780
15 | P.C.C. Approach Pavement, 8" | S.Y. | [5 empty] | 106 | [23 empty] | 50 | [8 empty] | 25 | 181 | 75 | 13575
16 | P.C.C. Sidewalk, 4" | S.F. | 2800 |  |  | 2550 | 1900 | 2800 |  |  |  |  | 425 | 450 |  |  |  | 400 | 325 | 4025 | 5475 |  | 275 |  |  |  | 925 |  |  | 450 | 550 | 600 | [8 empty] | 1000 | 24950 | 6 | 149700
17 | Detectable Warnings, ADA Ramps | S.F. | 80 |  |  | 60 | 20 | 20 |  |  |  |  | 20 | 20 |  |  |  | 20 | 40 | 20 | 220 | [8 empty] | 40 | 40 | 10 | [9 empty] | 610 | 25 | 15250
18 | Combination Curb and Gutter Removal | L.F. | 100 |  |  | 255 | 60 | 175 |  |  |  |  | 50 | 60 | 30 |  |  | 90 | 75 | 22 | 420 |  | 165 |  |  |  | 315 | 10 |  | 50 | 60 | 75 | [8 empty] | 500 | 2512 | 20 | 50240
19 | Sidewalk Removal | S.F. | 1450 |  |  | 2550 | 1900 | 2900 |  |  |  |  | 525 | 450 |  |  |  | 400 | 325 | 4075 | 5525 |  | 275 |  |  |  | 925 |  |  | 450 | 550 | 600 | [8 empty] | 1000 | 23900 | 2 | 47800
20 | Approach Pavement Removal | S.Y. |  |  |  | 79 | 14 | 183 | [11 empty] | 44 |  |  | 37 |  |  |  | 37 |  |  |  |  | 50 | [8 empty] | 50 | 494 | 40 | 19760
21 | Surface Removal, 2" | S.Y. | 1775 | 525 | 2300 | 2375 | 2650 | 4300 | 1800 | 5100 | 1625 | 700 | 875 | 6750 | 2600 | 1900 | 9100 | 1550 | 3250 | 2700 | 3775 | 1250 | 1150 | 1050 | 800 | 500 | 1350 | 850 | 125 | 1300 | 900 | 2800 | 1500 | 250 | 450 | 1850 | 950 | 2350 |  | 750 | 1000 | 76825 | 3 | 230475
22 | Surface Removal, 4.5" | S.Y. | [37 empty] | 1300 |  | 1300 | 5 | 6500
23 | Aggregate Shoulder | Tons | [36 empty] | 605 |  |  | 605 | 30 | 18150
24 | Pipe Underdrains, Type 3, 4" | L.F. | [36 empty] | 1300 |  |  | 1300 | 30 | 39000
25 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [5 empty] | 1 | [33 empty] | 1 | 300 | 300
26 | Manholes to be Adjusted | Each | 2 |  | 4 | 1 | 4 | 6 |  |  |  | 1 | 1 | 8 | 1 | 2 | 3 | 1 | 5 | 5 | 6 | 2 | 2 |  |  | 1 | 2 | 1 | 1 | 2 |  | 3 | 1 |  |  | 2 | 1 | 3 |  | 1 |  | 72 | 550 | 39600
27 | Manholes to be Adjusted with New Frame and Lid | Each |  |  |  |  | 2 | 1 | [10 empty] | 1 |  | 3 | 2 |  |  |  | 1 |  |  |  |  | 1 | 2 | [9 empty] | 13 | 800 | 10400
28 | Manholes to be Reconstructed | Each | [38 empty] | 1 | 1 | 1000 | 1000
29 | Manholes to be Reconstructed with New Frame and Lid | Each | [38 empty] | 1 | 1 | 1300 | 1300
30 | Inlets to be Adjusted | Each |  |  | 2 | 2 | 1 | [6 empty] | 3 |  |  | 1 |  |  | 1 | [7 empty] | 1 |  |  |  | 4 |  |  |  | 4 | [5 empty] | 19 | 1000 | 19000
31 | Inlets to be Adjusted with New Frame and Grate | Each |  |  |  |  | 1 | [20 empty] | 1 | [8 empty] | 1 |  |  |  |  | 3 | 1400 | 4200
32 | Inlets to be Reconstructed | Each | [38 empty] | 1 | 1 | 1500 | 1500
33 | Inlets to be Reconstructed with New Frame and Grate | Each | [38 empty] | 1 | 1 | 1900 | 1900
34 | Inlet Speicals to be Repaired | Each | [24 empty] | 1 | [14 empty] | 1 | 2200 | 2200
35 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 100 |  |  | 255 | 60 | 175 |  |  |  |  | 50 | 60 | 30 |  |  | 90 | 75 | 225 | 420 |  | 165 |  |  |  | 315 | 10 |  | 50 | 60 | 75 | [8 empty] | 500 | 2715 | 30 | 81450
36 | Traffic Control and Protection | Lsum | 0.03 | 0.01 | 0.02 | 0.03 | 0.03 | 0.05 | 0.01 | 0.03 | 0.01 | 0.01 | 0.01 | 0.06 | 0.02 | 0.02 | 0.07 | 0.02 | 0.03 | 0.04 | 0.06 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.2 | 0.03 |  | 1 | 50000 | 50000
37 | Thermoplastic Pavement Markings, 4" | L.F. | [36 empty] | 5420 |  |  | 5420 | 1.5 | 8130
38 | Thermoplastic Pavement Markings, 6" | L.F. | [18 empty] | 64 | [20 empty] | 64 | 2 | 128
39 | Thermoplastic Pavement Markings, 24" | L.F. | [5 empty] | 13 |  |  | 13 | [9 empty] | 14 | [17 empty] | 14 |  |  | 54 | 6 | 324
40 | Detector Loops | L.F. | [38 empty] | 50 | 50 | 30 | 1500
41 | Subgrade Undercutting | C.Y. | [36 empty] | 550 |  |  | 550 | 100 | 55000
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 58041 | 7976 | 34175 | 82216 | 64810 | 117863 | 23765 | 64610 | 21339 | 11030 | 21791 | 103015 | 38055 | 25725 | 119145 | 31805 | 55545 | 90225 | 134668 | 20750 | 34695 | 13590 | 10840 | 9245 | 52120 | 15575 | 3336 | 27945 | 24335 | 61230 | 21380 | 5075 | 7610 | 29270 | 15250 | 33485 | 383864 | 47540 | 92075 | #VALUE!
|  |  | 2725.668 | 318.309 | 1789.6038 | 3080.5236 | 3109.9967 | 5148.3531 | 848.824 | 3059.303 | 967.8951 | 549.3777 | 900.6965 | 5532.6817 | 1867.4127 | 1523.1674 | 6078.5227 | 1545.567 | 2792.8666 | 3852.7176 | 5755.498 | 1070.4613 | 1896.8858 | 738.0053 | 696.743 | 526.9782 | 2217.5526 | 745.0788 | 267.6153 | 1434.7483 | 1231.9737 | 2243.4889 | 1026.8412 | 308.8776 | 717.9636 | 1610.4077 | 826.4244 | 1611.5866 | 18862.7546 | 2593.6288 |  | 2015009
|  |  | 60766.668 | 8294.309 | 35964.6038 | 85296.5236 | 67919.9967 | 123011.3531 | 24613.824 | 67669.303 | 22306.8951 | 11579.3777 | 22691.6965 | 108547.6817 | 39922.4127 | 27248.1674 | 125223.5227 | 33350.567 | 58337.8666 | 94077.7176 | 140423.498 | 21820.4613 | 36591.8858 | 14328.0053 | 11536.743 | 9771.9782 | 54337.5526 | 16320.0788 | 3603.6153 | 29379.7483 | 25566.9737 | 63473.4889 | 22406.8412 | 5383.8776 | 8327.9636 | 30880.4077 | 16076.4244 | 35096.5866 | 402726.7546 | 50133.6288 |  | 2015009
|  |  | 57800 | 6750 | 37950 | 65325 | 65950 | 109175 | 18000 | 64875 | 20525 | 11650 | 19100 | 117325 | 39600 | 32300 | 128900 | 32775 | 59225 | 81700 | 122050 | 22700 | 40225 | 15650 | 14775 | 11175 | 47025 | 15800 | 5675 | 30425 | 26125 | 47575 | 21775 | 6550 | 15225 | 34150 | 17525 | 34175 | 400000 | 55000 | 0 | 1952525
#REF!
|  |  | 0.029603 | 0.0034571 | 0.019436 | 0.033457 | 0.033777 | 0.055915 | 0.0092188 | 0.033226 | 0.010512 | 0.0059666 | 0.0097822 | 0.060089 | 0.020281 | 0.016543 | 0.066017 | 0.016786 | 0.030333 | 0.041843 | 0.062509 | 0.011626 | 0.020602 | 0.0080153 | 0.0075671 | 0.0057234 | 0.024084 | 0.0080921 | 0.0029065 | 0.015582 | 0.01338 | 0.024366 | 0.011152 | 0.0033546 | 0.0077976 | 0.01749 | 0.0089756 | 0.017503 | 0.20486 | 0.028169 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Rock Road Companies |  | Curran Contracting |  | William Charles | [5 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Janesville, IL |  | Crystal Lake, IL |  | Rockford, IL | [5 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 3 - 2022 (Residential) | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond | [5 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 422-PW-036 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 2330 | 30 | 69900 | 27.77 | 64704.1 | 22 | 51260 | 27.12 | 63189.6 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 2330 | 30 | 69900 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 2330 | 30 | 69900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Geotechnical Fabric for Ground Stabilization | S.Y. | 3800 | 5 | 19000 | 2.83 | 10754 | 2.5 | 9500 | 1.37 | 5206 |  | 0 |  | 0 | 2 | Geotechnical Fabric for Ground Stabilization | S.Y. | 3800 | 5 | 19000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Geotechnical Fabric for Ground Stabilization | S.Y. | 3800 | 5 | 19000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Parkway Restoration | Lsum | 1 | 50000 | 50000 | 40000 | 40000 | 50000 | 50000 | 51641.57 | 51641.57 |  | 0 |  | 0 | 3 | Parkway Restoration | Lsum | 1 | 50000 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Parkway Restoration | Lsum | 1 | 50000 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Inlet and Pipe Protection | Each | 50 | 60 | 3000 | 75 | 3750 | 60 | 3000 | 75.8 | 3790 |  | 0 |  | 0 | 4 | Inlet and Pipe Protection | Each | 50 | 60 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Inlet and Pipe Protection | Each | 50 | 60 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Aggregate Subbase Improvement, CS-01, 9" | Tons | 1900 | 25 | 47500 | 21.71 | 41249 | 14.5 | 27550 | 16.28 | 30932 |  | 0 |  | 0 | 5 | Aggregate Subbase Improvement, CS-01, 9" | Tons | 1900 | 25 | 47500 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Aggregate Subbase Improvement, CS-01, 9" | Tons | 1900 | 25 | 47500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Aggregate Base Course, Type B, CA-6, 3" | Tons | 640 | 25 | 16000 | 23.99 | 15353.6 | 19.5 | 12480 | 19.1 | 12224 |  | 0 |  | 0 | 6 | Aggregate Base Course, Type B, CA-6, 3" | Tons | 640 | 25 | 16000 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate Base Course, Type B, CA-6, 3" | Tons | 640 | 25 | 16000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Aggregate Base Repair, 10" | S.Y. | 754 | 20 | 15080 | 0.01 | 7.54 | 20 | 15080 | 0.01 | 7.54 |  | 0 |  | 0 | 7 | Aggregate Base Repair, 10" | S.Y. | 754 | 20 | 15080 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Aggregate Base Repair, 10" | S.Y. | 754 | 20 | 15080 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Bituminous Materials (Prime Coat) | Gal | 7709 | 3 | 23127 | 0.01 | 77.09 | 2 | 15418 | 0.01 | 77.09 |  | 0 |  | 0 | 8 | Bituminous Materials (Prime Coat) | Gal | 7709 | 3 | 23127 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Bituminous Materials (Prime Coat) | Gal | 7709 | 3 | 23127 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Aggregate (Prime Coat) | Tons | 374 | 10 | 3740 | 0.01 | 3.74 | 0.01 | 3.74 | 0.01 | 3.74 |  | 0 |  | 0 | 9 | Aggregate (Prime Coat) | Tons | 374 | 10 | 3740 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Aggregate (Prime Coat) | Tons | 374 | 10 | 3740 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 225 | 75 | 16875 | 74 | 16650 | 72.5 | 16312.5 | 76 | 17100 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 225 | 75 | 16875 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 225 | 75 | 16875 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 950 | 75 | 71250 | 73 | 69350 | 69.5 | 66025 | 66.5 | 63175 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 950 | 75 | 71250 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 950 | 75 | 71250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 10525 | 75 | 789375 | 79.5 | 836737.5 | 77.5 | 815687.5 | 79 | 831475 |  | 0 |  | 0 | 12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 10525 | 75 | 789375 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 10525 | 75 | 789375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 | 76 | 760 | 200 | 2000 | 80 | 800 |  | 0 |  | 0 | 13 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | P.C.C. Approach Pavement, 6" | S.Y. | 313 | 60 | 18780 | 72.72 | 22761.36 | 90 | 28170 | 66.71 | 20880.23 |  | 0 |  | 0 | 14 | P.C.C. Approach Pavement, 6" | S.Y. | 313 | 60 | 18780 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Approach Pavement, 6" | S.Y. | 313 | 60 | 18780 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | P.C.C. Approach Pavement, 8" | S.Y. | 181 | 75 | 13575 | 84.84 | 15356.04 | 75 | 13575 | 79.84 | 14451.04 |  | 0 |  | 0 | 15 | P.C.C. Approach Pavement, 8" | S.Y. | 181 | 75 | 13575 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | P.C.C. Approach Pavement, 8" | S.Y. | 181 | 75 | 13575 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | P.C.C. Sidewalk, 4" | S.F. | 24950 | 6 | 149700 | 7.17 | 178891.5 | 7.5 | 187125 | 5.96 | 148702 |  | 0 |  | 0 | 16 | P.C.C. Sidewalk, 4" | S.F. | 24950 | 6 | 149700 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | P.C.C. Sidewalk, 4" | S.F. | 24950 | 6 | 149700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Detectable Warnings, ADA Ramps | S.F. | 610 | 25 | 15250 | 32.27 | 19684.7 | 30 | 18300 | 25.27 | 15414.7 |  | 0 |  | 0 | 17 | Detectable Warnings, ADA Ramps | S.F. | 610 | 25 | 15250 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Detectable Warnings, ADA Ramps | S.F. | 610 | 25 | 15250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Combination Curb and Gutter Removal | L.F. | 2512 | 20 | 50240 | 16.16 | 40593.92 | 15 | 37680 | 20.01 | 50265.12 |  | 0 |  | 0 | 18 | Combination Curb and Gutter Removal | L.F. | 2512 | 20 | 50240 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Combination Curb and Gutter Removal | L.F. | 2512 | 20 | 50240 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Sidewalk Removal | S.F. | 23900 | 2 | 47800 | 2.17 | 51863 | 2.25 | 53775 | 2.89 | 69071 |  | 0 |  | 0 | 19 | Sidewalk Removal | S.F. | 23900 | 2 | 47800 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Sidewalk Removal | S.F. | 23900 | 2 | 47800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Approach Pavement Removal | S.Y. | 494 | 40 | 19760 | 26.01 | 12848.94 | 20 | 9880 | 35.83 | 17700.02 |  | 0 |  | 0 | 20 | Approach Pavement Removal | S.Y. | 494 | 40 | 19760 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Approach Pavement Removal | S.Y. | 494 | 40 | 19760 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Surface Removal, 2" | S.Y. | 76825 | 3 | 230475 | 2.35 | 180538.75 | 2.55 | 195903.75 | 2.67 | 205122.75 |  | 0 |  | 0 | 21 | Surface Removal, 2" | S.Y. | 76825 | 3 | 230475 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Surface Removal, 2" | S.Y. | 76825 | 3 | 230475 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Surface Removal, 4.5" | S.Y. | 1300 | 5 | 6500 | 5.18 | 6734 | 4.5 | 5850 | 4.71 | 6123 |  | 0 |  | 0 | 22 | Surface Removal, 4.5" | S.Y. | 1300 | 5 | 6500 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Surface Removal, 4.5" | S.Y. | 1300 | 5 | 6500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Aggregate Shoulder | Tons | 605 | 30 | 18150 | 0.01 | 6.05 | 19 | 11495 | 0.01 | 6.05 |  | 0 |  | 0 | 23 | Aggregate Shoulder | Tons | 605 | 30 | 18150 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Aggregate Shoulder | Tons | 605 | 30 | 18150 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Pipe Underdrains, Type 3, 4" | L.F. | 1300 | 30 | 39000 | 19.55 | 25415 | 20 | 26000 | 27.91 | 36283 |  | 0 |  | 0 | 24 | Pipe Underdrains, Type 3, 4" | L.F. | 1300 | 30 | 39000 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Pipe Underdrains, Type 3, 4" | L.F. | 1300 | 30 | 39000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 1737077 |  | 1654089.83 |  | 1672070.49 |  | 1663640.45 | [5 empty] | Page 3 | Sub |  | As read | 1737077 | [9 empty] | Page 1 | Sub |  | As read | 1737077
| Award to Rock Road Companies | Total |  | As corrected | 1737077 |  | 1654089.83 |  | 1672070.49 |  | 1663640.45 | [5 empty] | Award to Rock Road Companies | Total |  | As corrected | 1737077 | [9 empty] | Award to Rock Road Companies | Total |  | As corrected | 1737077
25 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 300 | 300 | 469.65 | 469.65 | 400 | 400 | 574.67 | 574.67 |  | 0 |  | 0 | 25 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 300 | 300 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 300 | 300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Manholes to be Adjusted | Each | 72 | 550 | 39600 | 530.25 | 38178 | 725 | 52200 | 665.41 | 47909.52 |  | 0 |  | 0 | 26 | Manholes to be Adjusted | Each | 72 | 550 | 39600 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Manholes to be Adjusted | Each | 72 | 550 | 39600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Manholes to be Adjusted with New Frame and Lid | Each | 13 | 800 | 10400 | 977.68 | 12709.84 | 1200 | 15600 | 1025.23 | 13327.99 |  | 0 |  | 0 | 27 | Manholes to be Adjusted with New Frame and Lid | Each | 13 | 800 | 10400 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Manholes to be Adjusted with New Frame and Lid | Each | 13 | 800 | 10400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 | 1984.65 | 1984.65 | 1450 | 1450 | 1280.53 | 1280.53 |  | 0 |  | 0 | 28 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300 | 2377.54 | 2377.54 | 2200 | 2200 | 1640.33 | 1640.33 |  | 0 |  | 0 | 29 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Inlets to be Adjusted | Each | 19 | 1000 | 19000 | 1469.55 | 27921.45 | 1100 | 20900 | 1203.87 | 22873.53 |  | 0 |  | 0 | 30 | Inlets to be Adjusted | Each | 19 | 1000 | 19000 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Inlets to be Adjusted | Each | 19 | 1000 | 19000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Inlets to be Adjusted with New Frame and Grate | Each | 3 | 1400 | 4200 | 2124.03 | 6372.09 | 1950 | 5850 | 1743.89 | 5231.67 |  | 0 |  | 0 | 31 | Inlets to be Adjusted with New Frame and Grate | Each | 3 | 1400 | 4200 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Inlets to be Adjusted with New Frame and Grate | Each | 3 | 1400 | 4200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 | 2326.03 | 2326.03 | 1950 | 1950 | 1252.34 | 1252.34 |  | 0 |  | 0 | 32 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 1900 | 1900 | 2965.36 | 2965.36 | 2650 | 2650 | 1809.24 | 1809.24 |  | 0 |  | 0 | 33 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 1900 | 1900 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 1900 | 1900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | Inlet Speicals to be Repaired | Each | 1 | 2200 | 2200 | 3439.05 | 3439.05 | 2150 | 2150 | 2596.99 | 2596.99 |  | 0 |  | 0 | 34 | Inlet Speicals to be Repaired | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Inlet Speicals to be Repaired | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 2715 | 30 | 81450 | 44.89 | 121876.35 | 35 | 95025 | 34.36 | 93287.4 |  | 0 |  | 0 | 35 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 2715 | 30 | 81450 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 2715 | 30 | 81450 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | Traffic Control and Protection | Lsum | 1 | 50000 | 50000 | 34340 | 34340 | 65000 | 65000 | 101180 | 101180 |  | 0 |  | 0 | 36 | Traffic Control and Protection | Lsum | 1 | 50000 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 | 36 | Traffic Control and Protection | Lsum | 1 | 50000 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | Thermoplastic Pavement Markings, 4" | L.F. | 5420 | 1.5 | 8130 | 1 | 5420 | 1 | 5420 | 1.01 | 5474.2 |  | 0 |  | 0 | 37 | Thermoplastic Pavement Markings, 4" | L.F. | 5420 | 1.5 | 8130 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | Thermoplastic Pavement Markings, 4" | L.F. | 5420 | 1.5 | 8130 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | Thermoplastic Pavement Markings, 6" | L.F. | 64 | 2 | 128 | 1.5 | 96 | 1.5 | 96 | 1.52 | 97.28 |  | 0 |  | 0 | 38 | Thermoplastic Pavement Markings, 6" | L.F. | 64 | 2 | 128 |  | 0 |  | 0 |  | 0 |  | 0 | 38 | Thermoplastic Pavement Markings, 6" | L.F. | 64 | 2 | 128 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | Thermoplastic Pavement Markings, 24" | L.F. | 54 | 6 | 324 | 6 | 324 | 6 | 324 | 6.06 | 327.24 |  | 0 |  | 0 | 39 | Thermoplastic Pavement Markings, 24" | L.F. | 54 | 6 | 324 |  | 0 |  | 0 |  | 0 |  | 0 | 39 | Thermoplastic Pavement Markings, 24" | L.F. | 54 | 6 | 324 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | Detector Loops | L.F. | 50 | 30 | 1500 | 31.81 | 1590.5 | 31.5 | 1575 | 27.54 | 1377 |  | 0 |  | 0 | 40 | Detector Loops | L.F. | 50 | 30 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 40 | Detector Loops | L.F. | 50 | 30 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | Subgrade Undercutting | C.Y. | 550 | 100 | 55000 | 60.85 | 33467.5 | 38 | 20900 | 47.49 | 26119.5 |  | 0 |  | 0 | 41 | Subgrade Undercutting | C.Y. | 550 | 100 | 55000 |  | 0 |  | 0 |  | 0 |  | 0 | 41 | Subgrade Undercutting | C.Y. | 550 | 100 | 55000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 2015009 |  | 1949947.84 |  | 1965760.49 |  | 1989999.88 | [5 empty] | Page 4 | Total |  | As read | 2015009 | [9 empty] | Page 2 | Total |  | As read | 2015009
| Award to Rock Road Companies | Bid |  | As corrected |  |  | 1949947.84 | 0 | 1965760.49 | 0 | 1989999.88 | [5 empty] | Award to Rock Road Companies | Bid |  | As corrected | #VALUE! | [9 empty] | Award to Rock Road Companies | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Rock Road Companies | Bid |  | As corrected | [12 empty] | Award to Rock Road Companies | Bid |  | As corrected | [10 empty] | Award to Rock Road Companies | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Rock Road Companies | Bid |  | As corrected | [12 empty] | Award to Rock Road Companies | Bid |  | As corrected | [10 empty] | Award to Rock Road Companies | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 3 - 2022 (Residential)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 2330 |  | 0
2 | Geotechnical Fabric for Ground Stabilization | S.Y. | 3800 |  | 0
3 | Parkway Restoration | Lsum | 1 |  | 0
4 | Inlet and Pipe Protection | Each | 50 |  | 0
5 | Aggregate Subbase Improvement, CS-01, 9" | Tons | 1900 |  | 0
6 | Aggregate Base Course, Type B, CA-6, 3" | Tons | 640 |  | 0
7 | Aggregate Base Repair, 10" | S.Y. | 754 |  | 0
8 | Bituminous Materials (Prime Coat) | Gal | 7709 |  | 0
9 | Aggregate (Prime Coat) | Tons | 374 |  | 0
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 225 |  | 0
11 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 950 |  | 0
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 10525 |  | 0
13 | Hot-Mix Asphalt, Hand Method | Tons | 10 |  | 0
14 | P.C.C. Approach Pavement, 6" | S.Y. | 313 |  | 0
15 | P.C.C. Approach Pavement, 8" | S.Y. | 181 |  | 0
16 | P.C.C. Sidewalk, 4" | S.F. | 24950 |  | 0
17 | Detectable Warnings, ADA Ramps | S.F. | 610 |  | 0
18 | Combination Curb and Gutter Removal | L.F. | 2512 |  | 0
19 | Sidewalk Removal | S.F. | 23900 |  | 0
20 | Approach Pavement Removal | S.Y. | 494 |  | 0
21 | Surface Removal, 2" | S.Y. | 76825 |  | 0
22 | Surface Removal, 4.5" | S.Y. | 1300 |  | 0
23 | Aggregate Shoulder | Tons | 605 |  | 0
24 | Pipe Underdrains, Type 3, 4" | L.F. | 1300 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 |  | 0
26 | Manholes to be Adjusted | Each | 72 |  | 0
27 | Manholes to be Adjusted with New Frame and Lid | Each | 13 |  | 0
28 | Manholes to be Reconstructed | Each | 1 |  | 0
29 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 |  | 0
30 | Inlets to be Adjusted | Each | 19 |  | 0
31 | Inlets to be Adjusted with New Frame and Grate | Each | 3 |  | 0
32 | Inlets to be Reconstructed | Each | 1 |  | 0
33 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 |  | 0
34 | Inlet Speicals to be Repaired | Each | 1 |  | 0
35 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 2715
36 | Traffic Control and Protection | Lsum | 1
37 | Thermoplastic Pavement Markings, 4" | L.F. | 5420
38 | Thermoplastic Pavement Markings, 6" | L.F. | 64
39 | Thermoplastic Pavement Markings, 24" | L.F. | 54
40 | Detector Loops | L.F. | 50
41 | Subgrade Undercutting | C.Y. | 550
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2022 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 2330 | 30 | 69900
2 | Geotechnical Fabric for Ground Stabilization | S.Y. | 3800 | 5 | 19000
3 | Parkway Restoration | Lsum | 1 | 50000 | 50000
4 | Inlet and Pipe Protection | Each | 50 | 60 | 3000
5 | Aggregate Subbase Improvement, CS-01, 9" | Tons | 1900 | 25 | 47500
6 | Aggregate Base Course, Type B, CA-6, 3" | Tons | 640 | 25 | 16000
7 | Aggregate Base Repair, 10" | S.Y. | 754 | 20 | 15080
8 | Bituminous Materials (Prime Coat) | Gal | 7709 | 3 | 23127
9 | Aggregate (Prime Coat) | Tons | 374 | 10 | 3740
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 225 | 75 | 16875
11 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 950 | 75 | 71250
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 10525 | 75 | 789375
13 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000
14 | P.C.C. Approach Pavement, 6" | S.Y. | 313 | 60 | 18780
15 | P.C.C. Approach Pavement, 8" | S.Y. | 181 | 75 | 13575
16 | P.C.C. Sidewalk, 4" | S.F. | 24950 | 6 | 149700
17 | Detectable Warnings, ADA Ramps | S.F. | 610 | 25 | 15250
18 | Combination Curb and Gutter Removal | L.F. | 2512 | 20 | 50240
19 | Sidewalk Removal | S.F. | 23900 | 2 | 47800
20 | Approach Pavement Removal | S.Y. | 494 | 40 | 19760
21 | Surface Removal, 2" | S.Y. | 76825 | 3 | 230475
22 | Surface Removal, 4.5" | S.Y. | 1300 | 5 | 6500
23 | Aggregate Shoulder | Tons | 605 | 30 | 18150
24 | Pipe Underdrains, Type 3, 4" | L.F. | 1300 | 30 | 39000
|  |  |  | Sub Total | 1737077
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2022 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 300 | 300
26 | Manholes to be Adjusted | Each | 72 | 550 | 39600
27 | Manholes to be Adjusted with New Frame and Lid | Each | 13 | 800 | 10400
28 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000
29 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300
30 | Inlets to be Adjusted | Each | 19 | 1000 | 19000
31 | Inlets to be Adjusted with New Frame and Grate | Each | 3 | 1400 | 4200
32 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500
33 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 1900 | 1900
34 | Inlet Speicals to be Repaired | Each | 1 | 2200 | 2200
35 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 2715 | 30 | 81450
36 | Traffic Control and Protection | Lsum | 1 | 50000 | 50000
37 | Thermoplastic Pavement Markings, 4" | L.F. | 5420 | 1.5 | 8130
38 | Thermoplastic Pavement Markings, 6" | L.F. | 64 | 2 | 128
39 | Thermoplastic Pavement Markings, 24" | L.F. | 54 | 6 | 324
40 | Detector Loops | L.F. | 50 | 30 | 1500
41 | Subgrade Undercutting | C.Y. | 550 | 100 | 55000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2022 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2022 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | P.O. # 19305222 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: Janesville, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2022 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 2330 | C.Y. | 64704.1 |  |  |  |  | 27.77
2 | Geotechnical Fabric for Ground Stabilization | 3800 | S.Y. | 10754 |  |  |  |  | 2.83
3 | Parkway Restoration | 1 | Lsum | 40000 | 34 |  | 35 | Lsum | 40000 | 1400000
4 | Inlet and Pipe Protection | 50 | Each | 3750 |  |  |  |  | 75
5 | Aggregate Subbase Improvement, CS-01, 9" | 1900 | Tons | 41249 |  |  |  |  | 21.71
6 | Aggregate Base Course, Type B, CA-6, 3" | 640 | Tons | 15353.6 |  |  |  |  | 23.99
7 | Aggregate Base Repair, 10" | 754 | S.Y. | 7.54 |  |  |  |  | 0.01
8 | Bituminous Materials (Prime Coat) | 7709 | Gal | 77.09 |  |  |  |  | 0.01
9 | Aggregate (Prime Coat) | 374 | Tons | 3.74 |  |  |  |  | 0.01
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | 225 | Tons | 16650 | 1175 |  | 1400 | Tons | 74 | 103600
11 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | 950 | Tons | 69350 |  |  |  |  | 73
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 10525 | Tons | 836737.5 |  |  |  |  | 79.5
13 | Hot-Mix Asphalt, Hand Method | 10 | Tons | 760 | 2020 |  | 2030 | Tons | 76 | 154280
14 | P.C.C. Approach Pavement, 6" | 313 | S.Y. | 22761.36 |  |  |  |  | 72.72
15 | P.C.C. Approach Pavement, 8" | 181 | S.Y. | 15356.04 | 111 |  | 292 | S.Y. | 84.84 | 24773.28
16 | P.C.C. Sidewalk, 4" | 24950 | S.F. | 178891.5 |  |  |  |  | 7.17
17 | Detectable Warnings, ADA Ramps | 610 | S.F. | 19684.7 | 14484 |  | 15094 | S.F. | 32.27 | 487083.38
18 | Combination Curb and Gutter Removal | 2512 | L.F. | 40593.92 |  |  | 500 | L.F. | 16.16 | 8080
19 | Sidewalk Removal | 23900 | S.F. | 51863 |  |  | 1498 | S.F. | 2.17 | 3250.66
20 | Approach Pavement Removal | 494 | S.Y. | 12848.94 | 14750 |  | 15244 | S.Y. | 26.01 | 396496.44
21 | Surface Removal, 2" | 76825 | S.Y. | 180538.75 |  |  | 292 | S.Y. | 2.35 | 686.2
22 | Surface Removal, 4.5" | 1300 | S.Y. | 6734 |  |  |  |  | 5.18
23 | Aggregate Shoulder | 605 | Tons | 6.05 | 17600 |  | 18205 | Tons | 0.01 | 182.05
24 | Pipe Underdrains, Type 3, 4" | 1300 | L.F. | 25415 |  |  | 713 | L.F. | 19.55 | 13939.15
Sub Total |  |  |  | 1654089.83 | [5 empty] | 2592371.16
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2022 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each | 469.65 |  |  |  |  | 469.65
26 | Manholes to be Adjusted | 72 | Each | 38178 |  |  |  |  | 530.25
27 | Manholes to be Adjusted with New Frame and Lid | 13 | Each | 12709.84 |  |  |  |  | 977.68
28 | Manholes to be Reconstructed | 1 | Each | 1984.65 |  |  |  |  | 1984.65
29 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 2377.54 |  |  |  |  | 2377.54
30 | Inlets to be Adjusted | 19 | Each | 27921.45 |  |  | 10 | Each | 1469.55 | 14695.5
31 | Inlets to be Adjusted with New Frame and Grate | 3 | Each | 6372.09 |  |  |  |  | 2124.03
32 | Inlets to be Reconstructed | 1 | Each | 2326.03 |  |  |  |  | 2326.03
33 | Inlets to be Reconstructed with New Frame and Grate | 1 | Each | 2965.36 |  |  |  |  | 2965.36
34 | Inlet Speicals to be Repaired | 1 | Each | 3439.05 | 7 |  | 8 | Each | 3439.05 | 27512.4
35 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 2715 | L.F. | 121876.35 |  |  |  |  | 44.89
36 | Traffic Control and Protection | 1 | Lsum | 34340 |  |  |  |  | 34340
37 | Thermoplastic Pavement Markings, 4" | 5420 | L.F. | 5420 |  |  |  |  | 1
38 | Thermoplastic Pavement Markings, 6" | 64 | L.F. | 96 |  |  | 1 | L.F. | 1.5 | 1.5
39 | Thermoplastic Pavement Markings, 24" | 54 | L.F. | 324 | 1264 |  | 1318 | L.F. | 6 | 7908
40 | Detector Loops | 50 | L.F. | 1590.5 |  |  | 0.5 | L.F. | 31.81 | 15.905
41 | Subgrade Undercutting | 550 | C.Y. | 33467.5 |  |  |  |  | 60.85
Total |  |  |  | 1949947.84 | [5 empty] | 2642504.465
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 2642504.465
[8 empty] | DEDUCT RETAINAGE | 10% | 264250.4465
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 2378254.0185
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 2378254.0185
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2022 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 1949947.84 | [5 empty] | 2642504.465
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 2642504.465
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 2642504.465
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 2642504.465
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2022 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 1949947.84 | [5 empty] | 2642504.465
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 2642504.465
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 2642504.465
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 2642504.465
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Rock Road Companies
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.