## Item List
| City -Wide Street Repairs Group No. 4 - 2022 (Concrete) | [31 empty] | 2238395
Summary Of Quantities |  |  | 94003001 | 2nd Ward - 94003002 |  |  |  | 94003002 | 3rd Ward - 94003003 |  | 5th Ward - 94003005 |  | 94003005 | 94003007/94003013 | 94003008/94003010 | 9th Ward - 94003009 |  | 11th Ward - 94003011 |  |  |  | 94003012 | 13th Ward - 94003013 |  |  | 94003014 | W2211 | Neighborhood - W2211
No. | Item | Units | 1800 Plum Orchard Lane | 1717 2nd Avenue Curb and Gutter | 1500 Daisy Avenue Sidewalk | 1404 East State Street Curb | 306 North Rockford Avenue Sidewalk | 2305 Rural Street Drive Approach | 3731 Highcrest Road Sidewalk | 0100 North 3rd Street Sidewalk | 09001000 Sanford Street | 0500 South 3rd Street | 1400/1500 Harding Street Sidewalk | 0500 Furman Street | 1800 22nd Street | 2800 Conklin Drive | 3524-3704 Packard Parkway Sidewalk | 1600/1700 4th Street | 1428-1432 6th Avenue Sidewalk | 1315-1321 7th Avenue Sidewalk | 0300 Kishwaukee Street Sidewalk | 1100 Belmont Boulevard | 1200/1300 Andrews Street | 0500/0600 North Avon Sttreet | 0400 Orchard Park Street | Carter Court Approach | 1600/2000 7th Street | 2100 10th Street | 0600/0700 South 3rd Street | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. | [10 empty] | 34 |  |  | 215 | 55 | [13 empty] | 304 | 30 | 9120
2 | Parkway Restoration | Lsum | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.08 | 0.03 | 0.01 | 0.03 | 0.03 | 0.06 | 0.01 | 0.06 | 0.01 | 0.01 | 0.01 | 0.01 | 0.07 | 0.09 | 0.04 | 0 | 0.25 | 0.06 | 0.05 |  | 1 | 80000 | 80000
3 | Inlet and Pipe Protection | Each | 7 | [5 empty] | 1 |  | 7 | 2 | 1 | 9 | 4 | 7 | 3 | 9 |  |  |  |  | 8 | 5 | 2 |  | 35 | 4 | 3 |  | 107 | 60 | 6420
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | [13 empty] | 145 | [14 empty] | 145 | 25 | 3625
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | [13 empty] | 145 | [14 empty] | 145 | 25 | 3625
6 | Aggregate Base Repair, 10" | S.Y. | 9 | [7 empty] | 26 | 25 |  | 15 | 14 | 18 |  | 27 |  |  |  | 3 | 33 | 28 | 10 |  | 90 | 23 | 27 |  | 348 | 20 | 6960
7 | Bituminous Materials (Prime Coat) | Gal | 95 | [7 empty] | 260 | 250 |  | 150 | 140 | 222 |  | 272 |  |  |  | 37 | 330 | 282 | 105 |  | 900 | 230 | 275 |  | 3548 | 3 | 10644
8 | Aggregate (Prime Coat) | Tons | 5 | [7 empty] | 13 | 12 |  | 7 | 7 | 11 |  | 14 |  |  |  | 2 | 17 | 14 | 5 |  | 45 | 12 | 14 |  | 178 | 10 | 1780
9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | [27 empty] | 500 | 500 | 75 | 37500
10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | [13 empty] | 75 | [14 empty] | 75 | 75 | 5625
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 125 | [7 empty] | 325 | 300 |  | 200 | 175 | 275 |  | 350 |  |  |  | 50 | 400 | 350 | 150 |  | 1075 | 300 | 350 | 500 | 4925 | 75 | 369375
12 | Hot-Mix Asphalt, Hand Method | Tons |  | 4 |  | 8 | 2 | 3 |  | 3 | [5 empty] | 5 | 5 |  | 2 | 2 | 3 |  |  |  |  | 2 |  |  |  |  | 39 | 300 | 11700
13 | P.C.C. Approach Pavement, 6" | S.Y. | 46 | 12 |  |  | 18 | 26 | 40 |  | 101 | 56 |  | 72 | 63 | 85 | 20 | 106 | 18 | 22 |  | 22 | 111 | 174 | 50 | 20 | 154 | 52 | 98 | 50 | 1416 | 50 | 70800
14 | P.C.C. Approach Pavement, 8" | S.Y. | [8 empty] | 44 | [9 empty] | 15 | [5 empty] | 142 | 23 |  | 50 | 274 | 60 | 16440
15 | P.C.C. Sidewalk, 4" | S.F. | 350 | 250 | 550 |  | 400 | 200 | 325 | 900 | 7425 | 275 | 1750 | 3150 | 2925 | 1250 | 3000 | 5300 | 350 | 1000 | 1000 | 475 | 4075 | 7450 | 4050 | 150 | 14175 | 3825 | 4050 | 5000 | 73650 | 5 | 368250
16 | Detectable Warnings, ADA Ramps | S.F. | 20 | [7 empty] | 80 | 20 |  | 80 | 160 | 20 | 20 | 100 |  |  |  |  | 20 | 40 | 20 |  | 340 | 100 | 20 |  | 1040 | 20 | 20800
17 | Combination Curb and Gutter Removal | L.F. | 530 | 70 |  | 135 | 20 | 30 |  | 50 | 1425 | 850 |  | 585 | 585 | 880 | 50 | 1500 | 20 | 25 | 40 | 220 | 1595 | 1525 | 800 | 30 | 4025 | 1330 | 870 | 1000 | 18190 | 10 | 181900
18 | Sidewalk Removal | S.F. | 350 | 250 | 550 |  | 400 | 200 | 325 | 900 | 7425 | 275 |  | 3500 | 2925 | 1150 |  | 5350 | 350 | 1000 | 1000 | 475 | 4175 | 7550 | 4050 | 150 | 17825 | 3925 | 4050 | 5000 | 73150 | 2 | 146300
19 | Approach Pavement Removal | S.Y. | 46 | 12 |  |  | 18 | 26 | 40 |  | 145 | 56 |  | 72 | 63 | 111 | 20 | 118 | 18 | 22 | 15 | 22 | 154 | 174 | 50 |  | 348 | 75 | 120 | 100 | 1825 | 20 | 36500
20 | Surface Removal, 2" | S.Y. | 950 | [7 empty] | 2600 | 2500 |  | 1500 | 1400 | 1800 |  | 2725 |  |  |  | 375 | 3300 | 2825 | 1050 |  | 9000 | 2300 | 2750 | 1000 | 36075 | 3 | 108225
21 | Storm Sewers, PVC, 18" | L.F. | 150 | [27 empty] | 150 | 60 | 9000
22 | Storm Sewers, RCP, 12" | L.F. | [13 empty] | 60 | [14 empty] | 60 | 100 | 6000
23 | Storm Inlet, Type 700 | Each | [13 empty] | 2 | [14 empty] | 2 | 3000 | 6000
24 | Storm Inlet, Inlet Special No. 2 | Each | 1 | [27 empty] | 1 | 3000 | 3000
25 | Handhole to be Adjusted | Each | [24 empty] | 2 |  |  |  | 2 | 3000 | 6000
26 | Fiber Box to be Adjusted | Each | [24 empty] | 1 |  |  |  | 1 | 3000 | 3000
27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [9 empty] | 1 |  |  |  | 2 |  | 2 |  |  |  |  | 2 | 1 |  |  | 3 |  | 1 |  | 12 | 300 | 3600
28 | Manholes to be Adjusted | Each | 4 | [7 empty] | 4 | 5 |  | 3 | 5 | 3 |  | 3 |  |  |  |  | 6 | 6 | 3 |  | 17 | 6 | 3 |  | 68 | 550 | 37400
29 | Manholes to be Adjusted (AT&T Manholes) | Each | [24 empty] | 6 |  |  |  | 6 | 3000 | 18000
30 | Manholes to be Adjusted with New Frame and Lid | Each | [8 empty] | 4 |  |  |  | 1 | 1 | [6 empty] | 1 |  |  |  | 27 |  | 2 |  | 36 | 800 | 28800
31 | Manholes to be Reconstructed | Each | [11 empty] | 1 | [16 empty] | 1 | 1000 | 1000
32 | Manholes to be Reconstructed with New Frame and Lid | Each | [27 empty] | 1 | 1 | 1300 | 1300
33 | Inlets to be Adjusted | Each | [11 empty] | 2 | 2 | 1 |  | 2 |  |  |  |  | 3 | 2 |  |  | 20 |  |  |  | 32 | 1500 | 48000
34 | Inlets to be Adjusted with New Frame and Grate | Each | 1 | [10 empty] | 1 |  | 1 | [6 empty] | 2 | 3 | 2 |  | 5 | 1 | 2 |  | 18 | 1600 | 28800
35 | Inlets to be Reconstructed | Each | [27 empty] | 1 | 1 | 1500 | 1500
36 | Inlets to be Reconstructed with New Frame and Grate | Each | [8 empty] | 4 | [6 empty] | 4 |  |  |  |  | 1 |  |  |  |  | 3 |  |  | 12 | 1900 | 22800
37 | Inlet Special to be Repaired | Each | 2 | [12 empty] | 2 | [14 empty] | 4 | 2200 | 8800
38 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 530 | 70 |  | 135 | 20 | 30 |  | 50 | 1425 | 850 |  | 585 | 585 | 995 | 50 | 1500 | 20 | 25 | 40 | 220 | 1595 | 1525 | 800 | 30 | 4025 | 1330 | 870 | 1000 | 18305 | 25 | 457625
39 | Concrete "V" Gutter | L.F. | 35 | [27 empty] | 35 | 40 | 1400
40 | Traffic Control and Protection | Lsum | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.08 | 0.03 | 0.01 | 0.03 | 0.03 | 0.06 | 0.01 | 0.06 | 0.01 | 0.01 | 0.01 | 0.01 | 0.07 | 0.09 | 0.04 | 0 | 0.25 | 0.06 | 0.05 |  | 1 | 30000 | 30000
41 | Thermoplastic Pavement Markings, 4" | L.F. | [24 empty] | 530 |  |  |  | 530 | 2.5 | 1325
42 | Thermoplastic Pavement Markings, 6" | L.F. | [24 empty] | 664 |  |  |  | 664 | 4 | 2656
43 | Thermoplastic Pavement Markings, 24" | L.F. | [24 empty] | 150 |  |  |  | 150 | 12 | 1800
44 | Subgrade Undercutting | C.Y. | [27 empty] | 50 | 50 | 300 | 15000
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 61580 | 7340 | 4950 | 8225 | 6460 | 6270 | 6235 | 10050 | 169865 | 73835 | 10930 | 81275 | 76745 | 126651 | 22980 | 155271 | 6110 | 11115 | 11600 | 18731 | 157780 | 176576 | 84585 | 3700 | 522186 | 129115 | 114935 | 173300 | #VALUE!
|  |  | 4710.7298 | 674.6774 | 416.4181 | 786.79 | 544.5467 | 502.5045 | 532.5347 | 714.7176 | 14424.4827 | 6664.6916 | 1023.0272 | 6790.8182 | 5681.7047 | 10410.4525 | 1992 | 11996.0445 | 508.5106 | 936.9407 | 1001.005 | 1895.9036 | 12596.6475 | 15671.735 | 7507.5379 | 450.4523 | 44044.2221 | 10810.8545 | 10010.0505 |  | 2238395
|  |  | 66290.7298 | 8014.6774 | 5366.4181 | 9011.79 | 7004.5467 | 6772.5045 | 6767.5347 | 10764.7176 | 184289.4827 | 80499.6916 | 11953.0272 | 88065.8182 | 82426.7047 | 137061.4525 | 24972 | 167267.0445 | 6618.5106 | 12051.9407 | 12601.005 | 20626.9036 | 170376.6475 | 192247.735 | 92092.5379 | 4150.4523 | 566230.2221 | 139925.8545 | 124945.0505 |  | 2238395
|  |  | 58825 | 8425 | 5200 | 9825 | 6800 | 6275 | 6650 | 8925 | 180125 | 83225 | 12775 | 84800 | 70950 | 130000 | 24875 | 149800 | 6350 | 11700 | 12500 | 23675 | 157300 | 195700 | 93750 | 5625 | 550000 | 135000 | 125000 | 0 | 2164075
#REF!
|  |  | 0.027183 | 0.0038931 | 0.0024029 | 0.00454 | 0.0031422 | 0.0028996 | 0.0030729 | 0.0041242 | 0.083234 | 0.038458 | 0.0059032 | 0.039185 | 0.032785 | 0.060072 | 0.011495 | 0.069221 | 0.0029343 | 0.0054065 | 0.0057761 | 0.01094 | 0.072687 | 0.090431 | 0.043321 | 0.0025993 | 0.25415 | 0.062382 | 0.057761 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | TCI Concrete |  | Stenstrom Excavation | [7 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Rockford, IL |  | Rockford, IL | [7 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 4 - 2022 (Concrete) | [5 empty] | Bid Bond |  | Bid Bond | [7 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 621-PW-044 VENDORS NOTIFIED: 129 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 304 | 30 | 9120 | 250 | 76000 | 30 | 9120 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 304 | 30 | 9120 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 304 | 30 | 9120 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 80000 | 80000 | 76000 | 76000 | 167975 | 167975 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 80000 | 80000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 80000 | 80000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 107 | 60 | 6420 | 20 | 2140 | 75 | 8025 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 107 | 60 | 6420 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 107 | 60 | 6420 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 145 | 25 | 3625 | 20 | 2900 | 21 | 3045 |  | 0 |  | 0 |  | 0 | 4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 145 | 25 | 3625 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 145 | 25 | 3625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 145 | 25 | 3625 | 20 | 2900 | 23 | 3335 |  | 0 |  | 0 |  | 0 | 5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 145 | 25 | 3625 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 145 | 25 | 3625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Aggregate Base Repair, 10" | S.Y. | 348 | 20 | 6960 | 31 | 10788 | 22 | 7656 |  | 0 |  | 0 |  | 0 | 6 | Aggregate Base Repair, 10" | S.Y. | 348 | 20 | 6960 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate Base Repair, 10" | S.Y. | 348 | 20 | 6960 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Bituminous Materials (Prime Coat) | Gal | 3548 | 3 | 10644 | 0.01 | 35.48 | 0.01 | 35.48 |  | 0 |  | 0 |  | 0 | 7 | Bituminous Materials (Prime Coat) | Gal | 3548 | 3 | 10644 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Bituminous Materials (Prime Coat) | Gal | 3548 | 3 | 10644 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Aggregate (Prime Coat) | Tons | 178 | 10 | 1780 | 0.01 | 1.78 | 0.01 | 1.78 |  | 0 |  | 0 |  | 0 | 8 | Aggregate (Prime Coat) | Tons | 178 | 10 | 1780 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Aggregate (Prime Coat) | Tons | 178 | 10 | 1780 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 75 | 75 | 5625 | 98 | 7350 | 98 | 7350 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 500 | 75 | 5625 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 500 | 75 | 5625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 75 | 37500 | 80.27 | 40135 | 80.27 | 40135 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 75 | 75 | 37500 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 75 | 75 | 37500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 4925 | 75 | 369375 | 82.25 | 405081.25 | 82.25 | 405081.25 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 4925 | 75 | 369375 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 4925 | 75 | 369375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | Hot-Mix Asphalt, Hand Method | Tons | 39 | 300 | 11700 | 600 | 23400 | 200 | 7800 |  | 0 |  | 0 |  | 0 | 12 | Hot-Mix Asphalt, Hand Method | Tons | 39 | 300 | 11700 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | Hot-Mix Asphalt, Hand Method | Tons | 39 | 300 | 11700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | P.C.C. Approach Pavement, 6" | S.Y. | 1416 | 50 | 70800 | 55 | 77880 | 100 | 141600 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 6" | S.Y. | 1416 | 50 | 70800 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 6" | S.Y. | 1416 | 50 | 70800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | P.C.C. Approach Pavement, 8" | S.Y. | 274 | 60 | 16440 | 60 | 16440 | 120 | 32880 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Approach Pavement, 8" | S.Y. | 274 | 60 | 16440 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Approach Pavement, 8" | S.Y. | 274 | 60 | 16440 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | P.C.C. Sidewalk, 4" | S.F. | 73650 | 5 | 368250 | 7.5 | 552375 | 10 | 736500 |  | 0 |  | 0 |  | 0 | 15 | P.C.C. Sidewalk, 4" | S.F. | 73650 | 5 | 368250 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | P.C.C. Sidewalk, 4" | S.F. | 73650 | 5 | 368250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Detectable Warnings, ADA Ramps | S.F. | 1040 | 20 | 20800 | 14 | 14560 | 32.75 | 34060 |  | 0 |  | 0 |  | 0 | 16 | Detectable Warnings, ADA Ramps | S.F. | 1040 | 20 | 20800 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Detectable Warnings, ADA Ramps | S.F. | 1040 | 20 | 20800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Combination Curb and Gutter Removal | L.F. | 18190 | 10 | 181900 | 14 | 254660 | 17.6 | 320144 |  | 0 |  | 0 |  | 0 | 17 | Combination Curb and Gutter Removal | L.F. | 18190 | 10 | 181900 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Combination Curb and Gutter Removal | L.F. | 18190 | 10 | 181900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Sidewalk Removal | S.F. | 73150 | 2 | 146300 | 1.75 | 128012.5 | 2.8 | 204820 |  | 0 |  | 0 |  | 0 | 18 | Sidewalk Removal | S.F. | 73150 | 2 | 146300 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Sidewalk Removal | S.F. | 73150 | 2 | 146300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Approach Pavement Removal | S.Y. | 1825 | 20 | 36500 | 17 | 31025 | 28 | 51100 |  | 0 |  | 0 |  | 0 | 19 | Approach Pavement Removal | S.Y. | 1825 | 20 | 36500 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Approach Pavement Removal | S.Y. | 1825 | 20 | 36500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Surface Removal, 2" | S.Y. | 36075 | 3 | 108225 | 3.08 | 111111 | 3.08 | 111111 |  | 0 |  | 0 |  | 0 | 20 | Surface Removal, 2" | S.Y. | 36075 | 3 | 108225 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Surface Removal, 2" | S.Y. | 36075 | 3 | 108225 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Storm Sewers, PVC, 18" | L.F. | 150 | 60 | 9000 | 30 | 4500 | 110 | 16500 |  | 0 |  | 0 |  | 0 | 21 | Storm Sewers, PVC, 18" | L.F. | 150 | 60 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Storm Sewers, PVC, 18" | L.F. | 150 | 60 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Storm Sewers, RCP, 12" | L.F. | 60 | 100 | 6000 | 25 | 1500 | 95 | 5700 |  | 0 |  | 0 |  | 0 | 22 | Storm Sewers, RCP, 12" | L.F. | 60 | 100 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Storm Sewers, RCP, 12" | L.F. | 60 | 100 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Storm Inlet, Type 700 | Each | 2 | 3000 | 6000 | 1000 | 2000 | 1950 | 3900 |  | 0 |  | 0 |  | 0 | 23 | Storm Inlet, Type 700 | Each | 2 | 3000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Storm Inlet, Type 700 | Each | 2 | 3000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Storm Inlet, Inlet Special No. 2 | Each | 1 | 3000 | 3000 | 1000 | 1000 | 3200 | 3200 |  | 0 |  | 0 |  | 0 | 24 | Storm Inlet, Inlet Special No. 2 | Each | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Storm Inlet, Inlet Special No. 2 | Each | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 1519589 |  | 1841795.01 |  | 2321074.51 | [7 empty] | Page 3 | Sub |  | As read | 1519589 | [9 empty] | Page 1 | Sub |  | As read | 1519589
| Award to TCI Concrete | Total |  | As corrected | 1519589 |  | 1841795.01 |  | 2321074.51 | [7 empty] | Award to TCI Concrete | Total |  | As corrected | 1519589 | [9 empty] | Award to TCI Concrete | Total |  | As corrected | 1519589
25 | Handhole to be Adjusted | Each | 2 | 3000 | 6000 | 350 | 700 | 3435 | 6870 |  | 0 |  | 0 |  | 0 | 25 | Handhole to be Adjusted | Each | 2 | 3000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Handhole to be Adjusted | Each | 2 | 3000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Fiber Box to be Adjusted | Each | 1 | 3000 | 3000 | 200 | 200 | 2935 | 2935 |  | 0 |  | 0 |  | 0 | 26 | Fiber Box to be Adjusted | Each | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Fiber Box to be Adjusted | Each | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 12 | 300 | 3600 | 175 | 2100 | 480 | 5760 |  | 0 |  | 0 |  | 0 | 27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 12 | 300 | 3600 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 12 | 300 | 3600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Manholes to be Adjusted | Each | 68 | 550 | 37400 | 250 | 17000 | 800 | 54400 |  | 0 |  | 0 |  | 0 | 28 | Manholes to be Adjusted | Each | 68 | 550 | 37400 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Manholes to be Adjusted | Each | 68 | 550 | 37400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Manholes to be Adjusted (AT&T Manholes) | Each | 6 | 3000 | 18000 | 250 | 1500 | 1400 | 8400 |  | 0 |  | 0 |  | 0 | 29 | Manholes to be Adjusted (AT&T Manholes) | Each | 6 | 3000 | 18000 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Manholes to be Adjusted (AT&T Manholes) | Each | 6 | 3000 | 18000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Manholes to be Adjusted with New Frame and Lid | Each | 36 | 800 | 28800 | 1200 | 43200 | 1100 | 39600 |  | 0 |  | 0 |  | 0 | 30 | Manholes to be Adjusted with New Frame and Lid | Each | 36 | 800 | 28800 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Manholes to be Adjusted with New Frame and Lid | Each | 36 | 800 | 28800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 | 425 | 425 | 1320 | 1320 |  | 0 |  | 0 |  | 0 | 31 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300 | 1800 | 1800 | 1700 | 1700 |  | 0 |  | 0 |  | 0 | 32 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Inlets to be Adjusted | Each | 32 | 1500 | 48000 | 750 | 24000 | 1200 | 38400 |  | 0 |  | 0 |  | 0 | 33 | Inlets to be Adjusted | Each | 32 | 1500 | 48000 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Inlets to be Adjusted | Each | 32 | 1500 | 48000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | Inlets to be Adjusted with New Frame and Grate | Each | 18 | 1600 | 28800 | 500 | 9000 | 1700 | 30600 |  | 0 |  | 0 |  | 0 | 34 | Inlets to be Adjusted with New Frame and Grate | Each | 18 | 1600 | 28800 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Inlets to be Adjusted with New Frame and Grate | Each | 18 | 1600 | 28800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 | 600 | 600 | 1400 | 1400 |  | 0 |  | 0 |  | 0 | 35 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | Inlets to be Reconstructed with New Frame and Grate | Each | 12 | 1900 | 22800 | 800 | 9600 | 1900 | 22800 |  | 0 |  | 0 |  | 0 | 36 | Inlets to be Reconstructed with New Frame and Grate | Each | 12 | 1900 | 22800 |  | 0 |  | 0 |  | 0 |  | 0 | 36 | Inlets to be Reconstructed with New Frame and Grate | Each | 12 | 1900 | 22800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | Inlet Special to be Repaired | Each | 4 | 2200 | 8800 | 1000 | 4000 | 1320 | 5280 |  | 0 |  | 0 |  | 0 | 37 | Inlet Special to be Repaired | Each | 4 | 2200 | 8800 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | Inlet Special to be Repaired | Each | 4 | 2200 | 8800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 18305 | 25 | 457625 | 25 | 457625 | 36.5 | 668132.5 |  | 0 |  | 0 |  | 0 | 38 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 18305 | 25 | 457625 |  | 0 |  | 0 |  | 0 |  | 0 | 38 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 18305 | 25 | 457625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | Concrete "V" Gutter | L.F. | 35 | 40 | 1400 | 125 | 4375 | 60 | 2100 |  | 0 |  | 0 |  | 0 | 39 | Concrete "V" Gutter | L.F. | 35 | 40 | 1400 |  | 0 |  | 0 |  | 0 |  | 0 | 39 | Concrete "V" Gutter | L.F. | 35 | 40 | 1400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | Traffic Control and Protection | Lsum | 1 | 30000 | 30000 | 5000 | 5000 | 33500.79 | 33500.79 |  | 0 |  | 0 |  | 0 | 40 | Traffic Control and Protection | Lsum | 1 | 30000 | 30000 |  | 0 |  | 0 |  | 0 |  | 0 | 40 | Traffic Control and Protection | Lsum | 1 | 30000 | 30000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | Thermoplastic Pavement Markings, 4" | L.F. | 530 | 2.5 | 1325 | 1.7 | 901 | 1.7 | 901 |  | 0 |  | 0 |  | 0 | 41 | Thermoplastic Pavement Markings, 4" | L.F. | 530 | 2.5 | 1325 |  | 0 |  | 0 |  | 0 |  | 0 | 41 | Thermoplastic Pavement Markings, 4" | L.F. | 530 | 2.5 | 1325 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
42 | Thermoplastic Pavement Markings, 6" | L.F. | 664 | 4 | 2656 | 2.55 | 1693.2 | 2.55 | 1693.2 |  | 0 |  | 0 |  | 0 | 42 | Thermoplastic Pavement Markings, 6" | L.F. | 664 | 4 | 2656 |  | 0 |  | 0 |  | 0 |  | 0 | 42 | Thermoplastic Pavement Markings, 6" | L.F. | 664 | 4 | 2656 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
43 | Thermoplastic Pavement Markings, 24" | L.F. | 150 | 12 | 1800 | 10.2 | 1530 | 10.2 | 1530 |  | 0 |  | 0 |  | 0 | 43 | Thermoplastic Pavement Markings, 24" | L.F. | 150 | 12 | 1800 |  | 0 |  | 0 |  | 0 |  | 0 | 43 | Thermoplastic Pavement Markings, 24" | L.F. | 150 | 12 | 1800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
44 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000 | 350 | 17500 | 30 | 1500 |  | 0 |  | 0 |  | 0 | 44 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 | 44 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 2238395 |  | 2444544.21 |  | 3249897 | [7 empty] | Page 4 | Total |  | As read | 2238395 | [9 empty] | Page 2 | Total |  | As read | 2238395
| Award to TCI Concrete | Bid |  | As corrected |  |  | 2444544.21 | 0 | 3249897 | 0 | [6 empty] | Award to TCI Concrete | Bid |  | As corrected | #VALUE! | [9 empty] | Award to TCI Concrete | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to TCI Concrete | Bid |  | As corrected | [12 empty] | Award to TCI Concrete | Bid |  | As corrected | [10 empty] | Award to TCI Concrete | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to TCI Concrete | Bid |  | As corrected | [12 empty] | Award to TCI Concrete | Bid |  | As corrected | [10 empty] | Award to TCI Concrete | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 4 - 2022 (Concrete)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 304 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 107 |  | 0
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 145 |  | 0
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 145 |  | 0
6 | Aggregate Base Repair, 10" | S.Y. | 348 |  | 0
7 | Bituminous Materials (Prime Coat) | Gal | 3548 |  | 0
8 | Aggregate (Prime Coat) | Tons | 178 |  | 0
9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 75 |  | 0
10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 |  | 0
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 4925 |  | 0
12 | Hot-Mix Asphalt, Hand Method | Tons | 39 |  | 0
13 | P.C.C. Approach Pavement, 6" | S.Y. | 1416 |  | 0
14 | P.C.C. Approach Pavement, 8" | S.Y. | 274 |  | 0
15 | P.C.C. Sidewalk, 4" | S.F. | 73650 |  | 0
16 | Detectable Warnings, ADA Ramps | S.F. | 1040 |  | 0
17 | Combination Curb and Gutter Removal | L.F. | 18190 |  | 0
18 | Sidewalk Removal | S.F. | 73150 |  | 0
19 | Approach Pavement Removal | S.Y. | 1825 |  | 0
20 | Surface Removal, 2" | S.Y. | 36075 |  | 0
21 | Storm Sewers, PVC, 18" | L.F. | 150 |  | 0
22 | Storm Sewers, RCP, 12" | L.F. | 60 |  | 0
23 | Storm Inlet, Type 700 | Each | 2 |  | 0
24 | Storm Inlet, Inlet Special No. 2 | Each | 1 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Handhole to be Adjusted | Each | 2 |  | 0
26 | Fiber Box to be Adjusted | Each | 1 |  | 0
27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 12 |  | 0
28 | Manholes to be Adjusted | Each | 68 |  | 0
29 | Manholes to be Adjusted (AT&T Manholes) | Each | 6 |  | 0
30 | Manholes to be Adjusted with New Frame and Lid | Each | 36 |  | 0
31 | Manholes to be Reconstructed | Each | 1 |  | 0
32 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 |  | 0
33 | Inlets to be Adjusted | Each | 32 |  | 0
34 | Inlets to be Adjusted with New Frame and Grate | Each | 18 |  | 0
35 | Inlets to be Reconstructed | Each | 1
36 | Inlets to be Reconstructed with New Frame and Grate | Each | 12
37 | Inlet Special to be Repaired | Each | 4
38 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 18305
39 | Concrete "V" Gutter | L.F. | 35
40 | Traffic Control and Protection | Lsum | 1
41 | Thermoplastic Pavement Markings, 4" | L.F. | 530
42 | Thermoplastic Pavement Markings, 6" | L.F. | 664
43 | Thermoplastic Pavement Markings, 24" | L.F. | 150
44 | Subgrade Undercutting | C.Y. | 50
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2022 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 304 | 30 | 9120
2 | Parkway Restoration | Lsum | 1 | 80000 | 80000
3 | Inlet and Pipe Protection | Each | 107 | 60 | 6420
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 145 | 25 | 3625
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 145 | 25 | 3625
6 | Aggregate Base Repair, 10" | S.Y. | 348 | 20 | 6960
7 | Bituminous Materials (Prime Coat) | Gal | 3548 | 3 | 10644
8 | Aggregate (Prime Coat) | Tons | 178 | 10 | 1780
9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 75 | 75 | 5625
10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 75 | 37500
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 4925 | 75 | 369375
12 | Hot-Mix Asphalt, Hand Method | Tons | 39 | 300 | 11700
13 | P.C.C. Approach Pavement, 6" | S.Y. | 1416 | 50 | 70800
14 | P.C.C. Approach Pavement, 8" | S.Y. | 274 | 60 | 16440
15 | P.C.C. Sidewalk, 4" | S.F. | 73650 | 5 | 368250
16 | Detectable Warnings, ADA Ramps | S.F. | 1040 | 20 | 20800
17 | Combination Curb and Gutter Removal | L.F. | 18190 | 10 | 181900
18 | Sidewalk Removal | S.F. | 73150 | 2 | 146300
19 | Approach Pavement Removal | S.Y. | 1825 | 20 | 36500
20 | Surface Removal, 2" | S.Y. | 36075 | 3 | 108225
21 | Storm Sewers, PVC, 18" | L.F. | 150 | 60 | 9000
22 | Storm Sewers, RCP, 12" | L.F. | 60 | 100 | 6000
23 | Storm Inlet, Type 700 | Each | 2 | 3000 | 6000
24 | Storm Inlet, Inlet Special No. 2 | Each | 1 | 3000 | 3000
|  |  |  | Sub Total | 1519589
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2022 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Handhole to be Adjusted | Each | 2 | 3000 | 6000
26 | Fiber Box to be Adjusted | Each | 1 | 3000 | 3000
27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 12 | 300 | 3600
28 | Manholes to be Adjusted | Each | 68 | 550 | 37400
29 | Manholes to be Adjusted (AT&T Manholes) | Each | 6 | 3000 | 18000
30 | Manholes to be Adjusted with New Frame and Lid | Each | 36 | 800 | 28800
31 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000
32 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300
33 | Inlets to be Adjusted | Each | 32 | 1500 | 48000
34 | Inlets to be Adjusted with New Frame and Grate | Each | 18 | 1600 | 28800
35 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500
36 | Inlets to be Reconstructed with New Frame and Grate | Each | 12 | 1900 | 22800
37 | Inlet Special to be Repaired | Each | 4 | 2200 | 8800
38 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 18305 | 25 | 457625
39 | Concrete "V" Gutter | L.F. | 35 | 40 | 1400
40 | Traffic Control and Protection | Lsum | 1 | 30000 | 30000
41 | Thermoplastic Pavement Markings, 4" | L.F. | 530 | 2.5 | 1325
42 | Thermoplastic Pavement Markings, 6" | L.F. | 664 | 4 | 2656
43 | Thermoplastic Pavement Markings, 24" | L.F. | 150 | 12 | 1800
44 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2022 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2022 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 28th, 2019 | [7 empty] | (Road District)
| Payable to: TCI Concrete | P.O. # 19305224 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2022 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 304 | C.Y. | 76000 |  |  |  |  | 250
2 | Parkway Restoration | 1 | Lsum | 76000 |  |  |  |  | 76000
3 | Inlet and Pipe Protection | 107 | Each | 2140 |  |  |  |  | 20
4 | Subbase Granular Material, Type B, CA-2, 6" | 145 | Tons | 2900 |  |  |  |  | 20
5 | Aggregate Base Course, Type B, CA-6, 6" | 145 | Tons | 2900 |  |  |  |  | 20
6 | Aggregate Base Repair, 10" | 348 | S.Y. | 10788 |  |  |  |  | 31
7 | Bituminous Materials (Prime Coat) | 3548 | Gal | 35.48 |  |  |  |  | 0.01
8 | Aggregate (Prime Coat) | 178 | Tons | 1.78 |  |  |  |  | 0.01
9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | 75 | Tons | 7350 |  |  |  |  | 98
10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | 500 | Tons | 40135 |  |  |  |  | 80.27
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 4925 | Tons | 405081.25 |  |  |  |  | 82.25
12 | Hot-Mix Asphalt, Hand Method | 39 | Tons | 23400 |  |  |  |  | 600
13 | P.C.C. Approach Pavement, 6" | 1416 | S.Y. | 77880 |  |  |  |  | 55
14 | P.C.C. Approach Pavement, 8" | 274 | S.Y. | 16440 |  |  |  |  | 60
15 | P.C.C. Sidewalk, 4" | 73650 | S.F. | 552375 |  |  |  |  | 7.5
16 | Detectable Warnings, ADA Ramps | 1040 | S.F. | 14560 |  |  |  |  | 14
17 | Combination Curb and Gutter Removal | 18190 | L.F. | 254660 |  |  |  |  | 14
18 | Sidewalk Removal | 73150 | S.F. | 128012.5 |  |  |  |  | 1.75
19 | Approach Pavement Removal | 1825 | S.Y. | 31025 |  |  |  |  | 17
20 | Surface Removal, 2" | 36075 | S.Y. | 111111 |  |  |  |  | 3.08
21 | Storm Sewers, PVC, 18" | 150 | L.F. | 4500 |  |  |  |  | 30
22 | Storm Sewers, RCP, 12" | 60 | L.F. | 1500 |  |  |  |  | 25
23 | Storm Inlet, Type 700 | 2 | Each | 2000 |  |  |  |  | 1000
24 | Storm Inlet, Inlet Special No. 2 | 1 | Each | 1000 |  |  |  |  | 1000
Sub Total |  |  |  | 1841795.01 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 28th, 2019 | [7 empty] | (Road District)
| Payable to: TCI Concrete | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2022 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Handhole to be Adjusted | 2 | Each | 700 |  |  |  |  | 350
26 | Fiber Box to be Adjusted | 1 | Each | 200 |  |  |  |  | 200
27 | Sanitary Riser/Valve Boxes to be Adjusted | 12 | Each | 2100 |  |  |  |  | 175
28 | Manholes to be Adjusted | 68 | Each | 17000 |  |  |  |  | 250
29 | Manholes to be Adjusted (AT&T Manholes) | 6 | Each | 1500 |  |  |  |  | 250
30 | Manholes to be Adjusted with New Frame and Lid | 36 | Each | 43200 |  |  |  |  | 1200
31 | Manholes to be Reconstructed | 1 | Each | 425 |  |  |  |  | 425
32 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 1800 |  |  |  |  | 1800
33 | Inlets to be Adjusted | 32 | Each | 24000 |  |  |  |  | 750
34 | Inlets to be Adjusted with New Frame and Grate | 18 | Each | 9000 |  |  |  |  | 500
35 | Inlets to be Reconstructed | 1 | Each | 600 |  |  |  |  | 600
36 | Inlets to be Reconstructed with New Frame and Grate | 12 | Each | 9600 |  |  |  |  | 800
37 | Inlet Special to be Repaired | 4 | Each | 4000 |  |  |  |  | 1000
38 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 18305 | L.F. | 457625 |  |  |  |  | 25
39 | Concrete "V" Gutter | 35 | L.F. | 4375 |  |  |  |  | 125
40 | Traffic Control and Protection | 1 | Lsum | 5000 |  |  |  |  | 5000
41 | Thermoplastic Pavement Markings, 4" | 530 | L.F. | 901 |  |  |  |  | 1.7
42 | Thermoplastic Pavement Markings, 6" | 664 | L.F. | 1693.2 |  |  |  |  | 2.55
43 | Thermoplastic Pavement Markings, 24" | 150 | L.F. | 1530 |  |  |  |  | 10.2
44 | Subgrade Undercutting | 50 | C.Y. | 17500 |  |  |  |  | 350
Total |  |  |  | 2444544.21 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
[8 empty] | DEDUCT RETAINAGE | 10% | 0
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 28th, 2019 | [7 empty] | (Road District)
| Payable to: TCI Concrete | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2022 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 2444544.21 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 28th, 2019 | [7 empty] | (Road District)
| Payable to: TCI Concrete | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2022 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 2444544.21 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | TCI Concrete
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.