## Item List
| City -Wide Street Repairs Group No. 5 - (2022) Parking Lots | [13 empty] | 1560703
Summary Of Quantities |  |  | City Parking Fund |  |  |  | City Yards | Fire Department Fund
No. | Item | Units | Parking Lot No. 9 | Parking Lot No. 20 | Parking Lot No. 22 | Church Parking Lot | City Yards Parking Lot | Fire Station No. 1 Parking Lot | Fire Station No. 5 Parking Lot | Fire Station No. 6 Parking Lot | Fire Station No. 9 Parking Lot | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. |  |  |  |  | 40 |  | 470 | 2425 | 650 |  | 3585 | 30 | 107550
2 | Parkway Restoration | Lsum | 0 | 0.05 | 0.1 | 0.05 | 0 | 0 | 0.1 | 0.5 | 0.2 |  | 1 | 10000 | 10000
3 | Inlet and Pipe Protection | Each | 6 | 3 | 1 | 2 | 4 | 1 | 2 |  | 5 |  | 24 | 100 | 2400
4 | Aggregate Base Course, Type B, CA-2, 6" | Tons | [6 empty] | 335 | 1450 | 320 |  | 2105 | 25 | 52625
5 | Aggregate Base Course, Type B, CA-6, 6" | S.Y. | [6 empty] | 335 | 1850 | 320 |  | 2505 | 25 | 62625
6 | Aggregate Base Repair, 10" | S.Y. | 56 | 27 | 10 | 6 | 127 | 10 |  |  |  |  | 236 | 20 | 4720
7 | Bituminous Materials (Prime Coat) | Gal | 560 | 270 | 95 | 60 | 1275 | 95 |  |  |  |  | 2355 | 3 | 7065
8 | Aggregate (Prime Coat) | Tons | 56 | 27 | 10 | 6 | 127 | 10 |  |  |  |  | 236 | 10 | 2360
9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | [6 empty] | 250 | 125 | 250 |  | 625 | 115 | 71875
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | [7 empty] | 850 |  |  | 850 | 115 | 97750
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | [6 empty] | 100 |  | 125 |  | 225 | 115 | 25875
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 675 | 325 | 125 | 75 | 1550 | 125 |  | 525 | 25 | 500 | 3925 | 115 | 451375
13 | Hot-Mix Asphalt, Hand Method | Tons |  |  |  | 5 |  |  | 10 |  | 15 |  | 30 | 300 | 9000
14 | P.C.C. Approach Pavement, 8" | S.Y. | 9 | 40 | 45 | 59 |  | 16 | 57 | 150 | 31 | 50 | 457 | 75 | 34275
15 | P.C.C. Approach Pavement, 10" | S.Y. |  |  |  |  | 334 | 100 | 234 | 210 | 228 | 50 | 1156 | 80 | 92480
16 | P.C.C. Sidewalk, 4" | S.F. |  | 675 |  | 450 | 625 | 200 | 3100 | 2700 | 1825 | 1000 | 10575 | 8 | 84600
17 | P.C.C. Sidewalk, 10" | S.F. | [6 empty] | 400 |  | 275 |  | 675 | 15 | 10125
18 | Combination Curb and Gutter Removal | L.F. |  | 650 |  | 65 |  |  | 90 |  | 165 |  | 970 | 20 | 19400
19 | Sidewalk Removal | S.F. |  | 675 |  | 450 | 425 | 200 | 2300 | 725 | 2100 | 1000 | 7875 | 2 | 15750
20 | Approach Pavement Removal | S.Y. | 9 | 40 | 45 | 59 | 334 | 116 | 291 |  | 287 | 100 | 1281 | 30 | 38430
21 | Surface Removal, 2" | S.Y. | 5600 | 2700 | 950 | 600 | 12900 | 950 |  |  | 150 | 1000 | 24850 | 4 | 99400
22 | Storm Sewers, PVC, 6" | L.F. | [5 empty] | 18 | 46 |  |  |  | 64 | 60 | 3840
23 | Storm Sewers, PVC, 10" | L.F. | [5 empty] | 79 | 58 |  |  |  | 137 | 80 | 10960
24 | Storm Sewers, RCP, 10" | L.F. | [8 empty] | 90 |  | 90 | 100 | 9000
25 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each |  |  |  |  | 4 | 2 | 1 |  | 2 |  | 9 | 5000 | 45000
26 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [9 empty] | 1 | 1 | 500 | 500
27 | Manholes to be Adjusted | Each |  |  | 1 | [5 empty] | 2 |  | 3 | 800 | 2400
28 | Manholes to be Adjusted with Concrete Square | Each |  |  |  | 2 | [6 empty] | 2 | 2000 | 4000
29 | Inlets to be Adjusted | Each |  | 2 |  |  | 2 | [5 empty] | 4 | 1500 | 6000
30 | Inlets to be Adjusted with New Frame and Grate or Lid | Each |  |  |  |  | 2 |  |  |  |  | 1 | 3 | 2000 | 6000
31 | Combination Concrete Curb and Gutter, Type M-6.12 (Modified) | L.F. |  | 650 |  |  |  |  | 35 |  | 50 |  | 735 | 30 | 22050
32 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. |  |  |  | 65 | 310 |  | 90 | 1135 | 165 |  | 1765 | 30 | 52950
33 | Traffic Control and Protection | LSum | 0.08 | 0.07 | 0.02 | 0.03 | 0.22 | 0.04 | 0.1 | 0.34 | 0.1 |  | 1 | 5000 | 5000
34 | Paint Pavement Markings, 4" | L.F. |  |  |  | 2694 |  |  | 360 |  | 135 |  | 3189 | 2 | 6378
35 | Thermoplastic Pavement Markings, 4" | L.F. | 2778 | 1732 | 719 |  | 4703 | 324 | 360 |  | 419 |  | 11035 | 2 | 22070
36 | Accessible Parking Symbol Striping | Each | 4 | 6 | 2 | 6 | 4 | 1 | 1 |  | 1 |  | 25 | 200 | 5000
37 | Connect to Existing Down Spout | Each | [5 empty] | 3 | 2 |  |  |  | 5 | 500 | 2500
38 | Connect to Existing Storm Sewer | Each | [5 empty] | 1 | 1 |  |  |  | 2 | 500 | 1000
39 | Furnish and Install RAP | Tons | [7 empty] | 375 |  |  | 375 | 15 | 5625
40 | Regrade Millings | S.Y. | [7 empty] | 1250 |  |  | 1250 | 3 | 3750
41 | Subgrade Undercutting | C.Y. | [9 empty] | 50 | 50 | 100 | 5000
42 | Non-Special Waste Disposal (Fire Station No. 6) | C.Y. | [7 empty] | 200 |  |  | 200 | 60 | 12000
43 | Special Waste Disposal (Fire Station No. 6) | C.Y. | [7 empty] | 200 |  |  | 200 | 50 | 10000
44 | Soil Disposal Analysis (Fire Station No. 6) | Each | [7 empty] | 10 |  |  | 10 | 1500 | 15000
45 | Special Waste Plans and Reports (Special) (Fire Station No. 6) | LSum | [7 empty] | 1 |  |  | 1 | 5000 | 5000
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 111686 | 102059 | 27323 | 38268 | 329281 | 53988 | 164015 | 470975 | 173358 | 89750 | #VALUE!
|  |  | 7045.3034 | 6269.1259 | 1504.5902 | 2388.2384 | 20897.0862 | 3880.8874 | 8955.8941 | 29852.9803 | 8955.8941 |  | 1560703
|  |  | 118731.3034 | 108328.1259 | 28827.5902 | 40656.2384 | 350178.0862 | 57868.8874 | 172970.8941 | 500827.9803 | 182313.8941 |  | 1560703
|  |  | 118000 | 105000 | 25200 | 40000 | 350000 | 65000 | 150000 | 500000 | 150000 | 0 | 1503200
#REF!
|  |  | 0.078499 | 0.069851 | 0.016764 | 0.02661 | 0.23284 | 0.043241 | 0.099787 | 0.33262 | 0.099787 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Norwest Construction |  | Stenstrom Excavation |  | N-TRAK Group |  | Wiliam Charles Construction Co. Inc |  |  |  | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | South Beloit, IL |  | Rockford, IL |  | Loves Park, IL |  | Rockford, IL |  |  |  | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 5 - 2022 (Parking Lots) | [15 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 622-PW-056 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 3585 | 30 | 107550 | 33 | 118305 | 30.25 | 108446.25 | 25 | 89625 | 36 | 129060 |  | 0 | 1 | Earth Excavation | C.Y. | 3585 | 30 | 107550 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 3585 | 30 | 107550 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 | 30940 | 30940 | 29908 | 29908 | 20000 | 20000 | 25000 | 25000 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 24 | 100 | 2400 | 89 | 2136 | 80 | 1920 | 75 | 1800 | 75.82 | 1819.68 |  | 0 | 3 | Inlet and Pipe Protection | Each | 24 | 100 | 2400 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 24 | 100 | 2400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Aggregate Base Course, Type B, CA-2, 6" | Tons | 2105 | 25 | 52625 | 38.4 | 80832 | 28 | 58940 | 24 | 50520 | 21.97 | 46246.85 |  | 0 | 4 | Aggregate Base Course, Type B, CA-2, 6" | Tons | 2105 | 25 | 52625 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Course, Type B, CA-2, 6" | Tons | 2105 | 25 | 52625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Aggregate Base Course, Type B, CA-6, 6" | S.Y. | 2505 | 25 | 62625 | 22 | 55110 | 32 | 80160 | 10 | 25050 | 8.1 | 20290.5 |  | 0 | 5 | Aggregate Base Course, Type B, CA-6, 6" | S.Y. | 2505 | 25 | 62625 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Aggregate Base Course, Type B, CA-6, 6" | S.Y. | 2505 | 25 | 62625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Aggregate Base Repair, 10" | S.Y. | 236 | 20 | 4720 | 24 | 5664 | 22 | 5192 | 20 | 4720 | 32.06 | 7566.16 |  | 0 | 6 | Aggregate Base Repair, 10" | S.Y. | 236 | 20 | 4720 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate Base Repair, 10" | S.Y. | 236 | 20 | 4720 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Bituminous Materials (Prime Coat) | Gal | 2355 | 3 | 7065 | 0.1 | 235.5 | 1.95 | 4592.25 | 4 | 9420 | 5 | 11775 |  | 0 | 7 | Bituminous Materials (Prime Coat) | Gal | 2355 | 3 | 7065 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Bituminous Materials (Prime Coat) | Gal | 2355 | 3 | 7065 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Aggregate (Prime Coat) | Tons | 236 | 10 | 2360 | 0.1 | 23.6 | 0.01 | 2.36 | 0.01 | 2.36 | 0.01 | 2.36 |  | 0 | 8 | Aggregate (Prime Coat) | Tons | 236 | 10 | 2360 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Aggregate (Prime Coat) | Tons | 236 | 10 | 2360 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 625 | 115 | 71875 | 120.75 | 75468.75 | 102.5 | 64062.5 | 105 | 65625 | 95.2 | 59500 |  | 0 | 9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 625 | 115 | 71875 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 625 | 115 | 71875 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 850 | 115 | 97750 | 120.75 | 102637.5 | 95.25 | 80962.5 | 78 | 66300 | 78.4 | 66640 |  | 0 | 10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 850 | 115 | 97750 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 850 | 115 | 97750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 225 | 115 | 25875 | 120.75 | 27168.75 | 113.25 | 25481.25 | 128 | 28800 | 111.2 | 25020 |  | 0 | 11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 225 | 115 | 25875 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 225 | 115 | 25875 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3925 | 115 | 451375 | 120.75 | 473943.75 | 101.5 | 398387.5 | 92 | 361100 | 95.75 | 375818.75 |  | 0 | 12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3925 | 115 | 451375 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3925 | 115 | 451375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | Hot-Mix Asphalt, Hand Method | Tons | 30 | 300 | 9000 | 450 | 13500 | 133.5 | 4005 | 350 | 10500 | 0.01 | 0.3 |  | 0 | 13 | Hot-Mix Asphalt, Hand Method | Tons | 30 | 300 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | Hot-Mix Asphalt, Hand Method | Tons | 30 | 300 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | P.C.C. Approach Pavement, 8" | S.Y. | 457 | 75 | 34275 | 129 | 58953 | 86 | 39302 | 86 | 39302 | 83.14 | 37994.98 |  | 0 | 14 | P.C.C. Approach Pavement, 8" | S.Y. | 457 | 75 | 34275 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Approach Pavement, 8" | S.Y. | 457 | 75 | 34275 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | P.C.C. Approach Pavement, 10" | S.Y. | 1156 | 80 | 92480 | 134 | 154904 | 90 | 104040 | 95 | 109820 | 89.54 | 103508.24 |  | 0 | 15 | P.C.C. Approach Pavement, 10" | S.Y. | 1156 | 80 | 92480 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | P.C.C. Approach Pavement, 10" | S.Y. | 1156 | 80 | 92480 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | P.C.C. Sidewalk, 4" | S.F. | 10575 | 8 | 84600 | 10 | 105750 | 8 | 84600 | 8 | 84600 | 7.2 | 76140 |  | 0 | 16 | P.C.C. Sidewalk, 4" | S.F. | 10575 | 8 | 84600 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | P.C.C. Sidewalk, 4" | S.F. | 10575 | 8 | 84600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | P.C.C. Sidewalk, 10" | S.F. | 675 | 15 | 10125 | 16 | 10800 | 11.25 | 7593.75 | 18 | 12150 | 9.97 | 6729.75 |  | 0 | 17 | P.C.C. Sidewalk, 10" | S.F. | 675 | 15 | 10125 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | P.C.C. Sidewalk, 10" | S.F. | 675 | 15 | 10125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Combination Curb and Gutter Removal | L.F. | 970 | 20 | 19400 | 11 | 10670 | 17.25 | 16732.5 | 10 | 9700 | 28.12 | 27276.4 |  | 0 | 18 | Combination Curb and Gutter Removal | L.F. | 970 | 20 | 19400 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Combination Curb and Gutter Removal | L.F. | 970 | 20 | 19400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Sidewalk Removal | S.F. | 7875 | 2 | 15750 | 2 | 15750 | 3 | 23625 | 3 | 23625 | 3.24 | 25515 |  | 0 | 19 | Sidewalk Removal | S.F. | 7875 | 2 | 15750 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Sidewalk Removal | S.F. | 7875 | 2 | 15750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Approach Pavement Removal | S.Y. | 1281 | 30 | 38430 | 15 | 19215 | 27.75 | 35547.75 | 20 | 25620 | 29.45 | 37725.45 |  | 0 | 20 | Approach Pavement Removal | S.Y. | 1281 | 30 | 38430 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Approach Pavement Removal | S.Y. | 1281 | 30 | 38430 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Surface Removal, 2" | S.Y. | 24850 | 4 | 99400 | 5.81 | 144378.5 | 3.95 | 98157.5 | 4.5 | 111825 | 3.59 | 89211.5 |  | 0 | 21 | Surface Removal, 2" | S.Y. | 24850 | 4 | 99400 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Surface Removal, 2" | S.Y. | 24850 | 4 | 99400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Storm Sewers, PVC, 6" | L.F. | 64 | 60 | 3840 | 101 | 6464 | 99 | 6336 | 98 | 6272 | 123.43 | 7899.52 |  | 0 | 22 | Storm Sewers, PVC, 6" | L.F. | 64 | 60 | 3840 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Storm Sewers, PVC, 6" | L.F. | 64 | 60 | 3840 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Storm Sewers, PVC, 10" | L.F. | 137 | 80 | 10960 | 101 | 13837 | 105.75 | 14487.75 | 98 | 13426 | 74.17 | 10161.29 |  | 0 | 23 | Storm Sewers, PVC, 10" | L.F. | 137 | 80 | 10960 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Storm Sewers, PVC, 10" | L.F. | 137 | 80 | 10960 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Storm Sewers, RCP, 10" | L.F. | 90 | 100 | 9000 | 97 | 8730 | 140.75 | 12667.5 | 130 | 11700 | 94.47 | 8502.3 |  | 0 | 24 | Storm Sewers, RCP, 10" | L.F. | 90 | 100 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Storm Sewers, RCP, 10" | L.F. | 90 | 100 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 1323480 |  | 1535416.35 |  | 1305149.36 |  | 1181502.36 |  | 1199404.03 |  |  |  | Page 3 | Sub |  | As read | 1323480 | [9 empty] | Page 1 | Sub |  | As read | 1323480
| Award to N-TRAK Group | Total |  | As corrected | 1323480 |  | 1535416.35 |  | 1305149.36 |  | 1181502.36 |  | 1199404.03 |  |  |  | Award to Norwest Construction | Total |  | As corrected | 1323480 | [9 empty] | Award to Norwest Construction | Total |  | As corrected | 1323480
25 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 9 | 5000 | 45000 | 4579.8 | 41218.2 | 4275 | 38475 | 3500 | 31500 | 5008.93 | 45080.37 |  | 0 | 25 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 9 | 5000 | 45000 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 9 | 5000 | 45000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 | 330 | 330 | 470 | 470 | 500 | 500 | 580.44 | 580.44 |  | 0 | 26 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Manholes to be Adjusted | Each | 3 | 800 | 2400 | 1311 | 3933 | 1100 | 3300 | 1100 | 3300 | 1271.02 | 3813.06 |  | 0 | 27 | Manholes to be Adjusted | Each | 3 | 800 | 2400 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Manholes to be Adjusted | Each | 3 | 800 | 2400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Manholes to be Adjusted with Concrete Square | Each | 2 | 2000 | 4000 | 1989 | 3978 | 1750 | 3500 | 2000 | 4000 | 1920.04 | 3840.08 |  | 0 | 28 | Manholes to be Adjusted with Concrete Square | Each | 2 | 2000 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Manholes to be Adjusted with Concrete Square | Each | 2 | 2000 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Inlets to be Adjusted | Each | 4 | 1500 | 6000 | 1803 | 7212 | 1645 | 6580 | 1400 | 5600 | 1802.26 | 7209.04 |  | 0 | 29 | Inlets to be Adjusted | Each | 4 | 1500 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Inlets to be Adjusted | Each | 4 | 1500 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Inlets to be Adjusted with New Frame and Grate or Lid | Each | 3 | 2000 | 6000 | 2079 | 6237 | 2320 | 6960 | 2100 | 6300 | 2480.9 | 7442.7 |  | 0 | 30 | Inlets to be Adjusted with New Frame and Grate or Lid | Each | 3 | 2000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Inlets to be Adjusted with New Frame and Grate or Lid | Each | 3 | 2000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Combination Concrete Curb and Gutter, Type M-6.12 (Modified) | L.F. | 735 | 30 | 22050 | 39 | 28665 | 42.25 | 31053.75 | 43 | 31605 | 30.91 | 22718.85 |  | 0 | 31 | Combination Concrete Curb and Gutter, Type M-6.12 (Modified) | L.F. | 735 | 30 | 22050 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Combination Concrete Curb and Gutter, Type M-6.12 (Modified) | L.F. | 735 | 30 | 22050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 1765 | 30 | 52950 | 45 | 79425 | 34.75 | 61333.75 | 38 | 67070 | 33.04 | 58315.6 |  | 0 | 32 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 1765 | 30 | 52950 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 1765 | 30 | 52950 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Traffic Control and Protection | LSum | 1 | 5000 | 5000 | 13630 | 13630 | 24400 | 24400 | 70000 | 70000 | 65000 | 65000 |  | 0 | 33 | Traffic Control and Protection | LSum | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Traffic Control and Protection | LSum | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | Paint Pavement Markings, 4" | L.F. | 3189 | 2 | 6378 | 2 | 6378 | 1.4 | 4464.6 | 1.2 | 3826.8 | 1.21 | 3858.69 |  | 0 | 34 | Paint Pavement Markings, 4" | L.F. | 3189 | 2 | 6378 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Paint Pavement Markings, 4" | L.F. | 3189 | 2 | 6378 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | Thermoplastic Pavement Markings, 4" | L.F. | 11035 | 2 | 22070 | 2 | 22070 | 1.4 | 15449 | 1.3 | 14345.5 | 1.31 | 14455.85 |  | 0 | 35 | Thermoplastic Pavement Markings, 4" | L.F. | 11035 | 2 | 22070 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Thermoplastic Pavement Markings, 4" | L.F. | 11035 | 2 | 22070 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | Accessible Parking Symbol Striping | Each | 25 | 200 | 5000 | 296 | 7400 | 310 | 7750 | 290 | 7250 | 293.16 | 7329 |  | 0 | 36 | Accessible Parking Symbol Striping | Each | 25 | 200 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 | 36 | Accessible Parking Symbol Striping | Each | 25 | 200 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | Connect to Existing Down Spout | Each | 5 | 500 | 2500 | 850 | 4250 | 1370 | 6850 | 450 | 2250 | 542.27 | 2711.35 |  | 0 | 37 | Connect to Existing Down Spout | Each | 5 | 500 | 2500 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | Connect to Existing Down Spout | Each | 5 | 500 | 2500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | Connect to Existing Storm Sewer | Each | 2 | 500 | 1000 | 1650 | 3300 | 1154 | 2308 | 1500 | 3000 | 546.53 | 1093.06 |  | 0 | 38 | Connect to Existing Storm Sewer | Each | 2 | 500 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 38 | Connect to Existing Storm Sewer | Each | 2 | 500 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | Furnish and Install RAP | Tons | 375 | 15 | 5625 | 40 | 15000 | 30 | 11250 | 23 | 8625 | 21.28 | 7980 |  | 0 | 39 | Furnish and Install RAP | Tons | 375 | 15 | 5625 |  | 0 |  | 0 |  | 0 |  | 0 | 39 | Furnish and Install RAP | Tons | 375 | 15 | 5625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | Regrade Millings | S.Y. | 1250 | 3 | 3750 | 2 | 2500 | 3.15 | 3937.5 | 1.5 | 1875 | 1.21 | 1512.5 |  | 0 | 40 | Regrade Millings | S.Y. | 1250 | 3 | 3750 |  | 0 |  | 0 |  | 0 |  | 0 | 40 | Regrade Millings | S.Y. | 1250 | 3 | 3750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | Subgrade Undercutting | C.Y. | 50 | 100 | 5000 | 140 | 7000 | 76.5 | 3825 | 60 | 3000 | 101 | 5050 |  | 0 | 41 | Subgrade Undercutting | C.Y. | 50 | 100 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 | 41 | Subgrade Undercutting | C.Y. | 50 | 100 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
42 | Non-Special Waste Disposal (Fire Station No. 6) | C.Y. | 200 | 60 | 12000 | 85 | 17000 | 110.5 | 22100 | 0.01 | 2 | 34 | 6800 |  | 0 | 42 | Non-Special Waste Disposal (Fire Station No. 6) | C.Y. | 200 | 60 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 | 42 | Non-Special Waste Disposal (Fire Station No. 6) | C.Y. | 200 | 60 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
43 | Special Waste Disposal (Fire Station No. 6) | C.Y. | 200 | 50 | 10000 | 133 | 26600 | 115 | 23000 | 0.01 | 2 | 34 | 6800 |  | 0 | 43 | Special Waste Disposal (Fire Station No. 6) | C.Y. | 200 | 50 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 43 | Special Waste Disposal (Fire Station No. 6) | C.Y. | 200 | 50 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
44 | Soil Disposal Analysis (Fire Station No. 6) | Each | 10 | 1500 | 15000 | 1377 | 13770 | 1445 | 14450 | 0.01 | 0.1 | 100 | 1000 |  | 0 | 44 | Soil Disposal Analysis (Fire Station No. 6) | Each | 10 | 1500 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 | 44 | Soil Disposal Analysis (Fire Station No. 6) | Each | 10 | 1500 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
45 | Special Waste Plans and Reports (Special) (Fire Station No. 6) | LSum | 1 | 5000 | 5000 | 8264 | 8264 | 3450 | 3450 | 0.01 | 0.01 | 3200 | 3200 |  | 0 | 45 | Special Waste Plans and Reports (Special) (Fire Station No. 6) | LSum | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 | 45 | Special Waste Plans and Reports (Special) (Fire Station No. 6) | LSum | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 | 1760046.55 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 1560703 |  | 1853576.55 |  | 1600055.96 |  | 1445553.77 |  | 1475194.62 |  |  |  | Page 4 | Total |  | As read | 1560703 | [9 empty] | Page 2 | Total |  | As read | 1560703
| Award to N-TRAK Group | Bid |  | As corrected |  |  | 1853576.55 | 0 | 1600055.96 | 0 | 1445553.77 |  | 1475194.62 |  |  |  | Award to Norwest Construction | Bid |  | As corrected | #VALUE! | [9 empty] | Award to Norwest Construction | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Norwest Construction | Bid |  | As corrected | [12 empty] | Award to Norwest Construction | Bid |  | As corrected | [10 empty] | Award to Norwest Construction | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Norwest Construction | Bid |  | As corrected | [12 empty] | Award to Norwest Construction | Bid |  | As corrected | [10 empty] | Award to Norwest Construction | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 5 - 2022 (Parking Lots)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 3585 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 24 |  | 0
4 | Aggregate Base Course, Type B, CA-2, 6" | Tons | 2105 |  | 0
5 | Aggregate Base Course, Type B, CA-6, 6" | S.Y. | 2505 |  | 0
6 | Aggregate Base Repair, 10" | S.Y. | 236 |  | 0
7 | Bituminous Materials (Prime Coat) | Gal | 2355 |  | 0
8 | Aggregate (Prime Coat) | Tons | 236 |  | 0
9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 625 |  | 0
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 850 |  | 0
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 225 |  | 0
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3925 |  | 0
13 | Hot-Mix Asphalt, Hand Method | Tons | 30 |  | 0
14 | P.C.C. Approach Pavement, 8" | S.Y. | 457 |  | 0
15 | P.C.C. Approach Pavement, 10" | S.Y. | 1156 |  | 0
16 | P.C.C. Sidewalk, 4" | S.F. | 10575 |  | 0
17 | P.C.C. Sidewalk, 10" | S.F. | 675 |  | 0
18 | Combination Curb and Gutter Removal | L.F. | 970 |  | 0
19 | Sidewalk Removal | S.F. | 7875 |  | 0
20 | Approach Pavement Removal | S.Y. | 1281 |  | 0
21 | Surface Removal, 2" | S.Y. | 24850 |  | 0
22 | Storm Sewers, PVC, 6" | L.F. | 64 |  | 0
23 | Storm Sewers, PVC, 10" | L.F. | 137 |  | 0
24 | Storm Sewers, RCP, 10" | L.F. | 90 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 9 |  | 0
26 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1
27 | Manholes to be Adjusted | Each | 3
28 | Manholes to be Adjusted with Concrete Square | Each | 2
29 | Inlets to be Adjusted | Each | 4
30 | Inlets to be Adjusted with New Frame and Grate or Lid | Each | 3
31 | Combination Concrete Curb and Gutter, Type M-6.12 (Modified) | L.F. | 735
32 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 1765
33 | Traffic Control and Protection | LSum | 1
34 | Paint Pavement Markings, 4" | L.F. | 3189
35 | Thermoplastic Pavement Markings, 4" | L.F. | 11035
36 | Accessible Parking Symbol Striping | Each | 25
37 | Connect to Existing Down Spout | Each | 5
38 | Connect to Existing Storm Sewer | Each | 2
39 | Furnish and Install RAP | Tons | 375
40 | Regrade Millings | S.Y. | 1250
41 | Subgrade Undercutting | C.Y. | 50
42 | Non-Special Waste Disposal (Fire Station No. 6) | C.Y. | 200
43 | Special Waste Disposal (Fire Station No. 6) | C.Y. | 200
44 | Soil Disposal Analysis (Fire Station No. 6) | Each | 10
45 | Special Waste Plans and Reports (Special) (Fire Station No. 6) | LSum | 1
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 5 - 2022 (Parking Lots)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 3585 | 30 | 107550
2 | Parkway Restoration | Lsum | 1 | 10000 | 10000
3 | Inlet and Pipe Protection | Each | 24 | 100 | 2400
4 | Aggregate Base Course, Type B, CA-2, 6" | Tons | 2105 | 25 | 52625
5 | Aggregate Base Course, Type B, CA-6, 6" | S.Y. | 2505 | 25 | 62625
6 | Aggregate Base Repair, 10" | S.Y. | 236 | 20 | 4720
7 | Bituminous Materials (Prime Coat) | Gal | 2355 | 3 | 7065
8 | Aggregate (Prime Coat) | Tons | 236 | 10 | 2360
9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 625 | 115 | 71875
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 850 | 115 | 97750
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 225 | 115 | 25875
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3925 | 115 | 451375
13 | Hot-Mix Asphalt, Hand Method | Tons | 30 | 300 | 9000
14 | P.C.C. Approach Pavement, 8" | S.Y. | 457 | 75 | 34275
15 | P.C.C. Approach Pavement, 10" | S.Y. | 1156 | 80 | 92480
16 | P.C.C. Sidewalk, 4" | S.F. | 10575 | 8 | 84600
17 | P.C.C. Sidewalk, 10" | S.F. | 675 | 15 | 10125
18 | Combination Curb and Gutter Removal | L.F. | 970 | 20 | 19400
19 | Sidewalk Removal | S.F. | 7875 | 2 | 15750
20 | Approach Pavement Removal | S.Y. | 1281 | 30 | 38430
21 | Surface Removal, 2" | S.Y. | 24850 | 4 | 99400
22 | Storm Sewers, PVC, 6" | L.F. | 64 | 60 | 3840
23 | Storm Sewers, PVC, 10" | L.F. | 137 | 80 | 10960
24 | Storm Sewers, RCP, 10" | L.F. | 90 | 100 | 9000
|  |  |  | Sub Total | 1323480
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 5 - 2022 (Parking Lots)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 9 | 5000 | 45000
26 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500
27 | Manholes to be Adjusted | Each | 3 | 800 | 2400
28 | Manholes to be Adjusted with Concrete Square | Each | 2 | 2000 | 4000
29 | Inlets to be Adjusted | Each | 4 | 1500 | 6000
30 | Inlets to be Adjusted with New Frame and Grate or Lid | Each | 3 | 2000 | 6000
31 | Combination Concrete Curb and Gutter, Type M-6.12 (Modified) | L.F. | 735 | 30 | 22050
32 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 1765 | 30 | 52950
33 | Traffic Control and Protection | LSum | 1 | 5000 | 5000
34 | Paint Pavement Markings, 4" | L.F. | 3189 | 2 | 6378
35 | Thermoplastic Pavement Markings, 4" | L.F. | 11035 | 2 | 22070
36 | Accessible Parking Symbol Striping | Each | 25 | 200 | 5000
37 | Connect to Existing Down Spout | Each | 5 | 500 | 2500
38 | Connect to Existing Storm Sewer | Each | 2 | 500 | 1000
39 | Furnish and Install RAP | Tons | 375 | 15 | 5625
40 | Regrade Millings | S.Y. | 1250 | 3 | 3750
41 | Subgrade Undercutting | C.Y. | 50 | 100 | 5000
42 | Non-Special Waste Disposal (Fire Station No. 6) | C.Y. | 200 | 60 | 12000
43 | Special Waste Disposal (Fire Station No. 6) | C.Y. | 200 | 50 | 10000
44 | Soil Disposal Analysis (Fire Station No. 6) | Each | 10 | 1500 | 15000
45 | Special Waste Plans and Reports (Special) (Fire Station No. 6) | LSum | 1 | 5000 | 5000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 5 - 2022 (Parking Lots)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 5 - 2022 (Parking Lots)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | P.O. #18305125 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 5 - 2022 (Parking Lots)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 3585 | C.Y. | 118305 |  |  |  |  | 33
2 | Parkway Restoration | 1 | Lsum | 30940 |  |  |  |  | 30940
3 | Inlet and Pipe Protection | 24 | Each | 2136 |  |  |  |  | 89
4 | Aggregate Base Course, Type B, CA-2, 6" | 2105 | Tons | 80832 |  |  |  |  | 38.4
5 | Aggregate Base Course, Type B, CA-6, 6" | 2505 | S.Y. | 55110 |  |  |  |  | 22
6 | Aggregate Base Repair, 10" | 236 | S.Y. | 5664 |  |  |  |  | 24
7 | Bituminous Materials (Prime Coat) | 2355 | Gal | 235.5 |  |  |  |  | 0.1
8 | Aggregate (Prime Coat) | 236 | Tons | 23.6 |  |  |  |  | 0.1
9 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | 625 | Tons | 75468.75 |  |  |  |  | 120.75
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | 850 | Tons | 102637.5 |  |  |  |  | 120.75
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | 225 | Tons | 27168.75 |  |  |  |  | 120.75
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 3925 | Tons | 473943.75 |  |  |  |  | 120.75
13 | Hot-Mix Asphalt, Hand Method | 30 | Tons | 13500 |  |  |  |  | 450
14 | P.C.C. Approach Pavement, 8" | 457 | S.Y. | 58953 |  |  |  |  | 129
15 | P.C.C. Approach Pavement, 10" | 1156 | S.Y. | 154904 |  |  |  |  | 134
16 | P.C.C. Sidewalk, 4" | 10575 | S.F. | 105750 |  |  |  |  | 10
17 | P.C.C. Sidewalk, 10" | 675 | S.F. | 10800 |  |  |  |  | 16
18 | Combination Curb and Gutter Removal | 970 | L.F. | 10670 |  |  |  |  | 11
19 | Sidewalk Removal | 7875 | S.F. | 15750 |  |  |  |  | 2
20 | Approach Pavement Removal | 1281 | S.Y. | 19215 |  |  |  |  | 15
21 | Surface Removal, 2" | 24850 | S.Y. | 144378.5 |  |  |  |  | 5.81
22 | Storm Sewers, PVC, 6" | 64 | L.F. | 6464 |  |  |  |  | 101
23 | Storm Sewers, PVC, 10" | 137 | L.F. | 13837 |  |  |  |  | 101
24 | Storm Sewers, RCP, 10" | 90 | L.F. | 8730 |  |  |  |  | 97
Sub Total |  |  |  | 1535416.35 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 5 - 2022 (Parking Lots)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Storm Manhole, Type A, 4' Diameter, Open Lid | 9 | Each | 41218.2 |  |  |  |  | 4579.8
26 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each | 330 |  |  |  |  | 330
27 | Manholes to be Adjusted | 3 | Each | 3933 |  |  |  |  | 1311
28 | Manholes to be Adjusted with Concrete Square | 2 | Each | 3978 |  |  |  |  | 1989
29 | Inlets to be Adjusted | 4 | Each | 7212 |  |  |  |  | 1803
30 | Inlets to be Adjusted with New Frame and Grate or Lid | 3 | Each | 6237 |  |  |  |  | 2079
31 | Combination Concrete Curb and Gutter, Type M-6.12 (Modified) | 735 | L.F. | 28665 |  |  |  |  | 39
32 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 1765 | L.F. | 79425 |  |  |  |  | 45
33 | Traffic Control and Protection | 1 | LSum | 13630 |  |  |  |  | 13630
34 | Paint Pavement Markings, 4" | 3189 | L.F. | 6378 |  |  |  |  | 2
35 | Thermoplastic Pavement Markings, 4" | 11035 | L.F. | 22070 |  |  |  |  | 2
36 | Accessible Parking Symbol Striping | 25 | Each | 7400 |  |  |  |  | 296
37 | Connect to Existing Down Spout | 5 | Each | 4250 |  |  |  |  | 850
38 | Connect to Existing Storm Sewer | 2 | Each | 3300 |  |  |  |  | 1650
39 | Furnish and Install RAP | 375 | Tons | 15000 |  |  |  |  | 40
40 | Regrade Millings | 1250 | S.Y. | 2500 |  |  |  |  | 2
41 | Subgrade Undercutting | 50 | C.Y. | 7000 |  |  |  |  | 140
42 | Non-Special Waste Disposal (Fire Station No. 6) | 200 | C.Y. | 17000 |  |  |  |  | 85
43 | Special Waste Disposal (Fire Station No. 6) | 200 | C.Y. | 26600 |  |  |  |  | 133
44 | Soil Disposal Analysis (Fire Station No. 6) | 10 | Each | 13770 |  |  |  |  | 1377
45 | Special Waste Plans and Reports (Special) (Fire Station No. 6) | 1 | LSum | 8264 |  |  |  |  | 8264
|  |  |  | #VALUE! |  |  |  |  | 1760046.55
|  |  |  | #REF! |  |  |  |  | #REF!
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
[8 empty] | DEDUCT RETAINAGE | 10%
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 5 - 2022 (Parking Lots)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 5 - 2022 (Parking Lots)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Norwest Construction
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.