## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 497424.74
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UNIT | 260 | 26 | 6760
2 | EARTH EXCAVATION | CU YD | 4329 | 25 | 108225
3 | REMOVAL AND DISPOSAL OF UNSUITABLE MATERIAL | CU YD | 34 | 68 | 2312
4 | TRENCH BACKFILL | CU YD | 66.5 | 42 | 2793
5 | TOPSOIL EXCAVATION AND PLACEMENT | CU YD | 504 | 25 | 12600
6 | SEEDING, CLASS 1A | ACRE | 0.95 | 2700 | 2565
7 | NITROGEN FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96
8 | PHOSPHOROUS FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96
9 | POTASSIUM FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96
10 | EROSION CONTROL BLANKET | SQ YD | 3738 | 1.7 | 6354.6
11 | TURF REINFORCEMENT MAT | SQ YD | 547 | 6.5 | 3555.5
12 | TEMPORARY EROSION CONTROL SEEDING | POUND | 94.7 | 2.8 | 265.16
13 | INLET AND PIPE PROTECTION | EACH | 12 | 180 | 2160
14 | FILTER FABRIC | SQ YD | 300 | 4.5 | 1350
15 | ARTICULATED BLOCK REVETMENT MAT | SQ YD | 300 | 160 | 48000
16 | AGGREGATE SUBGRADE IMPROVEMENT | TON | 69 | 25 | 1725
17 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 226 | 25 | 5650
18 | AGGREGATE BASE COURSE, TYPE B | TON | 291 | 25 | 7275
19 | BITUMINOUS MATERIALS (PRIME COAT) | GALLON | 248 | 5 | 1240
20 | HOT-MIX ASPHALT BINDER COURSE, IL-9.5, N50 | TON | 95.1 | 130 | 12363
21 | HOT-MIX ASPHALT SURFACE COURSE, IL-9.5, MIX "D", N50 | TON | 57 | 110 | 6270
22 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | SQ YD | 156.5 | 68 | 10642
23 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 7" | SQ YD | 15 | 78 | 1170
24 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SQ FT | 1362 | 16 | 21792
25 | PAVEMENT REMOVAL | SQ YD | 675 | 20 | 13500
26 | DRIVEWAY PAVEMENT REMOVAL | SQ YD | 57.8 | 17 | 982.6
27 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 300 | 12 | 3600
28 | SIDEWALK REMOVAL | SQ FT | 1482 | 4.5 | 6669
29 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 18" | EACH | 3 | 1130 | 3390
30 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS, EQUIVALENT ROUND-SIZE 18" | EACH | 6 | 1320 | 7920
31 | PIPE CULVERTS, CLASS A, TYPE 1, EQUIVALENT ROUND-SIZE 18" | FOOT | 181 | 95 | 17195
32 | STORM SEWERS, CLASS A, TYPE 1, 12" | FOOT | 8 | 135 | 1080
33 | STORM SEWERS, CLASS A, TYPE 1, 18" | FOOT | 125 | 66 | 8250
34 | STORM SEWER REMOVAL, 12" | FOOT | 9 | 36.5 | 328.5
35 | STORM SEWER REMOVAL, 36" | FOOT | 12 | 47 | 564
36 | MANHOLES, TYPE A, 6'-DIAMETER, TYPE 1 FRAME, CLOSED LID | EACH | 1 | 5600 | 5600
37 | MANHOLES TO BE ADJUSTED | EACH | 1 | 870 | 870
38 | REMOVING INLETS | EACH | 6 | 580 | 3480
39 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 300 | 44 | 13200
40 | CHAIN LINK FENCE, 4' (SPECIAL) | FOOT | 69 | 35 | 2415
41 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 95 | 19000
42 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 250 | 50000
43 | SPECIAL WASTE PLANS AND REPORTS | L SUM | 1 | 6000 | 6000
44 | SOIL DISPOSAL ANALYSIS | EACH | 10 | 1250 | 12500
45 | MOBILIZATION | L SUM | 1 | 10000 | 10000
46 | WASHOUT BASIN | L SUM | 1 | 1650 | 1650
47 | DOUBLE INLETS, SPECIAL | EACH | 1 | 4590 | 4590
48 | INLETS, SPECIAL NO. 5 | EACH | 3 | 3850 | 11550
49 | CHAIN LINK FENCE REMOVAL | FOOT | 97 | 15.5 | 1503.5
50 | TRAFFIC CONTROL AND PROTECTION (SPECIAL) | L SUM | 1 | 10000 | 10000
51 | STABILIZED CONSTRUCTION ENTRANCE | SQ YD | 72 | 31 | 2232
52 | CONSTRUCTION LAYOUT | L SUM | 1 | 8700 | 8700
53 | SHED RELOCATION | EACH | 1 | 5000 | 5000
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Northern Illinois Service |  | Stenstrom Excavation |  | N-Trak Group |  | V3 Construction |  | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | DPI Construction |  | Fischer Excavation | [5 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Rockford, IL |  | Rockford, IL |  | Loves Park, IL |  | Woodridge, IL |  | City of Rockford | [5 empty] | Pecatonica, IL |  | Freeport, IL | [5 empty] | City of Rockford
Harmon Park - Phase 8 | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond |  | Harmon Park - Phase 8 | [5 empty] | Bid Bond |  | Bid Bond | [5 empty] | Harmon Park - Phase 8
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UNIT | 260 | 26 | 6760 | 31 | 8060 | 33.1 | 8606 | 31 | 8060 | 37 | 9620 | 1 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UNIT | 260 | 26 | 6760 | 41 | 10660 | 31 | 8060 |  | 0 |  | 0 | 1 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UNIT | 260 | 26 | 6760 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | EARTH EXCAVATION | CU YD | 4329 | 25 | 108225 | 24 | 103896 | 14.35 | 62121.15 | 20 | 86580 | 35 | 151515 | 2 | EARTH EXCAVATION | CU YD | 4329 | 25 | 108225 | 30 | 129870 | 24 | 103896 |  | 0 |  | 0 | 2 | EARTH EXCAVATION | CU YD | 4329 | 25 | 108225 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | REMOVAL AND DISPOSAL OF UNSUITABLE MATERIAL | CU YD | 34 | 68 | 2312 | 25 | 850 | 32 | 1088 | 20 | 680 | 60 | 2040 | 3 | REMOVAL AND DISPOSAL OF UNSUITABLE MATERIAL | CU YD | 34 | 68 | 2312 | 27 | 918 | 25 | 850 |  | 0 |  | 0 | 3 | REMOVAL AND DISPOSAL OF UNSUITABLE MATERIAL | CU YD | 34 | 68 | 2312 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | TRENCH BACKFILL | CU YD | 66.5 | 42 | 2793 | 14 | 931 | 0.01 | 0.665 | 20 | 1330 | 41 | 2726.5 | 4 | TRENCH BACKFILL | CU YD | 66.5 | 42 | 2793 | 33 | 2194.5 | 38 | 2527 |  | 0 |  | 0 | 4 | TRENCH BACKFILL | CU YD | 66.5 | 42 | 2793 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | TOPSOIL EXCAVATION AND PLACEMENT | CU YD | 504 | 25 | 12600 | 14 | 7056 | 22 | 11088 | 15 | 7560 | 17 | 8568 | 5 | TOPSOIL EXCAVATION AND PLACEMENT | CU YD | 504 | 25 | 12600 | 16 | 8064 | 26 | 13104 |  | 0 |  | 0 | 5 | TOPSOIL EXCAVATION AND PLACEMENT | CU YD | 504 | 25 | 12600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | SEEDING, CLASS 1A | ACRE | 0.95 | 2700 | 2565 | 4300 | 4085 | 4590 | 4360.5 | 5500 | 5225 | 8300 | 7885 | 6 | SEEDING, CLASS 1A | ACRE | 0.95 | 2700 | 2565 | 5304 | 5038.8 | 3300 | 3135 |  | 0 |  | 0 | 6 | SEEDING, CLASS 1A | ACRE | 0.95 | 2700 | 2565 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | NITROGEN FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96 | 4 | 340.8 | 4.3 | 366.36 | 6 | 511.2 | 5.25 | 447.3 | 7 | NITROGEN FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96 | 5 | 426 | 5 | 426 |  | 0 |  | 0 | 7 | NITROGEN FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | PHOSPHOROUS FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96 | 4 | 340.8 | 4.3 | 366.36 | 6 | 511.2 | 5.25 | 447.3 | 8 | PHOSPHOROUS FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96 | 5 | 426 | 5 | 426 |  | 0 |  | 0 | 8 | PHOSPHOROUS FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | POTASSIUM FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96 | 4 | 340.8 | 4.3 | 366.36 | 6 | 511.2 | 5.25 | 447.3 | 9 | POTASSIUM FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96 | 5 | 426 | 5 | 426 |  | 0 |  | 0 | 9 | POTASSIUM FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | EROSION CONTROL BLANKET | SQ YD | 3738 | 1.7 | 6354.6 | 1.7 | 6354.6 | 1.85 | 6915.3 | 2.1 | 7849.8 | 2 | 7476 | 10 | EROSION CONTROL BLANKET | SQ YD | 3738 | 1.7 | 6354.6 | 3 | 11214 | 1.3 | 4859.4 |  | 0 |  | 0 | 10 | EROSION CONTROL BLANKET | SQ YD | 3738 | 1.7 | 6354.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | TURF REINFORCEMENT MAT | SQ YD | 547 | 6.5 | 3555.5 | 5.8 | 3172.6 | 6.2 | 3391.4 | 6.85 | 3746.95 | 5.5 | 3008.5 | 11 | TURF REINFORCEMENT MAT | SQ YD | 547 | 6.5 | 3555.5 | 6 | 3282 | 10 | 5470 |  | 0 |  | 0 | 11 | TURF REINFORCEMENT MAT | SQ YD | 547 | 6.5 | 3555.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | TEMPORARY EROSION CONTROL SEEDING | POUND | 94.7 | 2.8 | 265.16 | 4.1 | 388.27 | 4.4 | 416.68 | 6.5 | 615.55 | 6.75 | 639.225 | 12 | TEMPORARY EROSION CONTROL SEEDING | POUND | 94.7 | 2.8 | 265.16 | 8 | 757.6 | 2 | 189.4 |  | 0 |  | 0 | 12 | TEMPORARY EROSION CONTROL SEEDING | POUND | 94.7 | 2.8 | 265.16 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | INLET AND PIPE PROTECTION | EACH | 12 | 180 | 2160 | 150 | 1800 | 80 | 960 | 125 | 1500 | 290 | 3480 | 13 | INLET AND PIPE PROTECTION | EACH | 12 | 180 | 2160 | 78 | 936 | 225 | 2700 |  | 0 |  | 0 | 13 | INLET AND PIPE PROTECTION | EACH | 12 | 180 | 2160 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | FILTER FABRIC | SQ YD | 300 | 4.5 | 1350 | 5 | 1500 | 3 | 900 | 2.75 | 825 | 2.25 | 675 | 14 | FILTER FABRIC | SQ YD | 300 | 4.5 | 1350 | 12 | 3600 | 4 | 1200 |  | 0 |  | 0 | 14 | FILTER FABRIC | SQ YD | 300 | 4.5 | 1350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | ARTICULATED BLOCK REVETMENT MAT | SQ YD | 300 | 160 | 48000 | 130 | 39000 | 220 | 66000 | 200 | 60000 | 210 | 63000 | 15 | ARTICULATED BLOCK REVETMENT MAT | SQ YD | 300 | 160 | 48000 | 213 | 63900 | 185 | 55500 |  | 0 |  | 0 | 15 | ARTICULATED BLOCK REVETMENT MAT | SQ YD | 300 | 160 | 48000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | AGGREGATE SUBGRADE IMPROVEMENT | TON | 69 | 25 | 1725 | 20 | 1380 | 17 | 1173 | 19 | 1311 | 34 | 2346 | 16 | AGGREGATE SUBGRADE IMPROVEMENT | TON | 69 | 25 | 1725 | 35.7 | 2463.3 | 37 | 2553 |  | 0 |  | 0 | 16 | AGGREGATE SUBGRADE IMPROVEMENT | TON | 69 | 25 | 1725 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 226 | 25 | 5650 | 20 | 4520 | 20.3 | 4587.8 | 23 | 5198 | 24 | 5424 | 17 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 226 | 25 | 5650 | 35.7 | 8068.2 | 25 | 5650 |  | 0 |  | 0 | 17 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 226 | 25 | 5650 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | AGGREGATE BASE COURSE, TYPE B | TON | 291 | 25 | 7275 | 20 | 5820 | 29.75 | 8657.25 | 23 | 6693 | 24 | 6984 | 18 | AGGREGATE BASE COURSE, TYPE B | TON | 291 | 25 | 7275 | 35.7 | 10388.7 | 25 | 7275 |  | 0 |  | 0 | 18 | AGGREGATE BASE COURSE, TYPE B | TON | 291 | 25 | 7275 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | BITUMINOUS MATERIALS (PRIME COAT) | GALLON | 248 | 5 | 1240 | 4.63 | 1148.24 | 0.01 | 2.48 | 0.01 | 2.48 | 5.25 | 1302 | 19 | BITUMINOUS MATERIALS (PRIME COAT) | GALLON | 248 | 5 | 1240 | 0.01 | 2.48 | 4.65 | 1153.2 |  | 0 |  | 0 | 19 | BITUMINOUS MATERIALS (PRIME COAT) | GALLON | 248 | 5 | 1240 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | HOT-MIX ASPHALT BINDER COURSE, IL-9.5, N50 | TON | 95.1 | 130 | 12363 | 108.5 | 10318.35 | 96.5 | 9177.15 | 106 | 10080.6 | 100 | 9510 | 20 | HOT-MIX ASPHALT BINDER COURSE, IL-9.5, N50 | TON | 95.1 | 130 | 12363 | 140.8 | 13390.08 | 108.5 | 10318.35 |  | 0 |  | 0 | 20 | HOT-MIX ASPHALT BINDER COURSE, IL-9.5, N50 | TON | 95.1 | 130 | 12363 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | HOT-MIX ASPHALT SURFACE COURSE, IL-9.5, MIX "D", N50 | TON | 57 | 110 | 6270 | 110 | 6270 | 141 | 8037 | 134 | 7638 | 120 | 6840 | 21 | HOT-MIX ASPHALT SURFACE COURSE, IL-9.5, MIX "D", N50 | TON | 57 | 110 | 6270 | 140.8 | 8025.6 | 110 | 6270 |  | 0 |  | 0 | 21 | HOT-MIX ASPHALT SURFACE COURSE, IL-9.5, MIX "D", N50 | TON | 57 | 110 | 6270 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | SQ YD | 156.5 | 68 | 10642 | 75 | 11737.5 | 62 | 9703 | 60 | 9390 | 84 | 13146 | 22 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | SQ YD | 156.5 | 68 | 10642 | 76 | 11894 | 73 | 11424.5 |  | 0 |  | 0 | 22 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | SQ YD | 156.5 | 68 | 10642 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 7" | SQ YD | 15 | 78 | 1170 | 87 | 1305 | 73 | 1095 | 143 | 2145 | 130 | 1950 | 23 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 7" | SQ YD | 15 | 78 | 1170 | 78.1 | 1171.5 | 83 | 1245 |  | 0 |  | 0 | 23 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 7" | SQ YD | 15 | 78 | 1170 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SQ FT | 1362 | 16 | 21792 | 7 | 9534 | 5.55 | 7559.1 | 6.75 | 9193.5 | 10 | 13620 | 24 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SQ FT | 1362 | 16 | 21792 | 7.4 | 10078.8 | 6 | 8172 |  | 0 |  | 0 | 24 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SQ FT | 1362 | 16 | 21792 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 265655.14 |  | 230148.96 |  | 216938.555 |  | 237157.48 |  | 323097.125 |  | Page 1 | Sub |  | As read | 265655.14 |  | 307195.56 |  | 256829.85 | [5 empty] | Page 1 | Sub |  | As read | 265655.14
| Award to Northern Illinois Service | Total |  | As corrected | 265655.14 |  | 230148.96 |  | 216938.555 |  | 237157.48 |  | 323097.125 |  | Award to Northern Illinois Service | Total |  | As corrected | 265655.14 |  | 307195.56 |  | 256829.85 | [5 empty] | Award to Northern Illinois Service | Total |  | As corrected | 265655.14
25 | PAVEMENT REMOVAL | SQ YD | 675 | 20 | 13500 | 5 | 3375 | 3.25 | 2193.75 | 8 | 5400 | 18 | 12150 | 25 | PAVEMENT REMOVAL | SQ YD | 675 | 20 | 13500 | 8.4 | 5670 | 12 | 8100 |  | 0 |  | 0 | 25 | PAVEMENT REMOVAL | SQ YD | 675 | 20 | 13500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | DRIVEWAY PAVEMENT REMOVAL | SQ YD | 57.8 | 17 | 982.6 | 5 | 289 | 9 | 520.2 | 9 | 520.2 | 9.5 | 549.1 | 26 | DRIVEWAY PAVEMENT REMOVAL | SQ YD | 57.8 | 17 | 982.6 | 26.5 | 1531.7 | 10 | 578 |  | 0 |  | 0 | 26 | DRIVEWAY PAVEMENT REMOVAL | SQ YD | 57.8 | 17 | 982.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 300 | 12 | 3600 | 5 | 1500 | 8 | 2400 | 4 | 1200 | 3.75 | 1125 | 27 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 300 | 12 | 3600 | 6.6 | 1980 | 5.5 | 1650 |  | 0 |  | 0 | 27 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 300 | 12 | 3600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | SIDEWALK REMOVAL | SQ FT | 1482 | 4.5 | 6669 | 0.5 | 741 | 1 | 1482 | 0.01 | 14.82 | 1.25 | 1852.5 | 28 | SIDEWALK REMOVAL | SQ FT | 1482 | 4.5 | 6669 | 1 | 1482 | 4 | 5928 |  | 0 |  | 0 | 28 | SIDEWALK REMOVAL | SQ FT | 1482 | 4.5 | 6669 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 18" | EACH | 3 | 1130 | 3390 | 900 | 2700 | 1360 | 4080 | 975 | 2925 | 1700 | 5100 | 29 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 18" | EACH | 3 | 1130 | 3390 | 984 | 2952 | 847 | 2541 |  | 0 |  | 0 | 29 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 18" | EACH | 3 | 1130 | 3390 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS, EQUIVALENT ROUND-SIZE 18" | EACH | 6 | 1320 | 7920 | 1000 | 6000 | 1435 | 8610 | 1050 | 6300 | 1900 | 11400 | 30 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS, EQUIVALENT ROUND-SIZE 18" | EACH | 6 | 1320 | 7920 | 1036 | 6216 | 921 | 5526 |  | 0 |  | 0 | 30 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS, EQUIVALENT ROUND-SIZE 18" | EACH | 6 | 1320 | 7920 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | PIPE CULVERTS, CLASS A, TYPE 1, EQUIVALENT ROUND-SIZE 18" | FOOT | 181 | 95 | 17195 | 85 | 15385 | 118 | 21358 | 100 | 18100 | 120 | 21720 | 31 | PIPE CULVERTS, CLASS A, TYPE 1, EQUIVALENT ROUND-SIZE 18" | FOOT | 181 | 95 | 17195 | 74 | 13394 | 104 | 18824 |  | 0 |  | 0 | 31 | PIPE CULVERTS, CLASS A, TYPE 1, EQUIVALENT ROUND-SIZE 18" | FOOT | 181 | 95 | 17195 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | STORM SEWERS, CLASS A, TYPE 1, 12" | FOOT | 8 | 135 | 1080 | 50 | 400 | 120 | 960 | 120 | 960 | 140 | 1120 | 32 | STORM SEWERS, CLASS A, TYPE 1, 12" | FOOT | 8 | 135 | 1080 | 39 | 312 | 61 | 488 |  | 0 |  | 0 | 32 | STORM SEWERS, CLASS A, TYPE 1, 12" | FOOT | 8 | 135 | 1080 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | STORM SEWERS, CLASS A, TYPE 1, 18" | FOOT | 125 | 66 | 8250 | 55 | 6875 | 78 | 9750 | 65 | 8125 | 84 | 10500 | 33 | STORM SEWERS, CLASS A, TYPE 1, 18" | FOOT | 125 | 66 | 8250 | 44 | 5500 | 67 | 8375 |  | 0 |  | 0 | 33 | STORM SEWERS, CLASS A, TYPE 1, 18" | FOOT | 125 | 66 | 8250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | STORM SEWER REMOVAL, 12" | FOOT | 9 | 36.5 | 328.5 | 5 | 45 | 27.2 | 244.8 | 30 | 270 | 82 | 738 | 34 | STORM SEWER REMOVAL, 12" | FOOT | 9 | 36.5 | 328.5 | 23.9 | 215.1 | 29 | 261 |  | 0 |  | 0 | 34 | STORM SEWER REMOVAL, 12" | FOOT | 9 | 36.5 | 328.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | STORM SEWER REMOVAL, 36" | FOOT | 12 | 47 | 564 | 5 | 60 | 20.35 | 244.2 | 30 | 360 | 82 | 984 | 35 | STORM SEWER REMOVAL, 36" | FOOT | 12 | 47 | 564 | 28.8 | 345.6 | 50 | 600 |  | 0 |  | 0 | 35 | STORM SEWER REMOVAL, 36" | FOOT | 12 | 47 | 564 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | MANHOLES, TYPE A, 6'-DIAMETER, TYPE 1 FRAME, CLOSED LID | EACH | 1 | 5600 | 5600 | 6000 | 6000 | 9155 | 9155 | 5300 | 5300 | 4900 | 4900 | 36 | MANHOLES, TYPE A, 6'-DIAMETER, TYPE 1 FRAME, CLOSED LID | EACH | 1 | 5600 | 5600 | 6741 | 6741 | 7470 | 7470 |  | 0 |  | 0 | 36 | MANHOLES, TYPE A, 6'-DIAMETER, TYPE 1 FRAME, CLOSED LID | EACH | 1 | 5600 | 5600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | MANHOLES TO BE ADJUSTED | EACH | 1 | 870 | 870 | 1000 | 1000 | 550 | 550 | 650 | 650 | 1700 | 1700 | 37 | MANHOLES TO BE ADJUSTED | EACH | 1 | 870 | 870 | 442 | 442 | 478 | 478 |  | 0 |  | 0 | 37 | MANHOLES TO BE ADJUSTED | EACH | 1 | 870 | 870 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | REMOVING INLETS | EACH | 6 | 580 | 3480 | 150 | 900 | 615 | 3690 | 350 | 2100 | 410 | 2460 | 38 | REMOVING INLETS | EACH | 6 | 580 | 3480 | 463 | 2778 | 413 | 2478 |  | 0 |  | 0 | 38 | REMOVING INLETS | EACH | 6 | 580 | 3480 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 300 | 44 | 13200 | 34.41 | 10323 | 32.55 | 9765 | 35 | 10500 | 32 | 9600 | 39 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 300 | 44 | 13200 | 26 | 7800 | 36 | 10800 |  | 0 |  | 0 | 39 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 300 | 44 | 13200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | CHAIN LINK FENCE, 4' (SPECIAL) | FOOT | 69 | 35 | 2415 | 51 | 3519 | 55.5 | 3829.5 | 51 | 3519 | 74 | 5106 | 40 | CHAIN LINK FENCE, 4' (SPECIAL) | FOOT | 69 | 35 | 2415 | 46 | 3174 | 51 | 3519 |  | 0 |  | 0 | 40 | CHAIN LINK FENCE, 4' (SPECIAL) | FOOT | 69 | 35 | 2415 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 95 | 19000 | 0.01 | 2 | 0.01 | 2 | 0.01 | 2 | 36 | 7200 | 41 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 95 | 19000 | 0.01 | 2 | 87 | 17400 |  | 0 |  | 0 | 41 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 95 | 19000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
42 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 250 | 50000 | 0.01 | 2 | 0.01 | 2 | 0.01 | 2 | 110 | 22000 | 42 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 250 | 50000 | 0.01 | 2 | 96 | 19200 |  | 0 |  | 0 | 42 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 250 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
43 | SPECIAL WASTE PLANS AND REPORTS | L SUM | 1 | 6000 | 6000 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 3200 | 3200 | 43 | SPECIAL WASTE PLANS AND REPORTS | L SUM | 1 | 6000 | 6000 | 0.01 | 0.01 | 2500 | 2500 |  | 0 |  | 0 | 43 | SPECIAL WASTE PLANS AND REPORTS | L SUM | 1 | 6000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
44 | SOIL DISPOSAL ANALYSIS | EACH | 10 | 1250 | 12500 | 100 | 1000 | 0.01 | 0.1 | 0.01 | 0.1 | 390 | 3900 | 44 | SOIL DISPOSAL ANALYSIS | EACH | 10 | 1250 | 12500 | 0.01 | 0.1 | 1150 | 11500 |  | 0 |  | 0 | 44 | SOIL DISPOSAL ANALYSIS | EACH | 10 | 1250 | 12500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
45 | MOBILIZATION | L SUM | 1 | 10000 | 10000 | 1000 | 1000 | 6325 | 6325 | 10000 | 10000 | 13700 | 13700 | 45 | MOBILIZATION | L SUM | 1 | 10000 | 10000 | 15810 | 15810 | 5100 | 5100 |  | 0 |  | 0 | 45 | MOBILIZATION | L SUM | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
46 | WASHOUT BASIN | L SUM | 1 | 1650 | 1650 | 400 | 400 | 375 | 375 | 300 | 300 | 580 | 580 | 46 | WASHOUT BASIN | L SUM | 1 | 1650 | 1650 | 153 | 153 | 400 | 400 |  | 0 |  | 0 | 46 | WASHOUT BASIN | L SUM | 1 | 1650 | 1650 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
47 | DOUBLE INLETS, SPECIAL | EACH | 1 | 4590 | 4590 | 4000 | 4000 | 5055 | 5055 | 5000 | 5000 | 3000 | 3000 | 47 | DOUBLE INLETS, SPECIAL | EACH | 1 | 4590 | 4590 | 4339 | 4339 | 4477 | 4477 |  | 0 |  | 0 | 47 | DOUBLE INLETS, SPECIAL | EACH | 1 | 4590 | 4590 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
48 | INLETS, SPECIAL NO. 5 | EACH | 3 | 3850 | 11550 | 3000 | 9000 | 3558 | 10674 | 5000 | 15000 | 2300 | 6900 | 48 | INLETS, SPECIAL NO. 5 | EACH | 3 | 3850 | 11550 | 3539 | 10617 | 4759 | 14277 |  | 0 |  | 0 | 48 | INLETS, SPECIAL NO. 5 | EACH | 3 | 3850 | 11550 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 469989.24 |  | 304664.97 |  | 318204.115 |  | 333705.61 |  | 474581.725 |  | Page 2 | Sub |  | As read | 469989.24 |  | 398652.07 |  | 409299.85 | [5 empty] | Page 2 | Sub |  | As read | 469989.24
| Award to Northern Illinois Service | Total |  | As corrected | 469989.24 |  | 304664.97 |  | 318204.115 |  | 333705.61 |  | 474581.725 |  | Award to Northern Illinois Service | Total |  | As corrected | 469989.24 |  | 398652.07 |  | 409299.85 | [5 empty] | Award to Northern Illinois Service | Total |  | As corrected | 469989.24
49 | CHAIN LINK FENCE REMOVAL | FOOT | 97 | 15.5 | 1503.5 | 5 | 485 | 6.95 | 674.15 | 8 | 776 | 8.25 | 800.25 | 49 | CHAIN LINK FENCE REMOVAL | FOOT | 97 | 15.5 | 1503.5 | 8 | 776 | 4.3 | 417.1 |  | 0 |  | 0 | 49 | CHAIN LINK FENCE REMOVAL | FOOT | 97 | 15.5 | 1503.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
50 | TRAFFIC CONTROL AND PROTECTION (SPECIAL) | L SUM | 1 | 10000 | 10000 | 11900 | 11900 | 7200.73 | 7200.73 | 3000 | 3000 | 1522.02 | 1522.02 | 50 | TRAFFIC CONTROL AND PROTECTION (SPECIAL) | L SUM | 1 | 10000 | 10000 | 3035 | 3035 | 2925 | 2925 |  | 0 |  | 0 | 50 | TRAFFIC CONTROL AND PROTECTION (SPECIAL) | L SUM | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
51 | STABILIZED CONSTRUCTION ENTRANCE | SQ YD | 72 | 31 | 2232 | 5 | 360 | 38.25 | 2754 | 15 | 1080 | 43 | 3096 | 51 | STABILIZED CONSTRUCTION ENTRANCE | SQ YD | 72 | 31 | 2232 | 32 | 2304 | 14 | 1008 |  | 0 |  | 0 | 51 | STABILIZED CONSTRUCTION ENTRANCE | SQ YD | 72 | 31 | 2232 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
52 | CONSTRUCTION LAYOUT | L SUM | 1 | 8700 | 8700 | 3600 | 3600 | 3310 | 3310 | 6000 | 6000 | 6900 | 6900 | 52 | CONSTRUCTION LAYOUT | L SUM | 1 | 8700 | 8700 | 5100 | 5100 | 4800 | 4800 |  | 0 |  | 0 | 52 | CONSTRUCTION LAYOUT | L SUM | 1 | 8700 | 8700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
53 | SHED RELOCATION | EACH | 1 | 5000 | 5000 | 500 | 500 | 1775 | 1775 | 500 | 500 | 2100 | 2100 | 53 | SHED RELOCATION | EACH | 1 | 5000 | 5000 | 1850 | 1850 | 926 | 926 |  | 0 |  | 0 | 53 | SHED RELOCATION | EACH | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 497424.74 |  | 321509.97 |  | 333917.995 |  | 345061.61 |  | 488999.995 |  | Page 3 | Total |  | As read | 497424.74 |  | 411717.07 |  | 419375.95 | [5 empty] | Page 3 | Total |  | As read | 497424.74
| Award to Northern Illinois Service | Bid |  | As corrected | 497424.74 |  | 321509.97 |  | 333917.995 |  | 345061.61 |  | 488999.995 |  | Award to Northern Illinois Service | Bid |  | As corrected | 497424.74 |  | 411717.07 |  | 419375.95 | [5 empty] | Award to Northern Illinois Service | Bid |  | As corrected | 497424.74
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Northern Illinois Service | Bid |  | As corrected | [10 empty] | Award to Northern Illinois Service | Bid |  | As corrected | [10 empty] | Award to Northern Illinois Service | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Harmon Park - Phase 8
Item No. | Items | Units | Quantity | Unit Price | Total
1 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UNIT | 260 |  | 0
2 | EARTH EXCAVATION | CU YD | 4329 |  | 0
3 | REMOVAL AND DISPOSAL OF UNSUITABLE MATERIAL | CU YD | 34 |  | 0
4 | TRENCH BACKFILL | CU YD | 66.5 |  | 0
5 | TOPSOIL EXCAVATION AND PLACEMENT | CU YD | 504 |  | 0
6 | SEEDING, CLASS 1A | ACRE | 0.95 |  | 0
7 | NITROGEN FERTILIZER NUTRIENT | POUND | 85.2 |  | 0
8 | PHOSPHOROUS FERTILIZER NUTRIENT | POUND | 85.2 |  | 0
9 | POTASSIUM FERTILIZER NUTRIENT | POUND | 85.2 |  | 0
10 | EROSION CONTROL BLANKET | SQ YD | 3738 |  | 0
11 | TURF REINFORCEMENT MAT | SQ YD | 547 |  | 0
12 | TEMPORARY EROSION CONTROL SEEDING | POUND | 94.7 |  | 0
13 | INLET AND PIPE PROTECTION | EACH | 12 |  | 0
14 | FILTER FABRIC | SQ YD | 300 |  | 0
15 | ARTICULATED BLOCK REVETMENT MAT | SQ YD | 300 |  | 0
16 | AGGREGATE SUBGRADE IMPROVEMENT | TON | 69 |  | 0
17 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 226 |  | 0
18 | AGGREGATE BASE COURSE, TYPE B | TON | 291 |  | 0
19 | BITUMINOUS MATERIALS (PRIME COAT) | GALLON | 248 |  | 0
20 | HOT-MIX ASPHALT BINDER COURSE, IL-9.5, N50 | TON | 95.1 |  | 0
21 | HOT-MIX ASPHALT SURFACE COURSE, IL-9.5, MIX "D", N50 | TON | 57 |  | 0
22 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | SQ YD | 156.5 |  | 0
23 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 7" | SQ YD | 15 |  | 0
24 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SQ FT | 1362 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | PAVEMENT REMOVAL | SQ YD | 675 |  | 0
26 | DRIVEWAY PAVEMENT REMOVAL | SQ YD | 57.8 |  | 0
27 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 300 |  | 0
28 | SIDEWALK REMOVAL | SQ FT | 1482 |  | 0
29 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 18" | EACH | 3 |  | 0
30 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS, EQUIVALENT ROUND-SIZE 18" | EACH | 6 |  | 0
31 | PIPE CULVERTS, CLASS A, TYPE 1, EQUIVALENT ROUND-SIZE 18" | FOOT | 181 |  | 0
32 | STORM SEWERS, CLASS A, TYPE 1, 12" | FOOT | 8 |  | 0
33 | STORM SEWERS, CLASS A, TYPE 1, 18" | FOOT | 125 |  | 0
34 | STORM SEWER REMOVAL, 12" | FOOT | 9 |  | 0
35 | STORM SEWER REMOVAL, 36" | FOOT | 12 |  | 0
36 | MANHOLES, TYPE A, 6'-DIAMETER, TYPE 1 FRAME, CLOSED LID | EACH | 1 |  | 0
37 | MANHOLES TO BE ADJUSTED | EACH | 1 |  | 0
38 | REMOVING INLETS | EACH | 6 |  | 0
39 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 300 |  | 0
40 | CHAIN LINK FENCE, 4' (SPECIAL) | FOOT | 69 |  | 0
41 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 |  | 0
42 | SPECIAL WASTE DISPOSAL | CU YD | 200 |  | 0
43 | SPECIAL WASTE PLANS AND REPORTS | L SUM | 1 |  | 0
44 | SOIL DISPOSAL ANALYSIS | EACH | 10 |  | 0
45 | MOBILIZATION | L SUM | 1 |  | 0
46 | WASHOUT BASIN | L SUM | 1 |  | 0
47 | DOUBLE INLETS, SPECIAL | EACH | 1 |  | 0
48 | INLETS, SPECIAL NO. 5 | EACH | 3 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | CHAIN LINK FENCE REMOVAL | FOOT | 97 |  | 0
50 | TRAFFIC CONTROL AND PROTECTION (SPECIAL) | L SUM | 1 |  | 0
51 | STABILIZED CONSTRUCTION ENTRANCE | SQ YD | 72 |  | 0
52 | CONSTRUCTION LAYOUT | L SUM | 1 |  | 0
53 | SHED RELOCATION | EACH | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Harmon Park - Phase 8
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UNIT | 260 | 26 | 6760
2 | EARTH EXCAVATION | CU YD | 4329 | 25 | 108225
3 | REMOVAL AND DISPOSAL OF UNSUITABLE MATERIAL | CU YD | 34 | 68 | 2312
4 | TRENCH BACKFILL | CU YD | 66.5 | 42 | 2793
5 | TOPSOIL EXCAVATION AND PLACEMENT | CU YD | 504 | 25 | 12600
6 | SEEDING, CLASS 1A | ACRE | 0.95 | 2700 | 2565
7 | NITROGEN FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96
8 | PHOSPHOROUS FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96
9 | POTASSIUM FERTILIZER NUTRIENT | POUND | 85.2 | 2.3 | 195.96
10 | EROSION CONTROL BLANKET | SQ YD | 3738 | 1.7 | 6354.6
11 | TURF REINFORCEMENT MAT | SQ YD | 547 | 6.5 | 3555.5
12 | TEMPORARY EROSION CONTROL SEEDING | POUND | 94.7 | 2.8 | 265.16
13 | INLET AND PIPE PROTECTION | EACH | 12 | 180 | 2160
14 | FILTER FABRIC | SQ YD | 300 | 4.5 | 1350
15 | ARTICULATED BLOCK REVETMENT MAT | SQ YD | 300 | 160 | 48000
16 | AGGREGATE SUBGRADE IMPROVEMENT | TON | 69 | 25 | 1725
17 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 226 | 25 | 5650
18 | AGGREGATE BASE COURSE, TYPE B | TON | 291 | 25 | 7275
19 | BITUMINOUS MATERIALS (PRIME COAT) | GALLON | 248 | 5 | 1240
20 | HOT-MIX ASPHALT BINDER COURSE, IL-9.5, N50 | TON | 95.1 | 130 | 12363
21 | HOT-MIX ASPHALT SURFACE COURSE, IL-9.5, MIX "D", N50 | TON | 57 | 110 | 6270
22 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | SQ YD | 156.5 | 68 | 10642
23 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 7" | SQ YD | 15 | 78 | 1170
24 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SQ FT | 1362 | 16 | 21792
|  |  |  | Sub Total | 265655.14
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Harmon Park - Phase 8
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | PAVEMENT REMOVAL | SQ YD | 675 | 20 | 13500
26 | DRIVEWAY PAVEMENT REMOVAL | SQ YD | 57.8 | 17 | 982.6
27 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 300 | 12 | 3600
28 | SIDEWALK REMOVAL | SQ FT | 1482 | 4.5 | 6669
29 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 18" | EACH | 3 | 1130 | 3390
30 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS, EQUIVALENT ROUND-SIZE 18" | EACH | 6 | 1320 | 7920
31 | PIPE CULVERTS, CLASS A, TYPE 1, EQUIVALENT ROUND-SIZE 18" | FOOT | 181 | 95 | 17195
32 | STORM SEWERS, CLASS A, TYPE 1, 12" | FOOT | 8 | 135 | 1080
33 | STORM SEWERS, CLASS A, TYPE 1, 18" | FOOT | 125 | 66 | 8250
34 | STORM SEWER REMOVAL, 12" | FOOT | 9 | 36.5 | 328.5
35 | STORM SEWER REMOVAL, 36" | FOOT | 12 | 47 | 564
36 | MANHOLES, TYPE A, 6'-DIAMETER, TYPE 1 FRAME, CLOSED LID | EACH | 1 | 5600 | 5600
37 | MANHOLES TO BE ADJUSTED | EACH | 1 | 870 | 870
38 | REMOVING INLETS | EACH | 6 | 580 | 3480
39 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 300 | 44 | 13200
40 | CHAIN LINK FENCE, 4' (SPECIAL) | FOOT | 69 | 35 | 2415
41 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 95 | 19000
42 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 250 | 50000
43 | SPECIAL WASTE PLANS AND REPORTS | L SUM | 1 | 6000 | 6000
44 | SOIL DISPOSAL ANALYSIS | EACH | 10 | 1250 | 12500
45 | MOBILIZATION | L SUM | 1 | 10000 | 10000
46 | WASHOUT BASIN | L SUM | 1 | 1650 | 1650
47 | DOUBLE INLETS, SPECIAL | EACH | 1 | 4590 | 4590
48 | INLETS, SPECIAL NO. 5 | EACH | 3 | 3850 | 11550
|  |  |  | Sub Total | 469989.24
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Harmon Park - Phase 8
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | CHAIN LINK FENCE REMOVAL | FOOT | 97 | 15.5 | 1503.5
50 | TRAFFIC CONTROL AND PROTECTION (SPECIAL) | L SUM | 1 | 10000 | 10000
51 | STABILIZED CONSTRUCTION ENTRANCE | SQ YD | 72 | 31 | 2232
52 | CONSTRUCTION LAYOUT | L SUM | 1 | 8700 | 8700
53 | SHED RELOCATION | EACH | 1 | 5000 | 5000
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 497424.74
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Harmon Park - Phase 8
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 497424.74
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Harmon Park - Phase 8
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | 260 | UNIT | 8060 |  | 260 |  |  | 31
2 | EARTH EXCAVATION | 4329 | CU YD | 103896 |  | 4329 |  |  | 24
3 | REMOVAL AND DISPOSAL OF UNSUITABLE MATERIAL | 34 | CU YD | 850 |  | 34 |  |  | 25
4 | TRENCH BACKFILL | 66.5 | CU YD | 931 |  | 66.5 |  |  | 14
5 | TOPSOIL EXCAVATION AND PLACEMENT | 504 | CU YD | 7056 |  | 504 |  |  | 14
6 | SEEDING, CLASS 1A | 0.95 | ACRE | 4085 |  | 0.95 |  |  | 4300
7 | NITROGEN FERTILIZER NUTRIENT | 85.2 | POUND | 340.8 |  | 85.2 |  |  | 4
8 | PHOSPHOROUS FERTILIZER NUTRIENT | 85.2 | POUND | 340.8 |  | 85.2 |  |  | 4
9 | POTASSIUM FERTILIZER NUTRIENT | 85.2 | POUND | 340.8 |  | 85.2 |  |  | 4
10 | EROSION CONTROL BLANKET | 3738 | SQ YD | 6354.6 |  | 3738 |  |  | 1.7
11 | TURF REINFORCEMENT MAT | 547 | SQ YD | 3172.6 |  | 547 |  |  | 5.8
12 | TEMPORARY EROSION CONTROL SEEDING | 94.7 | POUND | 388.27 |  | 94.7 |  |  | 4.1
13 | INLET AND PIPE PROTECTION | 12 | EACH | 1800 |  | 12 |  |  | 150
14 | FILTER FABRIC | 300 | SQ YD | 1500 |  | 300 |  |  | 5
15 | ARTICULATED BLOCK REVETMENT MAT | 300 | SQ YD | 39000 |  | 300 |  |  | 130
16 | AGGREGATE SUBGRADE IMPROVEMENT | 69 | TON | 1380 |  | 69 |  |  | 20
17 | SUBBASE GRANULAR MATERIAL, TYPE B | 226 | TON | 4520 |  | 226 |  |  | 20
18 | AGGREGATE BASE COURSE, TYPE B | 291 | TON | 5820 |  | 291 |  |  | 20
19 | BITUMINOUS MATERIALS (PRIME COAT) | 248 | GALLON | 1148.24 |  | 248 |  |  | 4.63
20 | HOT-MIX ASPHALT BINDER COURSE, IL-9.5, N50 | 95.1 | TON | 10318.35 |  | 95.1 |  |  | 108.5
21 | HOT-MIX ASPHALT SURFACE COURSE, IL-9.5, MIX "D", N50 | 57 | TON | 6270 |  | 57 |  |  | 110
22 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | 156.5 | SQ YD | 11737.5 |  | 156.5 |  |  | 75
23 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 7" | 15 | SQ YD | 1305 |  | 15 |  |  | 87
24 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | 1362 | SQ FT | 9534 |  | 1362 |  |  | 7
Sub Total |  |  |  | 230148.96 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Harmon Park - Phase 8
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | PAVEMENT REMOVAL | 675 | SQ YD | 3375 |  | 675 |  |  | 5
26 | DRIVEWAY PAVEMENT REMOVAL | 57.8 | SQ YD | 289 |  | 57.8 |  |  | 5
27 | COMBINATION CURB AND GUTTER REMOVAL | 300 | FOOT | 1500 |  | 300 |  |  | 5
28 | SIDEWALK REMOVAL | 1482 | SQ FT | 741 |  | 1482 |  |  | 0.5
29 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 18" | 3 | EACH | 2700 |  | 3 |  |  | 900
30 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS, EQUIVALENT ROUND-SIZE 18" | 6 | EACH | 6000 |  | 6 |  |  | 1000
31 | PIPE CULVERTS, CLASS A, TYPE 1, EQUIVALENT ROUND-SIZE 18" | 181 | FOOT | 15385 |  | 181 |  |  | 85
32 | STORM SEWERS, CLASS A, TYPE 1, 12" | 8 | FOOT | 400 |  | 8 |  |  | 50
33 | STORM SEWERS, CLASS A, TYPE 1, 18" | 125 | FOOT | 6875 |  | 125 |  |  | 55
34 | STORM SEWER REMOVAL, 12" | 9 | FOOT | 45 |  | 9 |  |  | 5
35 | STORM SEWER REMOVAL, 36" | 12 | FOOT | 60 |  | 12 |  |  | 5
36 | MANHOLES, TYPE A, 6'-DIAMETER, TYPE 1 FRAME, CLOSED LID | 1 | EACH | 6000 |  | 1 |  |  | 6000
37 | MANHOLES TO BE ADJUSTED | 1 | EACH | 1000 |  | 1 |  |  | 1000
38 | REMOVING INLETS | 6 | EACH | 900 |  | 6 |  |  | 150
39 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | 300 | FOOT | 10323 |  | 300 |  |  | 34.41
40 | CHAIN LINK FENCE, 4' (SPECIAL) | 69 | FOOT | 3519 |  | 69 |  |  | 51
41 | NON-SPECIAL WASTE DISPOSAL | 200 | CU YD | 2 |  | 200 |  |  | 0.01
42 | SPECIAL WASTE DISPOSAL | 200 | CU YD | 2 |  | 200 |  |  | 0.01
43 | SPECIAL WASTE PLANS AND REPORTS | 1 | L SUM | 0.01 |  | 1 |  |  | 0.01
44 | SOIL DISPOSAL ANALYSIS | 10 | EACH | 1000 |  | 10 |  |  | 100
45 | MOBILIZATION | 1 | L SUM | 1000 |  | 1 |  |  | 1000
46 | WASHOUT BASIN | 1 | L SUM | 400 |  | 1 |  |  | 400
47 | DOUBLE INLETS, SPECIAL | 1 | EACH | 4000 |  | 1 |  |  | 4000
48 | INLETS, SPECIAL NO. 5 | 3 | EACH | 9000 |  | 3 |  |  | 3000
Sub Total |  |  |  | 304664.97 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Harmon Park - Phase 8
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | CHAIN LINK FENCE REMOVAL | 97 | FOOT | 485 |  | 97 |  |  | 5
50 | TRAFFIC CONTROL AND PROTECTION (SPECIAL) | 1 | L SUM | 11900 |  | 1 |  |  | 11900
51 | STABILIZED CONSTRUCTION ENTRANCE | 72 | SQ YD | 360 |  | 72 |  |  | 5
52 | CONSTRUCTION LAYOUT | 1 | L SUM | 3600 |  | 1 |  |  | 3600
53 | SHED RELOCATION | 1 | EACH | 500 |  | 1 |  |  | 500
Total |  |  |  | 321509.97 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Harmon Park - Phase 8
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 321509.97 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Harmon Park - Phase 8
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Northern Illinois Service
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.