## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 148553
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | Public Water Service (Open-Cut), Complete | LF | 33 | 110 | 3630
2 | Sidewalk Removal | SF | 45 | 4 | 180
3 | Pavement Removal | SY | 15 | 10 | 150
4 | Combination Curb & Gutter Removal | LF | 10 | 12 | 120
5 | Pavement Patch, Class D | SY | 15 | 175 | 2625
6 | PCC Sidewalk, 4" | SF | 45 | 5 | 225
7 | Combination Concrete Curb and Gutter, Type M6.18 (Modified) | LF | 10 | 45 | 450
8 | Restoration, Open-Cut, Complete | LS | 1 | 1000 | 1000
9 | Traffic Control and Protection, Special | LS | 1 | 500 | 500
10 | Public Water Service (Bored), Complete | LF | 33 | 90 | 2970
11 | Sidewalk Removal | SF | 45 | 4 | 180
12 | Pavement Removal | SY | 10 | 10 | 100
13 | Pavement Patch, Class D | SY | 10 | 175 | 1750
14 | PCC Sidewalk, 4" | SF | 45 | 5 | 225
15 | Restoration, Bored, Complete | LS | 1 | 750 | 750
16 | Traffic Control and Protection, Special | LS | 1 | 500 | 500
17 | Private Water Service (Open-Cut), Complete | LF | 33 | 110 | 3630
18 | Sidewalk Removal | SF | 45 | 4 | 180
19 | Connection to Water Meter, Complete | EA | 1 | 2000 | 2000
20 | PCC Sidewalk, 4" | SF | 45 | 5 | 225
21 | Restoration, Open-Cut, Complete | LS | 1 | 1000 | 1000
22 | Traffic Control and Protection, Special | LS | 1 | 500 | 500
23 | Private Water Service (Bored), Complete | LF | 33 | 90 | 2970
24 | Sidewalk Removal | SF | 45 | 4 | 180
25 | Connection to Water Meter, Complete | EA | 1 | 2000 | 2000
26 | PCC Sidewalk, 4" | SF | 45 | 5 | 225
27 | Restoration, Bored, Complete | LS | 1 | 750 | 750
28 | Traffic Control and Protection, Special | LS | 1 | 500 | 500
29 | Approach Pavement Removal | SY | 110 | 20 | 2200
30 | PCC Pavement, Jointed, 9" | SY | 25 | 75 | 1875
31 | Tree Removal (6-15 Units) | UD | 10 | 35 | 350
32 | Tree Removal (Over 15 Units) | UD | 14 | 45 | 630
33 | Rock Excavation | CY | 30 | 150 | 4500
34 | PCC Approach Pavement, 6" | SY | 55 | 65 | 3575
35 | Hot Mix Asphalt Approach Pavement, 3" | SY | 55 | 85 | 4675
36 | Retaining Wall, Modular Block, Complete | SF | 45 | 100 | 4500
37 | Retaining Wall, PCC Concrete, Complete | SF | 45 | 100 | 4500
38 | Silt Fence | LF | 50 | 5 | 250
39 | Inlet Protection | EA | 15 | 200 | 3000
40 | Water Meter Relocation, Complete | LF | 15 | 80 | 1200
41 | Additional Set-up Boring Length | LF | 25 | 45 | 1125
42 | Public Water Service, Open-Cut, Complete, 1.5" | LF | 33 | 112 | 3696
43 | Public Water Service, Open-Cut, Complete, 2" | LF | 33 | 115 | 3795
44 | Private Water Service, Open-Cut, Complete, 1.5" | LF | 33 | 112 | 3696
45 | Private Water Service, Open-Cut, Complete, 2" | LF | 33 | 115 | 3795
46 | Public Water Service, Bored, Complete, 1.5" | LF | 33 | 92 | 3036
47 | Public Water Service, Bored, Complete, 2" | LF | 33 | 95 | 3135
48 | Private Water Service, Bored, Complete, 1.5" | LF | 33 | 92 | 3036
49 | Private Water Service, Bored, Complete, 2" | LF | 33 | 95 | 3135
50 | Public Water Service, Bored, Complete, 1" with 2" Casing | LF | 33 | 92 | 3036
51 | Public Water Service, Bored, Complete, 1.5" with 2" Casing | LF | 33 | 95 | 3135
52 | Public Water Service, Bored, Complete, 2" with 3" Casing | LF | 33 | 97 | 3201
53 | Public Water Service, Open-Cut, Complete, 1" with 2" Casing | LF | 33 | 112 | 3696
54 | Public Water Service, Open-Cut, Complete, 1.5" with 2" Casing | LF | 33 | 115 | 3795
55 | Public Water Service, Open-Cut, Complete, 2" with 3" Casing | LF | 33 | 117 | 3861
56 | Public Water Service Bored Through Rock, Complete, 1" with 2" Casing | LF | 33 | 190 | 6270
57 | Public Water Service Bored Through Rock, Complete, 1.5" with 2" Casing | LF | 33 | 195 | 6435
58 | Public Water Service Bored Through Rock, Complete, 2" with 3" Casing | LF | 33 | 200 | 6600
59 | Private Water Service Bored Through Rock, Complete, 1" with 2" Casing | LF | 33 | 190 | 6270
60 | Private Water Service Bored Through Rock, Complete, 1.5" with 2" Casing | LF | 33 | 195 | 6435
61 | Private Water Service Bored Through Rock, Complete, 2" with 3" Casing | LF | 33 | 200 | 6600
62 | Traffic Control and Protection, Special | LS | 1
63 | Brick Pavement, Complete | SY | 100
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89

## Tabulation of Bids
TABULATION OF BIDS |  | NAME AND ADDRESS OF BIDDER: |  |  |  | N-TRAK Group |  | Stenstrom Excavating |  | DPI Construction
City of Rockford | [5 empty] | Loves Park, IL |  | Rockford, IL |  | Pecatonica, IL
Bid On: Lead Service Line Replacement Phase 4 | [5 empty] | Ø
Bid No.: 1221-W-106 |  | EEOs: |  |  |  | x |  | x |  | x
Bid Opening: 4/14/2022 |  | Addendums 1 & 3: |  |  |  | x |  | x |  | x
Vendors Notified: 89 |  | Bid Bond: |  |  |  | x |  | x |  | x
|  | Apprenticeship: |  |  |  | x |  | x |  | x
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Public Water Service, Bored or Pulled, Copper, Complete, 1" | LF | 33 | 120 | 3960 | 100 | 3300 | 128 | 4224 | 116.84 | 3855.72 |  | 0
2 | Private Water Service, Bored or Pulled, Copper, Complete, 1" | LF | 33 | 125 | 4125 | 100 | 3300 | 127 | 4191 | 116.84 | 3855.72 |  | 0
3 | Private Water Service, Bored or Pulled, HDPE, Complete, 1" | LF | 33 | 110 | 3630 | 100 | 3300 | 120 | 3960 | 114 | 3762 |  | 0
4 | Sidewalk Removal & Replacement | SF | 45 | 35 | 1575 | 5 | 225 | 4 | 180 | 15.22 | 684.9 |  | 0
5 | Pavement Removal & Patch Replacement, Class D | SY | 15 | 75 | 1125 | 40 | 600 | 88 | 1320 | 71 | 1065 |  | 0
6 | Combination Curb and Gutter Removal & Replacement | LF | 10 | 45 | 450 | 20 | 200 | 40 | 400 | 30 | 300 |  | 0
7 | Connection to Water Meter (Basement/Crawlspace), Complete | EA | 1 | 500 | 500 | 400 | 400 | 375 | 375 | 1500 | 1500 |  | 0
8 | Restoration, Complete | LS | 1 | 250 | 250 | 300 | 300 | 100 | 100 | 275.5 | 275.5 |  | 0
9 | Traffic Control and Protection | LS | 1 | 150 | 150 | 1 | 1 | 100 | 100 | 100 | 100 |  | 0
| BASE BID ITEM #1: |  | 0 | 0 | 0 |  | 11626 |  | 14850 |  | 15398.84 |  | 0
15398.8
CONTINGENCY BID ITEMS
10 | PCC Pavement, Jointed, Removal and Replacement, 9" | SY | 110 | 175 | 19250 | 155 | 17050 | 140 | 15400 | 110 | 12100 |  | 0
11 | PCC Approach Pavement Removal & Replacement, 6" | SY | 55 | 75 | 4125 | 110 | 6050 | 120 | 6600 | 95 | 5225 |  | 0
12 | Tree Removal (6-15 Units) | UD | 10 | 50 | 500 | 50 | 500 | 46.5 | 465 | 35 | 350 |  | 0
13 | Tree Removal (Over 15 Units) | UD | 15 | 80 | 1200 | 80 | 1200 | 44 | 660 | 50 | 750 |  | 0
14 | Rock Excavation | CY | 30 | 150 | 4500 | 150 | 4500 | 100 | 3000 | 120 | 3600 |  | 0
15 | Hot-Mix Asphalt Approach Pavement Removal & Replacement, 3" | SY | 55 | 55 | 3025 | 85 | 4675 | 75.6 | 4158 | 45 | 2475 |  | 0
16 | Retaining Wall, Modular Block, Complete | SY | 45 | 75 | 3375 | 80 | 3600 | 85 | 3825 | 100 | 4500 |  | 0
17 | Retaining Wall, PCC Concrete, Complete | SF | 45 | 105 | 4725 | 100 | 4500 | 85 | 3825 | 200 | 9000 |  | 0
18 | Silt Fence | SF | 50 | 10 | 500 | 5 | 250 | 5 | 250 | 7 | 350 |  | 0
19 | Inlet and Pipe Protection | LF | 15 | 200 | 3000 | 100 | 1500 | 175 | 2625 | 10 | 150 |  | 0
20 | Restoration, Open-Cut, Complete | LS | 1 | 500 | 500 | 300 | 300 | 1950 | 1950 | 475 | 475 |  | 0
21 | Water Meter Relocation, Complete | EA | 15 | 100 | 1500 | 1000 | 15000 | 950 | 14250 | 1500 | 22500 |  | 0
22 | Additional Set-up Boring Length | LF | 25 | 45 | 1125 | 35 | 875 | 50 | 1250 | 45 | 1125 |  | 0
Page 1
Recommend Award to N-TRAK Group
23 | Public Water Service, Open-Cut, Copper, Complete, 1" | LF | 33 | 100 | 3300 | 125 | 4125 | 200.5 | 6616.5 | 125 | 4125 |  | 0
24 | Private Water Service, Open-Cut, Copper, Complete, 1" | LF | 33 | 105 | 3465 | 120 | 3960 | 175 | 5775 | 125 | 4125 |  | 0
25 | Private Water Service, Open-Cut, HDPE, Complete, 1" | LF | 33 | 110 | 3630 | 115 | 3795 | 170 | 5610 | 118 | 3894 |  | 0
26 | Public Water Service, Open-Cut, Copper, Complete, 1.5" | LF | 33 | 103 | 3399 | 135 | 4455 | 240 | 7920 | 175.76 | 5800.08 |  | 0
27 | Private Water Service, Open-Cut, Copper, Complete, 1.5" | LF | 33 | 108 | 3564 | 130 | 4290 | 200 | 6600 | 175.76 | 5800.08 |  | 0
28 | Private Water Service, Open-Cut, HDPE, Complete, 1.5" | LF | 33 | 113 | 3729 | 120 | 3960 | 195 | 6435 | 170.76 | 5635.08 |  | 0
29 | Public Water Service, Open-Cut, Copper, Complete, 2" | LF | 33 | 115 | 3795 | 150 | 4950 | 280 | 9240 | 188.12 | 6207.96 |  | 0
30 | Private Water Service, Open-Cut, Copper, Complete, 2" | LF | 33 | 120 | 3960 | 140 | 4620 | 230 | 7590 | 188.12 | 6207.96 |  | 0
31 | Private Water Service, Open-Cut, HDPE, Complete, 2" | LF | 33 | 125 | 4125 | 130 | 4290 | 220 | 7260 | 180.12 | 5943.96 |  | 0
32 | Public Water Service, Bored or Pulled, Copper, Complete 1.5" | LF | 33 | 125 | 4125 | 150 | 4950 | 205 | 6765 | 160.4 | 5293.2 |  | 0
33 | Private Water Service, Bored or Pulled, Copper, Complete 1.5" | LF | 33 | 130 | 4290 | 120 | 3960 | 170 | 5610 | 160.4 | 5293.2 |  | 0
34 | Private Water Service, Bored or Pulled, HDPE, Complete 1.5" | LF | 33 | 135 | 4455 | 115 | 3795 | 160 | 5280 | 155.4 | 5128.2 |  | 0
35 | Public Water Service, Bored or Pulled, Copper, Complete 2" | LF | 33 | 130 | 4290 | 150 | 4950 | 240 | 7920 | 180.11 | 5943.63 |  | 0
36 | Private Water Service, Bored or Pulled, Copper, Complete 2" | LF | 33 | 135 | 4455 | 135 | 4455 | 190 | 6270 | 180.11 | 5943.63 |  | 0
37 | Private Water Service, Bored or Pulled, HDPE, Complete 2" | LF | 33 | 145 | 4785 | 120 | 3960 | 180 | 5940 | 172.11 | 5679.63 |  | 0
38 | Water Service Casing | LF | 33 | 2.5 | 82.5 | 14 | 462 | 45 | 1485 | 75 | 2475 |  | 0
39 | Public Water Service Bored Through Rock, Copper, Complete, 1" with 2" Casing | LF | 33 | 160 | 5280 | 160 | 5280 | 260 | 8580 | 155 | 5115 |  | 0
40 | Private Water Service Bored Through Rock, Copper, Complete, 1" with 2" Casing | LF | 33 | 170 | 5610 | 150 | 4950 | 230 | 7590 | 155 | 5115 |  | 0
41 | Private Water Service Bored Through Rock, HDPE, Complete, 1" with 2" Casing | LF | 33 | 180 | 5940 | 140 | 4620 | 220 | 7260 | 150 | 4950 |  | 0
42 | Public Water Service Bored Through Rock, Copper, Complete, 1.5" with 2" Casing | LF | 33 | 170 | 5610 | 180 | 5940 | 305 | 10065 | 190 | 6270 |  | 0
43 | Private Water Service Bored Through Rock, Copper, Complete, 1.5" with 2" Casing | LF | 33 | 180 | 5940 | 165 | 5445 | 265 | 8745 | 190 | 6270 |  | 0
44 | Private Water Service Bored Through Rock, HDPE, Complete, 1.5" with 2" Casing | LF | 33 | 190 | 6270 | 155 | 5115 | 260 | 8580 | 185 | 6105 |  | 0
45 | Public Water Service Bored Through Rock, Copper, Complete, 2" with 3" Casing | LF | 33 | 190 | 6270 | 190 | 6270 | 350 | 11550 | 208 | 6864 |  | 0
46 | Private Water Service Bored Through Rock, Copper, Complete, 2" with 3" Casing | LF | 33 | 200 | 6600 | 180 | 5940 | 300 | 9900 | 208 | 6864 |  | 0
47 | Private Water Service Bored Through Rock, HDPE, Complete, 2" with 3" Casing | LF | 33 | 210 | 6930 | 170 | 5610 | 300 | 9900 | 200 | 6600 |  | 0
48 | Traffic Control and Protection, Special | LS | 1 | 1500 | 1500 | 1000 | 1000 | 5100 | 5100 | 2750 | 2750 |  | 0
49 | Connection to Water Meter (Slab on Grade), Complete | EA | 1 | 1000 | 1000 | 750 | 750 | 950 | 950 | 1800 | 1800 |  | 0
50 | Brick Pavement, Complete | SY | 10 | 150 | 1500 | 300 | 3000 | 2500 | 25000 | 55 | 550 |  | 0
51 | Exploratory Excavation, B-Box Service Material Identification | EA | 1 | 250 | 250 | 1000 | 1000 | 1600 | 1600 | 650 | 650 |  | 0
52 | Exploratory Excavation, Pulling Failure Reconnection | EA | 1 | 1000 | 1000 | 1000 | 1000 | 1600 | 1600 | 9000 | 9000 |  | 0
53 | Additional Service Line Abandonment | EA | 25 | 2000 | 50000 | 2200 | 55000 | 2700 | 67500 | 1750 | 43750 |  | 0
54 | Additional Corporation Stop Abandonment | EA | 20 | 1250 | 25000 | 2200 | 44000 | 2700 | 54000 | 850 | 17000 |  | 0
55 | Primary Electrical Grounding System Installation | EA | 25 | 1500 | 37500 | 2000 | 50000 | 2100 | 52500 | 550 | 13750 |  | 0
56 | Reconnection of Water Service Electrical Jumper Cable | EA | 1 | 350 | 350 | 1000 | 1000 | 1100 | 1100 | 150 | 150 |  | 0
| CONTINGENCY BID ITEMS TOTAL: |  | 0 | 0 | 0 |  | 330897 |  | 452094.5 |  | 289498.61 |  | 0
268649
| Total Bid Item 1 with Contingency: |  | 0 | 0 | 0 |  | 342523 |  | 466944.5 |  | 304897.45 |  | 0
| Page 2 |  |  | As read
| Recommend Award to N-TRAK Group |  |  | As corrected
As Corrected
As Read

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Vendors Notified: 89
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Public Water Service, Bored or Pulled, Copper, Complete, 1" | LF | 33 |  | 0
2 | Private Water Service, Bored or Pulled, Copper, Complete, 1" | LF | 33 |  | 0
3 | Private Water Service, Bored or Pulled, HDPE, Complete, 1" | LF | 33 |  | 0
4 | Sidewalk Removal & Replacement | SF | 45 |  | 0
5 | Pavement Removal & Patch Replacement, Class D | SY | 15 |  | 0
6 | Combination Curb and Gutter Removal & Replacement | LF | 10 |  | 0
7 | Connection to Water Meter (Basement/Crawlspace), Complete | EA | 1 |  | 0
8 | Restoration, Complete | LS | 1 |  | 0
9 | Traffic Control and Protection | LS | 1 |  | 0
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
0 | BASE BID ITEM #1: |  | 0 |  | 0
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
| Page 1 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
10 | PCC Pavement, Jointed, Removal and Replacement, 9" | SY | 110 |  | 0
11 | PCC Approach Pavement Removal & Replacement, 6" | SY | 55 |  | 0
12 | Tree Removal (6-15 Units) | UD | 10 |  | 0
13 | Tree Removal (Over 15 Units) | UD | 15 |  | 0
14 | Rock Excavation | CY | 30 |  | 0
15 | Hot-Mix Asphalt Approach Pavement Removal & Replacement, 3" | SY | 55 |  | 0
16 | Retaining Wall, Modular Block, Complete | SY | 45 |  | 0
17 | Retaining Wall, PCC Concrete, Complete | SF | 45 |  | 0
18 | Silt Fence | SF | 50 |  | 0
19 | Inlet and Pipe Protection | LF | 15 |  | 0
20 | Restoration, Open-Cut, Complete | LS | 1 |  | 0
21 | Water Meter Relocation, Complete | EA | 15 |  | 0
22 | Additional Set-up Boring Length | LF | 25 |  | 0
| Page 2 | Sub |  | As read | #REF!
|  | Total |  | As corrected | #REF!
23 | Public Water Service, Open-Cut, Copper, Complete, 1" | LF | 33 |  | 0
24 | Private Water Service, Open-Cut, Copper, Complete, 1" | LF | 33 |  | 0
25 | Private Water Service, Open-Cut, HDPE, Complete, 1" | LF | 33 |  | 0
26 | Public Water Service, Open-Cut, Copper, Complete, 1.5" | LF | 33 |  | 0
27 | Private Water Service, Open-Cut, Copper, Complete, 1.5" | LF | 33 |  | 0
28 | Private Water Service, Open-Cut, HDPE, Complete, 1.5" | LF | 33 |  | 0
29 | Public Water Service, Open-Cut, Copper, Complete, 2" | LF | 33 |  | 0
30 | Private Water Service, Open-Cut, Copper, Complete, 2" | LF | 33 |  | 0
31 | Private Water Service, Open-Cut, HDPE, Complete, 2" | LF | 33 |  | 0
32 | Public Water Service, Bored or Pulled, Copper, Complete 1.5" | LF | 33 |  | 0
33 | Private Water Service, Bored or Pulled, Copper, Complete 1.5" | LF | 33 |  | 0
34 | Private Water Service, Bored or Pulled, HDPE, Complete 1.5" | LF | 33 |  | 0
50 | Brick Pavement, Complete | SY | 10 |  | 0
51 | Exploratory Excavation, B-Box Service Material Identification | EA | 1 |  | 0
52 | Exploratory Excavation, Pulling Failure Reconnection | EA | 1 |  | 0
53 | Additional Service Line Abandonment | EA | 25 |  | 0
54 | Additional Corporation Stop Abandonment | EA | 20 |  | 0
55 | Primary Electrical Grounding System Installation | EA | 25 |  | 0
56 | Reconnection of Water Service Electrical Jumper Cable | EA | 1 |  | 0
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
0 | CONTINGENCY BID ITEMS TOTAL: |  | 0 |  | 0
#REF! | #REF! | #REF! | #REF! |  | #REF!
| Page 3 | Sub |  | As read | #REF!
|  | Total |  | As corrected | #REF!
0 | Total Bid Item 1 with Contingency: |  | 0 |  | 0
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Vendors Notified: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Public Water Service, Bored or Pulled, Copper, Complete, 1" | LF | 33 | 120 | 3960
2 | Private Water Service, Bored or Pulled, Copper, Complete, 1" | LF | 33 | 125 | 4125
3 | Private Water Service, Bored or Pulled, HDPE, Complete, 1" | LF | 33 | 110 | 3630
4 | Sidewalk Removal & Replacement | SF | 45 | 35 | 1575
5 | Pavement Removal & Patch Replacement, Class D | SY | 15 | 75 | 1125
6 | Combination Curb and Gutter Removal & Replacement | LF | 10 | 45 | 450
7 | Connection to Water Meter (Basement/Crawlspace), Complete | EA | 1 | 500 | 500
8 | Restoration, Complete | LS | 1 | 250 | 250
9 | Traffic Control and Protection | LS | 1 | 150 | 150
0 | BASE BID ITEM #1: |  | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Vendors Notified: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | PCC Pavement, Jointed, Removal and Replacement, 9" | SY | 110 | 175 | 19250
11 | PCC Approach Pavement Removal & Replacement, 6" | SY | 55 | 75 | 4125
12 | Tree Removal (6-15 Units) | UD | 10 | 50 | 500
13 | Tree Removal (Over 15 Units) | UD | 15 | 80 | 1200
14 | Rock Excavation | CY | 30 | 150 | 4500
15 | Hot-Mix Asphalt Approach Pavement Removal & Replacement, 3" | SY | 55 | 55 | 3025
16 | Retaining Wall, Modular Block, Complete | SY | 45 | 75 | 3375
17 | Retaining Wall, PCC Concrete, Complete | SF | 45 | 105 | 4725
18 | Silt Fence | SF | 50 | 10 | 500
19 | Inlet and Pipe Protection | LF | 15 | 200 | 3000
20 | Restoration, Open-Cut, Complete | LS | 1 | 500 | 500
21 | Water Meter Relocation, Complete | EA | 15 | 100 | 1500
22 | Additional Set-up Boring Length | LF | 25 | 45 | 1125
|  |  |  | Sub Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Vendors Notified: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
23 | Public Water Service, Open-Cut, Copper, Complete, 1" | LF | 33 | 100 | 3300
24 | Private Water Service, Open-Cut, Copper, Complete, 1" | LF | 33 | 105 | 3465
25 | Private Water Service, Open-Cut, HDPE, Complete, 1" | LF | 33 | 110 | 3630
26 | Public Water Service, Open-Cut, Copper, Complete, 1.5" | LF | 33 | 103 | 3399
27 | Private Water Service, Open-Cut, Copper, Complete, 1.5" | LF | 33 | 108 | 3564
28 | Private Water Service, Open-Cut, HDPE, Complete, 1.5" | LF | 33 | 113 | 3729
29 | Public Water Service, Open-Cut, Copper, Complete, 2" | LF | 33 | 115 | 3795
30 | Private Water Service, Open-Cut, Copper, Complete, 2" | LF | 33 | 120 | 3960
31 | Private Water Service, Open-Cut, HDPE, Complete, 2" | LF | 33 | 125 | 4125
32 | Public Water Service, Bored or Pulled, Copper, Complete 1.5" | LF | 33 | 125 | 4125
33 | Private Water Service, Bored or Pulled, Copper, Complete 1.5" | LF | 33 | 130 | 4290
34 | Private Water Service, Bored or Pulled, HDPE, Complete 1.5" | LF | 33 | 135 | 4455
50 | Brick Pavement, Complete | SY | 10 | 150 | 1500
51 | Exploratory Excavation, B-Box Service Material Identification | EA | 1 | 250 | 250
52 | Exploratory Excavation, Pulling Failure Reconnection | EA | 1 | 1000 | 1000
53 | Additional Service Line Abandonment | EA | 25 | 2000 | 50000
54 | Additional Corporation Stop Abandonment | EA | 20 | 1250 | 25000
55 | Primary Electrical Grounding System Installation | EA | 25 | 1500 | 37500
56 | Reconnection of Water Service Electrical Jumper Cable | EA | 1 | 350 | 350
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | CONTINGENCY BID ITEMS TOTAL: |  | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sub Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Vendors Notified: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
0 | Total Bid Item 1 with Contingency: |  | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
#REF!
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL Ø | [5 empty] | SECTION | Vendors Notified: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Public Water Service, Bored or Pulled, Copper, Complete, 1" | 33 | LF | 3300 |  | #REF! |  |  | 100
2 | Private Water Service, Bored or Pulled, Copper, Complete, 1" | 33 | LF | 3300 |  | #REF! |  |  | 100
3 | Private Water Service, Bored or Pulled, HDPE, Complete, 1" | 33 | LF | 3300 |  | #REF! |  |  | 100
4 | Sidewalk Removal & Replacement | 45 | SF | 225 |  | #REF! |  |  | 5
5 | Pavement Removal & Patch Replacement, Class D | 15 | SY | 600 |  | #REF! |  |  | 40
6 | Combination Curb and Gutter Removal & Replacement | 10 | LF | 200 |  | #REF! |  |  | 20
7 | Connection to Water Meter (Basement/Crawlspace), Complete | 1 | EA | 400 |  | #REF! |  |  | 400
8 | Restoration, Complete | 1 | LS | 300 |  | #REF! |  |  | 300
9 | Traffic Control and Protection | 1 | LS | 1 |  | #REF! |  |  | 1
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
| BASE BID ITEM #1: |  |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! |  |  |  | #REF!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | #REF!
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | #REF!
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | #REF!
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | #REF!
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL Ø | [5 empty] | SECTION | Vendors Notified: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
10 | PCC Pavement, Jointed, Removal and Replacement, 9" | 110 | SY | 17050 |  | 110 |  |  | 155
11 | PCC Approach Pavement Removal & Replacement, 6" | 55 | SY | 6050 |  | 55 |  |  | 110
12 | Tree Removal (6-15 Units) | 10 | UD | 500 |  | 10 |  |  | 50
13 | Tree Removal (Over 15 Units) | 15 | UD | 1200 |  | 15 |  |  | 80
14 | Rock Excavation | 30 | CY | 4500 |  | 30 |  |  | 150
15 | Hot-Mix Asphalt Approach Pavement Removal & Replacement, 3" | 55 | SY | 4675 |  | 55 |  |  | 85
16 | Retaining Wall, Modular Block, Complete | 45 | SY | 3600 |  | 45 |  |  | 80
17 | Retaining Wall, PCC Concrete, Complete | 45 | SF | 4500 |  | 45 |  |  | 100
18 | Silt Fence | 50 | SF | 250 |  | 50 |  |  | 5
19 | Inlet and Pipe Protection | 15 | LF | 1500 |  | 15 |  |  | 100
20 | Restoration, Open-Cut, Complete | 1 | LS | 300 |  | 1 |  |  | 300
21 | Water Meter Relocation, Complete | 15 | EA | 15000 |  | 15 |  |  | 1000
22 | Additional Set-up Boring Length | 25 | LF | 875 |  | 25 |  |  | 35
Sub Total |  |  |  | #REF!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL Ø | [5 empty] | SECTION | Vendors Notified: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
23 | Public Water Service, Open-Cut, Copper, Complete, 1" | 33 | LF | 4125 |  | 33 |  |  | 125
24 | Private Water Service, Open-Cut, Copper, Complete, 1" | 33 | LF | 3960 |  | 33 |  |  | 120
25 | Private Water Service, Open-Cut, HDPE, Complete, 1" | 33 | LF | 3795 |  | 33 |  |  | 115
26 | Public Water Service, Open-Cut, Copper, Complete, 1.5" | 33 | LF | 4455 |  | 33 |  |  | 135
27 | Private Water Service, Open-Cut, Copper, Complete, 1.5" | 33 | LF | 4290 |  | 33 |  |  | 130
28 | Private Water Service, Open-Cut, HDPE, Complete, 1.5" | 33 | LF | 3960 |  | 33 |  |  | 120
29 | Public Water Service, Open-Cut, Copper, Complete, 2" | 33 | LF | 4950 |  | 33 |  |  | 150
30 | Private Water Service, Open-Cut, Copper, Complete, 2" | 33 | LF | 4620 |  | 33 |  |  | 140
31 | Private Water Service, Open-Cut, HDPE, Complete, 2" | 33 | LF | 4290 |  | 33 |  |  | 130
32 | Public Water Service, Bored or Pulled, Copper, Complete 1.5" | 33 | LF | 4950 |  | 33 |  |  | 150
33 | Private Water Service, Bored or Pulled, Copper, Complete 1.5" | 33 | LF | 3960 |  | 33 |  |  | 120
34 | Private Water Service, Bored or Pulled, HDPE, Complete 1.5" | 33 | LF | 3795 |  | 33 |  |  | 115
50 | Brick Pavement, Complete | 10 | SY | 3000 |  | 10 |  |  | 300
51 | Exploratory Excavation, B-Box Service Material Identification | 1 | EA | 1000 |  | 1 |  |  | 1000
52 | Exploratory Excavation, Pulling Failure Reconnection | 1 | EA | 1000 |  | 1 |  |  | 1000
53 | Additional Service Line Abandonment | 25 | EA | 55000 |  | 25 |  |  | 2200
54 | Additional Corporation Stop Abandonment | 20 | EA | 44000 |  | 20 |  |  | 2200
55 | Primary Electrical Grounding System Installation | 25 | EA | 50000 |  | 25 |  |  | 2000
56 | Reconnection of Water Service Electrical Jumper Cable | 1 | EA | 1000 |  | 1 |  |  | 1000
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
CONTINGENCY BID ITEMS TOTAL:
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
Total |  |  |  | #REF!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL Ø | [5 empty] | SECTION | Vendors Notified: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total Bid Item 1 with Contingency:
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
Total |  |  |  | #REF!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Vendors Notified: 89
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | N-TRAK Group
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.