## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 5263452.3
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | Tree Removal, Acres | Acre | 4.78 | 12000 | 57360
2 | Earth Excavation, Special | Cu Yd | 41667 | 20 | 833340
3 | Removal and Disposal of Unsuitable Material | Cu Yd | 8100 | 20 | 162000
4 | Trench Backfill | Cu Yd | 502.2 | 18 | 9039.6
5 | Topsoil, Furnish and Place, 4" | Sq Yd | 45539 | 6 | 273234
6 | Seeding, Class 2A | Acre | 9.36 | 3000 | 28080
7 | Nitrogen Fertilizer Nutrient | Pound | 842.4 | 3 | 2527.2
8 | Phosphorous Fertilizer Nutrient | Pound | 842.4 | 3 | 2527.2
9 | Potassium Fertilizer Nutrient | Pound | 842.4 | 3 | 2527.2
10 | Erosion Control Blanket | Sq Yd | 45539 | 1.5 | 68308.5
11 | Temporary Erosion Control Seeding | Pound | 936 | 5 | 4680
12 | Temporary Ditch Checks | Foot | 383 | 10 | 3830
13 | Perimeter Erosion Barrier | Foot | 1000 | 2 | 2000
14 | Inlet and Pipe Protection | Each | 37 | 150 | 5550
15 | Stone Riprap, Class A4 | Sq Yd | 224.5 | 65 | 14592.5
16 | Stone Riprap, Class A5 | Sq Yd | 3066 | 85 | 260610
17 | Filter Fabric | Sq Yd | 3290.5 | 4 | 13162
18 | Aggregate Subgrade Improvement | Ton | 16605 | 18 | 298890
19 | Subbase Granular Material, Type B | Ton | 7662 | 18 | 137916
20 | Aggregate Base Course, Type B | Ton | 8005 | 20 | 160100
21 | Bituminous Materials (Prime Coat) | Gallon | 7122 | 0.5 | 3561
22 | Bituminous Materials (Tack Coat) | Gallon | 3074 | 0.5 | 1537
23 | Aggregate (Prime Coat) | Ton | 83 | 100 | 8300
24 | Hot-Mix Asphalt Binder Course, IL-19.0, N70 | Ton | 5908 | 70 | 413560
25 | Hot-Mix Asphalt Surface Course, IL-9.5, Mix "D", N70 | Ton | 3504 | 75 | 262800
26 | Portland Cement Concrete Driveway Pavement, 8" | Sq Yd | 1520.8 | 70 | 106456
27 | Hot-Mix Asphalt Surface Removal, 2" | Sq Yd | 6360 | 5 | 31800
28 | Aggregate Shoulders, Type B | Ton | 1731.6 | 20 | 34632
29 | Hot-Mix Asphalt Shoulders | Ton | 6 | 200 | 1200
30 | Concrete Headwall Removal | Each | 3 | 1000 | 3000
31 | Pipe Culvert Removal | Foot | 1185 | 10 | 11850
32 | Precast Reinforced Concrete Flared End Sections, 12" | Each | 18 | 700 | 12600
33 | Precast Reinforced Concrete Flared End Sections, 18" | Each | 1 | 1000 | 1000
34 | Traversable Pipe Grate For Concrete End Section | Foot | 606.1 | 60 | 36366
35 | Concrete End Section, Standard 542001, 15", 1:3 | Each | 3 | 2000 | 6000
36 | Concrete End Section, Standard 542001, 18", 1:3 | Each | 9 | 2500 | 22500
37 | Concrete End Section, Standard 542001, 21", 1:3 | Each | 1 | 3000 | 3000
38 | Concrete End Section, Standard 542001, 48", 1:3 | Each | 2 | 5000 | 10000
39 | Steel Flared End Sections, 12" | Each | 1 | 500 | 500
40 | Concrete End Section, Standard 542001, 36", 1:3 | Each | 1 | 4000 | 4000
41 | Concrete End Section, Standard 542011, 36", 1:3 | Each | 24 | 4800 | 115200
42 | Proposed Storm Sewer Connection to Existing Storm Sewer | Each | 1 | 500 | 500
43 | Pipe Culverts, Class A, Type 1, 12" | Foot | 617 | 50 | 30850
44 | Pipe Culverts, Class A, Type 1, 18" | Foot | 302 | 60 | 18120
45 | Pipe Culverts, Class A, Type 1, 21" | Foot | 56 | 70 | 3920
46 | Pipe Culverts, Class A, Type 1, 48" | Foot | 56 | 160 | 8960
47 | Pipe Culverts, Class A, Type 1, Equivalent Round-Size 36" | Foot | 624 | 175 | 109200
48 | Manholes, Type A, 4'-Diameter, Type 1 Frame, Closed Lid | Each | 1 | 3500 | 3500
49 | Manholes, Type A, 7'-Diameter, Type 1 Frame, Closed Lid | Each | 1 | 8000 | 8000
50 | Inlets, Type A, Special Grate | Each | 2 | 2500 | 5000
51 | Manholes To Be Adjusted | Each | 2 | 750 | 1500
52 | Manholes To Be Reconstructed | Each | 8 | 2000 | 16000
53 | Removing Manholes | Each | 2 | 1000 | 2000
54 | Combination Concrete Curb and Gutter, Type B-6.18 | Foot | 969.6 | 30 | 29088
55 | Chain Link Fence, 6' (Special) | Foot | 668 | 60 | 40080
56 | Chain Link Fence, 6' (Special) with Barbed Wire | Foot | 840 | 75 | 63000
57 | Non-Special Waste Disposal | Cu Yd | 500 | 25 | 12500
58 | Special Waste Disposal | Cu Yd | 500 | 30 | 15000
59 | Special Waste Plans and Reports | L Sum | 1 | 2000 | 2000
60 | Soil Disposal Analysis | Each | 25 | 500 | 12500
61 | Mobilization | L Sum | 1 | 20000 | 20000
62 | Traffic Control and Protection, Special | L Sum | 1 | 20000 | 20000
63 | Sign Panel - Type 1 | Sq Ft | 88 | 50 | 4400
64 | Telescoping Steel Sign Support | Foot | 168 | 30 | 5040
65 | Thermoplastic Pavement Marking-Letters and Symbols | Sq Ft | 145.1 | 6 | 870.6
66 | Thermoplastic Pavement Marking-Line 4" | Foot | 16806 | 1 | 16806
67 | Thermoplastic Pavement Marking-Line 8" | Foot | 763 | 4 | 3052
68 | Thermoplastic Pavement Marking-Line 12" | Foot | 661 | 4.5 | 2974.5
69 | Thermoplastic Pavement Marking-Line 24" | Foot | 320 | 5 | 1600
70 | Raised Reflective Pavement Marker Removal | Each | 68 | 20 | 1360
71 | Electric Service Installation | Each | 2 | 3000 | 6000
72 | Relocate Customer Service Pole and Accessories | L Sum | 1 | 5000 | 5000
73 | Underground Conduit, PVC, 2" Dia. | Foot | 179 | 15 | 2685
74 | Underground Conduit, PVC, 3" Dia. | Foot | 22 | 20 | 440
75 | Heavy-Duty Handhole, Portland Cement Concrete | Each | 2 | 1900 | 3800
76 | Handhole, Composite Concrete | Each | 1 | 900 | 900
77 | Electric Cable in Conduit, 600V (XLP-Type Use) 3/C, No. 10 | Foot | 246 | 5 | 1230
78 | Luminaire, LED, Horizontal Mount | Each | 2 | 1000 | 2000
79 | Lighting Controller, Pole Mounted, 120 Volt, 30 Amp | Each | 2 | 5000 | 10000
80 | Light Pole, Aluminum, 30 FT M.H., 8' Davit Arm | Each | 2 | 3500 | 7000
81 | Light Pole Foundation, 24" Diameter | Foot | 21 | 200 | 4200
82 | Removal of Pole Foundation | Each | 2 | 500 | 1000
83 | Relocate Existing Lighting Unit | Each | 4 | 1500 | 6000
84 | Electric Cable in Conduit, Signal, No. 14, 2C | Foot | 100 | 4 | 400
85 | Electric Cable in Conduit, Signal, No. 14, 3C | Foot | 100 | 4 | 400
86 | Electric Cable in Conduit, Signal, No. 14, 5C | Foot | 290 | 3 | 870
87 | Video Electric Cable in Conduit, No. 16, 3C | Foot | 100 | 5 | 500
88 | Video Cable in Conduit, Belden 8281 Coaxial | Foot | 100 | 5 | 500
89 | Preemptive Detector Device Cable in Conduit, No. 18, 3/C | Foot | 100 | 4 | 400
90 | Steel Combination Mast Arm Assembly and Pole, 48 Ft. | Each | 1 | 14000 | 14000
91 | Concrete Foundation, Type E, 36-Inch Diameter | Foot | 24 | 350 | 8400
92 | Signal Head, Polycarbonate, LED, 1-Face, 3-Section, Mast Arm Mounted | Each | 1 | 850 | 850
93 | Relocate Existing Signal Head | Each | 4 | 400 | 1600
94 | Relocate Existing Mast Arm Assembly and Pole | Each | 1 | 4500 | 4500
95 | Modify Existing Controller | Each | 1 | 1500 | 1500
96 | Remove Existing Handhole | Each | 2 | 400 | 800
97 | Remove Existing Concrete Foundation | Each | 2 | 700 | 1400
98 | Relocate Existing Traffic Signal Equipment, Special | L Sum | 1 | 15000 | 15000
99 | Remove Existing Traffic Signal Equipment, Special | L Sum | 1 | 5000 | 5000
100 | Construction Layout | L Sum | 1 | 20000 | 20000
101 | Fence Removal | Foot | 3058 | 5 | 15290
102 | Chain Link Gates To Be Removed and Re-erected | Each | 1 | 3500 | 3500
103 | Ductile Iron Water Main Complete, 6" | Foot | 15 | 200 | 3000
104 | Ductile Iron Water Main Complete, 8" | Foot | 32 | 200 | 6400
105 | Ductile Iron Water Main Complete, 12" | Foot | 4041 | 210 | 848610
106 | Gate Valve and Valve Box Complete, 6" | Each | 1 | 2500 | 2500
107 | Gate Valve and Valve Box Complete, 8" | Each | 2 | 3000 | 6000
108 | Butterfly Valve and Valve Box, Complete, 12" | Each | 11 | 4000 | 44000
109 | Fire Hydrant with 6" Valve and Valve Box, Complete | Each | 14 | 6500 | 91000
110 | Water Service (Open-Cut), Complete, 1" | Each | 1 | 1400 | 1400
111 | Water Service (Open-Cut), Complete, 1.5" | Each | 1 | 8500 | 8500
112 | Water Main Quality Casing Pipe, 24" | Foot | 304 | 80 | 24320
113 | Connect To Existing 6" Water Main, Complete | Each | 1 | 3000 | 3000
114 | Connect To Existing 8" Water Main, Complete | Each | 2 | 3500 | 7000
115 | Connect To Existing 12" Water Main, Complete | Each | 3 | 4000 | 12000
116 | Remove Fire Hydrant, Complete | Each | 3 | 1200 | 3600
117 | Water Main Line Stop, 6" | Each | 3 | 4000 | 12000
118 | Water Main Line Stop, 8" | Each | 2 | 5000 | 10000
119 | Water Main Line Stop, 12" | Each | 3 | 7500 | 22500
120 | Insertion Valve, Complete, 6" | Each | 3 | 5000 | 15000
121 | Insertion Valve, Complete, 8" | Each | 2 | 6000 | 12000
122 | Insertion Valve, Complete, 12" | Each | 3 | 11000 | 33000
123 | Sanitary Sewer, PVC - 12" (WMQ/SDR 26) | Foot | 150 | 160 | 24000
124 | Sanitary Inside Drop Manhole - 5' Dia. (Over Trunk Sewer) | Each | 1 | 18000 | 18000
125 | Sanitary Manhole - 5' Dia. | Each | 1 | 10000 | 10000
126 | Connect To Existing 42" Trunk Sewer | L Sum | 1 | 8000 | 8000
127 | Sanitary Sewer System Abandonment, Complete | L Sum | 1 | 4500 | 4500
128

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Northern Illinois Service |  | N-Trak Group |  | William Charles |  | Stenstrom Excavating
City of Rockford | [5 empty] | Rockford, IL |  | Loves Park, IL |  | Rockford, IL |  | Rockford, IL
Logistics Parkway - Phase II | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond
Bid No.: 622-PW-058 VENDORS NOTIFIED: 102
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Tree Removal, Acres | Acre | 4.78 | 12000 | 57360 | 7500 | 35850 | 8500 | 40630 | 7578.87 | 36226.9986 | 8000 | 38240 |  | 0 |  | 0
2 | Earth Excavation, Special | Cu Yd | 41667 | 20 | 833340 | 18.73 | 780422.91 | 20.5 | 854173.5 | 18.4 | 766672.8 | 19.65 | 818756.55 |  | 0 |  | 0
3 | Removal and Disposal of Unsuitable Material | Cu Yd | 8100 | 20 | 162000 | 20 | 162000 | 0.01 | 81 | 18.17 | 147177 | 23.8 | 192780 |  | 0 |  | 0
4 | Trench Backfill | Cu Yd | 502.2 | 18 | 9039.6 | 0.01 | 5.022 | 25 | 12555 | 0.01 | 5.022 | 1 | 502.2 |  | 0 |  | 0
5 | Topsoil, Furnish and Place, 4" | Sq Yd | 45539 | 6 | 273234 | 0.01 | 455.39 | 1.5 | 68308.5 | 0.01 | 455.39 | 4 | 182156 |  | 0 |  | 0
6 | Seeding, Class 2A | Acre | 9.36 | 3000 | 28080 | 3970 | 37159.2 | 3970 | 37159.2 | 3216.47 | 30106.1592 | 4235 | 39639.6 |  | 0 |  | 0
7 | Nitrogen Fertilizer Nutrient | Pound | 842.4 | 3 | 2527.2 | 3 | 2527.2 | 3 | 2527.2 | 3.03 | 2552.472 | 3.2 | 2695.68 |  | 0 |  | 0
8 | Phosphorous Fertilizer Nutrient | Pound | 842.4 | 3 | 2527.2 | 3 | 2527.2 | 3 | 2527.2 | 3.03 | 2552.472 | 3.2 | 2695.68 |  | 0 |  | 0
9 | Potassium Fertilizer Nutrient | Pound | 842.4 | 3 | 2527.2 | 3 | 2527.2 | 3 | 2527.2 | 3.03 | 2552.472 | 3.2 | 2695.68 |  | 0 |  | 0
10 | Erosion Control Blanket | Sq Yd | 45539 | 1.5 | 68308.5 | 1.45 | 66031.55 | 1.45 | 66031.55 | 1.21 | 55102.19 | 1.55 | 70585.45 |  | 0 |  | 0
11 | Temporary Erosion Control Seeding | Pound | 936 | 5 | 4680 | 1.5 | 1404 | 1.5 | 1404 | 6.06 | 5672.16 | 1.6 | 1497.6 |  | 0 |  | 0
12 | Temporary Ditch Checks | Foot | 383 | 10 | 3830 | 11 | 4213 | 11 | 4213 | 5.66 | 2167.78 | 11.75 | 4500.25 |  | 0 |  | 0
13 | Perimeter Erosion Barrier | Foot | 1000 | 2 | 2000 | 4.2 | 4200 | 4.2 | 4200 | 3.44 | 3440 | 4.5 | 4500 |  | 0 |  | 0
14 | Inlet and Pipe Protection | Each | 37 | 150 | 5550 | 120 | 4440 | 120 | 4440 | 101.05 | 3738.85 | 120 | 4440 |  | 0 |  | 0
15 | Stone Riprap, Class A4 | Sq Yd | 224.5 | 65 | 14592.5 | 55 | 12347.5 | 60 | 13470 | 54.37 | 12206.065 | 28.25 | 6342.125 |  | 0 |  | 0
16 | Stone Riprap, Class A5 | Sq Yd | 3066 | 85 | 260610 | 55 | 168630 | 67 | 205422 | 51.33 | 157377.78 | 27.65 | 84774.9 |  | 0 |  | 0
17 | Filter Fabric | Sq Yd | 3290.5 | 4 | 13162 | 4 | 13162 | 4 | 13162 | 5.65 | 18591.325 | 4.45 | 14642.725 |  | 0 |  | 0
18 | Aggregate Subgrade Improvement | Ton | 16605 | 18 | 298890 | 16 | 265680 | 0.01 | 166.05 | 13.3 | 220846.5 | 24.25 | 402671.25 |  | 0 |  | 0
19 | Subbase Granular Material, Type B | Ton | 7662 | 18 | 137916 | 16 | 122592 | 15 | 114930 | 14.21 | 108877.02 | 18.5 | 141747 |  | 0 |  | 0
20 | Aggregate Base Course, Type B | Ton | 8005 | 20 | 160100 | 16 | 128080 | 17 | 136085 | 16.8 | 134484 | 20.4 | 163302 |  | 0 |  | 0
21 | Bituminous Materials (Prime Coat) | Gallon | 7122 | 0.5 | 3561 | 0.01 | 71.22 | 0.01 | 71.22 | 2.5 | 17805 | 0.01 | 71.22 |  | 0 |  | 0
22 | Bituminous Materials (Tack Coat) | Gallon | 3074 | 0.5 | 1537 | 0.01 | 30.74 | 0.01 | 30.74 | 2.5 | 7685 | 0.01 | 30.74 |  | 0 |  | 0
23 | Aggregate (Prime Coat) | Ton | 83 | 100 | 8300 | 0.01 | 0.83 | 0.01 | 0.83 | 0.01 | 0.83 | 0.01 | 0.83 |  | 0 |  | 0
24 | Hot-Mix Asphalt Binder Course, IL-19.0, N70 | Ton | 5908 | 70 | 413560 | 80.25 | 474117 | 85 | 502180 | 79 | 466732 | 85.6 | 505724.8 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 2767232.2 |  | 2288473.962 |  | 2086295.19 |  | 2203027.2858 |  | 2684992.28
| Award to Northern Illinois Service | Total |  | As corrected | 2767232.2 |  | 2288473.962 |  | 2086295.19 |  | 2203027.2858 |  | 2684992.28
25 | Hot-Mix Asphalt Surface Course, IL-9.5, Mix "D", N70 | Ton | 3504 | 75 | 262800 | 86 | 301344 | 87 | 304848 | 87 | 304848 | 91.75 | 321492 |  | 0 |  | 0
26 | Portland Cement Concrete Driveway Pavement, 8" | Sq Yd | 1520.8 | 70 | 106456 | 65 | 98852 | 80 | 121664 | 65.68 | 99886.144 | 60 | 91248 |  | 0 |  | 0
27 | Hot-Mix Asphalt Surface Removal, 2" | Sq Yd | 6360 | 5 | 31800 | 2.74 | 17426.4 | 3.05 | 19398 | 5 | 31800 | 3.25 | 20670 |  | 0 |  | 0
28 | Aggregate Shoulders, Type B | Ton | 1731.6 | 20 | 34632 | 18 | 31168.8 | 18 | 31168.8 | 21.81 | 37766.196 | 29 | 50216.4 |  | 0 |  | 0
29 | Hot-Mix Asphalt Shoulders | Ton | 6 | 200 | 1200 | 75 | 450 | 150 | 900 | 350 | 2100 | 80 | 480 |  | 0 |  | 0
30 | Concrete Headwall Removal | Each | 3 | 1000 | 3000 | 250 | 750 | 400 | 1200 | 542.17 | 1626.51 | 360 | 1080 |  | 0 |  | 0
31 | Pipe Culvert Removal | Foot | 1185 | 10 | 11850 | 10 | 11850 | 20 | 23700 | 20.89 | 24754.65 | 28 | 33180 |  | 0 |  | 0
32 | Precast Reinforced Concrete Flared End Sections, 12" | Each | 18 | 700 | 12600 | 700 | 12600 | 950 | 17100 | 979.29 | 17627.22 | 930 | 16740 |  | 0 |  | 0
33 | Precast Reinforced Concrete Flared End Sections, 18" | Each | 1 | 1000 | 1000 | 800 | 800 | 1050 | 1050 | 1500 | 1500 | 1040 | 1040 |  | 0 |  | 0
34 | Traversable Pipe Grate For Concrete End Section | Foot | 606.1 | 60 | 36366 | 120 | 72732 | 120 | 72732 | 161.25 | 97733.625 | 130 | 78793 |  | 0 |  | 0
35 | Concrete End Section, Standard 542001, 15", 1:3 | Each | 3 | 2000 | 6000 | 1900 | 5700 | 2900 | 8700 | 1037.74 | 3113.22 | 670 | 2010 |  | 0 |  | 0
36 | Concrete End Section, Standard 542001, 18", 1:3 | Each | 9 | 2500 | 22500 | 2200 | 19800 | 3200 | 28800 | 2131.31 | 19181.79 | 900 | 8100 |  | 0 |  | 0
37 | Concrete End Section, Standard 542001, 21", 1:3 | Each | 1 | 3000 | 3000 | 2500 | 2500 | 3300 | 3300 | 5276.14 | 5276.14 | 2455 | 2455 |  | 0 |  | 0
38 | Concrete End Section, Standard 542001, 48", 1:3 | Each | 2 | 5000 | 10000 | 8000 | 16000 | 8600 | 17200 | 8628.46 | 17256.92 | 7545 | 15090 |  | 0 |  | 0
39 | Steel Flared End Sections, 12" | Each | 1 | 500 | 500 | 400 | 400 | 300 | 300 | 1000 | 1000 | 370 | 370 |  | 0 |  | 0
40 | Concrete End Section, Standard 542001, 36", 1:3 | Each | 1 | 4000 | 4000 | 4500 | 4500 | 6000 | 6000 | 4838.24 | 4838.24 | 4895 | 4895 |  | 0 |  | 0
41 | Concrete End Section, Standard 542011, 36", 1:3 | Each | 24 | 4800 | 115200 | 5500 | 132000 | 6600 | 158400 | 7263.88 | 174333.12 | 5485 | 131640 |  | 0 |  | 0
42 | Proposed Storm Sewer Connection to Existing Storm Sewer | Each | 1 | 500 | 500 | 1000 | 1000 | 1300 | 1300 | 209.98 | 209.98 | 750 | 750 |  | 0 |  | 0
43 | Pipe Culverts, Class A, Type 1, 12" | Foot | 617 | 50 | 30850 | 45 | 27765 | 70 | 43190 | 52.21 | 32213.57 | 76 | 46892 |  | 0 |  | 0
44 | Pipe Culverts, Class A, Type 1, 18" | Foot | 302 | 60 | 18120 | 50 | 15100 | 75 | 22650 | 60.88 | 18385.76 | 87 | 26274 |  | 0 |  | 0
45 | Pipe Culverts, Class A, Type 1, 21" | Foot | 56 | 70 | 3920 | 60 | 3360 | 80 | 4480 | 43.4 | 2430.4 | 106 | 5936 |  | 0 |  | 0
46 | Pipe Culverts, Class A, Type 1, 48" | Foot | 56 | 160 | 8960 | 130 | 7280 | 185 | 10360 | 140.15 | 7848.4 | 200 | 11200 |  | 0 |  | 0
47 | Pipe Culverts, Class A, Type 1, Equivalent Round-Size 36" | Foot | 624 | 175 | 109200 | 135 | 84240 | 175 | 109200 | 169.68 | 105880.32 | 192 | 119808 |  | 0 |  | 0
48 | Manholes, Type A, 4'-Diameter, Type 1 Frame, Closed Lid | Each | 1 | 3500 | 3500 | 3000 | 3000 | 2400 | 2400 | 1256.02 | 1256.02 | 3800 | 3800 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 3605186.2 |  | 3159092.162 |  | 3096335.99 |  | 3215893.5108 |  | 3679151.68
| Award to Northern Illinois Service | Total |  | As corrected | 3605186.2 |  | 3159092.162 |  | 3096335.99 |  | 3215893.5108 |  | 3679151.68
49 | Manholes, Type A, 7'-Diameter, Type 1 Frame, Closed Lid | Each | 1 | 8000 | 8000 | 12000 | 12000 | 8000 | 8000 | 7889.16 | 7889.16 | 8425 | 8425 |  | 0 |  | 0
50 | Inlets, Type A, Special Grate | Each | 2 | 2500 | 5000 | 2500 | 5000 | 1450 | 2900 | 1023.43 | 2046.86 | 2200 | 4400 |  | 0 |  | 0
51 | Manholes To Be Adjusted | Each | 2 | 750 | 1500 | 1000 | 2000 | 1300 | 2600 | 1279.12 | 2558.24 | 420 | 840 |  | 0 |  | 0
52 | Manholes To Be Reconstructed | Each | 8 | 2000 | 16000 | 2000 | 16000 | 3000 | 24000 | 3049.84 | 24398.72 | 2200 | 17600 |  | 0 |  | 0
53 | Removing Manholes | Each | 2 | 1000 | 2000 | 500 | 1000 | 1000 | 2000 | 500 | 1000 | 2500 | 5000 |  | 0 |  | 0
54 | Combination Concrete Curb and Gutter, Type B-6.18 | Foot | 969.6 | 30 | 29088 | 40.5 | 39268.8 | 32 | 31027.2 | 40.93 | 39685.728 | 32 | 31027.2 |  | 0 |  | 0
55 | Chain Link Fence, 6' (Special) | Foot | 668 | 60 | 40080 | 38.68 | 25838.24 | 57 | 38076 | 39.09 | 26112.12 | 41 | 27388 |  | 0 |  | 0
56 | Chain Link Fence, 6' (Special) with Barbed Wire | Foot | 840 | 75 | 63000 | 43.39 | 36447.6 | 59 | 49560 | 43.85 | 36834 | 46 | 38640 |  | 0 |  | 0
57 | Non-Special Waste Disposal | Cu Yd | 500 | 25 | 12500 | 0.01 | 5 | 0.01 | 5 | 40.05 | 20025 | 55 | 27500 |  | 0 |  | 0
58 | Special Waste Disposal | Cu Yd | 500 | 30 | 15000 | 0.01 | 5 | 0.01 | 5 | 40.02 | 20010 | 70 | 35000 |  | 0 |  | 0
59 | Special Waste Plans and Reports | L Sum | 1 | 2000 | 2000 | 0.01 | 0.01 | 0.01 | 0.01 | 2627.34 | 2627.34 | 6400 | 6400 |  | 0 |  | 0
60 | Soil Disposal Analysis | Each | 25 | 500 | 12500 | 0.01 | 0.25 | 0.01 | 0.25 | 1111.57 | 27789.25 | 960 | 24000 |  | 0 |  | 0
61 | Mobilization | L Sum | 1 | 20000 | 20000 | 119641.2 | 119641.2 | 275000 | 275000 | 268900 | 268900 | 32000 | 32000 |  | 0 |  | 0
62 | Traffic Control and Protection, Special | L Sum | 1 | 20000 | 20000 | 15000 | 15000 | 16000 | 16000 | 15915.63 | 15915.63 | 17000 | 17000 |  | 0 |  | 0
63 | Sign Panel - Type 1 | Sq Ft | 88 | 50 | 4400 | 30 | 2640 | 30 | 2640 | 30.32 | 2668.16 | 32 | 2816 |  | 0 |  | 0
64 | Telescoping Steel Sign Support | Foot | 168 | 30 | 5040 | 17 | 2856 | 17 | 2856 | 17.18 | 2886.24 | 18 | 3024 |  | 0 |  | 0
65 | Thermoplastic Pavement Marking-Letters and Symbols | Sq Ft | 145.1 | 6 | 870.6 | 5 | 725.5 | 5 | 725.5 | 5.05 | 732.755 | 5.35 | 776.285 |  | 0 |  | 0
66 | Thermoplastic Pavement Marking-Line 4" | Foot | 16806 | 1 | 16806 | 0.8 | 13444.8 | 0.8 | 13444.8 | 0.81 | 13612.86 | 0.85 | 14285.1 |  | 0 |  | 0
67 | Thermoplastic Pavement Marking-Line 8" | Foot | 763 | 4 | 3052 | 1.6 | 1220.8 | 1.6 | 1220.8 | 1.62 | 1236.06 | 1.75 | 1335.25 |  | 0 |  | 0
68 | Thermoplastic Pavement Marking-Line 12" | Foot | 661 | 4.5 | 2974.5 | 2.4 | 1586.4 | 2.4 | 1586.4 | 2.43 | 1606.23 | 2.6 | 1718.6 |  | 0 |  | 0
69 | Thermoplastic Pavement Marking-Line 24" | Foot | 320 | 5 | 1600 | 4.8 | 1536 | 4.8 | 1536 | 4.85 | 1552 | 5.15 | 1648 |  | 0 |  | 0
70 | Raised Reflective Pavement Marker Removal | Each | 68 | 20 | 1360 | 21 | 1428 | 15 | 1020 | 18.63 | 1266.84 | 22.45 | 1526.6 |  | 0 |  | 0
71 | Electric Service Installation | Each | 2 | 3000 | 6000 | 2582 | 5164 | 2582 | 5164 | 2403.31 | 4806.62 | 2755 | 5510 |  | 0 |  | 0
72 | Relocate Customer Service Pole and Accessories | L Sum | 1 | 5000 | 5000 | 23948 | 23948 | 23948 | 23948 | 22356.37 | 22356.37 | 25550 | 25550 |  | 0 |  | 0
| Page 3 | Sub |  | As read | 3898957.3 |  | 3485847.762 |  | 3599650.95 |  | 3764409.6938 |  | 4012561.715
| Award to Northern Illinois Service | Total |  | As corrected | 3898957.3 |  | 3485847.762 |  | 3599650.95 |  | 3764409.6938 |  | 4012561.715
73 | Underground Conduit, PVC, 2" Dia. | Foot | 179 | 15 | 2685 | 31 | 5549 | 31 | 5549 | 28.94 | 5180.26 | 33 | 5907 |  |  |  | 0
74 | Underground Conduit, PVC, 3" Dia. | Foot | 22 | 20 | 440 | 61.5 | 1353 | 61.5 | 1353 | 57.21 | 1258.62 | 66 | 1452 |  |  |  | 0
75 | Heavy-Duty Handhole, Portland Cement Concrete | Each | 2 | 1900 | 3800 | 3675 | 7350 | 3675 | 7350 | 3427.89 | 6855.78 | 3920 | 7840 |  |  |  | 0
76 | Handhole, Composite Concrete | Each | 1 | 900 | 900 | 3158 | 3158 | 3158 | 3158 | 2947.7 | 2947.7 | 3370 | 3370 |  |  |  | 0
77 | Electric Cable in Conduit, 600V (XLP-Type Use) 3/C, No. 10 | Foot | 246 | 5 | 1230 | 3.5 | 861 | 3.5 | 861 | 3.21 | 789.66 | 3.75 | 922.5 |  |  |  | 0
78 | Luminaire, LED, Horizontal Mount | Each | 2 | 1000 | 2000 | 1572 | 3144 | 1572 | 3144 | 1448.27 | 2896.54 | 1675 | 3350 |  |  |  | 0
79 | Lighting Controller, Pole Mounted, 120 Volt, 30 Amp | Each | 2 | 5000 | 10000 | 1849 | 3698 | 1849 | 3698 | 1721.47 | 3442.94 | 1975 | 3950 |  |  |  | 0
80 | Light Pole, Aluminum, 30 FT M.H., 8' Davit Arm | Each | 2 | 3500 | 7000 | 11476 | 22952 | 11476 | 22952 | 10565.32 | 21130.64 | 12250 | 24500 |  |  |  | 0
81 | Light Pole Foundation, 24" Diameter | Foot | 21 | 200 | 4200 | 296 | 6216 | 296 | 6216 | 274.68 | 5768.28 | 316 | 6636 |  |  |  | 0
82 | Removal of Pole Foundation | Each | 2 | 500 | 1000 | 350 | 700 | 350 | 700 | 327.07 | 654.14 | 375 | 750 |  |  |  | 0
83 | Relocate Existing Lighting Unit | Each | 4 | 1500 | 6000 | 760 | 3040 | 760 | 3040 | 709.88 | 2839.52 | 810 | 3240 |  |  |  | 0
84 | Electric Cable in Conduit, Signal, No. 14, 2C | Foot | 100 | 4 | 400 | 2.45 | 245 | 2.45 | 245 | 2.26 | 226 | 2.6 | 260 |  |  |  | 0
85 | Electric Cable in Conduit, Signal, No. 14, 3C | Foot | 100 | 4 | 400 | 2.8 | 280 | 2.8 | 280 | 2.57 | 257 | 3 | 300 |  |  |  | 0
86 | Electric Cable in Conduit, Signal, No. 14, 5C | Foot | 290 | 3 | 870 | 3.5 | 1015 | 3.5 | 1015 | 3.17 | 919.3 | 3.75 | 1087.5 |  |  |  | 0
87 | Video Electric Cable in Conduit, No. 16, 3C | Foot | 100 | 5 | 500 | 2.45 | 245 | 2.45 | 245 | 2.26 | 226 | 2.6 | 260 |  |  |  | 0
88 | Video Cable in Conduit, Belden 8281 Coaxial | Foot | 100 | 5 | 500 | 3.9 | 390 | 3.9 | 390 | 3.54 | 354 | 4.15 | 415 |  |  |  | 0
89 | Preemptive Detector Device Cable in Conduit, No. 18, 3/C | Foot | 100 | 4 | 400 | 3.5 | 350 | 3.5 | 350 | 3.23 | 323 | 3.75 | 375 |  |  |  | 0
90 | Steel Combination Mast Arm Assembly and Pole, 48 Ft. | Each | 1 | 14000 | 14000 | 26340 | 26340 | 26340 | 26340 | 24266.3 | 24266.3 | 28100 | 28100 |  |  |  | 0
91 | Concrete Foundation, Type E, 36-Inch Diameter | Foot | 24 | 350 | 8400 | 368 | 8832 | 368 | 8832 | 341.48 | 8195.52 | 390 | 9360 |  |  |  | 0
92 | Signal Head, Polycarbonate, LED, 1-Face, 3-Section, Mast Arm Mounted | Each | 1 | 850 | 850 | 1025 | 1025 | 1025 | 1025 | 950.22 | 950.22 | 1100 | 1100 |  |  |  | 0
93 | Relocate Existing Signal Head | Each | 4 | 400 | 1600 | 298 | 1192 | 298 | 1192 | 277.55 | 1110.2 | 315 | 1260 |  |  |  | 0
94 | Relocate Existing Mast Arm Assembly and Pole | Each | 1 | 4500 | 4500 | 3148 | 3148 | 3148 | 3148 | 2937.3 | 2937.3 | 3360 | 3360 |  |  |  | 0
95 | Modify Existing Controller | Each | 1 | 1500 | 1500 | 4710 | 4710 | 4710 | 4710 | 1271.87 | 1271.87 | 5025 | 5025 |  |  |  | 0
96 | Remove Existing Handhole | Each | 2 | 400 | 800 | 350 | 700 | 350 | 700 | 327.07 | 654.14 | 375 | 750 |  |  |  | 0
| Page 4 | Sub |  | As read | 3972932.3 |  | 3592340.762 |  | 3706143.95 |  | 3859864.6238 |  | 4126131.715
| Award to Northern Illinois Service | Total |  | As corrected | 3972932.3 |  | 3592340.762 |  | 3706143.95 |  | 3859864.6238 |  | 4126131.715
97 | Remove Existing Concrete Foundation | Each | 2 | 700 | 1400 | 350 | 700 | 350 | 700 | 327.07 | 654.14 | 375 | 750 |  |  |  | 0
98 | Relocate Existing Traffic Signal Equipment, Special | L Sum | 1 | 15000 | 15000 | 4230 | 4230 | 4230 | 4230 | 3956.1 | 3956.1 | 4520 | 4520 |  |  |  | 0
99 | Remove Existing Traffic Signal Equipment, Special | L Sum | 1 | 5000 | 5000 | 2116 | 2116 | 2116 | 2116 | 1978.05 | 1978.05 | 2260 | 2260 |  |  |  | 0
100 | Construction Layout | L Sum | 1 | 20000 | 20000 | 20000 | 20000 | 28150 | 28150 | 28446.04 | 28446.04 | 30000 | 30000 |  |  |  | 0
101 | Fence Removal | Foot | 3058 | 5 | 15290 | 5 | 15290 | 8 | 24464 | 3.3 | 10091.4 | 6.25 | 19112.5 |  |  |  | 0
102 | Chain Link Gates To Be Removed and Re-erected | Each | 1 | 3500 | 3500 | 1210 | 1210 | 4000 | 4000 | 1222.72 | 1222.72 | 1290 | 1290 |  |  |  | 0
103 | Ductile Iron Water Main Complete, 6" | Foot | 15 | 200 | 3000 | 145.7 | 2185.5 | 160 | 2400 | 344 | 5160 | 230 | 3450 |  |  |  | 0
104 | Ductile Iron Water Main Complete, 8" | Foot | 32 | 200 | 6400 | 145.7 | 4662.4 | 160 | 5120 | 253.54 | 8113.28 | 167 | 5344 |  |  |  | 0
105 | Ductile Iron Water Main Complete, 12" | Foot | 4041 | 210 | 848610 | 145.7 | 588773.7 | 130 | 525330 | 130.31 | 526582.71 | 161 | 650601 |  |  |  | 0
106 | Gate Valve and Valve Box Complete, 6" | Each | 1 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2342.45 | 2342.45 | 2000 | 2000 |  |  |  | 0
107 | Gate Valve and Valve Box Complete, 8" | Each | 2 | 3000 | 6000 | 3000 | 6000 | 3100 | 6200 | 2912.82 | 5825.64 | 2600 | 5200 |  |  |  | 0
108 | Butterfly Valve and Valve Box, Complete, 12" | Each | 11 | 4000 | 44000 | 4200 | 46200 | 4400 | 48400 | 4163.27 | 45795.97 | 3900 | 42900 |  |  |  | 0
109 | Fire Hydrant with 6" Valve and Valve Box, Complete | Each | 14 | 6500 | 91000 | 6500 | 91000 | 6000 | 84000 | 10058.39 | 140817.46 | 7345 | 102830 |  |  |  | 0
110 | Water Service (Open-Cut), Complete, 1" | Each | 1 | 1400 | 1400 | 2700 | 2700 | 3000 | 3000 | 4371.94 | 4371.94 | 5680 | 5680 |  |  |  | 0
111 | Water Service (Open-Cut), Complete, 1.5" | Each | 1 | 8500 | 8500 | 4000 | 4000 | 6500 | 6500 | 8369.6 | 8369.6 | 6875 | 6875 |  |  |  | 0
112 | Water Main Quality Casing Pipe, 24" | Foot | 304 | 80 | 24320 | 215 | 65360 | 200 | 60800 | 245.81 | 74726.24 | 215 | 65360 |  |  |  | 0
113 | Connect To Existing 6" Water Main, Complete | Each | 1 | 3000 | 3000 | 2000 | 2000 | 2000 | 2000 | 3385.19 | 3385.19 | 1900 | 1900 |  |  |  | 0
114 | Connect To Existing 8" Water Main, Complete | Each | 2 | 3500 | 7000 | 3000 | 6000 | 2200 | 4400 | 3465.62 | 6931.24 | 2660 | 5320 |  |  |  | 0
115 | Connect To Existing 12" Water Main, Complete | Each | 3 | 4000 | 12000 | 3000 | 9000 | 5100 | 15300 | 4576.06 | 13728.18 | 2820 | 8460 |  |  |  | 0
116 | Remove Fire Hydrant, Complete | Each | 3 | 1200 | 3600 | 500 | 1500 | 900 | 2700 | 784.32 | 2352.96 | 1250 | 3750 |  |  |  | 0
117 | Water Main Line Stop, 6" | Each | 3 | 4000 | 12000 | 4000 | 12000 | 5000 | 15000 | 8068.82 | 24206.46 | 5590 | 16770 |  |  |  | 0
118 | Water Main Line Stop, 8" | Each | 2 | 5000 | 10000 | 4500 | 9000 | 5200 | 10400 | 8555.28 | 17110.56 | 6000 | 12000 |  |  |  | 0
119 | Water Main Line Stop, 12" | Each | 3 | 7500 | 22500 | 7000 | 21000 | 7000 | 21000 | 11010.55 | 33031.65 | 7580 | 22740 |  |  |  | 0
120 | Insertion Valve, Complete, 6" | Each | 3 | 5000 | 15000 | 6000 | 18000 | 5500 | 16500 | 10259.69 | 30779.07 | 8615 | 25845 |  |  |  | 0
| Page 5 | Sub |  | As read | 5153952.3 |  | 4527768.362 |  | 4601353.95 |  | 4859843.6738 |  | 5171089.215
| Award to Northern Illinois Service | Total |  | As corrected | 5153952.3 |  | 4527768.362 |  | 4601353.95 |  | 4859843.6738 |  | 5171089.215
121 | Insertion Valve, Complete, 8" | Each | 2 | 6000 | 12000 | 8000 | 16000 | 7200 | 14400 | 11111.8 | 22223.6 | 9470 | 18940 |  | 0 |  | 0
122 | Insertion Valve, Complete, 12" | Each | 3 | 11000 | 33000 | 12100 | 36300 | 11750 | 35250 | 15377.5 | 46132.5 | 12880 | 38640 |  | 0 |  | 0
123 | Sanitary Sewer, PVC - 12" (WMQ/SDR 26) | Foot | 150 | 160 | 24000 | 175 | 26250 | 225 | 33750 | 149.27 | 22390.5 | 230 | 34500 |  | 0 |  | 0
124 | Sanitary Inside Drop Manhole - 5' Dia. (Over Trunk Sewer) | Each | 1 | 18000 | 18000 | 35000 | 35000 | 19500 | 19500 | 12708.48 | 12708.48 | 16755 | 16755 |  | 0 |  | 0
125 | Sanitary Manhole - 5' Dia. | Each | 1 | 10000 | 10000 | 6000 | 6000 | 9300 | 9300 | 8057.57 | 8057.57 | 14750 | 14750 |  | 0 |  | 0
126 | Connect To Existing 42" Trunk Sewer | L Sum | 1 | 8000 | 8000 | 5000 | 5000 | 10000 | 10000 | 11905.94 | 11905.94 | 8300 | 8300 |  | 0 |  | 0
127 | Sanitary Sewer System Abandonment, Complete | L Sum | 1 | 4500 | 4500 | 1000 | 1000 | 5000 | 5000 | 6681 | 6681 | 21555 | 21555 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 6 | Total |  | As read | 5263452.3 |  | 4653318.362 |  | 4728553.95 |  | 4989943.2638 |  | 5318622.22
| Award to Northern Illinois Service | Bid |  | As corrected | 5263452.3 |  | 4653318.362 |  | 4728553.95 |  | 4989943.2638 |  | 5324529.215
0

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Logistics Parkway - Phase II
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Tree Removal, Acres | Acre | 4.78 |  | 0
2 | Earth Excavation, Special | Cu Yd | 41667 |  | 0
3 | Removal and Disposal of Unsuitable Material | Cu Yd | 8100 |  | 0
4 | Trench Backfill | Cu Yd | 502.2 |  | 0
5 | Topsoil, Furnish and Place, 4" | Sq Yd | 45539 |  | 0
6 | Seeding, Class 2A | Acre | 9.36 |  | 0
7 | Nitrogen Fertilizer Nutrient | Pound | 842.4 |  | 0
8 | Phosphorous Fertilizer Nutrient | Pound | 842.4 |  | 0
9 | Potassium Fertilizer Nutrient | Pound | 842.4 |  | 0
10 | Erosion Control Blanket | Sq Yd | 45539 |  | 0
11 | Temporary Erosion Control Seeding | Pound | 936 |  | 0
12 | Temporary Ditch Checks | Foot | 383 |  | 0
13 | Perimeter Erosion Barrier | Foot | 1000 |  | 0
14 | Inlet and Pipe Protection | Each | 37 |  | 0
15 | Stone Riprap, Class A4 | Sq Yd | 224.5 |  | 0
16 | Stone Riprap, Class A5 | Sq Yd | 3066 |  | 0
17 | Filter Fabric | Sq Yd | 3290.5 |  | 0
18 | Aggregate Subgrade Improvement | Ton | 16605 |  | 0
19 | Subbase Granular Material, Type B | Ton | 7662 |  | 0
20 | Aggregate Base Course, Type B | Ton | 8005 |  | 0
21 | Bituminous Materials (Prime Coat) | Gallon | 7122 |  | 0
22 | Bituminous Materials (Tack Coat) | Gallon | 3074 |  | 0
23 | Aggregate (Prime Coat) | Ton | 83 |  | 0
24 | Hot-Mix Asphalt Binder Course, IL-19.0, N70 | Ton | 5908 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Hot-Mix Asphalt Surface Course, IL-9.5, Mix "D", N70 | Ton | 3504 |  | 0
26 | Portland Cement Concrete Driveway Pavement, 8" | Sq Yd | 1520.8 |  | 0
27 | Hot-Mix Asphalt Surface Removal, 2" | Sq Yd | 6360 |  | 0
28 | Aggregate Shoulders, Type B | Ton | 1731.6 |  | 0
29 | Hot-Mix Asphalt Shoulders | Ton | 6 |  | 0
30 | Concrete Headwall Removal | Each | 3 |  | 0
31 | Pipe Culvert Removal | Foot | 1185 |  | 0
32 | Precast Reinforced Concrete Flared End Sections, 12" | Each | 18 |  | 0
33 | Precast Reinforced Concrete Flared End Sections, 18" | Each | 1 |  | 0
34 | Traversable Pipe Grate For Concrete End Section | Foot | 606.1 |  | 0
35 | Concrete End Section, Standard 542001, 15", 1:3 | Each | 3 |  | 0
36 | Concrete End Section, Standard 542001, 18", 1:3 | Each | 9 |  | 0
37 | Concrete End Section, Standard 542001, 21", 1:3 | Each | 1 |  | 0
38 | Concrete End Section, Standard 542001, 48", 1:3 | Each | 2 |  | 0
39 | Steel Flared End Sections, 12" | Each | 1 |  | 0
40 | Concrete End Section, Standard 542001, 36", 1:3 | Each | 1 |  | 0
41 | Concrete End Section, Standard 542011, 36", 1:3 | Each | 24 |  | 0
42 | Proposed Storm Sewer Connection to Existing Storm Sewer | Each | 1 |  | 0
43 | Pipe Culverts, Class A, Type 1, 12" | Foot | 617 |  | 0
44 | Pipe Culverts, Class A, Type 1, 18" | Foot | 302 |  | 0
45 | Pipe Culverts, Class A, Type 1, 21" | Foot | 56 |  | 0
46 | Pipe Culverts, Class A, Type 1, 48" | Foot | 56 |  | 0
47 | Pipe Culverts, Class A, Type 1, Equivalent Round-Size 36" | Foot | 624 |  | 0
48 | Manholes, Type A, 4'-Diameter, Type 1 Frame, Closed Lid | Each | 1 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | Manholes, Type A, 7'-Diameter, Type 1 Frame, Closed Lid | Each | 1 |  | 0
50 | Inlets, Type A, Special Grate | Each | 2 |  | 0
51 | Manholes To Be Adjusted | Each | 2 |  | 0
52 | Manholes To Be Reconstructed | Each | 8 |  | 0
53 | Removing Manholes | Each | 2 |  | 0
54 | Combination Concrete Curb and Gutter, Type B-6.18 | Foot | 969.6 |  | 0
55 | Chain Link Fence, 6' (Special) | Foot | 668 |  | 0
56 | Chain Link Fence, 6' (Special) with Barbed Wire | Foot | 840 |  | 0
57 | Non-Special Waste Disposal | Cu Yd | 500 |  | 0
58 | Special Waste Disposal | Cu Yd | 500 |  | 0
59 | Special Waste Plans and Reports | L Sum | 1 |  | 0
60 | Soil Disposal Analysis | Each | 25 |  | 0
61 | Mobilization | L Sum | 1 |  | 0
62 | Traffic Control and Protection, Special | L Sum | 1 |  | 0
63 | Sign Panel - Type 1 | Sq Ft | 88 |  | 0
64 | Telescoping Steel Sign Support | Foot | 168 |  | 0
65 | Thermoplastic Pavement Marking-Letters and Symbols | Sq Ft | 145.1 |  | 0
66 | Thermoplastic Pavement Marking-Line 4" | Foot | 16806 |  | 0
67 | Thermoplastic Pavement Marking-Line 8" | Foot | 763 |  | 0
68 | Thermoplastic Pavement Marking-Line 12" | Foot | 661 |  | 0
69 | Thermoplastic Pavement Marking-Line 24" | Foot | 320 |  | 0
70 | Raised Reflective Pavement Marker Removal | Each | 68 |  | 0
71 | Electric Service Installation | Each | 2 |  | 0
72 | Relocate Customer Service Pole and Accessories | L Sum | 1 |  | 0
| Page 3 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
73 | Underground Conduit, PVC, 2" Dia. | Foot | 179 |  | 0
74 | Underground Conduit, PVC, 3" Dia. | Foot | 22 |  | 0
75 | Heavy-Duty Handhole, Portland Cement Concrete | Each | 2 |  | 0
76 | Handhole, Composite Concrete | Each | 1 |  | 0
77 | Electric Cable in Conduit, 600V (XLP-Type Use) 3/C, No. 10 | Foot | 246 |  | 0
78 | Luminaire, LED, Horizontal Mount | Each | 2 |  | 0
79 | Lighting Controller, Pole Mounted, 120 Volt, 30 Amp | Each | 2 |  | 0
80 | Light Pole, Aluminum, 30 FT M.H., 8' Davit Arm | Each | 2 |  | 0
81 | Light Pole Foundation, 24" Diameter | Foot | 21 |  | 0
82 | Removal of Pole Foundation | Each | 2 |  | 0
83 | Relocate Existing Lighting Unit | Each | 4 |  | 0
84 | Electric Cable in Conduit, Signal, No. 14, 2C | Foot | 100 |  | 0
85 | Electric Cable in Conduit, Signal, No. 14, 3C | Foot | 100 |  | 0
86 | Electric Cable in Conduit, Signal, No. 14, 5C | Foot | 290 |  | 0
87 | Video Electric Cable in Conduit, No. 16, 3C | Foot | 100 |  | 0
88 | Video Cable in Conduit, Belden 8281 Coaxial | Foot | 100 |  | 0
89 | Preemptive Detector Device Cable in Conduit, No. 18, 3/C | Foot | 100 |  | 0
90 | Steel Combination Mast Arm Assembly and Pole, 48 Ft. | Each | 1 |  | 0
91 | Concrete Foundation, Type E, 36-Inch Diameter | Foot | 24 |  | 0
92 | Signal Head, Polycarbonate, LED, 1-Face, 3-Section, Mast Arm Mounted | Each | 1 |  | 0
93 | Relocate Existing Signal Head | Each | 4 |  | 0
94 | Relocate Existing Mast Arm Assembly and Pole | Each | 1 |  | 0
95 | Modify Existing Controller | Each | 1 |  | 0
96 | Remove Existing Handhole | Each | 2 |  | 0
| Page 4 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
97 | Remove Existing Concrete Foundation | Each | 2 |  | 0
98 | Relocate Existing Traffic Signal Equipment, Special | L Sum | 1 |  | 0
99 | Remove Existing Traffic Signal Equipment, Special | L Sum | 1 |  | 0
100 | Construction Layout | L Sum | 1 |  | 0
101 | Fence Removal | Foot | 3058 |  | 0
102 | Chain Link Gates To Be Removed and Re-erected | Each | 1 |  | 0
103 | Ductile Iron Water Main Complete, 6" | Foot | 15 |  | 0
104 | Ductile Iron Water Main Complete, 8" | Foot | 32 |  | 0
105 | Ductile Iron Water Main Complete, 12" | Foot | 4041 |  | 0
106 | Gate Valve and Valve Box Complete, 6" | Each | 1 |  | 0
107 | Gate Valve and Valve Box Complete, 8" | Each | 2 |  | 0
108 | Butterfly Valve and Valve Box, Complete, 12" | Each | 11 |  | 0
109 | Fire Hydrant with 6" Valve and Valve Box, Complete | Each | 14 |  | 0
110 | Water Service (Open-Cut), Complete, 1" | Each | 1 |  | 0
111 | Water Service (Open-Cut), Complete, 1.5" | Each | 1 |  | 0
112 | Water Main Quality Casing Pipe, 24" | Foot | 304 |  | 0
113 | Connect To Existing 6" Water Main, Complete | Each | 1 |  | 0
114 | Connect To Existing 8" Water Main, Complete | Each | 2 |  | 0
115 | Connect To Existing 12" Water Main, Complete | Each | 3 |  | 0
116 | Remove Fire Hydrant, Complete | Each | 3 |  | 0
117 | Water Main Line Stop, 6" | Each | 3 |  | 0
118 | Water Main Line Stop, 8" | Each | 2 |  | 0
119 | Water Main Line Stop, 12" | Each | 3 |  | 0
120 | Insertion Valve, Complete, 6" | Each | 3 |  | 0
| Page 5 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
121 | Insertion Valve, Complete, 8" | Each | 2 |  | 0
122 | Insertion Valve, Complete, 12" | Each | 3 |  | 0
123 | Sanitary Sewer, PVC - 12" (WMQ/SDR 26) | Foot | 150 |  | 0
124 | Sanitary Inside Drop Manhole - 5' Dia. (Over Trunk Sewer) | Each | 1 |  | 0
125 | Sanitary Manhole - 5' Dia. | Each | 1 |  | 0
126 | Connect To Existing 42" Trunk Sewer | L Sum | 1 |  | 0
127 | Sanitary Sewer System Abandonment, Complete | L Sum | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 6 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Logistics Parkway - Phase II
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Tree Removal, Acres | Acre | 4.78 | 12000 | 57360
2 | Earth Excavation, Special | Cu Yd | 41667 | 20 | 833340
3 | Removal and Disposal of Unsuitable Material | Cu Yd | 8100 | 20 | 162000
4 | Trench Backfill | Cu Yd | 502.2 | 18 | 9039.6
5 | Topsoil, Furnish and Place, 4" | Sq Yd | 45539 | 6 | 273234
6 | Seeding, Class 2A | Acre | 9.36 | 3000 | 28080
7 | Nitrogen Fertilizer Nutrient | Pound | 842.4 | 3 | 2527.2
8 | Phosphorous Fertilizer Nutrient | Pound | 842.4 | 3 | 2527.2
9 | Potassium Fertilizer Nutrient | Pound | 842.4 | 3 | 2527.2
10 | Erosion Control Blanket | Sq Yd | 45539 | 1.5 | 68308.5
11 | Temporary Erosion Control Seeding | Pound | 936 | 5 | 4680
12 | Temporary Ditch Checks | Foot | 383 | 10 | 3830
13 | Perimeter Erosion Barrier | Foot | 1000 | 2 | 2000
14 | Inlet and Pipe Protection | Each | 37 | 150 | 5550
15 | Stone Riprap, Class A4 | Sq Yd | 224.5 | 65 | 14592.5
16 | Stone Riprap, Class A5 | Sq Yd | 3066 | 85 | 260610
17 | Filter Fabric | Sq Yd | 3290.5 | 4 | 13162
18 | Aggregate Subgrade Improvement | Ton | 16605 | 18 | 298890
19 | Subbase Granular Material, Type B | Ton | 7662 | 18 | 137916
20 | Aggregate Base Course, Type B | Ton | 8005 | 20 | 160100
21 | Bituminous Materials (Prime Coat) | Gallon | 7122 | 0.5 | 3561
22 | Bituminous Materials (Tack Coat) | Gallon | 3074 | 0.5 | 1537
23 | Aggregate (Prime Coat) | Ton | 83 | 100 | 8300
24 | Hot-Mix Asphalt Binder Course, IL-19.0, N70 | Ton | 5908 | 70 | 413560
|  |  |  | Sub Total | 2767232.2
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Logistics Parkway - Phase II
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Hot-Mix Asphalt Surface Course, IL-9.5, Mix "D", N70 | Ton | 3504 | 75 | 262800
26 | Portland Cement Concrete Driveway Pavement, 8" | Sq Yd | 1520.8 | 70 | 106456
27 | Hot-Mix Asphalt Surface Removal, 2" | Sq Yd | 6360 | 5 | 31800
28 | Aggregate Shoulders, Type B | Ton | 1731.6 | 20 | 34632
29 | Hot-Mix Asphalt Shoulders | Ton | 6 | 200 | 1200
30 | Concrete Headwall Removal | Each | 3 | 1000 | 3000
31 | Pipe Culvert Removal | Foot | 1185 | 10 | 11850
32 | Precast Reinforced Concrete Flared End Sections, 12" | Each | 18 | 700 | 12600
33 | Precast Reinforced Concrete Flared End Sections, 18" | Each | 1 | 1000 | 1000
34 | Traversable Pipe Grate For Concrete End Section | Foot | 606.1 | 60 | 36366
35 | Concrete End Section, Standard 542001, 15", 1:3 | Each | 3 | 2000 | 6000
36 | Concrete End Section, Standard 542001, 18", 1:3 | Each | 9 | 2500 | 22500
37 | Concrete End Section, Standard 542001, 21", 1:3 | Each | 1 | 3000 | 3000
38 | Concrete End Section, Standard 542001, 48", 1:3 | Each | 2 | 5000 | 10000
39 | Steel Flared End Sections, 12" | Each | 1 | 500 | 500
40 | Concrete End Section, Standard 542001, 36", 1:3 | Each | 1 | 4000 | 4000
41 | Concrete End Section, Standard 542011, 36", 1:3 | Each | 24 | 4800 | 115200
42 | Proposed Storm Sewer Connection to Existing Storm Sewer | Each | 1 | 500 | 500
43 | Pipe Culverts, Class A, Type 1, 12" | Foot | 617 | 50 | 30850
44 | Pipe Culverts, Class A, Type 1, 18" | Foot | 302 | 60 | 18120
45 | Pipe Culverts, Class A, Type 1, 21" | Foot | 56 | 70 | 3920
46 | Pipe Culverts, Class A, Type 1, 48" | Foot | 56 | 160 | 8960
47 | Pipe Culverts, Class A, Type 1, Equivalent Round-Size 36" | Foot | 624 | 175 | 109200
48 | Manholes, Type A, 4'-Diameter, Type 1 Frame, Closed Lid | Each | 1 | 3500 | 3500
|  |  |  | Sub Total | 3605186.2
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Logistics Parkway - Phase II
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | Manholes, Type A, 7'-Diameter, Type 1 Frame, Closed Lid | Each | 1 | 8000 | 8000
50 | Inlets, Type A, Special Grate | Each | 2 | 2500 | 5000
51 | Manholes To Be Adjusted | Each | 2 | 750 | 1500
52 | Manholes To Be Reconstructed | Each | 8 | 2000 | 16000
53 | Removing Manholes | Each | 2 | 1000 | 2000
54 | Combination Concrete Curb and Gutter, Type B-6.18 | Foot | 969.6 | 30 | 29088
55 | Chain Link Fence, 6' (Special) | Foot | 668 | 60 | 40080
56 | Chain Link Fence, 6' (Special) with Barbed Wire | Foot | 840 | 75 | 63000
57 | Non-Special Waste Disposal | Cu Yd | 500 | 25 | 12500
58 | Special Waste Disposal | Cu Yd | 500 | 30 | 15000
59 | Special Waste Plans and Reports | L Sum | 1 | 2000 | 2000
60 | Soil Disposal Analysis | Each | 25 | 500 | 12500
61 | Mobilization | L Sum | 1 | 20000 | 20000
62 | Traffic Control and Protection, Special | L Sum | 1 | 20000 | 20000
63 | Sign Panel - Type 1 | Sq Ft | 88 | 50 | 4400
64 | Telescoping Steel Sign Support | Foot | 168 | 30 | 5040
65 | Thermoplastic Pavement Marking-Letters and Symbols | Sq Ft | 145.1 | 6 | 870.6
66 | Thermoplastic Pavement Marking-Line 4" | Foot | 16806 | 1 | 16806
67 | Thermoplastic Pavement Marking-Line 8" | Foot | 763 | 4 | 3052
68 | Thermoplastic Pavement Marking-Line 12" | Foot | 661 | 4.5 | 2974.5
69 | Thermoplastic Pavement Marking-Line 24" | Foot | 320 | 5 | 1600
70 | Raised Reflective Pavement Marker Removal | Each | 68 | 20 | 1360
71 | Electric Service Installation | Each | 2 | 3000 | 6000
72 | Relocate Customer Service Pole and Accessories | L Sum | 1 | 5000 | 5000
|  |  |  | Sub Total | 3898957.3
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Logistics Parkway - Phase II
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
73 | Underground Conduit, PVC, 2" Dia. | Foot | 179 | 15 | 2685
74 | Underground Conduit, PVC, 3" Dia. | Foot | 22 | 20 | 440
75 | Heavy-Duty Handhole, Portland Cement Concrete | Each | 2 | 1900 | 3800
76 | Handhole, Composite Concrete | Each | 1 | 900 | 900
77 | Electric Cable in Conduit, 600V (XLP-Type Use) 3/C, No. 10 | Foot | 246 | 5 | 1230
78 | Luminaire, LED, Horizontal Mount | Each | 2 | 1000 | 2000
79 | Lighting Controller, Pole Mounted, 120 Volt, 30 Amp | Each | 2 | 5000 | 10000
80 | Light Pole, Aluminum, 30 FT M.H., 8' Davit Arm | Each | 2 | 3500 | 7000
81 | Light Pole Foundation, 24" Diameter | Foot | 21 | 200 | 4200
82 | Removal of Pole Foundation | Each | 2 | 500 | 1000
83 | Relocate Existing Lighting Unit | Each | 4 | 1500 | 6000
84 | Electric Cable in Conduit, Signal, No. 14, 2C | Foot | 100 | 4 | 400
85 | Electric Cable in Conduit, Signal, No. 14, 3C | Foot | 100 | 4 | 400
86 | Electric Cable in Conduit, Signal, No. 14, 5C | Foot | 290 | 3 | 870
87 | Video Electric Cable in Conduit, No. 16, 3C | Foot | 100 | 5 | 500
88 | Video Cable in Conduit, Belden 8281 Coaxial | Foot | 100 | 5 | 500
89 | Preemptive Detector Device Cable in Conduit, No. 18, 3/C | Foot | 100 | 4 | 400
90 | Steel Combination Mast Arm Assembly and Pole, 48 Ft. | Each | 1 | 14000 | 14000
91 | Concrete Foundation, Type E, 36-Inch Diameter | Foot | 24 | 350 | 8400
92 | Signal Head, Polycarbonate, LED, 1-Face, 3-Section, Mast Arm Mounted | Each | 1 | 850 | 850
93 | Relocate Existing Signal Head | Each | 4 | 400 | 1600
94 | Relocate Existing Mast Arm Assembly and Pole | Each | 1 | 4500 | 4500
95 | Modify Existing Controller | Each | 1 | 1500 | 1500
96 | Remove Existing Handhole | Each | 2 | 400 | 800
|  |  |  | Total | 3972932.3
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Logistics Parkway - Phase II
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
97 | Remove Existing Concrete Foundation | Each | 2 | 700 | 1400
98 | Relocate Existing Traffic Signal Equipment, Special | L Sum | 1 | 15000 | 15000
99 | Remove Existing Traffic Signal Equipment, Special | L Sum | 1 | 5000 | 5000
100 | Construction Layout | L Sum | 1 | 20000 | 20000
101 | Fence Removal | Foot | 3058 | 5 | 15290
102 | Chain Link Gates To Be Removed and Re-erected | Each | 1 | 3500 | 3500
103 | Ductile Iron Water Main Complete, 6" | Foot | 15 | 200 | 3000
104 | Ductile Iron Water Main Complete, 8" | Foot | 32 | 200 | 6400
105 | Ductile Iron Water Main Complete, 12" | Foot | 4041 | 210 | 848610
106 | Gate Valve and Valve Box Complete, 6" | Each | 1 | 2500 | 2500
107 | Gate Valve and Valve Box Complete, 8" | Each | 2 | 3000 | 6000
108 | Butterfly Valve and Valve Box, Complete, 12" | Each | 11 | 4000 | 44000
109 | Fire Hydrant with 6" Valve and Valve Box, Complete | Each | 14 | 6500 | 91000
110 | Water Service (Open-Cut), Complete, 1" | Each | 1 | 1400 | 1400
111 | Water Service (Open-Cut), Complete, 1.5" | Each | 1 | 8500 | 8500
112 | Water Main Quality Casing Pipe, 24" | Foot | 304 | 80 | 24320
113 | Connect To Existing 6" Water Main, Complete | Each | 1 | 3000 | 3000
114 | Connect To Existing 8" Water Main, Complete | Each | 2 | 3500 | 7000
115 | Connect To Existing 12" Water Main, Complete | Each | 3 | 4000 | 12000
116 | Remove Fire Hydrant, Complete | Each | 3 | 1200 | 3600
117 | Water Main Line Stop, 6" | Each | 3 | 4000 | 12000
118 | Water Main Line Stop, 8" | Each | 2 | 5000 | 10000
119 | Water Main Line Stop, 12" | Each | 3 | 7500 | 22500
120 | Insertion Valve, Complete, 6" | Each | 3 | 5000 | 15000
|  |  |  | Total | 5153952.3
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 5 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Logistics Parkway - Phase II
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
121 | Insertion Valve, Complete, 8" | Each | 2 | 6000 | 12000
122 | Insertion Valve, Complete, 12" | Each | 3 | 11000 | 33000
123 | Sanitary Sewer, PVC - 12" (WMQ/SDR 26) | Foot | 150 | 160 | 24000
124 | Sanitary Inside Drop Manhole - 5' Dia. (Over Trunk Sewer) | Each | 1 | 18000 | 18000
125 | Sanitary Manhole - 5' Dia. | Each | 1 | 10000 | 10000
126 | Connect To Existing 42" Trunk Sewer | L Sum | 1 | 8000 | 8000
127 | Sanitary Sewer System Abandonment, Complete | L Sum | 1 | 4500 | 4500
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 5263452.3
Made by: Dale K. Hamilton, P.E. (WHA) |  |  | Date: June 12, 2022
Checked by: |  |  | Date:
Page 6 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
Address: Rockford, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Tree Removal, Acres | 4.78 | Acre | 35850 |  | 4.78 |  |  | 7500
2 | Earth Excavation, Special | 41667 | Cu Yd | 780422.91 |  | 41667 |  |  | 18.73
3 | Removal and Disposal of Unsuitable Material | 8100 | Cu Yd | 162000 |  | 8100 |  |  | 20
4 | Trench Backfill | 502.2 | Cu Yd | 5.022 |  | 502.2 |  |  | 0.01
5 | Topsoil, Furnish and Place, 4" | 45539 | Sq Yd | 455.39 |  | 45539 |  |  | 0.01
6 | Seeding, Class 2A | 9.36 | Acre | 37159.2 |  | 9.36 |  |  | 3970
7 | Nitrogen Fertilizer Nutrient | 842.4 | Pound | 2527.2 |  | 842.4 |  |  | 3
8 | Phosphorous Fertilizer Nutrient | 842.4 | Pound | 2527.2 |  | 842.4 |  |  | 3
9 | Potassium Fertilizer Nutrient | 842.4 | Pound | 2527.2 |  | 842.4 |  |  | 3
10 | Erosion Control Blanket | 45539 | Sq Yd | 66031.55 |  | 45539 |  |  | 1.45
11 | Temporary Erosion Control Seeding | 936 | Pound | 1404 |  | 936 |  |  | 1.5
12 | Temporary Ditch Checks | 383 | Foot | 4213 |  | 383 |  |  | 11
13 | Perimeter Erosion Barrier | 1000 | Foot | 4200 |  | 1000 |  |  | 4.2
14 | Inlet and Pipe Protection | 37 | Each | 4440 |  | 37 |  |  | 120
15 | Stone Riprap, Class A4 | 224.5 | Sq Yd | 12347.5 |  | 224.5 |  |  | 55
16 | Stone Riprap, Class A5 | 3066 | Sq Yd | 168630 |  | 3066 |  |  | 55
17 | Filter Fabric | 3290.5 | Sq Yd | 13162 |  | 3290.5 |  |  | 4
18 | Aggregate Subgrade Improvement | 16605 | Ton | 265680 |  | 16605 |  |  | 16
19 | Subbase Granular Material, Type B | 7662 | Ton | 122592 |  | 7662 |  |  | 16
20 | Aggregate Base Course, Type B | 8005 | Ton | 128080 |  | 8005 |  |  | 16
21 | Bituminous Materials (Prime Coat) | 7122 | Gallon | 71.22 |  | 7122 |  |  | 0.01
22 | Bituminous Materials (Tack Coat) | 3074 | Gallon | 30.74 |  | 3074 |  |  | 0.01
23 | Aggregate (Prime Coat) | 83 | Ton | 0.83 |  | 83 |  |  | 0.01
24 | Hot-Mix Asphalt Binder Course, IL-19.0, N70 | 5908 | Ton | 474117 |  | 5908 |  |  | 80.25
Sub Total |  |  |  | 2288473.962 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
Address: Rockford, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Hot-Mix Asphalt Surface Course, IL-9.5, Mix "D", N70 | 3504 | Ton | 301344 |  | 3504 |  |  | 86
26 | Portland Cement Concrete Driveway Pavement, 8" | 1520.8 | Sq Yd | 98852 |  | 1520.8 |  |  | 65
27 | Hot-Mix Asphalt Surface Removal, 2" | 6360 | Sq Yd | 17426.4 |  | 6360 |  |  | 2.74
28 | Aggregate Shoulders, Type B | 1731.6 | Ton | 31168.8 |  | 1731.6 |  |  | 18
29 | Hot-Mix Asphalt Shoulders | 6 | Ton | 450 |  | 6 |  |  | 75
30 | Concrete Headwall Removal | 3 | Each | 750 |  | 3 |  |  | 250
31 | Pipe Culvert Removal | 1185 | Foot | 11850 |  | 1185 |  |  | 10
32 | Precast Reinforced Concrete Flared End Sections, 12" | 18 | Each | 12600 |  | 18 |  |  | 700
33 | Precast Reinforced Concrete Flared End Sections, 18" | 1 | Each | 800 |  | 1 |  |  | 800
34 | Traversable Pipe Grate For Concrete End Section | 606.1 | Foot | 72732 |  | 606.1 |  |  | 120
35 | Concrete End Section, Standard 542001, 15", 1:3 | 3 | Each | 5700 |  | 3 |  |  | 1900
36 | Concrete End Section, Standard 542001, 18", 1:3 | 9 | Each | 19800 |  | 9 |  |  | 2200
37 | Concrete End Section, Standard 542001, 21", 1:3 | 1 | Each | 2500 |  | 1 |  |  | 2500
38 | Concrete End Section, Standard 542001, 48", 1:3 | 2 | Each | 16000 |  | 2 |  |  | 8000
39 | Steel Flared End Sections, 12" | 1 | Each | 400 |  | 1 |  |  | 400
40 | Concrete End Section, Standard 542001, 36", 1:3 | 1 | Each | 4500 |  | 1 |  |  | 4500
41 | Concrete End Section, Standard 542011, 36", 1:3 | 24 | Each | 132000 |  | 24 |  |  | 5500
42 | Proposed Storm Sewer Connection to Existing Storm Sewer | 1 | Each | 1000 |  | 1 |  |  | 1000
43 | Pipe Culverts, Class A, Type 1, 12" | 617 | Foot | 27765 |  | 617 |  |  | 45
44 | Pipe Culverts, Class A, Type 1, 18" | 302 | Foot | 15100 |  | 302 |  |  | 50
45 | Pipe Culverts, Class A, Type 1, 21" | 56 | Foot | 3360 |  | 56 |  |  | 60
46 | Pipe Culverts, Class A, Type 1, 48" | 56 | Foot | 7280 |  | 56 |  |  | 130
47 | Pipe Culverts, Class A, Type 1, Equivalent Round-Size 36" | 624 | Foot | 84240 |  | 624 |  |  | 135
48 | Manholes, Type A, 4'-Diameter, Type 1 Frame, Closed Lid | 1 | Each | 3000 |  | 1 |  |  | 3000
Sub Total |  |  |  | 3159092.162 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
Address: Rockford, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | Manholes, Type A, 7'-Diameter, Type 1 Frame, Closed Lid | 1 | Each | 12000 |  | 1 |  |  | 12000
50 | Inlets, Type A, Special Grate | 2 | Each | 5000 |  | 2 |  |  | 2500
51 | Manholes To Be Adjusted | 2 | Each | 2000 |  | 2 |  |  | 1000
52 | Manholes To Be Reconstructed | 8 | Each | 16000 |  | 8 |  |  | 2000
53 | Removing Manholes | 2 | Each | 1000 |  | 2 |  |  | 500
54 | Combination Concrete Curb and Gutter, Type B-6.18 | 969.6 | Foot | 39268.8 |  | 969.6 |  |  | 40.5
55 | Chain Link Fence, 6' (Special) | 668 | Foot | 25838.24 |  | 668 |  |  | 38.68
56 | Chain Link Fence, 6' (Special) with Barbed Wire | 840 | Foot | 36447.6 |  | 840 |  |  | 43.39
57 | Non-Special Waste Disposal | 500 | Cu Yd | 5 |  | 500 |  |  | 0.01
58 | Special Waste Disposal | 500 | Cu Yd | 5 |  | 500 |  |  | 0.01
59 | Special Waste Plans and Reports | 1 | L Sum | 0.01 |  | 1 |  |  | 0.01
60 | Soil Disposal Analysis | 25 | Each | 0.25 |  | 25 |  |  | 0.01
61 | Mobilization | 1 | L Sum | 119641.2 |  | 1 |  |  | 119641.2
62 | Traffic Control and Protection, Special | 1 | L Sum | 15000 |  | 1 |  |  | 15000
63 | Sign Panel - Type 1 | 88 | Sq Ft | 2640 |  | 88 |  |  | 30
64 | Telescoping Steel Sign Support | 168 | Foot | 2856 |  | 168 |  |  | 17
65 | Thermoplastic Pavement Marking-Letters and Symbols | 145.1 | Sq Ft | 725.5 |  | 145.1 |  |  | 5
66 | Thermoplastic Pavement Marking-Line 4" | 16806 | Foot | 13444.8 |  | 16806 |  |  | 0.8
67 | Thermoplastic Pavement Marking-Line 8" | 763 | Foot | 1220.8 |  | 763 |  |  | 1.6
68 | Thermoplastic Pavement Marking-Line 12" | 661 | Foot | 1586.4 |  | 661 |  |  | 2.4
69 | Thermoplastic Pavement Marking-Line 24" | 320 | Foot | 1536 |  | 320 |  |  | 4.8
70 | Raised Reflective Pavement Marker Removal | 68 | Each | 1428 |  | 68 |  |  | 21
71 | Electric Service Installation | 2 | Each | 5164 |  | 2 |  |  | 2582
72 | Relocate Customer Service Pole and Accessories | 1 | L Sum | 23948 |  | 1 |  |  | 23948
Sub Total |  |  |  | 3485847.762 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
Address: Rockford, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
73 | Underground Conduit, PVC, 2" Dia. | 179 | Foot | 5549 |  | 179 |  |  | 31
74 | Underground Conduit, PVC, 3" Dia. | 22 | Foot | 1353 |  | 22 |  |  | 61.5
75 | Heavy-Duty Handhole, Portland Cement Concrete | 2 | Each | 7350 |  | 2 |  |  | 3675
76 | Handhole, Composite Concrete | 1 | Each | 3158 |  | 1 |  |  | 3158
77 | Electric Cable in Conduit, 600V (XLP-Type Use) 3/C, No. 10 | 246 | Foot | 861 |  | 246 |  |  | 3.5
78 | Luminaire, LED, Horizontal Mount | 2 | Each | 3144 |  | 2 |  |  | 1572
79 | Lighting Controller, Pole Mounted, 120 Volt, 30 Amp | 2 | Each | 3698 |  | 2 |  |  | 1849
80 | Light Pole, Aluminum, 30 FT M.H., 8' Davit Arm | 2 | Each | 22952 |  | 2 |  |  | 11476
81 | Light Pole Foundation, 24" Diameter | 21 | Foot | 6216 |  | 21 |  |  | 296
82 | Removal of Pole Foundation | 2 | Each | 700 |  | 2 |  |  | 350
83 | Relocate Existing Lighting Unit | 4 | Each | 3040 |  | 4 |  |  | 760
84 | Electric Cable in Conduit, Signal, No. 14, 2C | 100 | Foot | 245 |  | 100 |  |  | 2.45
85 | Electric Cable in Conduit, Signal, No. 14, 3C | 100 | Foot | 280 |  | 100 |  |  | 2.8
86 | Electric Cable in Conduit, Signal, No. 14, 5C | 290 | Foot | 1015 |  | 290 |  |  | 3.5
87 | Video Electric Cable in Conduit, No. 16, 3C | 100 | Foot | 245 |  | 100 |  |  | 2.45
88 | Video Cable in Conduit, Belden 8281 Coaxial | 100 | Foot | 390 |  | 100 |  |  | 3.9
89 | Preemptive Detector Device Cable in Conduit, No. 18, 3/C | 100 | Foot | 350 |  | 100 |  |  | 3.5
90 | Steel Combination Mast Arm Assembly and Pole, 48 Ft. | 1 | Each | 26340 |  | 1 |  |  | 26340
91 | Concrete Foundation, Type E, 36-Inch Diameter | 24 | Foot | 8832 |  | 24 |  |  | 368
92 | Signal Head, Polycarbonate, LED, 1-Face, 3-Section, Mast Arm Mounted | 1 | Each | 1025 |  | 1 |  |  | 1025
93 | Relocate Existing Signal Head | 4 | Each | 1192 |  | 4 |  |  | 298
94 | Relocate Existing Mast Arm Assembly and Pole | 1 | Each | 3148 |  | 1 |  |  | 3148
95 | Modify Existing Controller | 1 | Each | 4710 |  | 1 |  |  | 4710
96 | Remove Existing Handhole | 2 | Each | 700 |  | 2 |  |  | 350
Sub Total |  |  |  | 3592340.762 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
Address: Rockford, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
97 | Remove Existing Concrete Foundation | 2 | Each | 700 |  | 2 |  |  | 350
98 | Relocate Existing Traffic Signal Equipment, Special | 1 | L Sum | 4230 |  | 1 |  |  | 4230
99 | Remove Existing Traffic Signal Equipment, Special | 1 | L Sum | 2116 |  | 1 |  |  | 2116
100 | Construction Layout | 1 | L Sum | 20000 |  | 1 |  |  | 20000
101 | Fence Removal | 3058 | Foot | 15290 |  | 3058 |  |  | 5
102 | Chain Link Gates To Be Removed and Re-erected | 1 | Each | 1210 |  | 1 |  |  | 1210
103 | Ductile Iron Water Main Complete, 6" | 15 | Foot | 2185.5 |  | 15 |  |  | 145.7
104 | Ductile Iron Water Main Complete, 8" | 32 | Foot | 4662.4 |  | 32 |  |  | 145.7
105 | Ductile Iron Water Main Complete, 12" | 4041 | Foot | 588773.7 |  | 4041 |  |  | 145.7
106 | Gate Valve and Valve Box Complete, 6" | 1 | Each | 2500 |  | 1 |  |  | 2500
107 | Gate Valve and Valve Box Complete, 8" | 2 | Each | 6000 |  | 2 |  |  | 3000
108 | Butterfly Valve and Valve Box, Complete, 12" | 11 | Each | 46200 |  | 11 |  |  | 4200
109 | Fire Hydrant with 6" Valve and Valve Box, Complete | 14 | Each | 91000 |  | 14 |  |  | 6500
110 | Water Service (Open-Cut), Complete, 1" | 1 | Each | 2700 |  | 1 |  |  | 2700
111 | Water Service (Open-Cut), Complete, 1.5" | 1 | Each | 4000 |  | 1 |  |  | 4000
112 | Water Main Quality Casing Pipe, 24" | 304 | Foot | 65360 |  | 304 |  |  | 215
113 | Connect To Existing 6" Water Main, Complete | 1 | Each | 2000 |  | 1 |  |  | 2000
114 | Connect To Existing 8" Water Main, Complete | 2 | Each | 6000 |  | 2 |  |  | 3000
115 | Connect To Existing 12" Water Main, Complete | 3 | Each | 9000 |  | 3 |  |  | 3000
116 | Remove Fire Hydrant, Complete | 3 | Each | 1500 |  | 3 |  |  | 500
117 | Water Main Line Stop, 6" | 3 | Each | 12000 |  | 3 |  |  | 4000
118 | Water Main Line Stop, 8" | 2 | Each | 9000 |  | 2 |  |  | 4500
119 | Water Main Line Stop, 12" | 3 | Each | 21000 |  | 3 |  |  | 7000
120 | Insertion Valve, Complete, 6" | 3 | Each | 18000 |  | 3 |  |  | 6000
Sub Total |  |  |  | 12157682.086
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
Address: Rockford, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
121 | Insertion Valve, Complete, 8" | 2 | Each | 16000 |  | 2 |  |  | 8000
122 | Insertion Valve, Complete, 12" | 3 | Each | 36300 |  | 3 |  |  | 12100
123 | Sanitary Sewer, PVC - 12" (WMQ/SDR 26) | 150 | Foot | 26250 |  | 150 |  |  | 175
124 | Sanitary Inside Drop Manhole - 5' Dia. (Over Trunk Sewer) | 1 | Each | 35000 |  | 1 |  |  | 35000
125 | Sanitary Manhole - 5' Dia. | 1 | Each | 6000 |  | 1 |  |  | 6000
126 | Connect To Existing 42" Trunk Sewer | 1 | L Sum | 5000 |  | 1 |  |  | 5000
127 | Sanitary Sewer System Abandonment, Complete | 1 | L Sum | 1000 |  | 1 |  |  | 1000
Total |  |  |  | 20705494.81
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
Address: Rockford, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 37587806.258
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Logistics Parkway - Phase II
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Northern Illinois Service
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.