## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 845585
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LSUM | 1 | 10000 | 10000
2 | DEBRIS REMOVAL | LSUM | 1 | 10000 | 10000
3 | GEOCOMPOSITE WALL DRAIN | SQ YD | 37 | 50 | 1850
4 | MASONRY WALL CONSTRUCTION | SQ FT | 270 | 30 | 8100
5 | CA-7 DRAINAGE STONE | TON | 210 | 50 | 10500
6 | FILTER FABRIC | SQ YD | 42 | 25 | 1050
7 | INLET AND PIPE PROTECTION | EACH | 2 | 125 | 250
8 | ADJUST WATER VALVE | EACH | 4 | 600 | 2400
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 5-INCH | SQ FT | 9284 | 7.5 | 69630
10 | AGGREGATE BASE COURSE, TYPE B 4" | SQ YD | 1178 | 8 | 9424
11 | DETECTABLE WARNINGS | SQ FT | 20 | 30 | 600
12 | COMBINATION CURB AND GUTTER REMOVAL | FT | 80 | 35 | 2800
13 | PLANTER CURB | EACH | 10 | 300 | 3000
14 | SIDEWALK REMOVAL | SQ FT | 9343 | 15 | 140145
15 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FT | 80 | 35 | 2800
16 | REMOVING AND RESETTING STREET SIGNS | EACH | 1 | 50 | 50
17 | TUBULAR STEEL SIGN SUPPORT | FT | 160 | 15 | 2400
18 | SIGN PANEL, TYPE 1 | SQ FT | 44 | 45 | 1980
19 | TREE AND GRATE REMOVAL | EACH | 7 | 35 | 245
20 | REMOVE AND RELOCATE TRASH RECEPTACLE | EACH | 1 | 50 | 50
21 | REMOVE AND RELOCATE PARK BENCH | EACH | 1 | 200 | 200
22 | STAMPED, COLORED PORTLAND CEMENT CONCRETE SIDEWALK, 5 INCH | SQ FT | 1315 | 20 | 26300
23 | GINKO BILOBA / MAIDENHAIR TREE, 2.5" CALIPER | EACH | 8 | 500 | 4000
24 | ULMUS X 'FRONTIER' / FRONTIER ELM, 2.5" CALIPER | EACH | 2 | 500 | 1000
25 | PERENNIALS, #1 CONTAINER | EACH | 160 | 1900 | 304000
26 | GRASSES, #1 CONTAINER | EACH | 20 | 1900 | 38000
27 | CONSTRUCTION LAYOUT STAKES | LSUM | 1 | 19000 | 19000
28 | MOBILIZATION | LSUM | 1 | 10000 | 10000
29 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 4" DIA. | FOOT | 117 | 38 | 4446
30 | UNIT DUCT , 600V, 4-1C NO. 4, 1/C NO. 6 GROUND (XLP-TYPE USE),1 1/2" DIA. POLYETHYENE | FOOT | 703 | 60 | 42180
31 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 6 | FOOT | 275 | 2.4 | 660
32 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 4 | FOOT | 1925 | 2.4 | 4620
33 | LIGHT POLE FOUNDATION, 24" DIAMETER | FOOT | 140 | 200 | 28000
34 | REMOVAL OF LIGHTING UNIT, SALVAGE | EACH | 5 | 437 | 2185
35 | REMOVAL OF POLE FOUNDATION | EACH | 5 | 212 | 1060
36 | REMOVE EXISTING HANDHOLE | EACH | 5 | 500 | 2500
37 | DRILL EXISTING HANDHOLE | EACH | 1 | 1000 | 1000
38 | LUMINAIRE, LED, SPECIAL | EACH | 14 | 1440 | 20160
39 | LIGHT POLE , SPECIAL TYPE A | EACH | 4 | 4000 | 16000
40 | LIGHT POLE, SPECIAL TYPE B | EACH | 10 | 4000 | 40000
41 | MAINTENENACE OF LIGHTING SYSTEM | CAL MO | 3 | 1000 | 3000
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Copenhaver Construction |  | Alliance Contractors |  | Stenstrom Excavation |  |  |  | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Gilberts, IL |  | Woodstock, IL |  | Rockford, IL |  |  |  | City of Rockford | [13 empty] | City of Rockford
Project Name: Main Street Streetscape | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond |  |  |  | Project Name: | [13 empty] | Project Name:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LSUM | 1 | 10000 | 10000 | 49000 | 49000 | 7500 | 7500 | 32500 | 32500 |  | 0 | 1 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LSUM | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LSUM | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | DEBRIS REMOVAL | LSUM | 1 | 10000 | 10000 | 2900 | 2900 | 1000 | 1000 | 19500 | 19500 |  | 0 | 2 | DEBRIS REMOVAL | LSUM | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | DEBRIS REMOVAL | LSUM | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | GEOCOMPOSITE WALL DRAIN | SQ YD | 37 | 50 | 1850 | 25 | 925 | 10 | 370 | 110 | 4070 |  | 0 | 3 | GEOCOMPOSITE WALL DRAIN | SQ YD | 37 | 50 | 1850 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | GEOCOMPOSITE WALL DRAIN | SQ YD | 37 | 50 | 1850 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | MASONRY WALL CONSTRUCTION | SQ FT | 270 | 30 | 8100 | 84 | 22680 | 100 | 27000 | 100 | 27000 |  | 0 | 4 | MASONRY WALL CONSTRUCTION | SQ FT | 270 | 30 | 8100 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | MASONRY WALL CONSTRUCTION | SQ FT | 270 | 30 | 8100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | CA-7 DRAINAGE STONE | TON | 210 | 50 | 10500 | 38 | 7980 | 60 | 12600 | 52 | 10920 |  | 0 | 5 | CA-7 DRAINAGE STONE | TON | 210 | 50 | 10500 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | CA-7 DRAINAGE STONE | TON | 210 | 50 | 10500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | FILTER FABRIC | SQ YD | 42 | 25 | 1050 | 10 | 420 | 1 | 42 | 25 | 1050 |  | 0 | 6 | FILTER FABRIC | SQ YD | 42 | 25 | 1050 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | FILTER FABRIC | SQ YD | 42 | 25 | 1050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | INLET AND PIPE PROTECTION | EACH | 2 | 125 | 250 | 110 | 220 | 250 | 500 | 255 | 510 |  | 0 | 7 | INLET AND PIPE PROTECTION | EACH | 2 | 125 | 250 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | INLET AND PIPE PROTECTION | EACH | 2 | 125 | 250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | ADJUST WATER VALVE | EACH | 4 | 600 | 2400 | 370 | 1480 | 250 | 1000 | 775 | 3100 |  | 0 | 8 | ADJUST WATER VALVE | EACH | 4 | 600 | 2400 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | ADJUST WATER VALVE | EACH | 4 | 600 | 2400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 5-INCH | SQ FT | 9284 | 7.5 | 69630 | 10 | 92840 | 10.25 | 95161 | 12.75 | 118371 |  | 0 | 9 | PORTLAND CEMENT CONCRETE SIDEWALK, 5-INCH | SQ FT | 9284 | 7.5 | 69630 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | PORTLAND CEMENT CONCRETE SIDEWALK, 5-INCH | SQ FT | 9284 | 7.5 | 69630 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | AGGREGATE BASE COURSE, TYPE B 4" | SQ YD | 1178 | 8 | 9424 | 7 | 8246 | 8 | 9424 | 20 | 23560 |  | 0 | 10 | AGGREGATE BASE COURSE, TYPE B 4" | SQ YD | 1178 | 8 | 9424 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | AGGREGATE BASE COURSE, TYPE B 4" | SQ YD | 1178 | 8 | 9424 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | DETECTABLE WARNINGS | SQ FT | 20 | 30 | 600 | 40 | 800 | 25 | 500 | 50 | 1000 |  | 0 | 11 | DETECTABLE WARNINGS | SQ FT | 20 | 30 | 600 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | DETECTABLE WARNINGS | SQ FT | 20 | 30 | 600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | COMBINATION CURB AND GUTTER REMOVAL | FT | 80 | 35 | 2800 | 12 | 960 | 50 | 4000 | 37.5 | 3000 |  | 0 | 12 | COMBINATION CURB AND GUTTER REMOVAL | FT | 80 | 35 | 2800 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | COMBINATION CURB AND GUTTER REMOVAL | FT | 80 | 35 | 2800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | PLANTER CURB | EACH | 10 | 300 | 3000 | 1900 | 19000 | 3700 | 37000 | 2850 | 28500 |  | 0 | 13 | PLANTER CURB | EACH | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | PLANTER CURB | EACH | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | SIDEWALK REMOVAL | SQ FT | 9343 | 15 | 140145 | 3 | 28029 | 5 | 46715 | 6 | 56058 |  | 0 | 14 | SIDEWALK REMOVAL | SQ FT | 9343 | 15 | 140145 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | SIDEWALK REMOVAL | SQ FT | 9343 | 15 | 140145 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FT | 80 | 35 | 2800 | 32 | 2560 | 69 | 5520 | 92.5 | 7400 |  | 0 | 15 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FT | 80 | 35 | 2800 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FT | 80 | 35 | 2800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | REMOVING AND RESETTING STREET SIGNS | EACH | 1 | 50 | 50 | 600 | 600 | 500 | 500 | 700 | 700 |  | 0 | 16 | REMOVING AND RESETTING STREET SIGNS | EACH | 1 | 50 | 50 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | REMOVING AND RESETTING STREET SIGNS | EACH | 1 | 50 | 50 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | TUBULAR STEEL SIGN SUPPORT | FT | 160 | 15 | 2400 | 21 | 3360 | 100 | 16000 | 95 | 15200 |  | 0 | 17 | TUBULAR STEEL SIGN SUPPORT | FT | 160 | 15 | 2400 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | TUBULAR STEEL SIGN SUPPORT | FT | 160 | 15 | 2400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | SIGN PANEL, TYPE 1 | SQ FT | 44 | 45 | 1980 | 28 | 1232 | 65 | 2860 | 56.5 | 2486 |  | 0 | 18 | SIGN PANEL, TYPE 1 | SQ FT | 44 | 45 | 1980 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | SIGN PANEL, TYPE 1 | SQ FT | 44 | 45 | 1980 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | TREE AND GRATE REMOVAL | EACH | 7 | 35 | 245 | 800 | 5600 | 1250 | 8750 | 995 | 6965 |  | 0 | 19 | TREE AND GRATE REMOVAL | EACH | 7 | 35 | 245 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | TREE AND GRATE REMOVAL | EACH | 7 | 35 | 245 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | REMOVE AND RELOCATE TRASH RECEPTACLE | EACH | 1 | 50 | 50 | 600 | 600 | 2000 | 2000 | 575 | 575 |  | 0 | 20 | REMOVE AND RELOCATE TRASH RECEPTACLE | EACH | 1 | 50 | 50 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | REMOVE AND RELOCATE TRASH RECEPTACLE | EACH | 1 | 50 | 50 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | REMOVE AND RELOCATE PARK BENCH | EACH | 1 | 200 | 200 | 600 | 600 | 2000 | 2000 | 750 | 750 |  | 0 | 21 | REMOVE AND RELOCATE PARK BENCH | EACH | 1 | 200 | 200 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | REMOVE AND RELOCATE PARK BENCH | EACH | 1 | 200 | 200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | STAMPED, COLORED PORTLAND CEMENT CONCRETE SIDEWALK, 5 INCH | SQ FT | 1315 | 20 | 26300 | 25 | 32875 | 37 | 48655 | 28.75 | 37806.25 |  | 0 | 22 | STAMPED, COLORED PORTLAND CEMENT CONCRETE SIDEWALK, 5 INCH | SQ FT | 1315 | 20 | 26300 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | STAMPED, COLORED PORTLAND CEMENT CONCRETE SIDEWALK, 5 INCH | SQ FT | 1315 | 20 | 26300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | GINKO BILOBA / MAIDENHAIR TREE, 2.5" CALIPER | EACH | 8 | 500 | 4000 | 950 | 7600 | 800 | 6400 | 1380 | 11040 |  | 0 | 23 | GINKO BILOBA / MAIDENHAIR TREE, 2.5" CALIPER | EACH | 8 | 500 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | GINKO BILOBA / MAIDENHAIR TREE, 2.5" CALIPER | EACH | 8 | 500 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | ULMUS X 'FRONTIER' / FRONTIER ELM, 2.5" CALIPER | EACH | 2 | 500 | 1000 | 1100 | 2200 | 600 | 1200 | 1056 | 2112 |  | 0 | 24 | ULMUS X 'FRONTIER' / FRONTIER ELM, 2.5" CALIPER | EACH | 2 | 500 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | ULMUS X 'FRONTIER' / FRONTIER ELM, 2.5" CALIPER | EACH | 2 | 500 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 308774 |  | 292707 |  | 336697 |  | 414173.25 |  |  |  | Page 1 | Total |  | As read | 308774 | [9 empty] | Page 1 | Total |  | As read | 308774
| Award to Copenhaver Construction | Total |  | As corrected | 308774 |  | 292707 |  | 336697 |  | 414173.25 |  |  |  | Award to Copenhaver Construction | Bid |  | As corrected | 308774 | [9 empty] | Award to Copenhaver Construction | Bid |  | As corrected | 308774
25 | PERENNIALS, #1 CONTAINER | EACH | 160 | 1900 | 304000 | 22 | 3520 | 25 | 4000 | 42 | 6720 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | GRASSES, #1 CONTAINER | EACH | 20 | 1900 | 38000 | 23 | 460 | 25 | 500 | 42 | 840 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | CONSTRUCTION LAYOUT STAKES | LSUM | 1 | 19000 | 19000 | 11000 | 11000 | 2120 | 2120 | 6000 | 6000 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | MOBILIZATION | LSUM | 1 | 10000 | 10000 | 41000 | 41000 | 86034 | 86034 | 27500 | 27500 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 4" DIA. | FOOT | 117 | 38 | 4446 | 79 | 9243 | 68 | 7956 | 88 | 10296 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | UNIT DUCT , 600V, 4-1C NO. 4, 1/C NO. 6 GROUND (XLP-TYPE USE),1 1/2" DIA. POLYETHYENE | FOOT | 703 | 60 | 42180 | 23 | 16169 | 20 | 14060 | 29.5 | 20738.5 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 6 | FOOT | 275 | 2.4 | 660 | 3 | 825 | 1.7 | 467.5 | 5 | 1375 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 4 | FOOT | 1925 | 2.4 | 4620 | 3 | 5775 | 2.35 | 4523.75 | 3.75 | 7218.75 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | LIGHT POLE FOUNDATION, 24" DIAMETER | FOOT | 140 | 200 | 28000 | 230 | 32200 | 198 | 27720 | 240 | 33600 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | REMOVAL OF LIGHTING UNIT, SALVAGE | EACH | 5 | 437 | 2185 | 668 | 3340 | 580 | 2900 | 600 | 3000 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | REMOVAL OF POLE FOUNDATION | EACH | 5 | 212 | 1060 | 525 | 2625 | 457 | 2285 | 410 | 2050 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | REMOVE EXISTING HANDHOLE | EACH | 5 | 500 | 2500 | 200 | 1000 | 156 | 780 | 510 | 2550 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | DRILL EXISTING HANDHOLE | EACH | 1 | 1000 | 1000 | 330 | 330 | 301 | 301 | 525 | 525 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | LUMINAIRE, LED, SPECIAL | EACH | 14 | 1440 | 20160 | 5100 | 71400 | 4422 | 61908 | 1575 | 22050 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | LIGHT POLE , SPECIAL TYPE A | EACH | 4 | 4000 | 16000 | 7500 | 30000 | 6519 | 26076 | 14250 | 57000 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | LIGHT POLE, SPECIAL TYPE B | EACH | 10 | 4000 | 40000 | 7400 | 74000 | 6370 | 63700 | 13775 | 137750 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | MAINTENENACE OF LIGHTING SYSTEM | CAL MO | 3 | 1000 | 3000 | 700 | 2100 | 550 | 1650 | 4750 | 14250 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 845585 |  | 597694 |  | 643678.25 |  | 767636.5 |  |  |  | Page 2 | Total |  | As read | [10 empty] | Page 2 | Total |  | As read
| Award to Copenhaver Construction | Bid |  | As corrected | 845585 |  | 597694 |  | 643678.25 |  | 767636.5 |  |  |  | Award to Copenhaver Construction | Bid |  | As corrected | [10 empty] | Award to Copenhaver Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Copenhaver Construction | Bid |  | As corrected | [10 empty] | Award to Copenhaver Construction | Bid |  | As corrected | [10 empty] | Award to Copenhaver Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Copenhaver Construction | Bid |  | As corrected | [10 empty] | Award to Copenhaver Construction | Bid |  | As corrected | [10 empty] | Award to Copenhaver Construction | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Project Name: Main Street Streetscape
Item No. | Items | Units | Quantity | Unit Price | Total
1 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LSUM | 1 |  | 0
2 | DEBRIS REMOVAL | LSUM | 1 |  | 0
3 | GEOCOMPOSITE WALL DRAIN | SQ YD | 37 |  | 0
4 | MASONRY WALL CONSTRUCTION | SQ FT | 270 |  | 0
5 | CA-7 DRAINAGE STONE | TON | 210 |  | 0
6 | FILTER FABRIC | SQ YD | 42 |  | 0
7 | INLET AND PIPE PROTECTION | EACH | 2 |  | 0
8 | ADJUST WATER VALVE | EACH | 4 |  | 0
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 5-INCH | SQ FT | 9284 |  | 0
10 | AGGREGATE BASE COURSE, TYPE B 4" | SQ YD | 1178 |  | 0
11 | DETECTABLE WARNINGS | SQ FT | 20 |  | 0
12 | COMBINATION CURB AND GUTTER REMOVAL | FT | 80 |  | 0
13 | PLANTER CURB | EACH | 10 |  | 0
14 | SIDEWALK REMOVAL | SQ FT | 9343 |  | 0
15 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FT | 80 |  | 0
16 | REMOVING AND RESETTING STREET SIGNS | EACH | 1 |  | 0
17 | TUBULAR STEEL SIGN SUPPORT | FT | 160 |  | 0
18 | SIGN PANEL, TYPE 1 | SQ FT | 44 |  | 0
19 | TREE AND GRATE REMOVAL | EACH | 7 |  | 0
20 | REMOVE AND RELOCATE TRASH RECEPTACLE | EACH | 1 |  | 0
21 | REMOVE AND RELOCATE PARK BENCH | EACH | 1 |  | 0
22 | STAMPED, COLORED PORTLAND CEMENT CONCRETE SIDEWALK, 5 INCH | SQ FT | 1315 |  | 0
23 | GINKO BILOBA / MAIDENHAIR TREE, 2.5" CALIPER | EACH | 8 |  | 0
24 | ULMUS X 'FRONTIER' / FRONTIER ELM, 2.5" CALIPER | EACH | 2 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | PERENNIALS, #1 CONTAINER | EACH | 160 |  | 0
26 | GRASSES, #1 CONTAINER | EACH | 20 |  | 0
27 | CONSTRUCTION LAYOUT STAKES | LSUM | 1 |  | 0
28 | MOBILIZATION | LSUM | 1 |  | 0
29 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 4" DIA. | FOOT | 117 |  | 0
30 | UNIT DUCT , 600V, 4-1C NO. 4, 1/C NO. 6 GROUND (XLP-TYPE USE),1 1/2" DIA. POLYETHYENE | FOOT | 703 |  | 0
31 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 6 | FOOT | 275 |  | 0
32 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 4 | FOOT | 1925 |  | 0
33 | LIGHT POLE FOUNDATION, 24" DIAMETER | FOOT | 140 |  | 0
34 | REMOVAL OF LIGHTING UNIT, SALVAGE | EACH | 5 |  | 0
35 | REMOVAL OF POLE FOUNDATION | EACH | 5 |  | 0
36 | REMOVE EXISTING HANDHOLE | EACH | 5 |  | 0
37 | DRILL EXISTING HANDHOLE | EACH | 1 |  | 0
38 | LUMINAIRE, LED, SPECIAL | EACH | 14 |  | 0
39 | LIGHT POLE , SPECIAL TYPE A | EACH | 4 |  | 0
40 | LIGHT POLE, SPECIAL TYPE B | EACH | 10 |  | 0
41 | MAINTENENACE OF LIGHTING SYSTEM | CAL MO | 3 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Project Name: Main Street Streetscape
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LSUM | 1 | 10000 | 10000
2 | DEBRIS REMOVAL | LSUM | 1 | 10000 | 10000
3 | GEOCOMPOSITE WALL DRAIN | SQ YD | 37 | 50 | 1850
4 | MASONRY WALL CONSTRUCTION | SQ FT | 270 | 30 | 8100
5 | CA-7 DRAINAGE STONE | TON | 210 | 50 | 10500
6 | FILTER FABRIC | SQ YD | 42 | 25 | 1050
7 | INLET AND PIPE PROTECTION | EACH | 2 | 125 | 250
8 | ADJUST WATER VALVE | EACH | 4 | 600 | 2400
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 5-INCH | SQ FT | 9284 | 7.5 | 69630
10 | AGGREGATE BASE COURSE, TYPE B 4" | SQ YD | 1178 | 8 | 9424
11 | DETECTABLE WARNINGS | SQ FT | 20 | 30 | 600
12 | COMBINATION CURB AND GUTTER REMOVAL | FT | 80 | 35 | 2800
13 | PLANTER CURB | EACH | 10 | 300 | 3000
14 | SIDEWALK REMOVAL | SQ FT | 9343 | 15 | 140145
15 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FT | 80 | 35 | 2800
16 | REMOVING AND RESETTING STREET SIGNS | EACH | 1 | 50 | 50
17 | TUBULAR STEEL SIGN SUPPORT | FT | 160 | 15 | 2400
18 | SIGN PANEL, TYPE 1 | SQ FT | 44 | 45 | 1980
19 | TREE AND GRATE REMOVAL | EACH | 7 | 35 | 245
20 | REMOVE AND RELOCATE TRASH RECEPTACLE | EACH | 1 | 50 | 50
21 | REMOVE AND RELOCATE PARK BENCH | EACH | 1 | 200 | 200
22 | STAMPED, COLORED PORTLAND CEMENT CONCRETE SIDEWALK, 5 INCH | SQ FT | 1315 | 20 | 26300
23 | GINKO BILOBA / MAIDENHAIR TREE, 2.5" CALIPER | EACH | 8 | 500 | 4000
24 | ULMUS X 'FRONTIER' / FRONTIER ELM, 2.5" CALIPER | EACH | 2 | 500 | 1000
|  |  |  | Sub Total | 308774
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Project Name: Main Street Streetscape
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | PERENNIALS, #1 CONTAINER | EACH | 160 | 1900 | 304000
26 | GRASSES, #1 CONTAINER | EACH | 20 | 1900 | 38000
27 | CONSTRUCTION LAYOUT STAKES | LSUM | 1 | 19000 | 19000
28 | MOBILIZATION | LSUM | 1 | 10000 | 10000
29 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 4" DIA. | FOOT | 117 | 38 | 4446
30 | UNIT DUCT , 600V, 4-1C NO. 4, 1/C NO. 6 GROUND (XLP-TYPE USE),1 1/2" DIA. POLYETHYENE | FOOT | 703 | 60 | 42180
31 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 6 | FOOT | 275 | 2.4 | 660
32 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 4 | FOOT | 1925 | 2.4 | 4620
33 | LIGHT POLE FOUNDATION, 24" DIAMETER | FOOT | 140 | 200 | 28000
34 | REMOVAL OF LIGHTING UNIT, SALVAGE | EACH | 5 | 437 | 2185
35 | REMOVAL OF POLE FOUNDATION | EACH | 5 | 212 | 1060
36 | REMOVE EXISTING HANDHOLE | EACH | 5 | 500 | 2500
37 | DRILL EXISTING HANDHOLE | EACH | 1 | 1000 | 1000
38 | LUMINAIRE, LED, SPECIAL | EACH | 14 | 1440 | 20160
39 | LIGHT POLE , SPECIAL TYPE A | EACH | 4 | 4000 | 16000
40 | LIGHT POLE, SPECIAL TYPE B | EACH | 10 | 4000 | 40000
41 | MAINTENENACE OF LIGHTING SYSTEM | CAL MO | 3 | 1000 | 3000
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 845585
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Project Name: Main Street Streetscape
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 845585
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Project Name: Main Street Streetscape
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 845585
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Copenhaver Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Gilberts, IL Bid Bond | [5 empty] | SECTION | Project Name: Main Street Streetscape
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | 1 | LSUM | 49000 |  | 1 |  |  | 49000
2 | DEBRIS REMOVAL | 1 | LSUM | 2900 |  | 1 |  |  | 2900
3 | GEOCOMPOSITE WALL DRAIN | 37 | SQ YD | 925 |  | 37 |  |  | 25
4 | MASONRY WALL CONSTRUCTION | 270 | SQ FT | 22680 |  | 270 |  |  | 84
5 | CA-7 DRAINAGE STONE | 210 | TON | 7980 |  | 210 |  |  | 38
6 | FILTER FABRIC | 42 | SQ YD | 420 |  | 42 |  |  | 10
7 | INLET AND PIPE PROTECTION | 2 | EACH | 220 |  | 2 |  |  | 110
8 | ADJUST WATER VALVE | 4 | EACH | 1480 |  | 4 |  |  | 370
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 5-INCH | 9284 | SQ FT | 92840 |  | 9284 |  |  | 10
10 | AGGREGATE BASE COURSE, TYPE B 4" | 1178 | SQ YD | 8246 |  | 1178 |  |  | 7
11 | DETECTABLE WARNINGS | 20 | SQ FT | 800 |  | 20 |  |  | 40
12 | COMBINATION CURB AND GUTTER REMOVAL | 80 | FT | 960 |  | 80 |  |  | 12
13 | PLANTER CURB | 10 | EACH | 19000 |  | 10 |  |  | 1900
14 | SIDEWALK REMOVAL | 9343 | SQ FT | 28029 |  | 9343 |  |  | 3
15 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | 80 | FT | 2560 |  | 80 |  |  | 32
16 | REMOVING AND RESETTING STREET SIGNS | 1 | EACH | 600 |  | 1 |  |  | 600
17 | TUBULAR STEEL SIGN SUPPORT | 160 | FT | 3360 |  | 160 |  |  | 21
18 | SIGN PANEL, TYPE 1 | 44 | SQ FT | 1232 |  | 44 |  |  | 28
19 | TREE AND GRATE REMOVAL | 7 | EACH | 5600 |  | 7 |  |  | 800
20 | REMOVE AND RELOCATE TRASH RECEPTACLE | 1 | EACH | 600 |  | 1 |  |  | 600
21 | REMOVE AND RELOCATE PARK BENCH | 1 | EACH | 600 |  | 1 |  |  | 600
22 | STAMPED, COLORED PORTLAND CEMENT CONCRETE SIDEWALK, 5 INCH | 1315 | SQ FT | 32875 |  | 1315 |  |  | 25
23 | GINKO BILOBA / MAIDENHAIR TREE, 2.5" CALIPER | 8 | EACH | 7600 |  | 8 |  |  | 950
24 | ULMUS X 'FRONTIER' / FRONTIER ELM, 2.5" CALIPER | 2 | EACH | 2200 |  | 2 |  |  | 1100
Sub Total |  |  |  | 292707 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Copenhaver Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Gilberts, IL Bid Bond | [5 empty] | SECTION | Project Name: Main Street Streetscape
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | PERENNIALS, #1 CONTAINER | 160 | EACH | 3520 |  | 160 |  |  | 22
26 | GRASSES, #1 CONTAINER | 20 | EACH | 460 |  | 20 |  |  | 23
27 | CONSTRUCTION LAYOUT STAKES | 1 | LSUM | 11000 |  | 1 |  |  | 11000
28 | MOBILIZATION | 1 | LSUM | 41000 |  | 1 |  |  | 41000
29 | UNDERGROUND CONDUIT, GALVANIZED STEEL, 4" DIA. | 117 | FOOT | 9243 |  | 117 |  |  | 79
30 | UNIT DUCT , 600V, 4-1C NO. 4, 1/C NO. 6 GROUND (XLP-TYPE USE),1 1/2" DIA. POLYETHYENE | 703 | FOOT | 16169 |  | 703 |  |  | 23
31 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 6 | 275 | FOOT | 825 |  | 275 |  |  | 3
32 | ELECTRIC CABLE IN CONDUIT, 600V (XLP-TYPE USE) 1/C NO. 4 | 1925 | FOOT | 5775 |  | 1925 |  |  | 3
33 | LIGHT POLE FOUNDATION, 24" DIAMETER | 140 | FOOT | 32200 |  | 140 |  |  | 230
34 | REMOVAL OF LIGHTING UNIT, SALVAGE | 5 | EACH | 3340 |  | 5 |  |  | 668
35 | REMOVAL OF POLE FOUNDATION | 5 | EACH | 2625 |  | 5 |  |  | 525
36 | REMOVE EXISTING HANDHOLE | 5 | EACH | 1000 |  | 5 |  |  | 200
37 | DRILL EXISTING HANDHOLE | 1 | EACH | 330 |  | 1 |  |  | 330
38 | LUMINAIRE, LED, SPECIAL | 14 | EACH | 71400 |  | 14 |  |  | 5100
39 | LIGHT POLE , SPECIAL TYPE A | 4 | EACH | 30000 |  | 4 |  |  | 7500
40 | LIGHT POLE, SPECIAL TYPE B | 10 | EACH | 74000 |  | 10 |  |  | 7400
41 | MAINTENENACE OF LIGHTING SYSTEM | 3 | CAL MO | 2100 |  | 3 |  |  | 700
Total |  |  |  | 597694 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Copenhaver Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Gilberts, IL Bid Bond | [5 empty] | SECTION | Project Name: Main Street Streetscape
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 597694 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from May 12, 2008 to June 4, 2008 | [7 empty] | (Road District)
| Payable to: Copenhaver Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Gilberts, IL Bid Bond | [5 empty] | SECTION | Project Name: Main Street Streetscape
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 597694 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Project Name: Main Street Streetscape
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Copenhaver Construction
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.