## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 1947224.5
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 25000 | 25000
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 10000 | 10000
3 | INLET AND PIPE PROTECTION | EA | 53 | 150 | 7950
4 | CONCRETE TRUCK WASHOUT | EA | 3 | 750 | 2250
5 | PAVEMENT REMOVAL | SY | 4980 | 10.5 | 52290
6 | APPROACH PAVEMENT REMOVAL | SY | 85 | 9.5 | 807.5
7 | SIDEWALK REMOVAL | SF | 7150 | 2.5 | 17875
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 946 | 7 | 6622
9 | ROCK EXCAVATION | CY | 50 | 100 | 5000
10 | INLET TO BE RECONSTRUCTED | EA | 2 | 1750 | 3500
11 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 19 | 750 | 14250
12 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 5 | 1500 | 7500
13 | REMOVE FIRE HYDRANT, COMPLETE | EA | 5 | 850 | 4250
14 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M6.18 (MODIFIED) | LF | 610 | 45 | 27450
15 | PCC SIDEWALK, COMPLETE, 4" | SF | 6300 | 10 | 63000
16 | DETECTABLE WARNINGS | SF | 80 | 40 | 3200
17 | BRICK SIDEWALK REMOVAL AND REPLACEMENT, COMPLETE | SF | 100 | 45 | 4500
18 | PCC PAVEMENT, 6" (JOINTED) | SY | 92 | 105 | 9660
19 | PCC PAVEMENT, 9.5" (JOINTED) | SY | 151 | 115 | 17365
20 | PCC APPROACH PAVEMENT, 6" | SY | 53 | 95 | 5035
21 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 4980 | 7.5 | 37350
22 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 4980 | 7.5 | 37350
23 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N70, 3" | TON | 16 | 100 | 1600
24 | HOT MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 260 | 105 | 27300
25 | HOT MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 777 | 90 | 69930
26 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 8" | TON | 578 | 90 | 52020
27 | HOT-MIX ASPHALT APPROACH PAVEMENT, 3" | SY | 32 | 125 | 4000
28 | C-I-P-P WATER MAIN LINING, COMPLETE, 8" | LF | 1047 | 325 | 340275
29 | DUCTILE IRON WATER MAIN COMPLETE, 6" | LF | 20 | 150 | 3000
30 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 4125 | 110 | 453750
31 | DUCTILE IRON WATER MAIN COMPLETE, 12" | LF | 20 | 200 | 4000
32 | STORM SEWER, WATER MAIN QUALITY, 12" COMPLETE | LF | 51 | 85 | 4335
33 | STORM SEWER, WATER MAIN QUALITY, 15" COMPLETE | LF | 33 | 95 | 3135
34 | GATE VALVE AND VALVE BOX, COMPLETE, 4" | EA | 1 | 1750 | 1750
35 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 | 2000 | 2000
36 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 22 | 2250 | 49500
37 | BUTTERFLY VALVE AND VALVE BOX, COMPLETE, 12" | EA | 1 | 3500 | 3500
38 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 6 | 6500 | 39000
39 | WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 24 | 2750 | 66000
40 | WATER SERVICE (OPEN-CUT), COMPLETE, 1.5" | EA | 1 | 2750 | 2750
41 | WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 | 3000 | 3000
42 | 1" WATER SERVICE BORED WITH 2" CASING, COMPLETE, | LF | 690 | 90 | 62100
43 | RECONNECT 4" WATER SERVICE, COMPLETE | EA | 2 | 1750 | 3500
44 | RECONNECT 6" WATER SERVICE, COMPLETE | EA | 3 | 2000 | 6000
45 | CONNECT TO EXISTING 4" WATER MAIN, COMPLETE | EA | 2 | 3000 | 6000
46 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 1 | 3250 | 3250
47 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 12 | 3500 | 42000
48 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 2 | 3750 | 7500
49 | WATER MAIN PROTECTION, 12" | LF | 245 | 45 | 11025
50 | WATER SERVICE PROTECTION, 2" | LF | 355 | 10 | 3550
51 | WATER MAIN LINE STOP, 4" | EA | 2 | 4250 | 8500
52 | WATER MAIN LINE STOP, 6" | EA | 4 | 4750 | 19000
53 | WATER MAIN LINE STOP, 8" | EA | 5 | 6000 | 30000
54 | WATER MAIN LINE STOP, 12" | EA | 2 | 7500 | 15000
55 | INSERTION VALVE, COMPLETE, 4" | EA | 2 | 5500 | 11000
56 | INSERTION VALVE, COMPLETE, 6" | EA | 4 | 6000 | 24000
57 | INSERTION VALVE, COMPLETE, 8" | EA | 6 | 7000 | 42000
58 | INSERTION VALVE, COMPLETE, 12" | EA | 2 | 12500 | 25000
59 | PARKWAY RESTORATION | LS | 1 | 50000 | 50000
60 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 20000 | 20000
61 | RAILROAD FLAGGING | DAY | 5 | 2500 | 12500
62 | RAILROAD PROTECTIVE LIABILITY INSURANCE (IDOT PAY ITEM Z0048665) | LS | 1 | 2500 | 2500
63 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 150 | 3750
64 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 150 | 3750
65 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 | 750 | 750
66 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 1500 | 1500
67 | TEMPORARY POTABLE WATER BYPASS SYSTEM | LS | 1 | 40000 | 40000
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  | Name and Address | NAME AND ADDRESS OF BIDDER: |  | Northern Illinois Service |  | N-TRAK Group |  | Fischer Excavating
City of Rockford |  |  | of Bidder: |  |  | Rockford, IL |  | Loves Park, IL |  | Freeport, IL
Bid No.: 421-W-028 | [5 empty] | Ø
South 3rd St, Gregory St. & Seminary St. Water Main Replacement
VENDORS NOTIFIED: 89
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 25000 | 25000 | 31185 | 31185 | 25000 | 25000 | 20700 | 20700 |  | 0 |  | 0 |  | 0
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 10000 | 10000 | 3500 | 3500 | 5000 | 5000 | 4250 | 4250 |  | 0 |  | 0 |  | 0
3 | INLET AND PIPE PROTECTION | EA | 53 | 150 | 7950 | 100 | 5300 | 100 | 5300 | 57 | 3021 |  | 0 |  | 0 |  | 0
4 | CONCRETE TRUCK WASHOUT | EA | 3 | 750 | 2250 | 300 | 900 | 1 | 3 | 350 | 1050 |  | 0 |  | 0 |  | 0
5 | PAVEMENT REMOVAL | SY | 4980 | 10.5 | 52290 | 5 | 24900 | 4.5 | 22410 | 12.75 | 63495 |  | 0 |  | 0 |  | 0
6 | APPROACH PAVEMENT REMOVAL | SY | 85 | 9.5 | 807.5 | 5 | 425 | 4.5 | 382.5 | 7.6 | 646 |  | 0 |  | 0 |  | 0
7 | SIDEWALK REMOVAL | SF | 7150 | 2.5 | 17875 | 1 | 7150 | 1 | 7150 | 2.5 | 17875 |  | 0 |  | 0 |  | 0
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 946 | 7 | 6622 | 4 | 3784 | 4 | 3784 | 4 | 3784 |  | 0 |  | 0 |  | 0
9 | ROCK EXCAVATION | CY | 50 | 100 | 5000 | 200 | 10000 | 1 | 50 | 59 | 2950 |  | 0 |  | 0 |  | 0
10 | INLET TO BE RECONSTRUCTED | EA | 2 | 1750 | 3500 | 2000 | 4000 | 1000 | 2000 | 450 | 900 |  | 0 |  | 0 |  | 0
11 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 19 | 750 | 14250 | 400 | 7600 | 400 | 7600 | 427 | 8113 |  | 0 |  | 0 |  | 0
12 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 5 | 1500 | 7500 | 600 | 3000 | 400 | 2000 | 427 | 2135 |  | 0 |  | 0 |  | 0
13 | REMOVE FIRE HYDRANT, COMPLETE | EA | 5 | 850 | 4250 | 700 | 3500 | 700 | 3500 | 947 | 4735 |  | 0 |  | 0 |  | 0
14 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M6.18 (MODIFIED) | LF | 610 | 45 | 27450 | 26 | 15860 | 40 | 24400 | 34 | 20740 |  | 0 |  | 0 |  | 0
15 | PCC SIDEWALK, COMPLETE, 4" | SF | 6300 | 10 | 63000 | 5.25 | 33075 | 8.75 | 55125 | 8.25 | 51975 |  | 0 |  | 0 |  | 0
16 | DETECTABLE WARNINGS | SF | 80 | 40 | 3200 | 25 | 2000 | 25 | 2000 | 25 | 2000 |  | 0 |  | 0 |  | 0
17 | BRICK SIDEWALK REMOVAL AND REPLACEMENT, COMPLETE | SF | 100 | 45 | 4500 | 25 | 2500 | 24 | 2400 | 25 | 2500 |  | 0 |  | 0 |  | 0
18 | PCC PAVEMENT, 6" (JOINTED) | SY | 92 | 105 | 9660 | 76 | 6992 | 78 | 7176 | 75 | 6900 |  | 0 |  | 0 |  | 0
19 | PCC PAVEMENT, 9.5" (JOINTED) | SY | 151 | 115 | 17365 | 89 | 13439 | 78 | 11778 | 90 | 13590 |  | 0 |  | 0 |  | 0
20 | PCC APPROACH PAVEMENT, 6" | SY | 53 | 95 | 5035 | 69 | 3657 | 85 | 4505 | 81 | 4293 |  | 0 |  | 0 |  | 0
21 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 4980 | 7.5 | 37350 | 5.5 | 27390 | 4.5 | 22410 | 5.8 | 28884 |  | 0 |  | 0 |  | 0
22 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 4980 | 7.5 | 37350 | 5.5 | 27390 | 5.75 | 28635 | 16.5 | 82170 |  | 0 |  | 0 |  | 0
23 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N70, 3" | TON | 16 | 100 | 1600 | 170 | 2720 | 113 | 1808 | 170 | 2720 |  | 0 |  | 0 |  | 0
24 | HOT MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 260 | 105 | 27300 | 83 | 21580 | 113 | 29380 | 83 | 21580 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 391104.5 |  | 261847 |  | 273796.5 |  | 371006
| Award to Northern Illinois Service | Total |  | As corrected | 391104.5 |  | 261847 |  | 273796.5 |  | 371006
25 | HOT MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 777 | 90 | 69930 | 73 | 56721 | 89 | 69153 | 73 | 56721 |  | 0 |  | 0 |  | 0
26 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 8" | TON | 578 | 90 | 52020 | 79 | 45662 | 89 | 51442 | 79 | 45662 |  | 0 |  | 0 |  | 0
27 | HOT-MIX ASPHALT APPROACH PAVEMENT, 3" | SY | 32 | 125 | 4000 | 44 | 1408 | 75 | 2400 | 56.8 | 1817.6 |  | 0 |  | 0 |  | 0
28 | C-I-P-P WATER MAIN LINING, COMPLETE, 8" | LF | 1047 | 325 | 340275 | 128 | 134016 | 160 | 167520 | 171 | 179037 |  | 0 |  | 0 |  | 0
29 | DUCTILE IRON WATER MAIN COMPLETE, 6" | LF | 20 | 150 | 3000 | 185 | 3700 | 100 | 2000 | 255 | 5100 |  | 0 |  | 0 |  | 0
30 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 4125 | 110 | 453750 | 102.71 | 423678.75 | 100 | 412500 | 109.5 | 451687.5 |  | 0 |  | 0 |  | 0
31 | DUCTILE IRON WATER MAIN COMPLETE, 12" | LF | 20 | 200 | 4000 | 180 | 3600 | 225 | 4500 | 241 | 4820 |  | 0 |  | 0 |  | 0
32 | STORM SEWER, WATER MAIN QUALITY, 12" COMPLETE | LF | 51 | 85 | 4335 | 60 | 3060 | 100 | 5100 | 138 | 7038 |  | 0 |  | 0 |  | 0
33 | STORM SEWER, WATER MAIN QUALITY, 15" COMPLETE | LF | 33 | 95 | 3135 | 110 | 3630 | 135 | 4455 | 168.5 | 5560.5 |  | 0 |  | 0 |  | 0
34 | GATE VALVE AND VALVE BOX, COMPLETE, 4" | EA | 1 | 1750 | 1750 | 1400 | 1400 | 1350 | 1350 | 1370 | 1370 |  | 0 |  | 0 |  | 0
35 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 | 2000 | 2000 | 1500 | 1500 | 1500 | 1500 | 1375 | 1375 |  | 0 |  | 0 |  | 0
36 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 22 | 2250 | 49500 | 1900 | 41800 | 2200 | 48400 | 1560 | 34320 |  | 0 |  | 0 |  | 0
37 | BUTTERFLY VALVE AND VALVE BOX, COMPLETE, 12" | EA | 1 | 3500 | 3500 | 3500 | 3500 | 3400 | 3400 | 3006 | 3006 |  | 0 |  | 0 |  | 0
38 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 6 | 6500 | 39000 | 5500 | 33000 | 5500 | 33000 | 5720 | 34320 |  | 0 |  | 0 |  | 0
39 | WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 24 | 2750 | 66000 | 2600 | 62400 | 3100 | 74400 | 3020 | 72480 |  | 0 |  | 0 |  | 0
40 | WATER SERVICE (OPEN-CUT), COMPLETE, 1.5" | EA | 1 | 2750 | 2750 | 3400 | 3400 | 3200 | 3200 | 4448 | 4448 |  | 0 |  | 0 |  | 0
41 | WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 | 3000 | 3000 | 3900 | 3900 | 3300 | 3300 | 4836 | 4836 |  | 0 |  | 0 |  | 0
42 | 1" WATER SERVICE BORED WITH 2" CASING, COMPLETE, | LF | 690 | 90 | 62100 | 90 | 62100 | 71 | 48990 | 69.75 | 48127.5 |  | 0 |  | 0 |  | 0
43 | RECONNECT 4" WATER SERVICE, COMPLETE | EA | 2 | 1750 | 3500 | 1800 | 3600 | 3500 | 7000 | 8158 | 16316 |  | 0 |  | 0 |  | 0
44 | RECONNECT 6" WATER SERVICE, COMPLETE | EA | 3 | 2000 | 6000 | 1900 | 5700 | 3500 | 10500 | 8655 | 25965 |  | 0 |  | 0 |  | 0
45 | CONNECT TO EXISTING 4" WATER MAIN, COMPLETE | EA | 2 | 3000 | 6000 | 1800 | 3600 | 2500 | 5000 | 2565 | 5130 |  | 0 |  | 0 |  | 0
46 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 1 | 3250 | 3250 | 2000 | 2000 | 2500 | 2500 | 3187 | 3187 |  | 0 |  | 0 |  | 0
47 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 12 | 3500 | 42000 | 2000 | 24000 | 2500 | 30000 | 3070 | 36840 |  | 0 |  | 0 |  | 0
48 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 2 | 3750 | 7500 | 2000 | 4000 | 3000 | 6000 | 4281 | 8562 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 1623399.5 |  | 1193222.75 |  | 1271406.5 |  | 1428732.1
| Award to Northern Illinois Service | Total |  | As corrected | 1623399.5 |  | 1193222.75 |  | 1271406.5 |  | 1428732.1
49 | WATER MAIN PROTECTION, 12" | LF | 245 | 45 | 11025 | 30 | 7350 | 40 | 9800 | 58 | 14210 |  | 0 |  | 0 |  | 0
50 | WATER SERVICE PROTECTION, 2" | LF | 355 | 10 | 3550 | 10 | 3550 | 2 | 710 | 9.75 | 3461.25 |  | 0 |  | 0 |  | 0
51 | WATER MAIN LINE STOP, 4" | EA | 2 | 4250 | 8500 | 2500 | 5000 | 3000 | 6000 | 3785 | 7570 |  | 0 |  | 0 |  | 0
52 | WATER MAIN LINE STOP, 6" | EA | 4 | 4750 | 19000 | 2600 | 10400 | 3100 | 12400 | 4260 | 17040 |  | 0 |  | 0 |  | 0
53 | WATER MAIN LINE STOP, 8" | EA | 5 | 6000 | 30000 | 3000 | 15000 | 3500 | 17500 | 4700 | 23500 |  | 0 |  | 0 |  | 0
54 | WATER MAIN LINE STOP, 12" | EA | 2 | 7500 | 15000 | 7500 | 15000 | 5000 | 10000 | 6420 | 12840 |  | 0 |  | 0 |  | 0
55 | INSERTION VALVE, COMPLETE, 4" | EA | 2 | 5500 | 11000 | 5000 | 10000 | 4700 | 9400 | 5836 | 11672 |  | 0 |  | 0 |  | 0
56 | INSERTION VALVE, COMPLETE, 6" | EA | 4 | 6000 | 24000 | 5300 | 21200 | 5000 | 20000 | 6212 | 24848 |  | 0 |  | 0 |  | 0
57 | INSERTION VALVE, COMPLETE, 8" | EA | 6 | 7000 | 42000 | 5700 | 34200 | 5400 | 32400 | 6664 | 39984 |  | 0 |  | 0 |  | 0
58 | INSERTION VALVE, COMPLETE, 12" | EA | 2 | 12500 | 25000 | 9300 | 18600 | 9000 | 18000 | 11805 | 23610 |  | 0 |  | 0 |  | 0
59 | PARKWAY RESTORATION | LS | 1 | 50000 | 50000 | 20000 | 20000 | 16000 | 16000 | 11800 | 11800 |  | 0 |  | 0 |  | 0
60 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 20000 | 20000 | 7500 | 7500 | 20000 | 20000 | 3275 | 3275 |  | 0 |  | 0 |  | 0
61 | RAILROAD FLAGGING | DAY | 5 | 2500 | 12500 | 750 | 3750 | 1000 | 5000 | 1500 | 7500 |  | 0 |  | 0 |  | 0
62 | RAILROAD PROTECTIVE LIABILITY INSURANCE (IDOT PAY ITEM Z0048665) | LS | 1 | 2500 | 2500 | 3000 | 3000 | 1350 | 1350 | 7500 | 7500 |  | 0 |  | 0 |  | 0
63 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 150 | 3750 | 100 | 2500 | 35 | 875 | 84.5 | 2112.5 |  | 0 |  | 0 |  | 0
64 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 150 | 3750 | 100 | 2500 | 35 | 875 | 96.8 | 2420 |  | 0 |  | 0 |  | 0
65 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 | 750 | 750 | 2500 | 2500 | 1 | 1 | 2300 | 2300 |  | 0 |  | 0 |  | 0
66 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 1500 | 1500 | 1250 | 1250 | 2000 | 2000 | 1500 | 1500 |  | 0 |  | 0 |  | 0
67 | TEMPORARY POTABLE WATER BYPASS SYSTEM | LS | 1 | 40000 | 40000 | 43100 | 43100 | 60000 | 60000 | 43100 | 43100 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Additional Construction Costs to comply with Business Enterprise Program (BEP) goals defined by DCEO Opportunity Zone grant Program |  | 0 | 0 | 0 |  | 35000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total | As read | As read | 1947224.5 |  | 1419622.75 |  | 1513717.5 |  | 1688974.85
| Award to Northern Illinois Service | Bid | As corrected | As corrected | 1947224.5 |  | 1454622.75 |  | 1513717.5 |  | 1688974.85
|  |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read |  |  | 2909245.5
| Award to Northern Illinois Service | Bid |  | As corrected |  |  | 1419622.75

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
VENDORS NOTIFIED: 89
Item No. | Items | Units | Quantity | Unit Price | Total
1 | MOBILIZATION | LS | 1 |  | 0
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 |  | 0
3 | INLET AND PIPE PROTECTION | EA | 53 |  | 0
4 | CONCRETE TRUCK WASHOUT | EA | 3 |  | 0
5 | PAVEMENT REMOVAL | SY | 4980 |  | 0
6 | APPROACH PAVEMENT REMOVAL | SY | 85 |  | 0
7 | SIDEWALK REMOVAL | SF | 7150 |  | 0
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 946 |  | 0
9 | ROCK EXCAVATION | CY | 50 |  | 0
10 | INLET TO BE RECONSTRUCTED | EA | 2 |  | 0
11 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 19 |  | 0
12 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 5 |  | 0
13 | REMOVE FIRE HYDRANT, COMPLETE | EA | 5 |  | 0
14 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M6.18 (MODIFIED) | LF | 610 |  | 0
15 | PCC SIDEWALK, COMPLETE, 4" | SF | 6300 |  | 0
16 | DETECTABLE WARNINGS | SF | 80 |  | 0
17 | BRICK SIDEWALK REMOVAL AND REPLACEMENT, COMPLETE | SF | 100 |  | 0
18 | PCC PAVEMENT, 6" (JOINTED) | SY | 92 |  | 0
19 | PCC PAVEMENT, 9.5" (JOINTED) | SY | 151 |  | 0
20 | PCC APPROACH PAVEMENT, 6" | SY | 53 |  | 0
21 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 4980 |  | 0
22 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 4980 |  | 0
23 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N70, 3" | TON | 16 |  | 0
24 | HOT MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 260 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | HOT MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 777 |  | 0
26 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 8" | TON | 578 |  | 0
27 | HOT-MIX ASPHALT APPROACH PAVEMENT, 3" | SY | 32 |  | 0
28 | C-I-P-P WATER MAIN LINING, COMPLETE, 8" | LF | 1047 |  | 0
29 | DUCTILE IRON WATER MAIN COMPLETE, 6" | LF | 20 |  | 0
30 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 4125 |  | 0
31 | DUCTILE IRON WATER MAIN COMPLETE, 12" | LF | 20 |  | 0
32 | STORM SEWER, WATER MAIN QUALITY, 12" COMPLETE | LF | 51 |  | 0
33 | STORM SEWER, WATER MAIN QUALITY, 15" COMPLETE | LF | 33 |  | 0
34 | GATE VALVE AND VALVE BOX, COMPLETE, 4" | EA | 1 |  | 0
35 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 |  | 0
36 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 22 |  | 0
37 | BUTTERFLY VALVE AND VALVE BOX, COMPLETE, 12" | EA | 1 |  | 0
38 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 6 |  | 0
39 | WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 24 |  | 0
40 | WATER SERVICE (OPEN-CUT), COMPLETE, 1.5" | EA | 1 |  | 0
41 | WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 |  | 0
42 | 1" WATER SERVICE BORED WITH 2" CASING, COMPLETE, | LF | 690 |  | 0
43 | RECONNECT 4" WATER SERVICE, COMPLETE | EA | 2 |  | 0
44 | RECONNECT 6" WATER SERVICE, COMPLETE | EA | 3 |  | 0
45 | CONNECT TO EXISTING 4" WATER MAIN, COMPLETE | EA | 2 |  | 0
46 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 1 |  | 0
47 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 12 |  | 0
48 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 2 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | WATER MAIN PROTECTION, 12" | LF | 245 |  | 0
50 | WATER SERVICE PROTECTION, 2" | LF | 355 |  | 0
51 | WATER MAIN LINE STOP, 4" | EA | 2 |  | 0
52 | WATER MAIN LINE STOP, 6" | EA | 4 |  | 0
53 | WATER MAIN LINE STOP, 8" | EA | 5 |  | 0
54 | WATER MAIN LINE STOP, 12" | EA | 2 |  | 0
55 | INSERTION VALVE, COMPLETE, 4" | EA | 2 |  | 0
56 | INSERTION VALVE, COMPLETE, 6" | EA | 4 |  | 0
57 | INSERTION VALVE, COMPLETE, 8" | EA | 6 |  | 0
58 | INSERTION VALVE, COMPLETE, 12" | EA | 2 |  | 0
59 | PARKWAY RESTORATION | LS | 1 |  | 0
60 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 |  | 0
61 | RAILROAD FLAGGING | DAY | 5 |  | 0
62 | RAILROAD PROTECTIVE LIABILITY INSURANCE (IDOT PAY ITEM Z0048665) | LS | 1 |  | 0
63 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 |  | 0
64 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 |  | 0
65 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 |  | 0
66 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 |  | 0
67 | TEMPORARY POTABLE WATER BYPASS SYSTEM | LS | 1 |  | 0
|  |  | 0 |  | 0
0 | Additional Construction Costs to comply with Business Enterprise Program (BEP) goals defined by DCEO Opportunity Zone grant Program |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | VENDORS NOTIFIED: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 25000 | 25000
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 10000 | 10000
3 | INLET AND PIPE PROTECTION | EA | 53 | 150 | 7950
4 | CONCRETE TRUCK WASHOUT | EA | 3 | 750 | 2250
5 | PAVEMENT REMOVAL | SY | 4980 | 10.5 | 52290
6 | APPROACH PAVEMENT REMOVAL | SY | 85 | 9.5 | 807.5
7 | SIDEWALK REMOVAL | SF | 7150 | 2.5 | 17875
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 946 | 7 | 6622
9 | ROCK EXCAVATION | CY | 50 | 100 | 5000
10 | INLET TO BE RECONSTRUCTED | EA | 2 | 1750 | 3500
11 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 19 | 750 | 14250
12 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 5 | 1500 | 7500
13 | REMOVE FIRE HYDRANT, COMPLETE | EA | 5 | 850 | 4250
14 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M6.18 (MODIFIED) | LF | 610 | 45 | 27450
15 | PCC SIDEWALK, COMPLETE, 4" | SF | 6300 | 10 | 63000
16 | DETECTABLE WARNINGS | SF | 80 | 40 | 3200
17 | BRICK SIDEWALK REMOVAL AND REPLACEMENT, COMPLETE | SF | 100 | 45 | 4500
18 | PCC PAVEMENT, 6" (JOINTED) | SY | 92 | 105 | 9660
19 | PCC PAVEMENT, 9.5" (JOINTED) | SY | 151 | 115 | 17365
20 | PCC APPROACH PAVEMENT, 6" | SY | 53 | 95 | 5035
21 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 4980 | 7.5 | 37350
22 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 4980 | 7.5 | 37350
23 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N70, 3" | TON | 16 | 100 | 1600
24 | HOT MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 260 | 105 | 27300
|  |  |  | Sub Total | 391104.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | VENDORS NOTIFIED: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | HOT MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 777 | 90 | 69930
26 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 8" | TON | 578 | 90 | 52020
27 | HOT-MIX ASPHALT APPROACH PAVEMENT, 3" | SY | 32 | 125 | 4000
28 | C-I-P-P WATER MAIN LINING, COMPLETE, 8" | LF | 1047 | 325 | 340275
29 | DUCTILE IRON WATER MAIN COMPLETE, 6" | LF | 20 | 150 | 3000
30 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 4125 | 110 | 453750
31 | DUCTILE IRON WATER MAIN COMPLETE, 12" | LF | 20 | 200 | 4000
32 | STORM SEWER, WATER MAIN QUALITY, 12" COMPLETE | LF | 51 | 85 | 4335
33 | STORM SEWER, WATER MAIN QUALITY, 15" COMPLETE | LF | 33 | 95 | 3135
34 | GATE VALVE AND VALVE BOX, COMPLETE, 4" | EA | 1 | 1750 | 1750
35 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 | 2000 | 2000
36 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 22 | 2250 | 49500
37 | BUTTERFLY VALVE AND VALVE BOX, COMPLETE, 12" | EA | 1 | 3500 | 3500
38 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 6 | 6500 | 39000
39 | WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 24 | 2750 | 66000
40 | WATER SERVICE (OPEN-CUT), COMPLETE, 1.5" | EA | 1 | 2750 | 2750
41 | WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 | 3000 | 3000
42 | 1" WATER SERVICE BORED WITH 2" CASING, COMPLETE, | LF | 690 | 90 | 62100
43 | RECONNECT 4" WATER SERVICE, COMPLETE | EA | 2 | 1750 | 3500
44 | RECONNECT 6" WATER SERVICE, COMPLETE | EA | 3 | 2000 | 6000
45 | CONNECT TO EXISTING 4" WATER MAIN, COMPLETE | EA | 2 | 3000 | 6000
46 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 1 | 3250 | 3250
47 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 12 | 3500 | 42000
48 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 2 | 3750 | 7500
|  |  |  | Sub Total | 1623399.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | VENDORS NOTIFIED: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | WATER MAIN PROTECTION, 12" | LF | 245 | 45 | 11025
50 | WATER SERVICE PROTECTION, 2" | LF | 355 | 10 | 3550
51 | WATER MAIN LINE STOP, 4" | EA | 2 | 4250 | 8500
52 | WATER MAIN LINE STOP, 6" | EA | 4 | 4750 | 19000
53 | WATER MAIN LINE STOP, 8" | EA | 5 | 6000 | 30000
54 | WATER MAIN LINE STOP, 12" | EA | 2 | 7500 | 15000
55 | INSERTION VALVE, COMPLETE, 4" | EA | 2 | 5500 | 11000
56 | INSERTION VALVE, COMPLETE, 6" | EA | 4 | 6000 | 24000
57 | INSERTION VALVE, COMPLETE, 8" | EA | 6 | 7000 | 42000
58 | INSERTION VALVE, COMPLETE, 12" | EA | 2 | 12500 | 25000
59 | PARKWAY RESTORATION | LS | 1 | 50000 | 50000
60 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 20000 | 20000
61 | RAILROAD FLAGGING | DAY | 5 | 2500 | 12500
62 | RAILROAD PROTECTIVE LIABILITY INSURANCE (IDOT PAY ITEM Z0048665) | LS | 1 | 2500 | 2500
63 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 150 | 3750
64 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 150 | 3750
65 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 | 750 | 750
66 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 1500 | 1500
67 | TEMPORARY POTABLE WATER BYPASS SYSTEM | LS | 1 | 40000 | 40000
|  |  | 0 | 0 | 0
0 | Additional Construction Costs to comply with Business Enterprise Program (BEP) goals defined by DCEO Opportunity Zone grant Program |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1947224.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | VENDORS NOTIFIED: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1947224.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL | [5 empty] | SECTION | VENDORS NOTIFIED: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | MOBILIZATION | 1 | LS | 31185 |  | 1 |  |  | 31185
2 | CONSTRUCTION LAYOUT STAKES | 1 | LS | 3500 |  | 1 |  |  | 3500
3 | INLET AND PIPE PROTECTION | 53 | EA | 5300 |  | 53 |  |  | 100
4 | CONCRETE TRUCK WASHOUT | 3 | EA | 900 |  | 3 |  |  | 300
5 | PAVEMENT REMOVAL | 4980 | SY | 24900 |  | 4980 |  |  | 5
6 | APPROACH PAVEMENT REMOVAL | 85 | SY | 425 |  | 85 |  |  | 5
7 | SIDEWALK REMOVAL | 7150 | SF | 7150 |  | 7150 |  |  | 1
8 | COMBINATION CURB AND GUTTER REMOVAL | 946 | LF | 3784 |  | 946 |  |  | 4
9 | ROCK EXCAVATION | 50 | CY | 10000 |  | 50 |  |  | 200
10 | INLET TO BE RECONSTRUCTED | 2 | EA | 4000 |  | 2 |  |  | 2000
11 | REMOVE VALVE AND VALVE BOX, COMPLETE | 19 | EA | 7600 |  | 19 |  |  | 400
12 | REMOVE VALVE AND VALVE VAULT, COMPLETE | 5 | EA | 3000 |  | 5 |  |  | 600
13 | REMOVE FIRE HYDRANT, COMPLETE | 5 | EA | 3500 |  | 5 |  |  | 700
14 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M6.18 (MODIFIED) | 610 | LF | 15860 |  | 610 |  |  | 26
15 | PCC SIDEWALK, COMPLETE, 4" | 6300 | SF | 33075 |  | 6300 |  |  | 5.25
16 | DETECTABLE WARNINGS | 80 | SF | 2000 |  | 80 |  |  | 25
17 | BRICK SIDEWALK REMOVAL AND REPLACEMENT, COMPLETE | 100 | SF | 2500 |  | 100 |  |  | 25
18 | PCC PAVEMENT, 6" (JOINTED) | 92 | SY | 6992 |  | 92 |  |  | 76
19 | PCC PAVEMENT, 9.5" (JOINTED) | 151 | SY | 13439 |  | 151 |  |  | 89
20 | PCC APPROACH PAVEMENT, 6" | 53 | SY | 3657 |  | 53 |  |  | 69
21 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | 4980 | SY | 27390 |  | 4980 |  |  | 5.5
22 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | 4980 | SY | 27390 |  | 4980 |  |  | 5.5
23 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N70, 3" | 16 | TON | 2720 |  | 16 |  |  | 170
24 | HOT MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | 260 | TON | 21580 |  | 260 |  |  | 83
Sub Total |  |  |  | 261847 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL | [5 empty] | SECTION | VENDORS NOTIFIED: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | HOT MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | 777 | TON | 56721 |  | 777 |  |  | 73
26 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 8" | 578 | TON | 45662 |  | 578 |  |  | 79
27 | HOT-MIX ASPHALT APPROACH PAVEMENT, 3" | 32 | SY | 1408 |  | 32 |  |  | 44
28 | C-I-P-P WATER MAIN LINING, COMPLETE, 8" | 1047 | LF | 134016 |  | 1047 |  |  | 128
29 | DUCTILE IRON WATER MAIN COMPLETE, 6" | 20 | LF | 3700 |  | 20 |  |  | 185
30 | DUCTILE IRON WATER MAIN COMPLETE, 8" | 4125 | LF | 423678.75 |  | 4125 |  |  | 102.71
31 | DUCTILE IRON WATER MAIN COMPLETE, 12" | 20 | LF | 3600 |  | 20 |  |  | 180
32 | STORM SEWER, WATER MAIN QUALITY, 12" COMPLETE | 51 | LF | 3060 |  | 51 |  |  | 60
33 | STORM SEWER, WATER MAIN QUALITY, 15" COMPLETE | 33 | LF | 3630 |  | 33 |  |  | 110
34 | GATE VALVE AND VALVE BOX, COMPLETE, 4" | 1 | EA | 1400 |  | 1 |  |  | 1400
35 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | 1 | EA | 1500 |  | 1 |  |  | 1500
36 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | 22 | EA | 41800 |  | 22 |  |  | 1900
37 | BUTTERFLY VALVE AND VALVE BOX, COMPLETE, 12" | 1 | EA | 3500 |  | 1 |  |  | 3500
38 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | 6 | EA | 33000 |  | 6 |  |  | 5500
39 | WATER SERVICE (OPEN-CUT), COMPLETE, 1" | 24 | EA | 62400 |  | 24 |  |  | 2600
40 | WATER SERVICE (OPEN-CUT), COMPLETE, 1.5" | 1 | EA | 3400 |  | 1 |  |  | 3400
41 | WATER SERVICE (OPEN-CUT), COMPLETE, 2" | 1 | EA | 3900 |  | 1 |  |  | 3900
42 | 1" WATER SERVICE BORED WITH 2" CASING, COMPLETE, | 690 | LF | 62100 |  | 690 |  |  | 90
43 | RECONNECT 4" WATER SERVICE, COMPLETE | 2 | EA | 3600 |  | 2 |  |  | 1800
44 | RECONNECT 6" WATER SERVICE, COMPLETE | 3 | EA | 5700 |  | 3 |  |  | 1900
45 | CONNECT TO EXISTING 4" WATER MAIN, COMPLETE | 2 | EA | 3600 |  | 2 |  |  | 1800
46 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | 1 | EA | 2000 |  | 1 |  |  | 2000
47 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | 12 | EA | 24000 |  | 12 |  |  | 2000
48 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | 2 | EA | 4000 |  | 2 |  |  | 2000
Sub Total |  |  |  | 1193222.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL | [5 empty] | SECTION | VENDORS NOTIFIED: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | WATER MAIN PROTECTION, 12" | 245 | LF | 7350 |  | 245 |  |  | 30
50 | WATER SERVICE PROTECTION, 2" | 355 | LF | 3550 |  | 355 |  |  | 10
51 | WATER MAIN LINE STOP, 4" | 2 | EA | 5000 |  | 2 |  |  | 2500
52 | WATER MAIN LINE STOP, 6" | 4 | EA | 10400 |  | 4 |  |  | 2600
53 | WATER MAIN LINE STOP, 8" | 5 | EA | 15000 |  | 5 |  |  | 3000
54 | WATER MAIN LINE STOP, 12" | 2 | EA | 15000 |  | 2 |  |  | 7500
55 | INSERTION VALVE, COMPLETE, 4" | 2 | EA | 10000 |  | 2 |  |  | 5000
56 | INSERTION VALVE, COMPLETE, 6" | 4 | EA | 21200 |  | 4 |  |  | 5300
57 | INSERTION VALVE, COMPLETE, 8" | 6 | EA | 34200 |  | 6 |  |  | 5700
58 | INSERTION VALVE, COMPLETE, 12" | 2 | EA | 18600 |  | 2 |  |  | 9300
59 | PARKWAY RESTORATION | 1 | LS | 20000 |  | 1 |  |  | 20000
60 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | 1 | LS | 7500 |  | 1 |  |  | 7500
61 | RAILROAD FLAGGING | 5 | DAY | 3750 |  | 5 |  |  | 750
62 | RAILROAD PROTECTIVE LIABILITY INSURANCE (IDOT PAY ITEM Z0048665) | 1 | LS | 3000 |  | 1 |  |  | 3000
63 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | 25 | CY | 2500 |  | 25 |  |  | 100
64 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | 25 | CY | 2500 |  | 25 |  |  | 100
65 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | 1 | LS | 2500 |  | 1 |  |  | 2500
66 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | 1 | EA | 1250 |  | 1 |  |  | 1250
67 | TEMPORARY POTABLE WATER BYPASS SYSTEM | 1 | LS | 43100 |  | 1 |  |  | 43100
Additional Construction Costs to comply with Business Enterprise Program (BEP) goals defined by DCEO Opportunity Zone grant Program
Total |  |  |  | 1419622.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL | [5 empty] | SECTION | VENDORS NOTIFIED: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 1419622.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | VENDORS NOTIFIED: 89
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Northern Illinois Service
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.