## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 60650
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | Erosion Control Barrier | LF | 1250 | 4 | 5000
2 | Erosion Control Blanket | SY | 10900 | 1.5 | 16350
3 | Earth Excavation | CY | 4100 | 8 | 32800
4 | Construction Entrance | LS | 1 | 1500 | 1500
5 | Seeding and Restoration | LS | 1 | 5000 | 5000
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Dale's Plumbing |  | N-TRAK Group |  | Northern Illinois Service
City of Rockford | [5 empty] | Pecatonica, IL |  | Loves Park, IL |  | Rockford, IL
Auburn Street CCDD Site - Closure 2021
Bid No.: 721-PW-053
Vendors Notified: 89
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Erosion Control Barrier | LF | 1250 | 4 | 5000 | 2.5 | 3125 | 2.5 | 3125 | 2.5 | 3125 |  | 0 |  | 0 |  | 0
2 | Erosion Control Blanket | SY | 10900 | 1.5 | 16350 | 1.2 | 13080 | 1.5 | 16350 | 2.5 | 27250 |  | 0 |  | 0 |  | 0
3 | Earth Excavation | CY | 4100 | 8 | 32800 | 8.91 | 36531 | 9.5 | 38950 | 23.98 | 98318 |  | 0 |  | 0 |  | 0
4 | Construction Entrance | LS | 1 | 1500 | 1500 | 655 | 655 | 3000 | 3000 | 100 | 100 |  | 0 |  | 0 |  | 0
5 | Seeding and Restoration | LS | 1 | 5000 | 5000 | 3500 | 3500 | 5000 | 5000 | 2800 | 2800 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Total |  | As read | 60650 |  | 56891 |  | 66425 |  | 131593
| Award to Dale's Plumbing | Bid |  | As corrected | 60650 |  | 56891 |  | 66425 |  | 131593
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read
| Award to Dale's Plumbing | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read
| Award to Dale's Plumbing | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to Dale's Plumbing | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Auburn Street CCDD Site - Closure 2021
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Erosion Control Barrier | LF | 1250 |  | 0
2 | Erosion Control Blanket | SY | 10900 |  | 0
3 | Earth Excavation | CY | 4100 |  | 0
4 | Construction Entrance | LS | 1 |  | 0
5 | Seeding and Restoration | LS | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 1 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Auburn Street CCDD Site - Closure 2021
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Erosion Control Barrier | LF | 1250 | 4 | 5000
2 | Erosion Control Blanket | SY | 10900 | 1.5 | 16350
3 | Earth Excavation | CY | 4100 | 8 | 32800
4 | Construction Entrance | LS | 1 | 1500 | 1500
5 | Seeding and Restoration | LS | 1 | 5000 | 5000
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 60650
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Auburn Street CCDD Site - Closure 2021
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 60650
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Auburn Street CCDD Site - Closure 2021
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 60650
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Auburn Street CCDD Site - Closure 2021
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 60650
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Dale's Plumbing | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Pecatonica, IL | [5 empty] | SECTION | Auburn Street CCDD Site - Closure 2021
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Erosion Control Barrier | 1250 | LF | 3125 |  | 1250 |  |  | 2.5
2 | Erosion Control Blanket | 10900 | SY | 13080 |  | 10900 |  |  | 1.2
3 | Earth Excavation | 4100 | CY | 36531 |  | 4100 |  |  | 8.91
4 | Construction Entrance | 1 | LS | 655 |  | 1 |  |  | 655
5 | Seeding and Restoration | 1 | LS | 3500 |  | 1 |  |  | 3500
Total |  |  |  | 56891 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Dale's Plumbing | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Pecatonica, IL | [5 empty] | SECTION | Auburn Street CCDD Site - Closure 2021
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 56891 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Dale's Plumbing | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Pecatonica, IL | [5 empty] | SECTION | Auburn Street CCDD Site - Closure 2021
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 56891 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Dale's Plumbing | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Pecatonica, IL | [5 empty] | SECTION | Auburn Street CCDD Site - Closure 2021
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 56891 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Auburn Street CCDD Site - Closure 2021
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Dale's Plumbing
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.