## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 669506
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | INLET AND PIPE PROTECTION | EACH | 12 | 130 | 1560
2 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 1924 | 19 | 36556
3 | AGGREGATE BASE COURSE, TYPE B | TON | 2030 | 21 | 42630
4 | BITUMINOUS MATERIALS (PRIME COAT) | POUND | 12881 | 0.15 | 1932.15
5 | BITUMINOUS MATERIALS (TACK COAT) | POUND | 1319 | 0.15 | 197.85
6 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N90 | TON | 1898 | 70 | 132860
7 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N70 | TON | 659 | 70 | 46130
8 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6 INCH | SQ YD | 152 | 70 | 10640
9 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 8 INCH | SQ YD | 79 | 72 | 5688
10 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 9876 | 6 | 59256
11 | PAVEMENT REMOVAL | SQ YD | 5421 | 18 | 97578
12 | DRIVEWAY PAVEMENT REMOVAL | SQ YD | 119 | 15 | 1785
13 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 2460 | 6 | 14760
14 | SIDEWALK REMOVAL | SQ FT | 2583 | 4 | 10332
15 | WATER VALVES TO BE ADJUSTED | EACH | 5 | 375 | 1875
16 | FIRE HYDRANTS TO BE ADJUSTED | EACH | 2 | 1350 | 2700
17 | MANHOLES TO BE ADJUSTED WITH NEW TYPE 1 FRAME, CLOSED LID | EACH | 11 | 1065 | 11715
18 | INLETS TO BE RECONSTRUCTED | EACH | 1 | 1500 | 1500
19 | CONCRETE GUTTER, TYPE A | FOOT | 6 | 40 | 240
20 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 2549 | 22 | 56078
21 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 60 | 12000
22 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 58 | 11600
23 | SOIL DISPOSAL ANALYSIS | EACH | 1 | 1345 | 1345
24 | MOBILIZATION | L SUM | 1 | 7500 | 7500
25 | SIGN PANEL - TYPE 1 | SQ FT | 15.66 | 50 | 783
26 | METAL POST - TYPE A | FOOT | 39 | 21 | 819
27 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" | FOOT | 400 | 2 | 800
28 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | FOOT | 263 | 3 | 789
29 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" | FOOT | 57 | 12 | 684
30 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 | 6500 | 6500
31 | REMOVE AND RELOCATE SIGN PANEL AND POLE ASSEMBLY | EACH | 7 | 245 | 1715
32 | INLETS TO BE ADJUSTED WITH NEW FRAME AND GRATE (SPECIAL) | EACH | 10 | 1000 | 10000
33 | SANITARY MANHOLES TO BE ADJUSTED | EACH | 8 | 960 | 7680
34 | VALVE BOX | EACH | 1 | 1200 | 1200
35 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 | 4000 | 4000
36 | SIGN REMOVAL | EACH | 3 | 230 | 690
37 | PARKWAY RESTORATION | L SUM | 1 | 8500 | 8500
38 | CONCRETE TRUCK WASHOUT | L SUM | 1 | 520 | 520
39 | HOT-MIX ASPHALT SURFACE COURSE, SPECIAL | SQ YD | 27 | 33 | 891
40 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT REMOVAL | SQ YD | 234 | 5.5 | 1287
41 | CONSTRUCTION LAYOUT | L SUM | 1 | 5000 | 5000
42 | SUBGRADE UNDERCUTTING | CU YD | 750 | 60 | 45000
43 | ADA CURB RAMP, STD 424001 | EACH | 2 | 640 | 1280
44 | ADA CURB RAMP, STD 424021 | EACH | 2 | 875 | 1750
45 | ADA CURB RAMP, STD 424026 | EACH | 2 | 580 | 1160
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Northern Illinois Service |  | N-TRAK Group |  | Norwest Construction |  | Stenstrom Excavating |  | William Charles |  | Rock Road |  | Landmark Contractors
City of Rockford | [5 empty] | Rockford, IL |  | Loves Park, IL |  | South Beloit, IL |  | Rockford, IL |  | Rockford, IL |  | Janeville,WI |  | Huntley, IL
Bid No.: 221-PW-008
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | INLET AND PIPE PROTECTION | EACH | 12 | 130 | 1560 | 75 | 900 | 75 | 900 | 112.2 | 1346.4 | 80 | 960 | 202.11 | 2425.32 | 110 | 1320 | 101 | 1212
2 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 1924 | 19 | 36556 | 18 | 34632 | 13 | 25012 | 17.3 | 33285.2 | 16 | 30784 | 15.35 | 29533.4 | 17 | 32708 | 17.75 | 34151
3 | AGGREGATE BASE COURSE, TYPE B | TON | 2030 | 21 | 42630 | 18 | 36540 | 15 | 30450 | 19.4 | 39382 | 17.75 | 36032.5 | 18.96 | 38488.8 | 19 | 38570 | 17.75 | 36032.5
4 | BITUMINOUS MATERIALS (PRIME COAT) | POUND | 12881 | 0.15 | 1932.15 | 0.01 | 128.81 | 0.01 | 128.81 | 0.01 | 128.81 | 0.01 | 128.81 | 0.5 | 6440.5 | 0.01 | 128.81 | 0.01 | 128.81
5 | BITUMINOUS MATERIALS (TACK COAT) | POUND | 1319 | 0.15 | 197.85 | 0.57 | 751.83 | 0.01 | 13.19 | 0.01 | 13.19 | 0.6 | 791.4 | 0.5 | 659.5 | 0.57 | 751.83 | 0.57 | 751.83
6 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N90 | TON | 1898 | 70 | 132860 | 59 | 111982 | 68 | 129064 | 64.65 | 122705.7 | 64 | 121472 | 61.6 | 116916.8 | 60 | 113880 | 60 | 113880
7 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N70 | TON | 659 | 70 | 46130 | 64 | 42176 | 70 | 46130 | 71.85 | 47349.15 | 70.8 | 46657.2 | 64.9 | 42769.1 | 65 | 42835 | 65 | 42835
8 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6 INCH | SQ YD | 152 | 70 | 10640 | 45 | 6840 | 55 | 8360 | 53.2 | 8086.4 | 85.75 | 13034 | 71.76 | 10907.52 | 70 | 10640 | 65 | 9880
9 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 8 INCH | SQ YD | 79 | 72 | 5688 | 55 | 4345 | 88 | 6952 | 58.3 | 4605.7 | 102.6 | 8105.4 | 82.44 | 6512.76 | 80.85 | 6387.15 | 75 | 5925
10 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 9876 | 6 | 59256 | 4 | 39504 | 6.6 | 65181.6 | 6 | 59256 | 8 | 79008 | 6.38 | 63008.88 | 6.6 | 65181.6 | 7 | 69132
11 | PAVEMENT REMOVAL | SQ YD | 5421 | 18 | 97578 | 17 | 92157 | 13 | 70473 | 19.55 | 105980.55 | 16.5 | 89446.5 | 12.43 | 67383.03 | 15 | 81315 | 12.2 | 66136.2
12 | DRIVEWAY PAVEMENT REMOVAL | SQ YD | 119 | 15 | 1785 | 10 | 1190 | 5 | 595 | 18.4 | 2189.6 | 15 | 1785 | 12.36 | 1470.84 | 18 | 2142 | 11.1 | 1320.9
13 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 2460 | 6 | 14760 | 2 | 4920 | 2 | 4920 | 4.1 | 10086 | 3.5 | 8610 | 4.02 | 9889.2 | 4 | 9840 | 7 | 17220
14 | SIDEWALK REMOVAL | SQ FT | 2583 | 4 | 10332 | 1 | 2583 | 1 | 2583 | 3.1 | 8007.3 | 1.15 | 2970.45 | 0.77 | 1988.91 | 3 | 7749 | 0.75 | 1937.25
15 | WATER VALVES TO BE ADJUSTED | EACH | 5 | 375 | 1875 | 750 | 3750 | 300 | 1500 | 387.6 | 1938 | 280 | 1400 | 393.47 | 1967.35 | 380 | 1900 | 250 | 1250
16 | FIRE HYDRANTS TO BE ADJUSTED | EACH | 2 | 1350 | 2700 | 1750 | 3500 | 1300 | 2600 | 1530 | 3060 | 1400 | 2800 | 2135.3 | 4270.6 | 1500 | 3000 | 2455 | 4910
17 | MANHOLES TO BE ADJUSTED WITH NEW TYPE 1 FRAME, CLOSED LID | EACH | 11 | 1065 | 11715 | 1550 | 17050 | 900 | 9900 | 1224 | 13464 | 835 | 9185 | 1219.71 | 13416.81 | 1200 | 13200 | 650 | 7150
18 | INLETS TO BE RECONSTRUCTED | EACH | 1 | 1500 | 1500 | 1875 | 1875 | 1100 | 1100 | 1428 | 1428 | 3200 | 3200 | 1957.17 | 1957.17 | 1400 | 1400 | 1212 | 1212
19 | CONCRETE GUTTER, TYPE A | FOOT | 6 | 40 | 240 | 40 | 240 | 180 | 1080 | 75.3 | 451.8 | 58.5 | 351 | 42.74 | 256.44 | 34 | 204 | 30 | 180
20 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 2549 | 22 | 56078 | 16 | 40784 | 21 | 53529 | 33.4 | 85136.6 | 19.25 | 49068.25 | 21.62 | 55109.38 | 23.3 | 59391.7 | 22 | 56078
21 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 60 | 12000 | 0.01 | 2 | 0.01 | 2 | 1 | 200 | 1 | 200 | 24.75 | 4950 | 80 | 16000 | 65.8 | 13160
22 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 58 | 11600 | 0.01 | 2 | 0.01 | 2 | 1 | 200 | 1 | 200 | 26.56 | 5312 | 80 | 16000 | 55 | 11000
23 | SOIL DISPOSAL ANALYSIS | EACH | 1 | 1345 | 1345 | 750 | 750 | 1100 | 1100 | 7734 | 7734 | 1160 | 1160 | 1100 | 1100 | 1717 | 1717 | 2500 | 2500
24 | MOBILIZATION | L SUM | 1 | 7500 | 7500 | 3000 | 3000 | 5000 | 5000 | 8132 | 8132 | 10400 | 10400 | 33200 | 33200 | 14545.19 | 14545.19 | 21890 | 21890
| Page 1 | Sub |  | As read | 568458 |  | 449602.64 |  | 466575.6 |  | 564166.4 |  | 517749.51 |  | 519934.31 |  | 540806.28 |  | 519872.49
| Award to Northern Illinois Service | Total |  | As corrected | 568458 |  | 449602.64 |  | 466575.6 |  | 564166.4 |  | 517749.51 |  | 519934.31 |  | 540806.28 |  | 519872.49
25 | SIGN PANEL - TYPE 1 | SQ FT | 15.66 | 50 | 783 | 48 | 751.68 | 48 | 751.68 | 49 | 767.34 | 50.5 | 790.83 | 48.51 | 759.6666 | 48 | 751.68 | 17.5 | 274.05
26 | METAL POST - TYPE A | FOOT | 39 | 21 | 819 | 30 | 1170 | 30 | 1170 | 30.6 | 1193.4 | 31.6 | 1232.4 | 30.32 | 1182.48 | 30 | 1170 | 10 | 390
27 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" | FOOT | 400 | 2 | 800 | 2.5 | 1000 | 2.5 | 1000 | 2.6 | 1040 | 2.65 | 1060 | 2.53 | 1012 | 2.5 | 1000 | 5 | 2000
28 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | FOOT | 263 | 3 | 789 | 3.75 | 986.25 | 3.75 | 986.25 | 3.8 | 999.4 | 3.95 | 1038.85 | 3.79 | 996.77 | 3.75 | 986.25 | 8 | 2104
29 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" | FOOT | 57 | 12 | 684 | 15 | 855 | 15 | 855 | 15.3 | 872.1 | 15.8 | 900.6 | 15.16 | 864.12 | 15 | 855 | 32 | 1824
30 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 | 6500 | 6500 | 0.01 | 0.01 | 1 | 1 | 1836 | 1836 | 2750 | 2750 | 0.01 | 0.01 | 1818 | 1818 | 3000 | 3000
31 | REMOVE AND RELOCATE SIGN PANEL AND POLE ASSEMBLY | EACH | 7 | 245 | 1715 | 220 | 1540 | 220 | 1540 | 224 | 1568 | 235 | 1645 | 222.32 | 1556.24 | 220 | 1540 | 150 | 1050
32 | INLETS TO BE ADJUSTED WITH NEW FRAME AND GRATE (SPECIAL) | EACH | 10 | 1000 | 10000 | 1500 | 15000 | 1150 | 11500 | 1275 | 12750 | 1000 | 10000 | 1122.34 | 11223.4 | 1250 | 12500 | 650 | 6500
33 | SANITARY MANHOLES TO BE ADJUSTED | EACH | 8 | 960 | 7680 | 825 | 6600 | 850 | 6800 | 918 | 7344 | 870 | 6960 | 1209.26 | 9674.08 | 900 | 7200 | 960 | 7680
34 | VALVE BOX | EACH | 1 | 1200 | 1200 | 750 | 750 | 1200 | 1200 | 1530 | 1530 | 1015 | 1015 | 1907.56 | 1907.56 | 1500 | 1500 | 1000 | 1000
35 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 | 4000 | 4000 | 3500 | 3500 | 5000 | 5000 | 2550 | 2550 | 3700 | 3700 | 3536.91 | 3536.91 | 3500 | 3500 | 7000 | 7000
36 | SIGN REMOVAL | EACH | 3 | 230 | 690 | 50 | 150 | 150 | 450 | 153 | 459 | 160 | 480 | 113.1 | 339.3 | 150 | 450 | 50 | 150
37 | PARKWAY RESTORATION | L SUM | 1 | 8500 | 8500 | 15000 | 15000 | 9000 | 9000 | 17950 | 17950 | 14100.81 | 14100.81 | 17500 | 17500 | 13400 | 13400 | 13400 | 13400
38 | CONCRETE TRUCK WASHOUT | L SUM | 1 | 520 | 520 | 400 | 400 | 300 | 300 | 247.5 | 247.5 | 805 | 805 | 427.44 | 427.44 | 1000 | 1000 | 1000 | 1000
39 | HOT-MIX ASPHALT SURFACE COURSE, SPECIAL | SQ YD | 27 | 33 | 891 | 28 | 756 | 57 | 1539 | 45 | 1215 | 29.5 | 796.5 | 115 | 3105 | 28 | 756 | 28 | 756
40 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT REMOVAL | SQ YD | 234 | 5.5 | 1287 | 0.5 | 117 | 5 | 1170 | 12 | 2808 | 5 | 1170 | 5.24 | 1226.16 | 9 | 2106 | 11 | 2574
41 | CONSTRUCTION LAYOUT | L SUM | 1 | 5000 | 5000 | 2500 | 2500 | 4400 | 4400 | 3570 | 3570 | 3665 | 3665 | 2526.36 | 2526.36 | 3480 | 3480 | 4500 | 4500
42 | SUBGRADE UNDERCUTTING | CU YD | 750 | 60 | 45000 | 45 | 33750 | 37 | 27750 | 40.8 | 30600 | 43.95 | 32962.5 | 25 | 18750 | 40 | 30000 | 69.6 | 52200
43 | ADA CURB RAMP, STD 424001 | EACH | 2 | 640 | 1280 | 375 | 750 | 500 | 1000 | 2062.5 | 4125 | 1650 | 3300 | 400.72 | 801.44 | 1100 | 2200 | 1100 | 2200
44 | ADA CURB RAMP, STD 424021 | EACH | 2 | 875 | 1750 | 475.25 | 950.5 | 500 | 1000 | 2062.5 | 4125 | 1650 | 3300 | 507.85 | 1015.7 | 1100 | 2200 | 1100 | 2200
45 | ADA CURB RAMP, STD 424026 | EACH | 2 | 580 | 1160 | 375 | 750 | 500 | 1000 | 2062.5 | 4125 | 1650 | 3300 | 400.72 | 801.44 | 1100 | 2200 | 1100 | 2200
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 669506 |  | 536879.08 |  | 544988.53 |  | 665843.94 |  | 612722 |  | 599140.3866 |  | 631419.21 |  | 632686.54
| Award to Northern Illinois Service | Bid |  | As corrected | 669506 |  | 536879.08 |  | 544988.53 |  | 665843.94 |  | 612722 |  | 599140.3866 |  | 631419.21 |  | 633874.54
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read
| Award to Northern Illinois Service | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to Northern Illinois Service | Bid |  | As corrected
1331685.08

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
0
Item No. | Items | Units | Quantity | Unit Price | Total
1 | INLET AND PIPE PROTECTION | EACH | 12 |  | 0
2 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 1924 |  | 0
3 | AGGREGATE BASE COURSE, TYPE B | TON | 2030 |  | 0
4 | BITUMINOUS MATERIALS (PRIME COAT) | POUND | 12881 |  | 0
5 | BITUMINOUS MATERIALS (TACK COAT) | POUND | 1319 |  | 0
6 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N90 | TON | 1898 |  | 0
7 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N70 | TON | 659 |  | 0
8 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6 INCH | SQ YD | 152 |  | 0
9 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 8 INCH | SQ YD | 79 |  | 0
10 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 9876 |  | 0
11 | PAVEMENT REMOVAL | SQ YD | 5421 |  | 0
12 | DRIVEWAY PAVEMENT REMOVAL | SQ YD | 119 |  | 0
13 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 2460 |  | 0
14 | SIDEWALK REMOVAL | SQ FT | 2583 |  | 0
15 | WATER VALVES TO BE ADJUSTED | EACH | 5 |  | 0
16 | FIRE HYDRANTS TO BE ADJUSTED | EACH | 2 |  | 0
17 | MANHOLES TO BE ADJUSTED WITH NEW TYPE 1 FRAME, CLOSED LID | EACH | 11 |  | 0
18 | INLETS TO BE RECONSTRUCTED | EACH | 1 |  | 0
19 | CONCRETE GUTTER, TYPE A | FOOT | 6 |  | 0
20 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 2549 |  | 0
21 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 |  | 0
22 | SPECIAL WASTE DISPOSAL | CU YD | 200 |  | 0
23 | SOIL DISPOSAL ANALYSIS | EACH | 1 |  | 0
24 | MOBILIZATION | L SUM | 1 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | SIGN PANEL - TYPE 1 | SQ FT | 15.66 |  | 0
26 | METAL POST - TYPE A | FOOT | 39 |  | 0
27 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" | FOOT | 400 |  | 0
28 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | FOOT | 263 |  | 0
29 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" | FOOT | 57 |  | 0
30 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 |  | 0
31 | REMOVE AND RELOCATE SIGN PANEL AND POLE ASSEMBLY | EACH | 7 |  | 0
32 | INLETS TO BE ADJUSTED WITH NEW FRAME AND GRATE (SPECIAL) | EACH | 10 |  | 0
33 | SANITARY MANHOLES TO BE ADJUSTED | EACH | 8 |  | 0
34 | VALVE BOX | EACH | 1 |  | 0
35 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 |  | 0
36 | SIGN REMOVAL | EACH | 3 |  | 0
37 | PARKWAY RESTORATION | L SUM | 1 |  | 0
38 | CONCRETE TRUCK WASHOUT | L SUM | 1 |  | 0
39 | HOT-MIX ASPHALT SURFACE COURSE, SPECIAL | SQ YD | 27 |  | 0
40 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT REMOVAL | SQ YD | 234 |  | 0
41 | CONSTRUCTION LAYOUT | L SUM | 1 |  | 0
42 | SUBGRADE UNDERCUTTING | CU YD | 750 |  | 0
43 | ADA CURB RAMP, STD 424001 | EACH | 2 |  | 0
44 | ADA CURB RAMP, STD 424021 | EACH | 2 |  | 0
45 | ADA CURB RAMP, STD 424026 | EACH | 2 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | INLET AND PIPE PROTECTION | EACH | 12 | 130 | 1560
2 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 1924 | 19 | 36556
3 | AGGREGATE BASE COURSE, TYPE B | TON | 2030 | 21 | 42630
4 | BITUMINOUS MATERIALS (PRIME COAT) | POUND | 12881 | 0.15 | 1932.15
5 | BITUMINOUS MATERIALS (TACK COAT) | POUND | 1319 | 0.15 | 197.85
6 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N90 | TON | 1898 | 70 | 132860
7 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N70 | TON | 659 | 70 | 46130
8 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6 INCH | SQ YD | 152 | 70 | 10640
9 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 8 INCH | SQ YD | 79 | 72 | 5688
10 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 9876 | 6 | 59256
11 | PAVEMENT REMOVAL | SQ YD | 5421 | 18 | 97578
12 | DRIVEWAY PAVEMENT REMOVAL | SQ YD | 119 | 15 | 1785
13 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 2460 | 6 | 14760
14 | SIDEWALK REMOVAL | SQ FT | 2583 | 4 | 10332
15 | WATER VALVES TO BE ADJUSTED | EACH | 5 | 375 | 1875
16 | FIRE HYDRANTS TO BE ADJUSTED | EACH | 2 | 1350 | 2700
17 | MANHOLES TO BE ADJUSTED WITH NEW TYPE 1 FRAME, CLOSED LID | EACH | 11 | 1065 | 11715
18 | INLETS TO BE RECONSTRUCTED | EACH | 1 | 1500 | 1500
19 | CONCRETE GUTTER, TYPE A | FOOT | 6 | 40 | 240
20 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 2549 | 22 | 56078
21 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 60 | 12000
22 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 58 | 11600
23 | SOIL DISPOSAL ANALYSIS | EACH | 1 | 1345 | 1345
24 | MOBILIZATION | L SUM | 1 | 7500 | 7500
|  |  |  | Sub Total | 568458
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | SIGN PANEL - TYPE 1 | SQ FT | 15.66 | 50 | 783
26 | METAL POST - TYPE A | FOOT | 39 | 21 | 819
27 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" | FOOT | 400 | 2 | 800
28 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | FOOT | 263 | 3 | 789
29 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" | FOOT | 57 | 12 | 684
30 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 | 6500 | 6500
31 | REMOVE AND RELOCATE SIGN PANEL AND POLE ASSEMBLY | EACH | 7 | 245 | 1715
32 | INLETS TO BE ADJUSTED WITH NEW FRAME AND GRATE (SPECIAL) | EACH | 10 | 1000 | 10000
33 | SANITARY MANHOLES TO BE ADJUSTED | EACH | 8 | 960 | 7680
34 | VALVE BOX | EACH | 1 | 1200 | 1200
35 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 | 4000 | 4000
36 | SIGN REMOVAL | EACH | 3 | 230 | 690
37 | PARKWAY RESTORATION | L SUM | 1 | 8500 | 8500
38 | CONCRETE TRUCK WASHOUT | L SUM | 1 | 520 | 520
39 | HOT-MIX ASPHALT SURFACE COURSE, SPECIAL | SQ YD | 27 | 33 | 891
40 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT REMOVAL | SQ YD | 234 | 5.5 | 1287
41 | CONSTRUCTION LAYOUT | L SUM | 1 | 5000 | 5000
42 | SUBGRADE UNDERCUTTING | CU YD | 750 | 60 | 45000
43 | ADA CURB RAMP, STD 424001 | EACH | 2 | 640 | 1280
44 | ADA CURB RAMP, STD 424021 | EACH | 2 | 875 | 1750
45 | ADA CURB RAMP, STD 424026 | EACH | 2 | 580 | 1160
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 669506
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 669506
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 669506
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | INLET AND PIPE PROTECTION | 12 | EACH | 900 |  | 12 |  |  | 75
2 | SUBBASE GRANULAR MATERIAL, TYPE B | 1924 | TON | 34632 |  | 1924 |  |  | 18
3 | AGGREGATE BASE COURSE, TYPE B | 2030 | TON | 36540 |  | 2030 |  |  | 18
4 | BITUMINOUS MATERIALS (PRIME COAT) | 12881 | POUND | 128.81 |  | 12881 |  |  | 0.01
5 | BITUMINOUS MATERIALS (TACK COAT) | 1319 | POUND | 751.83 |  | 1319 |  |  | 0.57
6 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N90 | 1898 | TON | 111982 |  | 1898 |  |  | 59
7 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N70 | 659 | TON | 42176 |  | 659 |  |  | 64
8 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6 INCH | 152 | SQ YD | 6840 |  | 152 |  |  | 45
9 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 8 INCH | 79 | SQ YD | 4345 |  | 79 |  |  | 55
10 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | 9876 | SQ FT | 39504 |  | 9876 |  |  | 4
11 | PAVEMENT REMOVAL | 5421 | SQ YD | 92157 |  | 5421 |  |  | 17
12 | DRIVEWAY PAVEMENT REMOVAL | 119 | SQ YD | 1190 |  | 119 |  |  | 10
13 | COMBINATION CURB AND GUTTER REMOVAL | 2460 | FOOT | 4920 |  | 2460 |  |  | 2
14 | SIDEWALK REMOVAL | 2583 | SQ FT | 2583 |  | 2583 |  |  | 1
15 | WATER VALVES TO BE ADJUSTED | 5 | EACH | 3750 |  | 5 |  |  | 750
16 | FIRE HYDRANTS TO BE ADJUSTED | 2 | EACH | 3500 |  | 2 |  |  | 1750
17 | MANHOLES TO BE ADJUSTED WITH NEW TYPE 1 FRAME, CLOSED LID | 11 | EACH | 17050 |  | 11 |  |  | 1550
18 | INLETS TO BE RECONSTRUCTED | 1 | EACH | 1875 |  | 1 |  |  | 1875
19 | CONCRETE GUTTER, TYPE A | 6 | FOOT | 240 |  | 6 |  |  | 40
20 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | 2549 | FOOT | 40784 |  | 2549 |  |  | 16
21 | NON-SPECIAL WASTE DISPOSAL | 200 | CU YD | 2 |  | 200 |  |  | 0.01
22 | SPECIAL WASTE DISPOSAL | 200 | CU YD | 2 |  | 200 |  |  | 0.01
23 | SOIL DISPOSAL ANALYSIS | 1 | EACH | 750 |  | 1 |  |  | 750
24 | MOBILIZATION | 1 | L SUM | 3000 |  | 1 |  |  | 3000
Sub Total |  |  |  | 449602.64 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | SIGN PANEL - TYPE 1 | 15.66 | SQ FT | 751.68 |  | 15.66 |  |  | 48
26 | METAL POST - TYPE A | 39 | FOOT | 1170 |  | 39 |  |  | 30
27 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" | 400 | FOOT | 1000 |  | 400 |  |  | 2.5
28 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | 263 | FOOT | 986.25 |  | 263 |  |  | 3.75
29 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" | 57 | FOOT | 855 |  | 57 |  |  | 15
30 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | 1 | L SUM | 0.01 |  | 1 |  |  | 0.01
31 | REMOVE AND RELOCATE SIGN PANEL AND POLE ASSEMBLY | 7 | EACH | 1540 |  | 7 |  |  | 220
32 | INLETS TO BE ADJUSTED WITH NEW FRAME AND GRATE (SPECIAL) | 10 | EACH | 15000 |  | 10 |  |  | 1500
33 | SANITARY MANHOLES TO BE ADJUSTED | 8 | EACH | 6600 |  | 8 |  |  | 825
34 | VALVE BOX | 1 | EACH | 750 |  | 1 |  |  | 750
35 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | 1 | L SUM | 3500 |  | 1 |  |  | 3500
36 | SIGN REMOVAL | 3 | EACH | 150 |  | 3 |  |  | 50
37 | PARKWAY RESTORATION | 1 | L SUM | 15000 |  | 1 |  |  | 15000
38 | CONCRETE TRUCK WASHOUT | 1 | L SUM | 400 |  | 1 |  |  | 400
39 | HOT-MIX ASPHALT SURFACE COURSE, SPECIAL | 27 | SQ YD | 756 |  | 27 |  |  | 28
40 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT REMOVAL | 234 | SQ YD | 117 |  | 234 |  |  | 0.5
41 | CONSTRUCTION LAYOUT | 1 | L SUM | 2500 |  | 1 |  |  | 2500
42 | SUBGRADE UNDERCUTTING | 750 | CU YD | 33750 |  | 750 |  |  | 45
43 | ADA CURB RAMP, STD 424001 | 2 | EACH | 750 |  | 2 |  |  | 375
44 | ADA CURB RAMP, STD 424021 | 2 | EACH | 950.5 |  | 2 |  |  | 475.25
45 | ADA CURB RAMP, STD 424026 | 2 | EACH | 750 |  | 2 |  |  | 375
Total |  |  |  | 536879.08 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 536879.08 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 536879.08 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | 0
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Northern Illinois Service
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.