## Item List
| City -Wide Street Repairs Group No. 1 - 2021 (Residential) | [70 empty] | 2482416
Summary Of Quantities |  |  | 1st Ward - 94003001 |  |  |  |  | 1st Ward - 94003001 |  |  |  | 2nd Ward | 2nd Ward - 94003002 |  |  |  | 3rd Ward | 3rd Ward - 94003003 |  |  |  | 3rd Ward - 94003003 |  | 4th Ward - 94003004 |  |  | 4th Ward - 94003004 |  |  |  |  | 4th Ward | 8th Ward - 94003008 |  |  |  | 8th Ward - 94003008 |  |  | 9th Ward - 94003009 |  | 9th Ward | 11th Ward - 94003011 |  |  | 12th Ward | 12th Ward - 94003012 |  |  |  |  | 12th Ward - 94003012 |  |  |  |  | 12th Ward | 14th Ward - 94003014 |  |  |  | 14th Ward - 94003014 |  |  |  |  | 14th Ward - 94003014
No. | Item | Units | 7500/7600 Blairmore Drive | 1400/1500 Bonnybridge Lane | 7200 Centinnial Trail | 1500 Livingston Drive | 1800/2400 Reid Farm Road | 7500/7600 Royal Troon Drive | 1200 Sunflower Drive | 1200 Woodcreek Bend | 1400 Woodcreek Bend | 1900/2100 12th Avenue | 1000 15th Avenue | 0100/0200 North Highland Avenue | Mayfair Place Patching | 0300 South Prospect Street | 3500 Brendenwood Road Patching | 2600/2700 Burrmont Road | Church Street Patching | 2000/2100 El Rancho Lane | 1200/1300 Grenham Place | 0900/1100 Scottswood Road | 3400/3600 Westminster Drive | 5000 Crofton Drive | 1500 Farmington Close | 4700 Innsbruck Drive | 4700 Landau Place | 3600 Laura Lane | 5600 Northcliffe Lane | 6200 Palo Verde Drive | 3300 Plaza Court | 3200/3300 Windsong Court | 2000/2100 23rd Street Patching | 2200/2400 26th Street | 1500 East Gate Parkway Patching | 1700 East Gate Parkway Patching | 2800/2900 Greendale Drive | 2100 Idaho Parkway Patching | 2700/3000 Norway Pine Road Patching | 2500/2900 Cameron Avenue | 3200/3300 Idlewood Terrace | 1500/1700 Quincy Street | 2100/2200 7th Street | 1000 9th Avenue | 1300/1500 18th Avenue | 5000/5300 Browns Beach Patching | 2200 Cerro Vista Court | 2300/2500 Cerro Vista Drive | 2200/2300 Clinton Place | 2500 Harlem Boulevard | 2400 Harris Road | 3100/3200 Landstrom Road | 3000 North Church Street | 3300 North View Road | 2500 West Chickadee Trail | 2400 Westbrook Drive | 2200 Willow Lane | 4500 Apple Orchard Lane | 5100 Carol Court | 1100 Geneva Avenue | 5400/5500 Midvale Drive | 0600 Phelps Avenue | 1400 Phelps Avenue Patching | 1100 Post Drive | 1300 Post Drive | 4400 Samuelson Road | 3000 Stowmarket Avenue | 5600 Woodbine Drive | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. | [37 empty] | 30 | [12 empty] | 10 | [15 empty] | 100 | 140 | 25 | 3500
2 | Parkway Restoration | Lsum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0.15 | 0.07 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0.04 | 0.02 | 0 | 0.02 | 0 | 0.01 | 0.03 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0.03 | 0 | 0 | 0.11 | 0 | 0 | 0.12 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0 | 0 | 0 | 0 | 0.07 | 0.01 | 0 | 0.04 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0.01 |  | 1 | 50000 | 50000
3 | Inlet and Pipe Protection | Each | 3 | 3 | 3 | 3 | 16 | 4 |  | 3 | 2 | 6 | 4 | 2 |  |  |  | 2 |  |  | 3 | 6 |  | 3 |  |  | 6 | 1 |  |  |  | 1 |  |  |  |  | 5 |  | 4 | 8 | 5 | 10 |  | 2 |  |  | 2 |  | 2 |  |  |  | 4 |  |  |  |  | 4 | 3 |  | 4 | 1 | [5 empty] | 2 |  | 127 | 60 | 7620
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | [66 empty] | 50 | 50 | 25 | 1250
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | [66 empty] | 50 | 50 | 25 | 1250
6 | Aggregate Base Repair, 10" | S.Y. | 20 | 20 | 17 | 26 | 103 | 19 | 17 | 17 | 12 | 33 | 10 | 23 | 6 | 13 | 7 | 15 | 4 | 37 | 18 | 34 | 27 | 14 | 15 | 17 | 29 | 26 | 13 | 21 | 10 | 43 | 20 | 53 | 8 | 9 | 32 | 7 | 17 | 55 | 29 | 21 | 47 | 12 | 58 | 26 | 11 | 31 | 23 | 12 | 18 | 13 | 20 | 14 | 17 | 12 | 7 | 22 | 5 | 16 | 25 | 14 | 3 | 13 | 19 | 25 | 12 | 4 |  | 1396 | 20 | 27920
7 | Bituminous Materials (Prime Coat) | Gal | 205 | 205 | 175 | 265 | 1030 | 195 | 175 | 175 | 120 | 330 | 105 | 230 | 60 | 130 | 70 | 155 | 45 | 370 | 180 | 345 | 275 | 145 | 150 | 175 | 290 | 265 | 130 | 210 | 105 | 435 | 200 | 530 | 80 | 90 | 325 | 70 | 175 | 552 | 290 | 215 | 470 | 125 | 585 | 260 | 115 | 310 | 235 | 120 | 185 | 135 | 205 | 140 | 170 | 125 | 75 | 220 | 50 | 165 | 250 | 145 | 30 | 130 | 190 | 250 | 120 | 40 |  | 14117 | 3 | 42351
8 | Aggregate (Prime Coat) | Tons | 10 | 10 | 9 | 13 | 52 | 10 | 8 | 8 | 6 | 17 | 5 | 12 | 3 | 7 | 4 | 8 | 2 | 19 | 9 | 17 | 14 | 7 | 8 | 9 | 15 | 13 | 7 | 11 | 5 | 22 | 10 | 27 | 4 | 5 | 16 | 4 | 8 | 28 | 15 | 11 | 24 | 6 | 29 | 13 | 6 | 16 | 12 | 6 | 9 | 7 | 10 | 7 | 9 | 7 | 4 | 11 | 3 | 8 | 13 | 7 | 2 | 7 | 10 | 13 | 6 | 2 |  | 715 | 10 | 7150
9 | Polymerized Leveling Binder, IL-4.75, N50, 0.5" | Tons | [10 empty] | 50 | [56 empty] | 50 | 80 | 4000
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | [66 empty] | 100 | 100 | 65 | 6500
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | [40 empty] | 375 |  | 450 | [23 empty] | 500 | 1325 | 65 | 86125
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | [10 empty] | 100 | [56 empty] | 100 | 60 | 6000
13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 250 | 250 | 225 | 325 | 1200 | 250 | 225 | 225 | 150 | 400 |  | 275 | 75 | 150 | 100 | 200 | 75 | 450 | 225 | 425 | 325 | 175 | 175 | 225 | 350 | 325 | 150 | 250 | 125 | 525 | 250 | 625 | 100 | 125 | 400 | 100 | 225 | 650 | 350 | 250 |  | 150 |  | 325 | 150 | 375 | 275 | 150 | 225 | 175 | 250 | 175 | 200 | 150 | 100 | 275 | 75 | 200 | 300 | 175 | 50 | 150 | 225 | 300 | 150 | 50 | 500 | 16325 | 60 | 979500
14 | Hot-Mix Asphalt, Hand Method | Tons | [21 empty] | 20 |  |  | 20 | [30 empty] | 10 | [10 empty] | 10 | 60 | 300 | 18000
15 | P.C.C. Approach Pavement, 6" | S.Y. | [9 empty] | 14 | [5 empty] | 7 |  |  | 13 | 99 |  |  |  |  | 24 | [9 empty] | 78 |  |  |  | 153 | [16 empty] | 55 |  |  | 89 | [8 empty] | 532 | 60 | 31920
16 | P.C.C. Approach Pavement, 8" | S.Y. | [55 empty] | 26 | [10 empty] | 50 | 76 | 75 | 5700
17 | P.C.C. Sidewalk, 4" | S.F. | [7 empty] | 325 |  | 5475 | 1975 |  |  |  |  | 300 |  |  | 1100 | 900 |  |  |  | 350 |  | 350 |  |  |  | 200 |  | 1350 |  |  | 3175 |  |  | 4400 | 2650 | 2375 | [10 empty] | 1425 |  |  |  |  | 2425 | 250 |  | 1375 | 500 | [5 empty] | 300 | 1000 | 32200 | 6 | 193200
18 | Detectable Warnings, ADA Ramps | S.F. | [7 empty] | 20 |  | 80 | 40 | [7 empty] | 80 |  |  |  |  | 20 |  | 20 |  |  |  | 20 |  | 100 |  |  | 40 |  |  | 40 | 40 | [11 empty] | 20 |  |  |  |  | 20 | 20 |  | 10 | 60 | [5 empty] | 20 |  | 650 | 25 | 16250
19 | Combination Curb and Gutter Removal | L.F. | [7 empty] | 20 |  | 135 | 70 |  |  |  |  | 25 |  |  | 125 | 290 |  | 170 |  | 50 | 260 | 25 |  |  |  | 20 |  | 170 |  |  | 475 |  |  | 250 | 405 | 230 | [10 empty] | 60 |  |  |  |  | 275 | 75 |  | 195 | 95 | [5 empty] | 40 | 500 | 3960 | 20 | 79200
20 | Sidewalk Removal | S.F. | [7 empty] | 325 |  | 5475 | 1975 |  |  |  |  | 300 |  |  | 1100 | 900 |  |  |  | 450 |  | 350 |  |  |  | 200 |  | 1350 |  |  | 3375 |  |  | 3200 | 2850 | 2375 | [10 empty] | 1125 |  |  |  |  | 2425 | 350 |  | 1450 | 500 | [5 empty] | 350 | 1000 | 31425 | 2 | 62850
21 | Approach Pavement Removal | S.Y. | [9 empty] | 14 | [5 empty] | 7 |  |  | 13 | 99 |  |  |  |  | 24 | [9 empty] | 78 |  |  |  | 153 | [16 empty] | 81 |  |  | 89 | [7 empty] | 50 | 608 | 40 | 24320
22 | Surface Removal, 1.25" | S.Y. | [40 empty] | 4700 |  | 4800 | [23 empty] | 1000 | 10500 | 2.5 | 26250
23 | Surface Removal, 2" | S.Y. | 2050 | 2050 | 1750 | 2650 | 10300 | 1950 |  | 1750 | 1200 | 3300 |  | 2300 | 600 | 1300 | 700 | 1550 | 450 | 3700 | 1800 | 3450 | 3750 | 1450 | 1500 | 1750 | 2900 | 2650 | 1300 | 2100 | 1050 | 4350 | 2000 | 5300 | 800 | 900 | 3250 | 700 | 1750 | 5525 | 2900 | 2150 |  | 1250 |  | 2600 | 1150 | 3100 | 2750 | 1200 |  |  | 2050 |  | 1700 |  | 750 | 2200 | 500 |  | 2500 | 1450 | 300 |  |  | 2500 | 1200 | 400 | 1000 | 119525 | 3 | 358575
24 | Surface Removal, Butt Joints | S.Y. | [6 empty] | 214 |  |  |  | 135 | [37 empty] | 126 | 108 |  | 131 |  | 82 |  |  |  | 64 |  |  |  | 110 | 175 |  |  |  |  | 1145 | 5 | 5725
25 | Concrete Surface Removal, 1.25" | S.Y. | [42 empty] | 1050 | [24 empty] | 1050 | 4 | 4200
26 | Concrete Surface Removal, 1.5" | S.Y. | [10 empty] | 915 | [56 empty] | 915 | 4 | 3660
27 | Aggregate Shoulder | Tons | [6 empty] | 60 | [41 empty] | 50 | 40 |  | 40 |  | 40 |  |  |  | 60 |  |  |  | 60 | 60 |  |  |  |  | 410 | 35 | 14350
28 | Remove Existing CMP Storm Pipe | L.F. | [6 empty] | 45 | [60 empty] | 45 | 20 | 900
29 | Storm Sewers, PVC, 10" | L.F. | [57 empty] | 150 | [9 empty] | 150 | 75 | 11250
30 | Storm Sewers, RCP, 12" | L.F. | [6 empty] | 45 | [60 empty] | 45 | 100 | 4500
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | [57 empty] | 1 | [9 empty] | 1 | 5000 | 5000
32 | Storm Inlet, Type 700 | Each | [57 empty] | 1 | [9 empty] | 1 | 3000 | 3000
33 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [13 empty] | 4 | [53 empty] | 4 | 300 | 1200
34 | Manholes to be Adjusted | Each | 2 | 2 | 3 | 3 |  | 4 | 2 | 1 |  | 4 | 1 | 4 |  | 1 |  | 1 | 1 | 1 |  | 5 | 2 | 4 | 1 | 2 | 7 | 2 | 2 | 2 | 1 | 4 | 4 | 6 |  |  | 5 | 1 | 2 | 10 | 4 | 4 | 5 | 1 | 5 | 3 | 2 | 6 | 1 | 2 | 1 |  | 1 | 1 |  |  |  | 3 |  | 3 | 2 |  |  | 2 | 3 |  | 1 |  |  | 140 | 550 | 77000
35 | Manholes to be Adjusted with New Frame and Lid | Each | [9 empty] | 2 | 6 | 1 |  |  |  | 1 |  | 9 |  |  |  | 2 |  |  | 1 | [6 empty] | 3 |  |  | 1 |  |  | 2 | 1 |  | 12 |  |  |  | 1 | 3 | 1 | [8 empty] | 2 | [11 empty] | 48 | 800 | 38400
36 | Manholes to be Reconstructed | Each | [66 empty] | 1 | 1 | 1000 | 1000
37 | Manholes to be Reconstructed with New Frame and Lid | Each | [66 empty] | 1 | 1 | 1500 | 1500
38 | Inlets to be Adjusted | Each | 1 | [9 empty] | 1 | 1 |  |  |  | 1 |  |  |  | 5 |  |  |  |  | 1 | 1 | [11 empty] | 1 | 4 | [6 empty] | 1 |  |  |  |  | 3 |  |  |  |  | 2 |  |  | 1 | [8 empty] | 23 | 1000 | 23000
39 | Inlets to be Adjusted with New Frame and Grate | Each | [15 empty] | 2 | [5 empty] | 1 |  |  | 2 | [6 empty] | 4 |  |  | 1 |  |  | 4 | [6 empty] | 2 | 3 | 1 | [8 empty] | 2 | [11 empty] | 22 | 1400 | 30800
40 | Inlets to be Reconstructed | Each | [50 empty] | 1 | [15 empty] | 1 | 2 | 1500 | 3000
41 | Inlets to be Reconstructed with New Frame and Grate | Each | [9 empty] | 4 | 1 | [30 empty] | 2 | [25 empty] | 7 | 1900 | 13300
42 | Inlet Speicals to be Repaired | Each | [31 empty] | 2 |  |  | 2 | [23 empty] | 2 | [8 empty] | 6 | 2200 | 13200
43 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | [7 empty] | 20 |  | 135 | 70 |  |  |  |  | 25 |  |  | 215 | 290 |  | 170 |  | 50 | 260 | 25 |  |  |  | 20 |  | 170 |  |  | 475 |  |  | 250 | 405 | 230 | [10 empty] | 60 |  |  |  |  | 275 | 75 |  | 195 | 95 | [5 empty] | 40 | 500 | 4050 | 30 | 121500
44 | Traffic Control and Protection | Lsum | 0.01 | 0.01 | 0.01 | 0.01 | 0.05 | 0.01 | 0.01 | 0.01 | 0.01 | 0.05 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.02 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.03 | 0.01 | 0.01 | 0.04 | 0.01 | 0.01 | 0.05 | 0.02 | 0.03 | 0.02 | 0.01 | 0.03 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.03 | 0.01 | 0.01 | 0.03 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 1 | 50000 | 50000
45 | Thermoplastic Pavement Markings, 4" | L.F. |  |  |  |  | 383 | [35 empty] | 260 |  | 2200 |  |  |  |  | 600 | [11 empty] | 526 |  |  |  | 1551 |  |  |  | 5520 | 1.5 | 8280
46 | Thermoplastic Pavement Markings, 6" | L.F. |  |  |  |  | 550 | [11 empty] | 33 |  | 120 | [12 empty] | 62 | [28 empty] | 105 | [6 empty] | 870 | 2 | 1740
47 | Thermoplastic Pavement Markings, 12" | L.F. |  |  |  |  | 176 | [58 empty] | 248 |  |  |  | 424 | 4 | 1696
48 | Thermoplastic Pavement Markings, 24" | L.F. |  |  |  |  | 32 | [26 empty] | 14 | [9 empty] | 16 | 18 | [17 empty] | 20 |  |  | 38 |  |  |  | 138 | 6 | 828
49 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. |  |  |  |  | 224 | [55 empty] | 83 | [6 empty] | 307 | 8 | 2456
50 | Detector Loops | L.F. | [66 empty] | 50 | 50 | 30 | 1500
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 25045 | 24045 | 22035 | 31225 | 116392.5 | 24855 | 24615 | 25525 | 13880 | 111430 | 47690 | 29290 | 7130 | 15870 | 8990 | 28115 | 7201 | 48890 | 44360 | 79445 | 33855 | 37015 | 16880 | 27805 | 64010 | 36105 | 15220 | 24060 | 12265 | 53795 | 24800 | 97028 | 9340 | 11200 | 111025 | 9540 | 21535 | 128341 | 102750 | 62425 | 52455 | 18491 | 56313 | 30880 | 18395 | 45410 | 29405 | 15760 | 17935 | 13675 | 45105 | 14375 | 18540 | 11995 | 9155 | 82740 | 13910 | 36715 | 67170 | 28234 | 5564 | 13970 | 19675 | 30926.5 | 14310 | 10540 | 126750 | #VALUE!
|  |  | 1363.8682 | 1358.8122 | 1267.8034 | 1743.0716 | 6237.8959 | 1344.9081 | 1477.6292 | 1399.2605 | 791.2711 | 6527.3545 | 2310.6127 | 1011.2091 | 321.0589 | 917.6722 | 523.3007 | 1300.6677 | 423.4438 | 2921.1302 | 2564.679 | 3122.108 | 1717.7914 | 1689.9831 | 951.8005 | 1753.1837 | 2469.8781 | 2280.2764 | 864.5837 | 2081.8267 | 712.9024 | 2912.2821 | 1456.1411 | 4895.5159 | 514.4526 | 942.9525 | 5899.1409 | 581.4452 | 973.2887 | 6786.4768 | 3325.6138 | 4193.9896 | 2729.0005 | 1035.2253 | 4116.8849 | 1281.7075 | 1060.5055 | 2610.1834 | 1691.2472 | 980.8728 | 1191.9627 | 1288.0275 | 2281.5404 | 953.0645 | 1165.4184 | 901.2401 | 774.8389 | 3948.7714 | 687.6222 | 1947.8415 | 3618.8644 | 1523.1337 | 309.6828 | 850.6796 | 1136.3462 | 1668.495 | 821.6074 | 243.9542 |  | 2482416
|  |  | 26408.8682 | 25403.8122 | 23302.8034 | 32968.0716 | 122630.3959 | 26199.9081 | 26092.6292 | 26924.2605 | 14671.2711 | 117957.3545 | 50000.6127 | 30301.2091 | 7451.0589 | 16787.6722 | 9513.3007 | 29415.6677 | 7624.4438 | 51811.1302 | 46924.679 | 82567.108 | 35572.7914 | 38704.9831 | 17831.8005 | 29558.1837 | 66479.8781 | 38385.2764 | 16084.5837 | 26141.8267 | 12977.9024 | 56707.2821 | 26256.1411 | 101923.5159 | 9854.4526 | 12142.9525 | 116924.1409 | 10121.4452 | 22508.2887 | 135127.4768 | 106075.6138 | 66618.9896 | 55184.0005 | 19526.2253 | 60429.8849 | 32161.7075 | 19455.5055 | 48020.1834 | 31096.2472 | 16740.8728 | 19126.9627 | 14963.0275 | 47386.5404 | 15328.0645 | 19705.4184 | 12896.2401 | 9929.8389 | 86688.7714 | 14597.6222 | 38662.8415 | 70788.8644 | 29757.1337 | 5873.6828 | 14820.6796 | 20811.3462 | 32594.995 | 15131.6074 | 10783.9542 |  | 2483416
|  |  | 26975 | 26875 | 25075 | 34475 | 123375 | 26600 | 29225 | 27675 | 15650 | 129100 | 45700 | 20000 | 6350 | 18150 | 10350 | 25725 | 8375 | 57775 | 50725 | 61750 | 33975 | 33425 | 18825 | 34675 | 48850 | 45100 | 17100 | 41175 | 14100 | 57600 | 28800 | 96825 | 10175 | 18650 | 116675 | 11500 | 19250 | 134225 | 65775 | 82950 | 53975 | 20475 | 81425 | 25350 | 20975 | 51625 | 33450 | 19400 | 23575 | 25475 | 45125 | 18850 | 23050 | 17825 | 15325 | 78100 | 13600 | 38525 | 71575 | 30125 | 6125 | 16825 | 22475 | 33000 | 16250 | 4825 | 0 | 2506900
#REF!
|  |  | 0.01076 | 0.01072 | 0.010002 | 0.013752 | 0.049214 | 0.010611 | 0.011658 | 0.01104 | 0.0062428 | 0.051498 | 0.01823 | 0.007978 | 0.002533 | 0.00724 | 0.0041286 | 0.010262 | 0.0033408 | 0.023046 | 0.020234 | 0.024632 | 0.013553 | 0.013333 | 0.0075093 | 0.013832 | 0.019486 | 0.01799 | 0.0068212 | 0.016425 | 0.0056245 | 0.022977 | 0.011488 | 0.038623 | 0.0040588 | 0.0074395 | 0.046542 | 0.0045873 | 0.0076788 | 0.053542 | 0.026238 | 0.033089 | 0.021531 | 0.0081675 | 0.03248 | 0.010112 | 0.0083669 | 0.020593 | 0.013343 | 0.0077386 | 0.009404 | 0.010162 | 0.018 | 0.0075192 | 0.0091946 | 0.0071104 | 0.0061131 | 0.031154 | 0.005425 | 0.015368 | 0.028551 | 0.012017 | 0.0024433 | 0.0067115 | 0.0089653 | 0.013164 | 0.0064821 | 0.0019247 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | William Charles Construction |  | Curran Contracting |  | Rock Road Companies | [5 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Rockford, IL |  | Crystal Lake, IL |  | Janesville, WI | [5 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 1 - 2021 (Residential) | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond | [5 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 521-PW-030 VENDORS NOTIFIED: 89 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 140 | 25 | 3500 | 30.97 | 4335.8 | 27 | 3780 | 71.71 | 10039.4 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 140 | 25 | 3500 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 140 | 25 | 3500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 50000 | 50000 | 44823.79 | 44823.79 | 50000 | 50000 | 48480 | 48480 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 50000 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 50000 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 127 | 60 | 7620 | 57.76 | 7335.52 | 65 | 8255 | 68.68 | 8722.36 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 127 | 60 | 7620 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 127 | 60 | 7620 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 50 | 25 | 1250 | 23.24 | 1162 | 30 | 1500 | 27.27 | 1363.5 |  | 0 |  | 0 | 4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 50 | 25 | 1250 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 50 | 25 | 1250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 50 | 25 | 1250 | 29.68 | 1484 | 30 | 1500 | 27.27 | 1363.5 |  | 0 |  | 0 | 5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 50 | 25 | 1250 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 50 | 25 | 1250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Aggregate Base Repair, 10" | S.Y. | 1396 | 20 | 27920 | 0.01 | 13.96 | 20 | 27920 | 20.2 | 28199.2 |  | 0 |  | 0 | 6 | Aggregate Base Repair, 10" | S.Y. | 1396 | 20 | 27920 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate Base Repair, 10" | S.Y. | 1396 | 20 | 27920 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Bituminous Materials (Prime Coat) | Gal | 14117 | 3 | 42351 | 1.66 | 23434.22 | 2.8 | 39527.6 | 0.01 | 141.17 |  | 0 |  | 0 | 7 | Bituminous Materials (Prime Coat) | Gal | 14117 | 3 | 42351 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Bituminous Materials (Prime Coat) | Gal | 14117 | 3 | 42351 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Aggregate (Prime Coat) | Tons | 715 | 10 | 7150 | 0.01 | 7.15 | 0.01 | 7.15 | 0.01 | 7.15 |  | 0 |  | 0 | 8 | Aggregate (Prime Coat) | Tons | 715 | 10 | 7150 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Aggregate (Prime Coat) | Tons | 715 | 10 | 7150 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Polymerized Leveling Binder, IL-4.75, N50, 0.5" | Tons | 50 | 80 | 4000 | 104.04 | 5202 | 97.5 | 4875 | 89 | 4450 |  | 0 |  | 0 | 9 | Polymerized Leveling Binder, IL-4.75, N50, 0.5" | Tons | 50 | 80 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Polymerized Leveling Binder, IL-4.75, N50, 0.5" | Tons | 50 | 80 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 100 | 65 | 6500 | 55.66 | 5566 | 64 | 6400 | 65 | 6500 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 100 | 65 | 6500 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 100 | 65 | 6500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | 1325 | 65 | 86125 | 58.34 | 77300.5 | 62.5 | 82812.5 | 63 | 83475 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | 1325 | 65 | 86125 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | 1325 | 65 | 86125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 100 | 60 | 6000 | 63.34 | 6334 | 64 | 6400 | 63 | 6300 |  | 0 |  | 0 | 12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 100 | 60 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 100 | 60 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 16325 | 60 | 979500 | 58.39 | 953216.75 | 63 | 1028475 | 63 | 1028475 |  | 0 |  | 0 | 13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 16325 | 60 | 979500 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 16325 | 60 | 979500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | Hot-Mix Asphalt, Hand Method | Tons | 60 | 300 | 18000 | 158.67 | 9520.2 | 240 | 14400 | 64 | 3840 |  | 0 |  | 0 | 14 | Hot-Mix Asphalt, Hand Method | Tons | 60 | 300 | 18000 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | Hot-Mix Asphalt, Hand Method | Tons | 60 | 300 | 18000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | P.C.C. Approach Pavement, 6" | S.Y. | 532 | 60 | 31920 | 78.81 | 41926.92 | 60 | 31920 | 68.17 | 36266.44 |  | 0 |  | 0 | 15 | P.C.C. Approach Pavement, 6" | S.Y. | 532 | 60 | 31920 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | P.C.C. Approach Pavement, 6" | S.Y. | 532 | 60 | 31920 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | P.C.C. Approach Pavement, 8" | S.Y. | 76 | 75 | 5700 | 80.89 | 6147.64 | 75 | 5700 | 76.25 | 5795 |  | 0 |  | 0 | 16 | P.C.C. Approach Pavement, 8" | S.Y. | 76 | 75 | 5700 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | P.C.C. Approach Pavement, 8" | S.Y. | 76 | 75 | 5700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | P.C.C. Sidewalk, 4" | S.F. | 32200 | 6 | 193200 | 6.24 | 200928 | 5.25 | 169050 | 6.92 | 222824 |  | 0 |  | 0 | 17 | P.C.C. Sidewalk, 4" | S.F. | 32200 | 6 | 193200 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | P.C.C. Sidewalk, 4" | S.F. | 32200 | 6 | 193200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Detectable Warnings, ADA Ramps | S.F. | 650 | 25 | 16250 | 19.19 | 12473.5 | 29 | 18850 | 31.31 | 20351.5 |  | 0 |  | 0 | 18 | Detectable Warnings, ADA Ramps | S.F. | 650 | 25 | 16250 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Detectable Warnings, ADA Ramps | S.F. | 650 | 25 | 16250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Combination Curb and Gutter Removal | L.F. | 3960 | 20 | 79200 | 17.12 | 67795.2 | 12 | 47520 | 16.16 | 63993.6 |  | 0 |  | 0 | 19 | Combination Curb and Gutter Removal | L.F. | 3960 | 20 | 79200 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Combination Curb and Gutter Removal | L.F. | 3960 | 20 | 79200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Sidewalk Removal | S.F. | 31425 | 2 | 62850 | 2.52 | 79191 | 2.25 | 70706.25 | 2.27 | 71334.75 |  | 0 |  | 0 | 20 | Sidewalk Removal | S.F. | 31425 | 2 | 62850 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Sidewalk Removal | S.F. | 31425 | 2 | 62850 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Approach Pavement Removal | S.Y. | 608 | 40 | 24320 | 42.5 | 25840 | 20 | 12160 | 22.22 | 13509.76 |  | 0 |  | 0 | 21 | Approach Pavement Removal | S.Y. | 608 | 40 | 24320 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Approach Pavement Removal | S.Y. | 608 | 40 | 24320 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Surface Removal, 1.25" | S.Y. | 10500 | 2.5 | 26250 | 2.4 | 25200 | 1.6 | 16800 | 2.14 | 22470 |  | 0 |  | 0 | 22 | Surface Removal, 1.25" | S.Y. | 10500 | 2.5 | 26250 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Surface Removal, 1.25" | S.Y. | 10500 | 2.5 | 26250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Surface Removal, 2" | S.Y. | 119525 | 3 | 358575 | 2.35 | 280883.75 | 2.3 | 274907.5 | 2 | 239050 |  | 0 |  | 0 | 23 | Surface Removal, 2" | S.Y. | 119525 | 3 | 358575 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Surface Removal, 2" | S.Y. | 119525 | 3 | 358575 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Surface Removal, Butt Joints | S.Y. | 1145 | 5 | 5725 | 11.33 | 12972.85 | 16 | 18320 | 11.51 | 13178.95 |  | 0 |  | 0 | 24 | Surface Removal, Butt Joints | S.Y. | 1145 | 5 | 5725 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Surface Removal, Butt Joints | S.Y. | 1145 | 5 | 5725 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 2045156 |  | 1893094.75 |  | 1941786 |  | 1940130.28 | [5 empty] | Page 3 | Sub |  | As read | 2045156 | [9 empty] | Page 1 | Sub |  | As read | 2045156
| Award to William Charles Construction | Total |  | As corrected | 2045156 |  | 1893094.75 |  | 1941786 |  | 1940130.28 | [5 empty] | Award to William Charles Construction | Total |  | As corrected | 2045156 | [9 empty] | Award to William Charles Construction | Total |  | As corrected | 2045156
25 | Concrete Surface Removal, 1.25" | S.Y. | 1050 | 4 | 4200 | 5.86 | 6153 | 3 | 3150 | 5.57 | 5848.5 |  | 0 |  | 0 | 25 | Concrete Surface Removal, 1.25" | S.Y. | 1050 | 4 | 4200 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Concrete Surface Removal, 1.25" | S.Y. | 1050 | 4 | 4200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Concrete Surface Removal, 1.5" | S.Y. | 915 | 4 | 3660 | 4.97 | 4547.55 | 3.5 | 3202.5 | 5.74 | 5252.1 |  | 0 |  | 0 | 26 | Concrete Surface Removal, 1.5" | S.Y. | 915 | 4 | 3660 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Concrete Surface Removal, 1.5" | S.Y. | 915 | 4 | 3660 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Aggregate Shoulder | Tons | 410 | 35 | 14350 | 0.01 | 4.1 | 19 | 7790 | 21.56 | 8839.6 |  | 0 |  | 0 | 27 | Aggregate Shoulder | Tons | 410 | 35 | 14350 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Aggregate Shoulder | Tons | 410 | 35 | 14350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Remove Existing CMP Storm Pipe | L.F. | 45 | 20 | 900 | 17.33 | 779.85 | 20 | 900 | 18.18 | 818.1 |  | 0 |  | 0 | 28 | Remove Existing CMP Storm Pipe | L.F. | 45 | 20 | 900 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Remove Existing CMP Storm Pipe | L.F. | 45 | 20 | 900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Storm Sewers, PVC, 10" | L.F. | 150 | 75 | 11250 | 55.72 | 8358 | 68 | 10200 | 75.75 | 11362.5 |  | 0 |  | 0 | 29 | Storm Sewers, PVC, 10" | L.F. | 150 | 75 | 11250 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Storm Sewers, PVC, 10" | L.F. | 150 | 75 | 11250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Storm Sewers, RCP, 12" | L.F. | 45 | 100 | 4500 | 75.37 | 3391.65 | 68 | 3060 | 90.9 | 4090.5 |  | 0 |  | 0 | 30 | Storm Sewers, RCP, 12" | L.F. | 45 | 100 | 4500 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Storm Sewers, RCP, 12" | L.F. | 45 | 100 | 4500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 1 | 5000 | 5000 | 2155.58 | 2155.58 | 2100 | 2100 | 2525 | 2525 |  | 0 |  | 0 | 31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Storm Inlet, Type 700 | Each | 1 | 3000 | 3000 | 1925.64 | 1925.64 | 2100 | 2100 | 2171.5 | 2171.5 |  | 0 |  | 0 | 32 | Storm Inlet, Type 700 | Each | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Storm Inlet, Type 700 | Each | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 4 | 300 | 1200 | 262.62 | 1050.48 | 500 | 2000 | 343.4 | 1373.6 |  | 0 |  | 0 | 33 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 4 | 300 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 4 | 300 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | Manholes to be Adjusted | Each | 140 | 550 | 77000 | 531.83 | 74456.2 | 575 | 80500 | 530.25 | 74235 |  | 0 |  | 0 | 34 | Manholes to be Adjusted | Each | 140 | 550 | 77000 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Manholes to be Adjusted | Each | 140 | 550 | 77000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | Manholes to be Adjusted with New Frame and Lid | Each | 48 | 800 | 38400 | 798.42 | 38324.16 | 875 | 42000 | 656.5 | 31512 |  | 0 |  | 0 | 35 | Manholes to be Adjusted with New Frame and Lid | Each | 48 | 800 | 38400 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Manholes to be Adjusted with New Frame and Lid | Each | 48 | 800 | 38400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 | 1041.72 | 1041.72 | 1100 | 1100 | 909 | 909 |  | 0 |  | 0 | 36 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 36 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1500 | 1500 | 1308.33 | 1308.33 | 1400 | 1400 | 1111 | 1111 |  | 0 |  | 0 | 37 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | Inlets to be Adjusted | Each | 23 | 1000 | 23000 | 1001.16 | 23026.68 | 975 | 22425 | 1164.53 | 26784.19 |  | 0 |  | 0 | 38 | Inlets to be Adjusted | Each | 23 | 1000 | 23000 |  | 0 |  | 0 |  | 0 |  | 0 | 38 | Inlets to be Adjusted | Each | 23 | 1000 | 23000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | Inlets to be Adjusted with New Frame and Grate | Each | 22 | 1400 | 30800 | 1369.07 | 30119.54 | 1400 | 30800 | 1518.03 | 33396.66 |  | 0 |  | 0 | 39 | Inlets to be Adjusted with New Frame and Grate | Each | 22 | 1400 | 30800 |  | 0 |  | 0 |  | 0 |  | 0 | 39 | Inlets to be Adjusted with New Frame and Grate | Each | 22 | 1400 | 30800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | Inlets to be Reconstructed | Each | 2 | 1500 | 3000 | 1041.41 | 2082.82 | 1250 | 2500 | 1442.28 | 2884.56 |  | 0 |  | 0 | 40 | Inlets to be Reconstructed | Each | 2 | 1500 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 40 | Inlets to be Reconstructed | Each | 2 | 1500 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | Inlets to be Reconstructed with New Frame and Grate | Each | 7 | 1900 | 13300 | 1424.71 | 9972.97 | 1750 | 12250 | 1795.78 | 12570.46 |  | 0 |  | 0 | 41 | Inlets to be Reconstructed with New Frame and Grate | Each | 7 | 1900 | 13300 |  | 0 |  | 0 |  | 0 |  | 0 | 41 | Inlets to be Reconstructed with New Frame and Grate | Each | 7 | 1900 | 13300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
42 | Inlet Speicals to be Repaired | Each | 6 | 2200 | 13200 | 1956.21 | 11737.26 | 1900 | 11400 | 2452.28 | 14713.68 |  | 0 |  | 0 | 42 | Inlet Speicals to be Repaired | Each | 6 | 2200 | 13200 |  | 0 |  | 0 |  | 0 |  | 0 | 42 | Inlet Speicals to be Repaired | Each | 6 | 2200 | 13200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
43 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 4050 | 30 | 121500 | 27.79 | 112549.5 | 30 | 121500 | 33.83 | 137011.5 |  | 0 |  | 0 | 43 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 4050 | 30 | 121500 |  | 0 |  | 0 |  | 0 |  | 0 | 43 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 4050 | 30 | 121500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
44 | Traffic Control and Protection | Lsum | 1 | 50000 | 50000 | 52333.85 | 52333.85 | 55125 | 55125 | 29290 | 29290 |  | 0 |  | 0 | 44 | Traffic Control and Protection | Lsum | 1 | 50000 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 | 44 | Traffic Control and Protection | Lsum | 1 | 50000 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
45 | Thermoplastic Pavement Markings, 4" | L.F. | 5520 | 1.5 | 8280 | 0.91 | 5023.2 | 0.9 | 4968 | 0.83 | 4581.6 |  | 0 |  | 0 | 45 | Thermoplastic Pavement Markings, 4" | L.F. | 5520 | 1.5 | 8280 |  | 0 |  | 0 |  | 0 |  | 0 | 45 | Thermoplastic Pavement Markings, 4" | L.F. | 5520 | 1.5 | 8280 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
46 | Thermoplastic Pavement Markings, 6" | L.F. | 870 | 2 | 1740 | 1.36 | 1183.2 | 1.35 | 1174.5 | 1.51 | 1313.7 |  | 0 |  | 0 | 46 | Thermoplastic Pavement Markings, 6" | L.F. | 870 | 2 | 1740 |  | 0 |  | 0 |  | 0 |  | 0 | 46 | Thermoplastic Pavement Markings, 6" | L.F. | 870 | 2 | 1740 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
47 | Thermoplastic Pavement Markings, 12" | L.F. | 424 | 4 | 1696 | 2.73 | 1157.52 | 2.7 | 1144.8 | 2.52 | 1068.48 |  | 0 |  | 0 | 47 | Thermoplastic Pavement Markings, 12" | L.F. | 424 | 4 | 1696 |  | 0 |  | 0 |  | 0 |  | 0 | 47 | Thermoplastic Pavement Markings, 12" | L.F. | 424 | 4 | 1696 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
48 | Thermoplastic Pavement Markings, 24" | L.F. | 138 | 6 | 828 | 5.45 | 752.1 | 5.4 | 745.2 | 5.05 | 696.9 |  | 0 |  | 0 | 48 | Thermoplastic Pavement Markings, 24" | L.F. | 138 | 6 | 828 |  | 0 |  | 0 |  | 0 |  | 0 | 48 | Thermoplastic Pavement Markings, 24" | L.F. | 138 | 6 | 828 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 2478460 |  | 2286529.65 |  | 2365321 |  | 2354490.41 | [5 empty] | Page 4 | Total |  | As read | 2478460 | [9 empty] | Page 2 | Total |  | As read | 2478460
| Award to William Charles Construction | Total |  | As corrected |  |  | 2286529.65 | 0 | 2365321 | 0 | 2354490.41 | [5 empty] | Award to William Charles Construction | Bid |  | As corrected | 2478460 | [9 empty] | Award to William Charles Construction | Bid |  | As corrected | 2478460
49 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 307 | 8 | 2456 | 5.45 | 1673.15 | 5.4 | 1657.8 | 5.05 | 1550.35 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
50 | Detector Loops | L.F. | 50 | 30 | 1500 | 28.23 | 1411.5 | 60 | 3000 | 39.14 | 1957 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 2482416 |  | 2289614.3 |  | 2369978.8 |  | 2357997.76 | [5 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to William Charles Construction | Bid |  | As corrected | [12 empty] | Award to William Charles Construction | Bid |  | As corrected | [10 empty] | Award to William Charles Construction | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to William Charles Construction | Bid |  | As corrected | [12 empty] | Award to William Charles Construction | Bid |  | As corrected | [10 empty] | Award to William Charles Construction | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 1 - 2021 (Residential)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 140 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 127 |  | 0
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 50 |  | 0
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 50 |  | 0
6 | Aggregate Base Repair, 10" | S.Y. | 1396 |  | 0
7 | Bituminous Materials (Prime Coat) | Gal | 14117 |  | 0
8 | Aggregate (Prime Coat) | Tons | 715 |  | 0
9 | Polymerized Leveling Binder, IL-4.75, N50, 0.5" | Tons | 50 |  | 0
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 100 |  | 0
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | 1325 |  | 0
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 100 |  | 0
13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 16325 |  | 0
14 | Hot-Mix Asphalt, Hand Method | Tons | 60 |  | 0
15 | P.C.C. Approach Pavement, 6" | S.Y. | 532 |  | 0
16 | P.C.C. Approach Pavement, 8" | S.Y. | 76 |  | 0
17 | P.C.C. Sidewalk, 4" | S.F. | 32200 |  | 0
18 | Detectable Warnings, ADA Ramps | S.F. | 650 |  | 0
19 | Combination Curb and Gutter Removal | L.F. | 3960 |  | 0
20 | Sidewalk Removal | S.F. | 31425 |  | 0
21 | Approach Pavement Removal | S.Y. | 608 |  | 0
22 | Surface Removal, 1.25" | S.Y. | 10500 |  | 0
23 | Surface Removal, 2" | S.Y. | 119525 |  | 0
24 | Surface Removal, Butt Joints | S.Y. | 1145 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Concrete Surface Removal, 1.25" | S.Y. | 1050 |  | 0
26 | Concrete Surface Removal, 1.5" | S.Y. | 915 |  | 0
27 | Aggregate Shoulder | Tons | 410 |  | 0
28 | Remove Existing CMP Storm Pipe | L.F. | 45 |  | 0
29 | Storm Sewers, PVC, 10" | L.F. | 150 |  | 0
30 | Storm Sewers, RCP, 12" | L.F. | 45 |  | 0
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 1 |  | 0
32 | Storm Inlet, Type 700 | Each | 1 |  | 0
33 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 4 |  | 0
34 | Manholes to be Adjusted | Each | 140 |  | 0
35 | Manholes to be Adjusted with New Frame and Lid | Each | 48
36 | Manholes to be Reconstructed | Each | 1
37 | Manholes to be Reconstructed with New Frame and Lid | Each | 1
38 | Inlets to be Adjusted | Each | 23
39 | Inlets to be Adjusted with New Frame and Grate | Each | 22
40 | Inlets to be Reconstructed | Each | 2
41 | Inlets to be Reconstructed with New Frame and Grate | Each | 7
42 | Inlet Speicals to be Repaired | Each | 6
43 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 4050
44 | Traffic Control and Protection | Lsum | 1
45 | Thermoplastic Pavement Markings, 4" | L.F. | 5520
46 | Thermoplastic Pavement Markings, 6" | L.F. | 870
47 | Thermoplastic Pavement Markings, 12" | L.F. | 424
48 | Thermoplastic Pavement Markings, 24" | L.F. | 138
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected
49 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 307
50 | Detector Loops | L.F. | 50
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2021 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 140 | 25 | 3500
2 | Parkway Restoration | Lsum | 1 | 50000 | 50000
3 | Inlet and Pipe Protection | Each | 127 | 60 | 7620
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 50 | 25 | 1250
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 50 | 25 | 1250
6 | Aggregate Base Repair, 10" | S.Y. | 1396 | 20 | 27920
7 | Bituminous Materials (Prime Coat) | Gal | 14117 | 3 | 42351
8 | Aggregate (Prime Coat) | Tons | 715 | 10 | 7150
9 | Polymerized Leveling Binder, IL-4.75, N50, 0.5" | Tons | 50 | 80 | 4000
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 100 | 65 | 6500
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | 1325 | 65 | 86125
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 100 | 60 | 6000
13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 16325 | 60 | 979500
14 | Hot-Mix Asphalt, Hand Method | Tons | 60 | 300 | 18000
15 | P.C.C. Approach Pavement, 6" | S.Y. | 532 | 60 | 31920
16 | P.C.C. Approach Pavement, 8" | S.Y. | 76 | 75 | 5700
17 | P.C.C. Sidewalk, 4" | S.F. | 32200 | 6 | 193200
18 | Detectable Warnings, ADA Ramps | S.F. | 650 | 25 | 16250
19 | Combination Curb and Gutter Removal | L.F. | 3960 | 20 | 79200
20 | Sidewalk Removal | S.F. | 31425 | 2 | 62850
21 | Approach Pavement Removal | S.Y. | 608 | 40 | 24320
22 | Surface Removal, 1.25" | S.Y. | 10500 | 2.5 | 26250
23 | Surface Removal, 2" | S.Y. | 119525 | 3 | 358575
24 | Surface Removal, Butt Joints | S.Y. | 1145 | 5 | 5725
|  |  |  | Sub Total | 2045156
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2021 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Concrete Surface Removal, 1.25" | S.Y. | 1050 | 4 | 4200
26 | Concrete Surface Removal, 1.5" | S.Y. | 915 | 4 | 3660
27 | Aggregate Shoulder | Tons | 410 | 35 | 14350
28 | Remove Existing CMP Storm Pipe | L.F. | 45 | 20 | 900
29 | Storm Sewers, PVC, 10" | L.F. | 150 | 75 | 11250
30 | Storm Sewers, RCP, 12" | L.F. | 45 | 100 | 4500
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 1 | 5000 | 5000
32 | Storm Inlet, Type 700 | Each | 1 | 3000 | 3000
33 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 4 | 300 | 1200
34 | Manholes to be Adjusted | Each | 140 | 550 | 77000
35 | Manholes to be Adjusted with New Frame and Lid | Each | 48 | 800 | 38400
36 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000
37 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1500 | 1500
38 | Inlets to be Adjusted | Each | 23 | 1000 | 23000
39 | Inlets to be Adjusted with New Frame and Grate | Each | 22 | 1400 | 30800
40 | Inlets to be Reconstructed | Each | 2 | 1500 | 3000
41 | Inlets to be Reconstructed with New Frame and Grate | Each | 7 | 1900 | 13300
42 | Inlet Speicals to be Repaired | Each | 6 | 2200 | 13200
43 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 4050 | 30 | 121500
44 | Traffic Control and Protection | Lsum | 1 | 50000 | 50000
45 | Thermoplastic Pavement Markings, 4" | L.F. | 5520 | 1.5 | 8280
46 | Thermoplastic Pavement Markings, 6" | L.F. | 870 | 2 | 1740
47 | Thermoplastic Pavement Markings, 12" | L.F. | 424 | 4 | 1696
48 | Thermoplastic Pavement Markings, 24" | L.F. | 138 | 6 | 828
|  |  |  | Sub Total | 2478460
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2021 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 307 | 8 | 2456
50 | Detector Loops | L.F. | 50 | 30 | 1500
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2021 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: William Charles Construction | P.O. # 19305222 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2021 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 140 | C.Y. | 4335.8 |  | 140 |  |  | 30.97
2 | Parkway Restoration | 1 | Lsum | 44823.79 |  | 1 |  |  | 44823.79
3 | Inlet and Pipe Protection | 127 | Each | 7335.52 |  | 92 | 35 | Each | 57.76 | 2021.6
4 | Subbase Granular Material, Type B, CA-2, 6" | 50 | Tons | 1162 |  | 50 |  |  | 23.24
5 | Aggregate Base Course, Type B, CA-6, 6" | 50 | Tons | 1484 |  | 50 |  |  | 29.68
6 | Aggregate Base Repair, 10" | 1396 | S.Y. | 13.96 |  | 1396 |  |  | 0.01
7 | Bituminous Materials (Prime Coat) | 14117 | Gal | 23434.22 |  | 14117 |  |  | 1.66
8 | Aggregate (Prime Coat) | 715 | Tons | 7.15 |  | 715 |  |  | 0.01
9 | Polymerized Leveling Binder, IL-4.75, N50, 0.5" | 50 | Tons | 5202 |  | 50 |  |  | 104.04
10 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | 100 | Tons | 5566 | 1300 |  | 1400 | Tons | 55.66 | 77924
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | 1325 | Tons | 77300.5 |  | 1325 |  |  | 58.34
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | 100 | Tons | 6334 |  | 100 |  |  | 63.34
13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 16325 | Tons | 953216.75 |  | 14295 | 2030 | Tons | 58.39 | 118531.7
14 | Hot-Mix Asphalt, Hand Method | 60 | Tons | 9520.2 |  | 60 |  |  | 158.67
15 | P.C.C. Approach Pavement, 6" | 532 | S.Y. | 41926.92 |  | 240 | 292 | S.Y. | 78.81 | 23012.52
16 | P.C.C. Approach Pavement, 8" | 76 | S.Y. | 6147.64 |  | 76 |  |  | 80.89
17 | P.C.C. Sidewalk, 4" | 32200 | S.F. | 200928 |  | 17106 | 15094 | S.F. | 6.24 | 94186.56
18 | Detectable Warnings, ADA Ramps | 650 | S.F. | 12473.5 |  | 150 | 500 | S.F. | 19.19 | 9595
19 | Combination Curb and Gutter Removal | 3960 | L.F. | 67795.2 |  | 2462 | 1498 | L.F. | 17.12 | 25645.76
20 | Sidewalk Removal | 31425 | S.F. | 79191 |  | 16181 | 15244 | S.F. | 2.52 | 38414.88
21 | Approach Pavement Removal | 608 | S.Y. | 25840 |  | 316 | 292 | S.Y. | 42.5 | 12410
22 | Surface Removal, 1.25" | 10500 | S.Y. | 25200 |  | 10500 |  |  | 2.4
23 | Surface Removal, 2" | 119525 | S.Y. | 280883.75 |  | 101320 | 18205 | S.Y. | 2.35 | 42781.75
24 | Surface Removal, Butt Joints | 1145 | S.Y. | 12972.85 |  | 432 | 713 | S.Y. | 11.33 | 8078.29
Sub Total |  |  |  | 1893094.75 | [5 empty] | 452602.06
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: William Charles Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2021 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Concrete Surface Removal, 1.25" | 1050 | S.Y. | 6153 |  | 1050 |  |  | 5.86
26 | Concrete Surface Removal, 1.5" | 915 | S.Y. | 4547.55 |  | 915 |  |  | 4.97
27 | Aggregate Shoulder | 410 | Tons | 4.1 |  | 410 |  |  | 0.01
28 | Remove Existing CMP Storm Pipe | 45 | L.F. | 779.85 |  | 45 |  |  | 17.33
29 | Storm Sewers, PVC, 10" | 150 | L.F. | 8358 |  | 150 |  |  | 55.72
30 | Storm Sewers, RCP, 12" | 45 | L.F. | 3391.65 |  | 35 | 10 | L.F. | 75.37 | 753.7
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | 1 | Each | 2155.58 |  | 1 |  |  | 2155.58
32 | Storm Inlet, Type 700 | 1 | Each | 1925.64 |  | 1 |  |  | 1925.64
33 | Sanitary Riser/Valve Boxes to be Adjusted | 4 | Each | 1050.48 |  | 4 |  |  | 262.62
34 | Manholes to be Adjusted | 140 | Each | 74456.2 |  | 132 | 8 | Each | 531.83 | 4254.64
35 | Manholes to be Adjusted with New Frame and Lid | 48 | Each | 38324.16 |  | 48 |  |  | 798.42
36 | Manholes to be Reconstructed | 1 | Each | 1041.72 |  | 1 |  |  | 1041.72
37 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 1308.33 |  | 1 |  |  | 1308.33
38 | Inlets to be Adjusted | 23 | Each | 23026.68 |  | 22 | 1 | Each | 1001.16 | 1001.16
39 | Inlets to be Adjusted with New Frame and Grate | 22 | Each | 30119.54 | 1296 |  | 1318 | Each | 1369.07 | 1804434.26
40 | Inlets to be Reconstructed | 2 | Each | 2082.82 |  | 1.5 | 0.5 | Each | 1041.41 | 520.705
41 | Inlets to be Reconstructed with New Frame and Grate | 7 | Each | 9972.97 |  | 7 |  |  | 1424.71
42 | Inlet Speicals to be Repaired | 6 | Each | 11737.26 |  | 6 |  |  | 1956.21
43 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 4050 | L.F. | 112549.5 |  | 4050 |  |  | 27.79
44 | Traffic Control and Protection | 1 | Lsum | 52333.85 |  | 1 |  |  | 52333.85
45 | Thermoplastic Pavement Markings, 4" | 5520 | L.F. | 5023.2 |  | 5520 |  |  | 0.91
46 | Thermoplastic Pavement Markings, 6" | 870 | L.F. | 1183.2 |  | 870 |  |  | 1.36
47 | Thermoplastic Pavement Markings, 12" | 424 | L.F. | 1157.52 |  | 424 |  |  | 2.73
48 | Thermoplastic Pavement Markings, 24" | 138 | L.F. | 752.1 |  | 138 |  |  | 5.45
Sub Total |  |  |  | 2286529.65 | [5 empty] | 2263566.525
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
[8 empty] | DEDUCT RETAINAGE | 10% | #VALUE!
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: William Charles Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2021 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | Thermoplastic Pavement Markings, Letters and Symbols | 307 | S.F. | 1673.15 |  | 307 |  |  | 5.45
50 | Detector Loops | 50 | L.F. | 1411.5 |  | 50 |  |  | 28.23
Total |  |  |  | 2289614.3 | [5 empty] | 2263566.525
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 2263566.525
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 2263566.525
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 2263566.525
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: William Charles Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2021 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 2289614.3 | [5 empty] | 2263566.525
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 2263566.525
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 2263566.525
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 2263566.525
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | William Charles Construction
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.