## Item List
| City -Wide Street Repairs Group No. 3 - 2021 (Alleys) | [19 empty] | 354798
Summary Of Quantities |  |  | 2nd Ward - 94003002 |  |  | 2nd Ward | 3rd Ward - 94003003 |  | 6th Ward | 11th Ward - 94003011 |  | 11th Ward - 94003011 |  |  | 12th Ward | 13th Ward | Parking
No. | Item | Units | Alleys 110 and 118 | Alley 663 | Alley 754 | Alley 757 | Alley 456 | Alley 778 | Alley 59 | Alley 224 | Alley 245 | Alley 267 | Alley 285 | Alley 291 | Alley 576 | Alley 987 | Parking Lot 7 | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. | [6 empty] | 185 | [9 empty] | 185 | 30 | 5550
2 | Parkway Restoration | Lsum | 0.08 | 0.04 | 0.03 | 0.02 | 0.05 | 0.07 | 0.08 | 0.08 | 0.05 | 0.06 | 0.07 | 0.04 | 0.05 | 0.07 | 0.21 |  | 1 | 10000 | 10000
3 | Inlet and Pipe Protection | Each | [14 empty] | 1 |  | 1 | 100 | 100
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | [6 empty] | 280 | [8 empty] | 100 | 380 | 25 | 9500
5 | Aggregate Base Repair, 10" | S.Y. | 107 | 42 |  |  | 40 | 70 |  | 67 | 75 | 60 | 50 | 25 | 50 | 45 | 270 |  | 901 | 25 | 22525
6 | Bituminous Materials (Prime Coat) | Gal | 107 | 42 |  |  | 40 | 70 |  | 67 | 75 | 60 | 50 | 25 | 50 | 45 | 270 |  | 901 | 3 | 2703
7 | Aggregate (Prime Coat) | Tons | 11 | 4 |  |  | 4 | 7 |  | 6 | 8 | 6 | 5 | 2 | 5 | 4 | 27 |  | 89 | 10 | 890
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | [6 empty] | 60 | [8 empty] | 100 | 160 | 90 | 14400
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | [6 empty] | 60 | [8 empty] | 100 | 160 | 90 | 14400
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 150 | 75 |  |  | 75 | 100 |  | 100 | 110 | 90 | 75 | 40 | 75 | 70 | 350 | 100 | 1410 | 90 | 126900
11 | Hot-Mix Asphalt, Hand Method | Tons | [15 empty] | 10 | 10 | 300 | 3000
12 | P.C.C. Approach Pavement, 6" | S.Y. | [10 empty] | 21 |  |  |  |  | 50 | 71 | 60 | 4260
13 | P.C.C. Approach Pavement, 8" | S.Y. |  |  |  |  | 20 | 20 |  | 43 |  | 14 | 25 | 19 |  | 43 |  | 50 | 234 | 75 | 17550
14 | P.C.C. Sidewalk, 4" | S.F. |  |  |  |  | 300 | 175 |  | 275 |  | 225 | 200 | 125 |  | 500 |  | 1000 | 2800 | 6 | 16800
15 | Combination Curb and Gutter Removal | L.F. |  |  |  |  | 30 | 30 |  | 60 |  | 55 | 60 | 30 |  |  |  | 100 | 365 | 20 | 7300
16 | Sidewalk Removal | S.F. |  |  |  |  | 300 | 175 |  | 275 |  | 225 | 200 | 125 |  | 500 |  | 1000 | 2800 | 2 | 5600
17 | Approach Pavement Removal | S.Y. |  |  |  |  | 20 | 20 |  | 43 |  | 14 | 46 | 19 |  | 43 |  | 100 | 305 | 30 | 9150
18 | Surface Removal, 2" | S.Y. | 1075 | 425 |  |  | 400 | 700 |  | 675 | 750 | 600 | 500 | 250 | 500 | 450 | 2700 | 1000 | 10025 | 4 | 40100
19 | Surface Removal, Butt Joints | S.Y. | [15 empty] | 100 | 100 | 10 | 1000
20 | Aggregate Shoulder | Tons | [15 empty] | 100 | 100 | 40 | 4000
21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [15 empty] | 1 | 1 | 500 | 500
22 | Manholes to be Adjusted | Each | [15 empty] | 1 | 1 | 800 | 800
23 | Manholes to be Adjusted with New Frame and Grate or Lid | Each | [14 empty] | 1 |  | 1 | 1000 | 1000
24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. |  |  |  |  | 30 | 30 |  | 60 |  | 55 | 60 | 30 |  |  |  | 100 | 365 | 30 | 10950
25 | Traffic Control and Protection | LSum | 0.08 | 0.04 | 0.03 | 0.02 | 0.05 | 0.07 | 0.08 | 0.08 | 0.05 | 0.06 | 0.07 | 0.04 | 0.05 | 0.07 | 0.21 |  | 1 | 10000 | 10000
26 | Thermoplastic Pavement Markings, 4" | L.F. | [14 empty] | 1785 |  | 1785 | 2 | 3570
27 | Accessible Parking Symbol Striping | Each | [14 empty] | 5 |  | 5 | 200 | 1000
28 | Bituminous Hump (2' Wide x 6" High) | L.F. |  |  | 35 | 55 | [12 empty] | 90 | 125 | 11250
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 22506 | 10466 | 4975 | 7275 | 16510 | 20230 | 24950 | 24951 | 16080 | 19460 | 20715 | 10615 | 11200 | 19315 | 60000 | 65550 | #VALUE!
|  |  | 5326.9541 | 2602.4814 | 1626.5509 | 929.4576 | 3165.9651 | 4647.2882 | 5477.991 | 5419.8999 | 3526.1299 | 4002.477 | 4490.4422 | 2794.182 | 3078.8284 | 4519.4878 | 13941.8646 |  | 354798
|  |  | 27832.9541 | 13068.4814 | 6601.5509 | 8204.4576 | 19675.9651 | 24877.2882 | 30427.991 | 30370.8999 | 19606.1299 | 23462.477 | 25205.4422 | 13409.182 | 14278.8284 | 23834.4878 | 73941.8646 |  | 354798
|  |  | 22925 | 11200 | 7000 | 4000 | 13625 | 20000 | 23575 | 23325 | 15175 | 17225 | 19325 | 12025 | 13250 | 19450 | 60000 | 0 | 282100
#REF!
|  |  | 0.081266 | 0.039702 | 0.024814 | 0.014179 | 0.048298 | 0.070897 | 0.08357 | 0.082683 | 0.053793 | 0.06106 | 0.068504 | 0.042627 | 0.046969 | 0.068947 | 0.21269 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Norwest Construction |  | William Charles |  | N-TRAK Group |  | Schroeder Asphalt |  |  |  | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | South Beloit, IL |  | Rockford, IL |  | Loves Park, IL |  | Huntley, IL |  |  |  | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 3 - 2021 (Alleys) | [15 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 621-PW-045 VENDORS NOTIFIED: 89 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 185 | 30 | 5550 | 34.2 | 6327 | 52.35 | 9684.75 | 35 | 6475 | 50 | 9250 |  | 0 | 1 | Earth Excavation | C.Y. | 185 | 30 | 5550 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 185 | 30 | 5550 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 | 5752 | 5752 | 24000 | 24000 | 20000 | 20000 | 8000 | 8000 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 1 | 100 | 100 | 132.5 | 132.5 | 130 | 130 | 100 | 100 | 125 | 125 |  | 0 | 3 | Inlet and Pipe Protection | Each | 1 | 100 | 100 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 1 | 100 | 100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 380 | 25 | 9500 | 35.8 | 13604 | 29.3 | 11134 | 25 | 9500 | 21 | 7980 |  | 0 | 4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 380 | 25 | 9500 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 380 | 25 | 9500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Aggregate Base Repair, 10" | S.Y. | 901 | 25 | 22525 | 0.1 | 90.1 | 0.01 | 9.01 | 20 | 18020 | 21 | 18921 |  | 0 | 5 | Aggregate Base Repair, 10" | S.Y. | 901 | 25 | 22525 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Aggregate Base Repair, 10" | S.Y. | 901 | 25 | 22525 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Bituminous Materials (Prime Coat) | Gal | 901 | 3 | 2703 | 0.01 | 9.01 | 4.5 | 4054.5 | 6 | 5406 | 0.01 | 9.01 |  | 0 | 6 | Bituminous Materials (Prime Coat) | Gal | 901 | 3 | 2703 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Bituminous Materials (Prime Coat) | Gal | 901 | 3 | 2703 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Aggregate (Prime Coat) | Tons | 89 | 10 | 890 | 0.01 | 0.89 | 0.01 | 0.89 | 0.01 | 0.89 | 0.01 | 0.89 |  | 0 | 7 | Aggregate (Prime Coat) | Tons | 89 | 10 | 890 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Aggregate (Prime Coat) | Tons | 89 | 10 | 890 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 160 | 90 | 14400 | 94 | 15040 | 93.7 | 14992 | 92 | 14720 | 92 | 14720 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 160 | 90 | 14400 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 160 | 90 | 14400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 160 | 90 | 14400 | 94 | 15040 | 93.7 | 14992 | 92 | 14720 | 96 | 15360 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 160 | 90 | 14400 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 160 | 90 | 14400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1410 | 90 | 126900 | 94 | 132540 | 96 | 135360 | 92 | 129720 | 88 | 124080 |  | 0 | 10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1410 | 90 | 126900 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1410 | 90 | 126900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 | 300 | 3000 | 300 | 3000 | 450 | 4500 | 600 | 6000 |  | 0 | 11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 71 | 60 | 4260 | 60 | 4260 | 77 | 5467 | 79 | 5609 | 90 | 6390 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 71 | 60 | 4260 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 71 | 60 | 4260 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 234 | 75 | 17550 | 76 | 17784 | 86.75 | 20299.5 | 88 | 20592 | 95 | 22230 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 234 | 75 | 17550 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 234 | 75 | 17550 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 2800 | 6 | 16800 | 6.6 | 18480 | 8 | 22400 | 8 | 22400 | 9 | 25200 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 2800 | 6 | 16800 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 2800 | 6 | 16800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Combination Curb and Gutter Removal | L.F. | 365 | 20 | 7300 | 22 | 8030 | 22 | 8030 | 20 | 7300 | 7 | 2555 |  | 0 | 15 | Combination Curb and Gutter Removal | L.F. | 365 | 20 | 7300 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Combination Curb and Gutter Removal | L.F. | 365 | 20 | 7300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Sidewalk Removal | S.F. | 2800 | 2 | 5600 | 2.7 | 7560 | 4.75 | 13300 | 3 | 8400 | 1.5 | 4200 |  | 0 | 16 | Sidewalk Removal | S.F. | 2800 | 2 | 5600 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Sidewalk Removal | S.F. | 2800 | 2 | 5600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Approach Pavement Removal | S.Y. | 305 | 30 | 9150 | 35.7 | 10888.5 | 35 | 10675 | 25 | 7625 | 13 | 3965 |  | 0 | 17 | Approach Pavement Removal | S.Y. | 305 | 30 | 9150 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Approach Pavement Removal | S.Y. | 305 | 30 | 9150 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Surface Removal, 2" | S.Y. | 10025 | 4 | 40100 | 4.65 | 46616.25 | 4.95 | 49623.75 | 5.25 | 52631.25 | 3.75 | 37593.75 |  | 0 | 18 | Surface Removal, 2" | S.Y. | 10025 | 4 | 40100 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Surface Removal, 2" | S.Y. | 10025 | 4 | 40100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Surface Removal, Butt Joints | S.Y. | 100 | 10 | 1000 | 1 | 100 | 12 | 1200 | 5.25 | 525 | 6 | 600 |  | 0 | 19 | Surface Removal, Butt Joints | S.Y. | 100 | 10 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Surface Removal, Butt Joints | S.Y. | 100 | 10 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Aggregate Shoulder | Tons | 100 | 40 | 4000 | 1 | 100 | 0.01 | 1 | 50 | 5000 | 47 | 4700 |  | 0 | 20 | Aggregate Shoulder | Tons | 100 | 40 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Aggregate Shoulder | Tons | 100 | 40 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 | 166 | 166 | 560 | 560 | 450 | 450 | 60 | 60 |  | 0 | 21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Manholes to be Adjusted | Each | 1 | 800 | 800 | 900 | 900 | 1200 | 1200 | 950 | 950 | 700 | 700 |  | 0 | 22 | Manholes to be Adjusted | Each | 1 | 800 | 800 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Manholes to be Adjusted | Each | 1 | 800 | 800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Manholes to be Adjusted with New Frame and Grate or Lid | Each | 1 | 1000 | 1000 | 1250 | 1250 | 1750 | 1750 | 1300 | 1300 | 1400 | 1400 |  | 0 | 23 | Manholes to be Adjusted with New Frame and Grate or Lid | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Manholes to be Adjusted with New Frame and Grate or Lid | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 365 | 30 | 10950 | 37.4 | 13651 | 39.5 | 14417.5 | 39 | 14235 | 55 | 20075 |  | 0 | 24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 365 | 30 | 10950 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 365 | 30 | 10950 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 328978 |  | 321321.25 |  | 366280.9 |  | 370179.14 |  | 334114.65 |  |  |  | Page 3 | Sub |  | As read | 328978 | [9 empty] | Page 1 | Sub |  | As read | 328978
| Award to Norwest Construction | Total |  | As corrected | 328978 |  | 321321.25 |  | 366280.9 |  | 370179.14 |  | 334114.65 |  |  |  | Award to Norwest Construction | Total |  | As corrected | 328978 | [9 empty] | Award to Norwest Construction | Total |  | As corrected | 328978
25 | Traffic Control and Protection | LSum | 1 | 10000 | 10000 | 7455 | 7455 | 35000 | 35000 | 14000 | 14000 | 20000 | 20000 |  | 0 | 25 | Traffic Control and Protection | LSum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Traffic Control and Protection | LSum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Thermoplastic Pavement Markings, 4" | L.F. | 1785 | 2 | 3570 | 1.6 | 2856 | 1.5 | 2677.5 | 1.6 | 2856 | 1.6 | 2856 |  | 0 | 26 | Thermoplastic Pavement Markings, 4" | L.F. | 1785 | 2 | 3570 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Thermoplastic Pavement Markings, 4" | L.F. | 1785 | 2 | 3570 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Accessible Parking Symbol Striping | Each | 5 | 200 | 1000 | 262.5 | 1312.5 | 250 | 1250 | 275 | 1375 | 185 | 925 |  | 0 | 27 | Accessible Parking Symbol Striping | Each | 5 | 200 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Accessible Parking Symbol Striping | Each | 5 | 200 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Bituminous Hump (2' Wide x 6" High) | L.F. | 90 | 125 | 11250 | 40 | 3600 | 50 | 4500 | 26 | 2340 | 50 | 4500 |  | 0 | 28 | Bituminous Hump (2' Wide x 6" High) | L.F. | 90 | 125 | 11250 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Bituminous Hump (2' Wide x 6" High) | L.F. | 90 | 125 | 11250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 354798 |  | 336544.75 |  | 409708.4 |  | 390750.14 |  | 362395.65 |  |  |  | Page 4 | Total |  | As read | 354798 | [9 empty] | Page 2 | Total |  | As read | 354798
| Award to Norwest Construction | Bid |  | As corrected |  |  | 336544.75 | 0 | 409708.4 | 0 | 390750.14 |  | 362395.65 |  |  |  | Award to Norwest Construction | Bid |  | As corrected | #VALUE! | [9 empty] | Award to Norwest Construction | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Norwest Construction | Bid |  | As corrected | [12 empty] | Award to Norwest Construction | Bid |  | As corrected | [10 empty] | Award to Norwest Construction | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Norwest Construction | Bid |  | As corrected | [12 empty] | Award to Norwest Construction | Bid |  | As corrected | [10 empty] | Award to Norwest Construction | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 3 - 2021 (Alleys)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 185 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 1 |  | 0
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 380 |  | 0
5 | Aggregate Base Repair, 10" | S.Y. | 901 |  | 0
6 | Bituminous Materials (Prime Coat) | Gal | 901 |  | 0
7 | Aggregate (Prime Coat) | Tons | 89 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 160 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 160 |  | 0
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1410 |  | 0
11 | Hot-Mix Asphalt, Hand Method | Tons | 10 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 71 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 234 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 2800 |  | 0
15 | Combination Curb and Gutter Removal | L.F. | 365 |  | 0
16 | Sidewalk Removal | S.F. | 2800 |  | 0
17 | Approach Pavement Removal | S.Y. | 305 |  | 0
18 | Surface Removal, 2" | S.Y. | 10025 |  | 0
19 | Surface Removal, Butt Joints | S.Y. | 100 |  | 0
20 | Aggregate Shoulder | Tons | 100 |  | 0
21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 |  | 0
22 | Manholes to be Adjusted | Each | 1 |  | 0
23 | Manholes to be Adjusted with New Frame and Grate or Lid | Each | 1 |  | 0
24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 365 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Traffic Control and Protection | LSum | 1 |  | 0
26 | Thermoplastic Pavement Markings, 4" | L.F. | 1785
27 | Accessible Parking Symbol Striping | Each | 5
28 | Bituminous Hump (2' Wide x 6" High) | L.F. | 90
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2021 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 185 | 30 | 5550
2 | Parkway Restoration | Lsum | 1 | 10000 | 10000
3 | Inlet and Pipe Protection | Each | 1 | 100 | 100
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 380 | 25 | 9500
5 | Aggregate Base Repair, 10" | S.Y. | 901 | 25 | 22525
6 | Bituminous Materials (Prime Coat) | Gal | 901 | 3 | 2703
7 | Aggregate (Prime Coat) | Tons | 89 | 10 | 890
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 160 | 90 | 14400
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 160 | 90 | 14400
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1410 | 90 | 126900
11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000
12 | P.C.C. Approach Pavement, 6" | S.Y. | 71 | 60 | 4260
13 | P.C.C. Approach Pavement, 8" | S.Y. | 234 | 75 | 17550
14 | P.C.C. Sidewalk, 4" | S.F. | 2800 | 6 | 16800
15 | Combination Curb and Gutter Removal | L.F. | 365 | 20 | 7300
16 | Sidewalk Removal | S.F. | 2800 | 2 | 5600
17 | Approach Pavement Removal | S.Y. | 305 | 30 | 9150
18 | Surface Removal, 2" | S.Y. | 10025 | 4 | 40100
19 | Surface Removal, Butt Joints | S.Y. | 100 | 10 | 1000
20 | Aggregate Shoulder | Tons | 100 | 40 | 4000
21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500
22 | Manholes to be Adjusted | Each | 1 | 800 | 800
23 | Manholes to be Adjusted with New Frame and Grate or Lid | Each | 1 | 1000 | 1000
24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 365 | 30 | 10950
|  |  |  | Sub Total | 328978
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2021 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Traffic Control and Protection | LSum | 1 | 10000 | 10000
26 | Thermoplastic Pavement Markings, 4" | L.F. | 1785 | 2 | 3570
27 | Accessible Parking Symbol Striping | Each | 5 | 200 | 1000
28 | Bituminous Hump (2' Wide x 6" High) | L.F. | 90 | 125 | 11250
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2021 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2021 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | P.O. #18305125 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2021 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 185 | C.Y. | 6327 |  |  |  |  | 34.2
2 | Parkway Restoration | 1 | Lsum | 5752 |  |  |  |  | 5752
3 | Inlet and Pipe Protection | 1 | Each | 132.5 |  |  |  |  | 132.5
4 | Aggregate Base Course, Type B, CA-6, 10" | 380 | Tons | 13604 |  |  |  |  | 35.8
5 | Aggregate Base Repair, 10" | 901 | S.Y. | 90.1 |  |  |  |  | 0.1
6 | Bituminous Materials (Prime Coat) | 901 | Gal | 9.01 |  |  |  |  | 0.01
7 | Aggregate (Prime Coat) | 89 | Tons | 0.89 |  |  |  |  | 0.01
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | 160 | Tons | 15040 |  |  |  |  | 94
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | 160 | Tons | 15040 |  |  |  |  | 94
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 1410 | Tons | 132540 |  |  |  |  | 94
11 | Hot-Mix Asphalt, Hand Method | 10 | Tons | 3000 |  |  |  |  | 300
12 | P.C.C. Approach Pavement, 6" | 71 | S.Y. | 4260 |  |  |  |  | 60
13 | P.C.C. Approach Pavement, 8" | 234 | S.Y. | 17784 |  |  |  |  | 76
14 | P.C.C. Sidewalk, 4" | 2800 | S.F. | 18480 |  |  |  |  | 6.6
15 | Combination Curb and Gutter Removal | 365 | L.F. | 8030 |  |  |  |  | 22
16 | Sidewalk Removal | 2800 | S.F. | 7560 |  |  |  |  | 2.7
17 | Approach Pavement Removal | 305 | S.Y. | 10888.5 |  |  |  |  | 35.7
18 | Surface Removal, 2" | 10025 | S.Y. | 46616.25 |  |  |  |  | 4.65
19 | Surface Removal, Butt Joints | 100 | S.Y. | 100 |  |  |  |  | 1
20 | Aggregate Shoulder | 100 | Tons | 100 |  |  |  |  | 1
21 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each | 166 |  |  |  |  | 166
22 | Manholes to be Adjusted | 1 | Each | 900 |  |  |  |  | 900
23 | Manholes to be Adjusted with New Frame and Grate or Lid | 1 | Each | 1250 |  |  |  |  | 1250
24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 365 | L.F. | 13651 |  |  |  |  | 37.4
Sub Total |  |  |  | 321321.25 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2021 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Traffic Control and Protection | 1 | LSum | 7455 |  |  |  |  | 7455
26 | Thermoplastic Pavement Markings, 4" | 1785 | L.F. | 2856 |  |  |  |  | 1.6
27 | Accessible Parking Symbol Striping | 5 | Each | 1312.5 |  |  |  |  | 262.5
28 | Bituminous Hump (2' Wide x 6" High) | 90 | L.F. | 3600 |  |  |  |  | 40
Total |  |  |  | 336544.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
[8 empty] | DEDUCT RETAINAGE | 10% | 0
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2021 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 336544.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2021 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 336544.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Norwest Construction
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.