## Item List
| City -Wide Street Repairs Group No. 4 - 2021 (Residential) | [27 empty] | 1244352
Summary Of Quantities |  |  | 5th Ward - 94003005 |  |  | 94003007 | 7th Ward - 94003007 |  |  |  | 7th Ward - 94003007 |  | 10th Ward - 94003010 |  | 10th Ward - 94003010 |  | 94003012 | 94003014 | Drainage - W2138 | Patching - W2147 | ADA - W2150 |  | ADA - W2150 | Sidewalk - W2151
No. | Item | Units | Rose Avenue/Blake Street Intersection | 0500 Southrock Drive | 1600/1800 West Street | 1500 Arthur Avenue | 3100/3200 Gilbert Avenue | 0900 Irving Avenue Patching | 1500/1600 North Horsman Street | 0600 North Independence Avenue | 0700 Oakley Avenue | 1500/1600 Pauline Avenue | 3000/3200 Greenwood Avenue | 3500/3600 Larson Avenue | 1500 Silvan Road | 5600 Strathmoor Drive | 0300 Harper Avenue Alley Approach | 3014 Rutgers Place Drive Approach | 3537 Lansdale | Mulford Road P.C.C. Patching | Crosby/Regan ADA Ramps | Crosby/Summit ADA Ramps | State Street/Rockford Avenue ADA Ramps | 820 7th Street Sidewalk | 1001 South Main Street Sidewalk | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. | [11 empty] | 15 |  | 50 |  |  |  |  | 40 | 35 |  |  |  | 50 | 190 | 25 | 4750
2 | Parkway Restoration | Lsum | 0.04 | 0.04 | 0.06 | 0.05 | 0.09 | 0.02 | 0.12 | 0.05 | 0.05 | 0.1 | 0.06 | 0.07 | 0.06 | 0.04 | 0.01 | 0.01 | 0.01 | 0 | 0.03 | 0.03 | 0.02 | 0.02 | 0.02 |  | 1 | 30000 | 30000
3 | Inlet and Pipe Protection | Each | 6 | 1 | 4 | 3 | 5 |  | 4 | 4 |  | 6 | 10 | 7 | 2 | 4 | [10 empty] | 56 | 60 | 3360
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | [23 empty] | 50 | 50 | 25 | 1250
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | [23 empty] | 50 | 50 | 25 | 1250
6 | Aggregate Base Repair, 10" | S.Y. | 4 | 27 | 37 | 9 | 28 | 4 | 24 | 10 | 9 | 26 | 27 | 27 | 13 | 25 | [10 empty] | 270 | 20 | 5400
7 | Bituminous Materials (Prime Coat) | Gal | 45 | 270 | 372 | 95 | 285 | 45 | 245 | 105 | 95 | 260 | 270 | 270 | 135 | 250 | [10 empty] | 2742 | 3 | 8226
8 | Aggregate (Prime Coat) | Tons | 2 | 14 | 19 | 5 | 14 | 2 | 12 | 5 | 5 | 13 | 14 | 14 | 7 | 12.5 | [10 empty] | 138.5 | 10 | 1385
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 75 | 325 | 450 | 125 | 350 | 75 | 300 | 125 | 125 | 325 | 325 | 325 | 175 | 300 | [9 empty] | 500 | 3900 | 65 | 253500
10 | Hot-Mix Asphalt, Hand Method | Tons | [18 empty] | 5 | 5 | 5 |  |  | 10 | 25 | 300 | 7500
11 | P.C.C. Approach Pavement, 6" | S.Y. |  |  | 34 |  |  |  | 50 |  |  | 15 |  | 47 | 17 | 22 |  | 15 | [7 empty] | 50 | 250 | 60 | 15000
12 | P.C.C. Approach Pavement, 8" | S.Y. |  |  |  |  | 31 | [7 empty] | 60 |  | 38 | [8 empty] | 50 | 179 | 75 | 13425
13 | P.C.C. Sidewalk, 4" | S.F. | 1000 | 375 | 775 | 1850 | 1350 | 275 | 3575 | 1950 | 1175 | 4700 | 2275 | 3850 | 1500 | 2600 | 500 | 200 |  |  | 500 | 800 |  | 500 | 375 | 1000 | 31125 | 6 | 186750
14 | P.C.C. Sidewalk, 5" | S.F. | [20 empty] | 500 |  |  |  | 500 | 12 | 6000
15 | Detectable Warnings, ADA Ramps | S.F. | 80 |  |  | 80 | 40 | 20 | 20 | 40 | 40 | 20 | 110 | 140 | [6 empty] | 20 | 20 | 40 |  |  |  | 670 | 25 | 16750
16 | Class B Patch, Type IV, 10" | S.Y. | [17 empty] | 1345 | [6 empty] | 1345 | 125 | 168125
17 | Dowel Bars | Each | [17 empty] | 600 | [6 empty] | 600 | 18 | 10800
18 | No. 6 Transverse Tie Bars | Each | [17 empty] | 500 | [6 empty] | 500 | 15 | 7500
19 | Welded Wire Reinforcement | S.Y. | [17 empty] | 1345 | [6 empty] | 1345 | 10 | 13450
20 | Combination Curb and Gutter Removal | L.F. | 140 | 40 | 100 | 120 | 105 | 30 | 500 | 40 | 115 | 85 | 130 | 340 | 265 | 1215 | 40 | 25 | 70 |  | 50 | 40 | 75 |  |  | 500 | 4025 | 20 | 80500
21 | Sidewalk Removal | S.F. | 1000 | 375 | 775 | 1850 | 1350 | 275 | 3675 | 1950 | 1175 | 4700 | 2325 | 3200 | 1500 |  | 500 | 200 |  |  | 500 | 800 | 525 | 500 | 375 | 1000 | 28550 | 2 | 57100
22 | Approach Pavement Removal | S.Y. |  |  | 34 |  | 31 |  | 50 |  |  | 15 |  | 47 | 77 | 22 | 38 | 15 | [7 empty] | 50 | 379 | 40 | 15160
23 | Surface Removal, 2" | S.Y. | 450 | 2700 | 3725 | 950 | 2850 | 450 | 2450 | 1050 | 950 | 2600 | 2700 | 2700 | 1350 | 2500 | [9 empty] | 1000 | 28425 | 3 | 85275
24 | Pedestrian Railing | L.F. | [18 empty] | 30 | [5 empty] | 30 | 200 | 6000
25 | Concrete Retaining Wall | S.F. | [18 empty] | 45 | 56 |  |  |  |  | 101 | 200 | 20200
26 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 |  | 2 | [17 empty] | 1 |  |  |  | 4 | 300 | 1200
27 | Manholes to be Adjusted | Each | 3 | 1 | 5 |  | 6 | 1 | 5 | 1 | 2 | 6 | 3 | 1 | 2 | [7 empty] | 1 |  |  |  | 37 | 550 | 20350
28 | Manholes to be Adjusted with New Frame and Lid | Each | 2 |  | 4 | 1 | 4 |  | 1 |  |  | 4 |  | 1 |  | 2 | [10 empty] | 19 | 800 | 15200
29 | Manholes to be Reconstructed | Each | [23 empty] | 1 | 1 | 1000 | 1000
30 | Manholes to be Reconstructed with New Frame and Lid | Each | [23 empty] | 1 | 1 | 1300 | 1300
31 | Inlets to be Adjusted | Each |  |  |  |  | 1 |  |  |  |  | 1 |  | 4 |  | 4 |  |  | 1 | [7 empty] | 11 | 1000 | 11000
32 | Inlets to be Adjusted with New Frame and Grate | Each |  |  | 4 | [21 empty] | 4 | 1400 | 5600
33 | Inlets to be Reconstructed | Each | [10 empty] | 1 | [13 empty] | 1 | 1500 | 1500
34 | Inlets to be Reconstructed with New Frame and Grate | Each | 2 | [5 empty] | 4 |  |  | 1 | [14 empty] | 7 | 1900 | 13300
35 | Inlet Speicals to be Repaired | Each | [21 empty] | 1 |  |  | 1 | 2200 | 2200
36 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 140 | 40 | 100 | 120 | 105 | 30 | 500 | 40 | 115 | 85 | 130 | 340 | 265 | 1215 | 40 | 25 | 70 |  | 50 | 40 | 75 |  |  | 500 | 4025 | 30 | 120750
37 | Concrete Curb Head | L.F. | [22 empty] | 60 |  | 60 | 25 | 1500
38 | Traffic Control and Protection | Lsum | 0.03 | 0.04 | 0.06 | 0.04 | 0.08 | 0.01 | 0.07 | 0.03 | 0.03 | 0.09 | 0.06 | 0.05 | 0.05 | 0.04 | 0.01 | 0.01 | 0.01 | 0.19 | 0.03 | 0.03 | 0.02 | 0.01 | 0.01 |  | 1 | 20000 | 20000
39 | Thermoplastic Pavement Markings, 4" | L.F. |  | 1385 | 1374 | [21 empty] | 2759 | 2 | 5518
40 | Thermoplastic Pavement Markings, 6" | L.F. |  | 327 | [8 empty] | 58 |  |  | 53 | [6 empty] | 94 |  |  |  | 532 | 2 | 1064
41 | Thermoplastic Pavement Markings, 12" | L.F. | [20 empty] | 126 |  |  |  | 126 | 3 | 378
42 | Thermoplastic Pavement Markings, 24" | L.F. | [13 empty] | 12 | [6 empty] | 19 |  |  |  | 31 | 4 | 124
43 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. |  | 89 | [22 empty] | 89 | 8 | 712
44 | Detector Loops | L.F. | [23 empty] | 100 | 100 | 30 | 3000
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 32970 | 42461 | 75209 | 37570 | 65570 | 12010 | 103875 | 33330 | 30840 | 88765 | 65131 | 94660 | 54030 | 116169 | 10870 | 4850 | 5000 | 203675 | 26000 | 23975 | 15792 | 7000 | 5300 | 89300 | #VALUE!
|  |  | 2583.967 | 3731.4381 | 5256.3668 | 3714.1829 | 7298.9517 | 1108.6469 | 6444.8191 | 2739.2638 | 2652.9878 | 7872.6873 | 5189.5029 | 4829.3005 | 4372.0376 | 3983.7955 | 1035.3123 | 517.6562 | 517.6562 | 17255.2051 | 2588.2808 | 2588.2808 | 1725.5205 | 776.4842 | 517.6562 |  | 1244352
|  |  | 35553.967 | 46192.4381 | 80465.3668 | 41284.1829 | 72868.9517 | 13118.6469 | 110319.8191 | 36069.2638 | 33492.9878 | 96637.6873 | 70320.5029 | 99489.3005 | 58402.0376 | 120152.7955 | 11905.3123 | 5367.6562 | 5517.6562 | 220930.2051 | 28588.2808 | 26563.2808 | 17517.5205 | 7776.4842 | 5817.6562 |  | 1244352
|  |  | 29950 | 43250 | 60925 | 43050 | 84600 | 12850 | 74700 | 31750 | 30750 | 91250 | 60150 | 55975 | 50675 | 46175 | 12000 | 6000 | 6000 | 200000 | 30000 | 30000 | 20000 | 9000 | 6000 | 0 | 1035050
#REF!
|  |  | 0.028936 | 0.041785 | 0.058862 | 0.041592 | 0.081735 | 0.012415 | 0.07217 | 0.030675 | 0.029709 | 0.08816 | 0.058113 | 0.05408 | 0.048959 | 0.044611 | 0.011594 | 0.0057968 | 0.0057968 | 0.19323 | 0.028984 | 0.028984 | 0.019323 | 0.0086952 | 0.0057968 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | TCI CONCRETE
City of Rockford | [5 empty] | ROCKFORD, IL
Bid On: City-Wide Street Repairs Group No. 4 - 2021 (Residential)
Bid No.:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 190 | 25 | 4750 | 240 | 45600 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 30000 | 30000 | 10000 | 10000 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 56 | 60 | 3360 | 55 | 3080 |  | 0 |  | 0
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 50 | 25 | 1250 | 24 | 1200 |  | 0 |  | 0
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 50 | 25 | 1250 | 24 | 1200 |  | 0 |  | 0
6 | Aggregate Base Repair, 10" | S.Y. | 270 | 20 | 5400 | 24 | 6480 |  | 0 |  | 0
7 | Bituminous Materials (Prime Coat) | Gal | 2742 | 3 | 8226 | 0.01 | 27.42 |  | 0 |  | 0
8 | Aggregate (Prime Coat) | Tons | 138.5 | 10 | 1385 | 0.01 | 1.385 |  | 0 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3900 | 65 | 253500 | 68 | 265200 |  | 0 |  | 0
10 | Hot-Mix Asphalt, Hand Method | Tons | 25 | 300 | 7500 | 750 | 18750 |  | 0 |  | 0
11 | P.C.C. Approach Pavement, 6" | S.Y. | 250 | 60 | 15000 | 45 | 11250 |  | 0 |  | 0
12 | P.C.C. Approach Pavement, 8" | S.Y. | 179 | 75 | 13425 | 55 | 9845 |  | 0 |  | 0
13 | P.C.C. Sidewalk, 4" | S.F. | 31125 | 6 | 186750 | 6.2 | 192975 |  | 0 |  | 0
14 | P.C.C. Sidewalk, 5" | S.F. | 500 | 12 | 6000 | 6.5 | 3250 |  | 0 |  | 0
15 | Detectable Warnings, ADA Ramps | S.F. | 670 | 25 | 16750 | 25 | 16750 |  | 0 |  | 0
16 | Class B Patch, Type IV, 10" | S.Y. | 1345 | 125 | 168125 | 110 | 147950 |  | 0 |  | 0
17 | Dowel Bars | Each | 600 | 18 | 10800 | 17 | 10200 |  | 0 |  | 0
18 | No. 6 Transverse Tie Bars | Each | 500 | 15 | 7500 | 10 | 5000 |  | 0 |  | 0
19 | Welded Wire Reinforcement | S.Y. | 1345 | 10 | 13450 | 2 | 2690 |  | 0 |  | 0
20 | Combination Curb and Gutter Removal | L.F. | 4025 | 20 | 80500 | 12 | 48300 |  | 0 |  | 0
21 | Sidewalk Removal | S.F. | 28550 | 2 | 57100 | 1.5 | 42825 |  | 0 |  | 0
22 | Approach Pavement Removal | S.Y. | 379 | 40 | 15160 | 40 | 15160 |  | 0 |  | 0
23 | Surface Removal, 2" | S.Y. | 28425 | 3 | 85275 | 1.75 | 49743.75 |  | 0 |  | 0
24 | Pedestrian Railing | L.F. | 30 | 200 | 6000 | 100 | 3000 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 998456 |  | 910477.555
| Award to TCI CONCRETE | Total |  | As corrected | 998456 |  | 910477.555
25 | Concrete Retaining Wall | S.F. | 101 | 200 | 20200 | 450 | 45450 |  | 0 |  | 0
26 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 4 | 300 | 1200 | 350 | 1400 |  | 0 |  | 0
27 | Manholes to be Adjusted | Each | 37 | 550 | 20350 | 400 | 14800 |  | 0 |  | 0
28 | Manholes to be Adjusted with New Frame and Lid | Each | 19 | 800 | 15200 | 600 | 11400 |  | 0 |  | 0
29 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 | 400 | 400 |  | 0 |  | 0
30 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300 | 600 | 600 |  | 0 |  | 0
31 | Inlets to be Adjusted | Each | 11 | 1000 | 11000 | 600 | 6600 |  | 0 |  | 0
32 | Inlets to be Adjusted with New Frame and Grate | Each | 4 | 1400 | 5600 | 800 | 3200 |  | 0 |  | 0
33 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 | 700 | 700 |  | 0 |  | 0
34 | Inlets to be Reconstructed with New Frame and Grate | Each | 7 | 1900 | 13300 | 900 | 6300 |  | 0 |  | 0
35 | Inlet Speicals to be Repaired | Each | 1 | 2200 | 2200 | 1000 | 1000 |  | 0 |  | 0
36 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 4025 | 30 | 120750 | 50 | 201250 |  | 0 |  | 0
37 | Concrete Curb Head | L.F. | 60 | 25 | 1500 | 200 | 12000 |  | 0 |  | 0
38 | Traffic Control and Protection | Lsum | 1 | 20000 | 20000 | 10000 | 10000 |  | 0 |  | 0
39 | Thermoplastic Pavement Markings, 4" | L.F. | 2759 | 2 | 5518 | 1.4 | 3862.6 |  | 0 |  | 0
40 | Thermoplastic Pavement Markings, 6" | L.F. | 532 | 2 | 1064 | 2.1 | 1117.2 |  | 0 |  | 0
41 | Thermoplastic Pavement Markings, 12" | L.F. | 126 | 3 | 378 | 4.2 | 529.2 |  | 0 |  | 0
42 | Thermoplastic Pavement Markings, 24" | L.F. | 31 | 4 | 124 | 8.4 | 260.4 |  | 0 |  | 0
43 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 89 | 8 | 712 | 8.4 | 747.6 |  | 0 |  | 0
44 | Detector Loops | L.F. | 100 | 30 | 3000 | 34.25 | 3425 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 1244352 |  | 1235519.555
| Award to TCI CONCRETE | Bid |  | As corrected |  |  | 1235519.555 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read
| Award to TCI CONCRETE | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to TCI CONCRETE | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 4 - 2021 (Residential)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 190 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 56 |  | 0
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 50 |  | 0
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 50 |  | 0
6 | Aggregate Base Repair, 10" | S.Y. | 270 |  | 0
7 | Bituminous Materials (Prime Coat) | Gal | 2742 |  | 0
8 | Aggregate (Prime Coat) | Tons | 138.5 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3900 |  | 0
10 | Hot-Mix Asphalt, Hand Method | Tons | 25 |  | 0
11 | P.C.C. Approach Pavement, 6" | S.Y. | 250 |  | 0
12 | P.C.C. Approach Pavement, 8" | S.Y. | 179 |  | 0
13 | P.C.C. Sidewalk, 4" | S.F. | 31125 |  | 0
14 | P.C.C. Sidewalk, 5" | S.F. | 500 |  | 0
15 | Detectable Warnings, ADA Ramps | S.F. | 670 |  | 0
16 | Class B Patch, Type IV, 10" | S.Y. | 1345 |  | 0
17 | Dowel Bars | Each | 600 |  | 0
18 | No. 6 Transverse Tie Bars | Each | 500 |  | 0
19 | Welded Wire Reinforcement | S.Y. | 1345 |  | 0
20 | Combination Curb and Gutter Removal | L.F. | 4025 |  | 0
21 | Sidewalk Removal | S.F. | 28550 |  | 0
22 | Approach Pavement Removal | S.Y. | 379 |  | 0
23 | Surface Removal, 2" | S.Y. | 28425 |  | 0
24 | Pedestrian Railing | L.F. | 30 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Concrete Retaining Wall | S.F. | 101 |  | 0
26 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 4 |  | 0
27 | Manholes to be Adjusted | Each | 37 |  | 0
28 | Manholes to be Adjusted with New Frame and Lid | Each | 19 |  | 0
29 | Manholes to be Reconstructed | Each | 1 |  | 0
30 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 |  | 0
31 | Inlets to be Adjusted | Each | 11 |  | 0
32 | Inlets to be Adjusted with New Frame and Grate | Each | 4 |  | 0
33 | Inlets to be Reconstructed | Each | 1 |  | 0
34 | Inlets to be Reconstructed with New Frame and Grate | Each | 7 |  | 0
35 | Inlet Speicals to be Repaired | Each | 1
36 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 4025
37 | Concrete Curb Head | L.F. | 60
38 | Traffic Control and Protection | Lsum | 1
39 | Thermoplastic Pavement Markings, 4" | L.F. | 2759
40 | Thermoplastic Pavement Markings, 6" | L.F. | 532
41 | Thermoplastic Pavement Markings, 12" | L.F. | 126
42 | Thermoplastic Pavement Markings, 24" | L.F. | 31
43 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 89
44 | Detector Loops | L.F. | 100
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2021 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 190 | 25 | 4750
2 | Parkway Restoration | Lsum | 1 | 30000 | 30000
3 | Inlet and Pipe Protection | Each | 56 | 60 | 3360
4 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 50 | 25 | 1250
5 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 50 | 25 | 1250
6 | Aggregate Base Repair, 10" | S.Y. | 270 | 20 | 5400
7 | Bituminous Materials (Prime Coat) | Gal | 2742 | 3 | 8226
8 | Aggregate (Prime Coat) | Tons | 138.5 | 10 | 1385
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3900 | 65 | 253500
10 | Hot-Mix Asphalt, Hand Method | Tons | 25 | 300 | 7500
11 | P.C.C. Approach Pavement, 6" | S.Y. | 250 | 60 | 15000
12 | P.C.C. Approach Pavement, 8" | S.Y. | 179 | 75 | 13425
13 | P.C.C. Sidewalk, 4" | S.F. | 31125 | 6 | 186750
14 | P.C.C. Sidewalk, 5" | S.F. | 500 | 12 | 6000
15 | Detectable Warnings, ADA Ramps | S.F. | 670 | 25 | 16750
16 | Class B Patch, Type IV, 10" | S.Y. | 1345 | 125 | 168125
17 | Dowel Bars | Each | 600 | 18 | 10800
18 | No. 6 Transverse Tie Bars | Each | 500 | 15 | 7500
19 | Welded Wire Reinforcement | S.Y. | 1345 | 10 | 13450
20 | Combination Curb and Gutter Removal | L.F. | 4025 | 20 | 80500
21 | Sidewalk Removal | S.F. | 28550 | 2 | 57100
22 | Approach Pavement Removal | S.Y. | 379 | 40 | 15160
23 | Surface Removal, 2" | S.Y. | 28425 | 3 | 85275
24 | Pedestrian Railing | L.F. | 30 | 200 | 6000
|  |  |  | Sub Total | 998456
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2021 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Concrete Retaining Wall | S.F. | 101 | 200 | 20200
26 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 4 | 300 | 1200
27 | Manholes to be Adjusted | Each | 37 | 550 | 20350
28 | Manholes to be Adjusted with New Frame and Lid | Each | 19 | 800 | 15200
29 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000
30 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300
31 | Inlets to be Adjusted | Each | 11 | 1000 | 11000
32 | Inlets to be Adjusted with New Frame and Grate | Each | 4 | 1400 | 5600
33 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500
34 | Inlets to be Reconstructed with New Frame and Grate | Each | 7 | 1900 | 13300
35 | Inlet Speicals to be Repaired | Each | 1 | 2200 | 2200
36 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 4025 | 30 | 120750
37 | Concrete Curb Head | L.F. | 60 | 25 | 1500
38 | Traffic Control and Protection | Lsum | 1 | 20000 | 20000
39 | Thermoplastic Pavement Markings, 4" | L.F. | 2759 | 2 | 5518
40 | Thermoplastic Pavement Markings, 6" | L.F. | 532 | 2 | 1064
41 | Thermoplastic Pavement Markings, 12" | L.F. | 126 | 3 | 378
42 | Thermoplastic Pavement Markings, 24" | L.F. | 31 | 4 | 124
43 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 89 | 8 | 712
44 | Detector Loops | L.F. | 100 | 30 | 3000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2021 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2021 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: TCI CONCRETE | P.O. # 19305222 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: ROCKFORD, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2021 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 190 | C.Y. | 45600 |  |  |  |  | 240
2 | Parkway Restoration | 1 | Lsum | 10000 |  |  |  |  | 10000
3 | Inlet and Pipe Protection | 56 | Each | 3080 |  |  | 35 | Each | 55 | 1925
4 | Subbase Granular Material, Type B, CA-2, 6" | 50 | Tons | 1200 |  |  |  |  | 24
5 | Aggregate Base Course, Type B, CA-6, 6" | 50 | Tons | 1200 |  |  |  |  | 24
6 | Aggregate Base Repair, 10" | 270 | S.Y. | 6480 |  |  |  |  | 24
7 | Bituminous Materials (Prime Coat) | 2742 | Gal | 27.42 |  |  |  |  | 0.01
8 | Aggregate (Prime Coat) | 138.5 | Tons | 1.385 |  |  |  |  | 0.01
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 3900 | Tons | 265200 |  |  |  |  | 68
10 | Hot-Mix Asphalt, Hand Method | 25 | Tons | 18750 | 1375 |  | 1400 | Tons | 750 | 1050000
11 | P.C.C. Approach Pavement, 6" | 250 | S.Y. | 11250 |  |  |  |  | 45
12 | P.C.C. Approach Pavement, 8" | 179 | S.Y. | 9845 |  |  |  |  | 55
13 | P.C.C. Sidewalk, 4" | 31125 | S.F. | 192975 |  |  | 2030 | S.F. | 6.2 | 12586
14 | P.C.C. Sidewalk, 5" | 500 | S.F. | 3250 |  |  |  |  | 6.5
15 | Detectable Warnings, ADA Ramps | 670 | S.F. | 16750 |  |  | 292 | S.F. | 25 | 7300
16 | Class B Patch, Type IV, 10" | 1345 | S.Y. | 147950 |  |  |  |  | 110
17 | Dowel Bars | 600 | Each | 10200 | 14494 |  | 15094 | Each | 17 | 256598
18 | No. 6 Transverse Tie Bars | 500 | Each | 5000 |  |  | 500 | Each | 10 | 5000
19 | Welded Wire Reinforcement | 1345 | S.Y. | 2690 | 153 |  | 1498 | S.Y. | 2 | 2996
20 | Combination Curb and Gutter Removal | 4025 | L.F. | 48300 | 11219 |  | 15244 | L.F. | 12 | 182928
21 | Sidewalk Removal | 28550 | S.F. | 42825 |  |  | 292 | S.F. | 1.5 | 438
22 | Approach Pavement Removal | 379 | S.Y. | 15160 |  |  |  |  | 40
23 | Surface Removal, 2" | 28425 | S.Y. | 49743.75 |  |  | 18205 | S.Y. | 1.75 | 31858.75
24 | Pedestrian Railing | 30 | L.F. | 3000 | 683 |  | 713 | L.F. | 100 | 71300
Sub Total |  |  |  | 910477.555 | [5 empty] | 1622929.75
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: TCI CONCRETE | [5 empty] | MUNICIPALITY | City of Rockford
| Address: ROCKFORD, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2021 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Concrete Retaining Wall | 101 | S.F. | 45450 |  |  |  |  | 450
26 | Sanitary Riser/Valve Boxes to be Adjusted | 4 | Each | 1400 |  |  |  |  | 350
27 | Manholes to be Adjusted | 37 | Each | 14800 |  |  |  |  | 400
28 | Manholes to be Adjusted with New Frame and Lid | 19 | Each | 11400 |  |  |  |  | 600
29 | Manholes to be Reconstructed | 1 | Each | 400 |  |  |  |  | 400
30 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 600 | 9 |  | 10 | Each | 600 | 6000
31 | Inlets to be Adjusted | 11 | Each | 6600 |  |  |  |  | 600
32 | Inlets to be Adjusted with New Frame and Grate | 4 | Each | 3200 |  |  |  |  | 800
33 | Inlets to be Reconstructed | 1 | Each | 700 |  |  |  |  | 700
34 | Inlets to be Reconstructed with New Frame and Grate | 7 | Each | 6300 | 1 |  | 8 | Each | 900 | 7200
35 | Inlet Speicals to be Repaired | 1 | Each | 1000 |  |  |  |  | 1000
36 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 4025 | L.F. | 201250 |  |  |  |  | 50
37 | Concrete Curb Head | 60 | L.F. | 12000 |  |  |  |  | 200
38 | Traffic Control and Protection | 1 | Lsum | 10000 |  |  | 1 | Lsum | 10000 | 10000
39 | Thermoplastic Pavement Markings, 4" | 2759 | L.F. | 3862.6 |  |  | 1318 | L.F. | 1.4 | 1845.2
40 | Thermoplastic Pavement Markings, 6" | 532 | L.F. | 1117.2 |  |  | 0.5 | L.F. | 2.1 | 1.05
41 | Thermoplastic Pavement Markings, 12" | 126 | L.F. | 529.2 |  |  |  |  | 4.2
42 | Thermoplastic Pavement Markings, 24" | 31 | L.F. | 260.4 |  |  |  |  | 8.4
43 | Thermoplastic Pavement Markings, Letters and Symbols | 89 | S.F. | 747.6 |  |  |  |  | 8.4
44 | Detector Loops | 100 | L.F. | 3425 |  |  |  |  | 34.25
Total |  |  |  | 1235519.555 | [5 empty] | 1647976
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 1647976
[8 empty] | DEDUCT RETAINAGE | 10% | 164797.6
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 1483178.4
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 1483178.4
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: TCI CONCRETE | [5 empty] | MUNICIPALITY | City of Rockford
| Address: ROCKFORD, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2021 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 1235519.555 | [5 empty] | 1647976
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 1647976
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 1647976
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 1647976
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: TCI CONCRETE | [5 empty] | MUNICIPALITY | City of Rockford
| Address: ROCKFORD, IL | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2021 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 1235519.555 | [5 empty] | 1647976
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 1647976
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 1647976
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 1647976
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | TCI CONCRETE
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.