## Item List
| City -Wide Street Repairs Group No. 6 - 2021 (Parking Lots) | [7 empty] | 330741
Summary Of Quantities |  |  | Parking Fund |  |  | General Maintenance
No. | Item | Units | Parking Lot 2 | Parking Lot 28 | Parking Lot 30 | City Yards Garage | TOTAL QUANTITY | Unit Price | Total
1 | Inlet and Pipe Protection | Each |  | 3 |  |  | 3 | 100 | 300
2 | Aggregate Base Repair, 10" | S.Y. | 177 | 600 | 185 |  | 962 | 25 | 24050
3 | Bituminous Materials (Prime Coat) | Gal | 177 | 315 | 185 | 190 | 867 | 3 | 2601
4 | Aggregate (Prime Coat) | Tons | 17 | 31 | 18 |  | 66 | 10 | 660
5 | Hot-Mis Asphalt Binder Course, IL - 9.5, N50, 1.5" | Tons |  | 300 | 175 | 200 | 675 | 95 | 64125
6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons |  | 300 | 175 | 200 | 675 | 95 | 64125
7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 225 |  |  |  | 225 | 95 | 21375
8 | Hot-Mix Asphalt, Hand Method | Tons |  | 5 |  |  | 5 | 300 | 1500
9 | P.C.C. Approach Pavement, 8" | S.Y. | 36 | 85 | 29 |  | 150 | 80 | 12000
10 | P.C.C. Sidewalk, 4" | S.F. |  | 675 |  |  | 675 | 8 | 5400
11 | Combination Curb and Gutter Removal | L.F. |  | 110 |  |  | 110 | 20 | 2200
12 | Sidewalk Removal | S.F. |  | 675 |  |  | 675 | 3 | 2025
13 | Approach Pavement Removal | S.Y. | 36 | 90 | 29 |  | 155 | 30 | 4650
14 | Surface Removal, 2" | S.Y. | 1775 | 3150 | 1800 |  | 6725 | 4 | 26900
15 | Concrete Surface Removal, Butt Joints, 1.5" | S.Y. |  |  |  | 1000 | 1000 | 10 | 10000
16 | Storm Sewers PVC, 6" | L.F. |  | 60 |  |  | 60 | 60 | 3600
17 | Storm Sewers PVC, 10" | L.F. |  | 15 |  |  | 15 | 60 | 900
18 | Storm Sewers PVC, 15" | L.F. |  | 218 |  |  | 218 | 60 | 13080
19 | Storm Sewer Pipe Removal | L.F. |  | 15 |  |  | 15 | 20 | 300
20 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each |  | 2 |  |  | 2 | 3000 | 6000
21 | Storm Manhole, Type A, 6' Diameter, Open Lid | Each |  | 1 |  |  | 1 | 5000 | 5000
22 | Storm Inlet, Type 700 | Each |  | 1 |  |  | 1 | 3000 | 3000
23 | Manhole to be Removed | Each |  | 1 |  |  | 1 | 1000 | 1000
24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. |  | 110 |  |  | 110 | 50 | 5500
25 | Underground Conduit, 2" | L.F. |  | 350 | 260 |  | 610 | 5 | 3050
26 | Traffic Control and Protection | LSum | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 5000 | 5000
27 | Thermoplastic Pavement Markings, 4" | L.F. | 1833 | 1876 | 941 |  | 4650 | 2 | 9300
28 | Accessible Parking Symbol Striping | Each | 4 | 2 | 2 |  | 8 | 200 | 1600
29 | Connect to Existing Down Spout | Each |  | 5 |  |  | 5 | 500 | 2500
30 | Subgrade Undercutting | C.Y. |  | 200 |  |  | 200 | 100 | 20000
31 | Concrete Surface Removal, 1" | S.Y. |  |  |  | 900 | 900 | 10 | 9000
32 | [7 empty] | 0
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 43277 | 174812 | 53832 | 58820 | #VALUE!
330741
271921
|  |  | 50000 | 175000 | 60000 | 50000 | 335000
#REF!
|  |  | 0.14925 | 0.52239 | 0.1791 | 0.14925

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Rock Road Companies |  | William Charles Construction | [7 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Janesville, WI |  | Rockford, IL | [7 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 6 - 2021 (Parking Lots) | [15 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 921-PW-073 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Inlet and Pipe Protection | Each | 3 | 100 | 300 | 155 | 465 | 155.58 | 466.74 |  | 0 |  | 0 |  | 0 | 1 | Inlet and Pipe Protection | Each | 3 | 100 | 300 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Inlet and Pipe Protection | Each | 3 | 100 | 300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Aggregate Base Repair, 10" | S.Y. | 962 | 25 | 24050 | 19 | 18278 | 0.01 | 9.62 |  | 0 |  | 0 |  | 0 | 2 | Aggregate Base Repair, 10" | S.Y. | 962 | 25 | 24050 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Aggregate Base Repair, 10" | S.Y. | 962 | 25 | 24050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Bituminous Materials (Prime Coat) | Gal | 867 | 3 | 2601 | 0.01 | 8.67 | 1.87 | 1621.29 |  | 0 |  | 0 |  | 0 | 3 | Bituminous Materials (Prime Coat) | Gal | 867 | 3 | 2601 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Bituminous Materials (Prime Coat) | Gal | 867 | 3 | 2601 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Aggregate (Prime Coat) | Tons | 66 | 10 | 660 | 0.01 | 0.66 | 0.01 | 0.66 |  | 0 |  | 0 |  | 0 | 4 | Aggregate (Prime Coat) | Tons | 66 | 10 | 660 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate (Prime Coat) | Tons | 66 | 10 | 660 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Hot-Mis Asphalt Binder Course, IL - 9.5, N50, 1.5" | Tons | 675 | 95 | 64125 | 84 | 56700 | 70.55 | 47621.25 |  | 0 |  | 0 |  | 0 | 5 | Hot-Mis Asphalt Binder Course, IL - 9.5, N50, 1.5" | Tons | 675 | 95 | 64125 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Hot-Mis Asphalt Binder Course, IL - 9.5, N50, 1.5" | Tons | 675 | 95 | 64125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 675 | 95 | 64125 | 86 | 58050 | 75.22 | 50773.5 |  | 0 |  | 0 |  | 0 | 6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 675 | 95 | 64125 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 675 | 95 | 64125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 225 | 95 | 21375 | 86 | 19350 | 79.55 | 17898.75 |  | 0 |  | 0 |  | 0 | 7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 225 | 95 | 21375 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 225 | 95 | 21375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Hot-Mix Asphalt, Hand Method | Tons | 5 | 300 | 1500 | 275 | 1375 | 525 | 2625 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt, Hand Method | Tons | 5 | 300 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt, Hand Method | Tons | 5 | 300 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | P.C.C. Approach Pavement, 8" | S.Y. | 150 | 80 | 12000 | 90.39 | 13558.5 | 98.83 | 14824.5 |  | 0 |  | 0 |  | 0 | 9 | P.C.C. Approach Pavement, 8" | S.Y. | 150 | 80 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | P.C.C. Approach Pavement, 8" | S.Y. | 150 | 80 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | P.C.C. Sidewalk, 4" | S.F. | 675 | 8 | 5400 | 13.25 | 8943.75 | 6.18 | 4171.5 |  | 0 |  | 0 |  | 0 | 10 | P.C.C. Sidewalk, 4" | S.F. | 675 | 8 | 5400 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | P.C.C. Sidewalk, 4" | S.F. | 675 | 8 | 5400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Combination Curb and Gutter Removal | L.F. | 110 | 20 | 2200 | 36.85 | 4053.5 | 24.41 | 2685.1 |  | 0 |  | 0 |  | 0 | 11 | Combination Curb and Gutter Removal | L.F. | 110 | 20 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Combination Curb and Gutter Removal | L.F. | 110 | 20 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | Sidewalk Removal | S.F. | 675 | 3 | 2025 | 5 | 3375 | 4.17 | 2814.75 |  | 0 |  | 0 |  | 0 | 12 | Sidewalk Removal | S.F. | 675 | 3 | 2025 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | Sidewalk Removal | S.F. | 675 | 3 | 2025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | Approach Pavement Removal | S.Y. | 155 | 30 | 4650 | 43.5 | 6742.5 | 33.29 | 5159.95 |  | 0 |  | 0 |  | 0 | 13 | Approach Pavement Removal | S.Y. | 155 | 30 | 4650 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | Approach Pavement Removal | S.Y. | 155 | 30 | 4650 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | Surface Removal, 2" | S.Y. | 6725 | 4 | 26900 | 3.44 | 23134 | 4.25 | 28581.25 |  | 0 |  | 0 |  | 0 | 14 | Surface Removal, 2" | S.Y. | 6725 | 4 | 26900 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | Surface Removal, 2" | S.Y. | 6725 | 4 | 26900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Concrete Surface Removal, Butt Joints, 1.5" | S.Y. | 1000 | 10 | 10000 | 5.6 | 5600 | 6.45 | 6450 |  | 0 |  | 0 |  | 0 | 15 | Concrete Surface Removal, Butt Joints, 1.5" | S.Y. | 1000 | 10 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Concrete Surface Removal, Butt Joints, 1.5" | S.Y. | 1000 | 10 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Storm Sewers PVC, 6" | L.F. | 60 | 60 | 3600 | 44 | 2640 | 108.57 | 6514.2 |  | 0 |  | 0 |  | 0 | 16 | Storm Sewers PVC, 6" | L.F. | 60 | 60 | 3600 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Storm Sewers PVC, 6" | L.F. | 60 | 60 | 3600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Storm Sewers PVC, 10" | L.F. | 15 | 60 | 900 | 62 | 930 | 129.02 | 1935.3 |  | 0 |  | 0 |  | 0 | 17 | Storm Sewers PVC, 10" | L.F. | 15 | 60 | 900 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Storm Sewers PVC, 10" | L.F. | 15 | 60 | 900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Storm Sewers PVC, 15" | L.F. | 218 | 60 | 13080 | 78 | 17004 | 119.61 | 26074.98 |  | 0 |  | 0 |  | 0 | 18 | Storm Sewers PVC, 15" | L.F. | 218 | 60 | 13080 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Storm Sewers PVC, 15" | L.F. | 218 | 60 | 13080 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Storm Sewer Pipe Removal | L.F. | 15 | 20 | 300 | 21 | 315 | 10.96 | 164.4 |  | 0 |  | 0 |  | 0 | 19 | Storm Sewer Pipe Removal | L.F. | 15 | 20 | 300 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Storm Sewer Pipe Removal | L.F. | 15 | 20 | 300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 2 | 3000 | 6000 | 3100 | 6200 | 2370.83 | 4741.66 |  | 0 |  | 0 |  | 0 | 20 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 2 | 3000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 2 | 3000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Storm Manhole, Type A, 6' Diameter, Open Lid | Each | 1 | 5000 | 5000 | 9200 | 9200 | 5915.89 | 5915.89 |  | 0 |  | 0 |  | 0 | 21 | Storm Manhole, Type A, 6' Diameter, Open Lid | Each | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Storm Manhole, Type A, 6' Diameter, Open Lid | Each | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Storm Inlet, Type 700 | Each | 1 | 3000 | 3000 | 2900 | 2900 | 2935.43 | 2935.43 |  | 0 |  | 0 |  | 0 | 22 | Storm Inlet, Type 700 | Each | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Storm Inlet, Type 700 | Each | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Manhole to be Removed | Each | 1 | 1000 | 1000 | 500 | 500 | 201.71 | 201.71 |  | 0 |  | 0 |  | 0 | 23 | Manhole to be Removed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Manhole to be Removed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 110 | 50 | 5500 | 41 | 4510 | 38.91 | 4280.1 |  | 0 |  | 0 |  | 0 | 24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 110 | 50 | 5500 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 110 | 50 | 5500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 280291 |  | 263833.58 |  | 238467.53 | [7 empty] | Page 3 | Sub |  | As read | 280291 | [9 empty] | Page 1 | Sub |  | As read | 280291
| Award to Rock Road Companies | Total |  | As corrected | 280291 |  | 263833.58 |  | 238467.53 | [7 empty] | Award to Rock Road Companies | Total |  | As corrected | 280291 | [9 empty] | Award to Rock Road Companies | Total |  | As corrected | 280291
25 | Underground Conduit, 2" | L.F. | 610 | 5 | 3050 | 17.98 | 10967.8 | 14.21 | 8668.1 |  | 0 |  | 0 |  | 0 | 25 | Underground Conduit, 2" | L.F. | 610 | 5 | 3050 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Underground Conduit, 2" | L.F. | 610 | 5 | 3050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Traffic Control and Protection | LSum | 1 | 5000 | 5000 | 5100 | 5100 | 45736.28 | 45736.28 |  | 0 |  | 0 |  | 0 | 26 | Traffic Control and Protection | LSum | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Traffic Control and Protection | LSum | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Thermoplastic Pavement Markings, 4" | L.F. | 4650 | 2 | 9300 | 1.75 | 8137.5 | 1.76 | 8184 |  | 0 |  | 0 |  | 0 | 27 | Thermoplastic Pavement Markings, 4" | L.F. | 4650 | 2 | 9300 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Thermoplastic Pavement Markings, 4" | L.F. | 4650 | 2 | 9300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Accessible Parking Symbol Striping | Each | 8 | 200 | 1600 | 360 | 2880 | 363.02 | 2904.16 |  | 0 |  | 0 |  | 0 | 28 | Accessible Parking Symbol Striping | Each | 8 | 200 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Accessible Parking Symbol Striping | Each | 8 | 200 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Connect to Existing Down Spout | Each | 5 | 500 | 2500 | 825 | 4125 | 197.39 | 986.95 |  | 0 |  | 0 |  | 0 | 29 | Connect to Existing Down Spout | Each | 5 | 500 | 2500 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Connect to Existing Down Spout | Each | 5 | 500 | 2500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Subgrade Undercutting | C.Y. | 200 | 100 | 20000 | 25 | 5000 | 0.01 | 2 |  | 0 |  | 0 |  | 0 | 30 | Subgrade Undercutting | C.Y. | 200 | 100 | 20000 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Subgrade Undercutting | C.Y. | 200 | 100 | 20000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Concrete Surface Removal, 1" | S.Y. | 900 | 10 | 9000 | 11.5 | 10350 | 15 | 13500 |  | 0 |  | 0 |  | 0 | 31 | Concrete Surface Removal, 1" | S.Y. | 900 | 10 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Concrete Surface Removal, 1" | S.Y. | 900 | 10 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 330741 |  | 310393.88 |  | 318449.02 | [7 empty] | Page 4 | Total |  | As read | 330741 | [9 empty] | Page 2 | Total |  | As read | 330741
| Award to Rock Road Companies | Bid |  | As corrected |  |  | 310393.88 | 0 | 318449.02 | 0 |  |  | 715415 |  |  |  | Award to Rock Road Companies | Bid |  | As corrected | #VALUE! | [9 empty] | Award to Rock Road Companies | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Rock Road Companies | Bid |  | As corrected | [12 empty] | Award to Rock Road Companies | Bid |  | As corrected | [10 empty] | Award to Rock Road Companies | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Rock Road Companies | Bid |  | As corrected | [12 empty] | Award to Rock Road Companies | Bid |  | As corrected | [10 empty] | Award to Rock Road Companies | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 6 - 2021 (Parking Lots)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Inlet and Pipe Protection | Each | 3 |  | 0
2 | Aggregate Base Repair, 10" | S.Y. | 962 |  | 0
3 | Bituminous Materials (Prime Coat) | Gal | 867 |  | 0
4 | Aggregate (Prime Coat) | Tons | 66 |  | 0
5 | Hot-Mis Asphalt Binder Course, IL - 9.5, N50, 1.5" | Tons | 675 |  | 0
6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 675 |  | 0
7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 225 |  | 0
8 | Hot-Mix Asphalt, Hand Method | Tons | 5 |  | 0
9 | P.C.C. Approach Pavement, 8" | S.Y. | 150 |  | 0
10 | P.C.C. Sidewalk, 4" | S.F. | 675 |  | 0
11 | Combination Curb and Gutter Removal | L.F. | 110 |  | 0
12 | Sidewalk Removal | S.F. | 675 |  | 0
13 | Approach Pavement Removal | S.Y. | 155 |  | 0
14 | Surface Removal, 2" | S.Y. | 6725 |  | 0
15 | Concrete Surface Removal, Butt Joints, 1.5" | S.Y. | 1000 |  | 0
16 | Storm Sewers PVC, 6" | L.F. | 60 |  | 0
17 | Storm Sewers PVC, 10" | L.F. | 15 |  | 0
18 | Storm Sewers PVC, 15" | L.F. | 218 |  | 0
19 | Storm Sewer Pipe Removal | L.F. | 15 |  | 0
20 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 2 |  | 0
21 | Storm Manhole, Type A, 6' Diameter, Open Lid | Each | 1 |  | 0
22 | Storm Inlet, Type 700 | Each | 1 |  | 0
23 | Manhole to be Removed | Each | 1 |  | 0
24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 110 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Underground Conduit, 2" | L.F. | 610 |  | 0
26 | Traffic Control and Protection | LSum | 1
27 | Thermoplastic Pavement Markings, 4" | L.F. | 4650
28 | Accessible Parking Symbol Striping | Each | 8
29 | Connect to Existing Down Spout | Each | 5
30 | Subgrade Undercutting | C.Y. | 200
31 | Concrete Surface Removal, 1" | S.Y. | 900
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 6 - 2021 (Parking Lots)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Inlet and Pipe Protection | Each | 3 | 100 | 300
2 | Aggregate Base Repair, 10" | S.Y. | 962 | 25 | 24050
3 | Bituminous Materials (Prime Coat) | Gal | 867 | 3 | 2601
4 | Aggregate (Prime Coat) | Tons | 66 | 10 | 660
5 | Hot-Mis Asphalt Binder Course, IL - 9.5, N50, 1.5" | Tons | 675 | 95 | 64125
6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 675 | 95 | 64125
7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 225 | 95 | 21375
8 | Hot-Mix Asphalt, Hand Method | Tons | 5 | 300 | 1500
9 | P.C.C. Approach Pavement, 8" | S.Y. | 150 | 80 | 12000
10 | P.C.C. Sidewalk, 4" | S.F. | 675 | 8 | 5400
11 | Combination Curb and Gutter Removal | L.F. | 110 | 20 | 2200
12 | Sidewalk Removal | S.F. | 675 | 3 | 2025
13 | Approach Pavement Removal | S.Y. | 155 | 30 | 4650
14 | Surface Removal, 2" | S.Y. | 6725 | 4 | 26900
15 | Concrete Surface Removal, Butt Joints, 1.5" | S.Y. | 1000 | 10 | 10000
16 | Storm Sewers PVC, 6" | L.F. | 60 | 60 | 3600
17 | Storm Sewers PVC, 10" | L.F. | 15 | 60 | 900
18 | Storm Sewers PVC, 15" | L.F. | 218 | 60 | 13080
19 | Storm Sewer Pipe Removal | L.F. | 15 | 20 | 300
20 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 2 | 3000 | 6000
21 | Storm Manhole, Type A, 6' Diameter, Open Lid | Each | 1 | 5000 | 5000
22 | Storm Inlet, Type 700 | Each | 1 | 3000 | 3000
23 | Manhole to be Removed | Each | 1 | 1000 | 1000
24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 110 | 50 | 5500
|  |  |  | Sub Total | 280291
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 6 - 2021 (Parking Lots)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Underground Conduit, 2" | L.F. | 610 | 5 | 3050
26 | Traffic Control and Protection | LSum | 1 | 5000 | 5000
27 | Thermoplastic Pavement Markings, 4" | L.F. | 4650 | 2 | 9300
28 | Accessible Parking Symbol Striping | Each | 8 | 200 | 1600
29 | Connect to Existing Down Spout | Each | 5 | 500 | 2500
30 | Subgrade Undercutting | C.Y. | 200 | 100 | 20000
31 | Concrete Surface Removal, 1" | S.Y. | 900 | 10 | 9000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 6 - 2021 (Parking Lots)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 6 - 2021 (Parking Lots)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | P.O. #18305125 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: Janesville, WI | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 6 - 2021 (Parking Lots)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Inlet and Pipe Protection | 3 | Each | 465 |  |  |  |  | 155
2 | Aggregate Base Repair, 10" | 962 | S.Y. | 18278 |  |  |  |  | 19
3 | Bituminous Materials (Prime Coat) | 867 | Gal | 8.67 |  |  |  |  | 0.01
4 | Aggregate (Prime Coat) | 66 | Tons | 0.66 |  |  |  |  | 0.01
5 | Hot-Mis Asphalt Binder Course, IL - 9.5, N50, 1.5" | 675 | Tons | 56700 |  |  |  |  | 84
6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | 675 | Tons | 58050 |  |  |  |  | 86
7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 225 | Tons | 19350 |  |  |  |  | 86
8 | Hot-Mix Asphalt, Hand Method | 5 | Tons | 1375 |  |  |  |  | 275
9 | P.C.C. Approach Pavement, 8" | 150 | S.Y. | 13558.5 |  |  |  |  | 90.39
10 | P.C.C. Sidewalk, 4" | 675 | S.F. | 8943.75 |  |  |  |  | 13.25
11 | Combination Curb and Gutter Removal | 110 | L.F. | 4053.5 |  |  |  |  | 36.85
12 | Sidewalk Removal | 675 | S.F. | 3375 |  |  |  |  | 5
13 | Approach Pavement Removal | 155 | S.Y. | 6742.5 |  |  |  |  | 43.5
14 | Surface Removal, 2" | 6725 | S.Y. | 23134 |  |  |  |  | 3.44
15 | Concrete Surface Removal, Butt Joints, 1.5" | 1000 | S.Y. | 5600 |  |  |  |  | 5.6
16 | Storm Sewers PVC, 6" | 60 | L.F. | 2640 |  |  |  |  | 44
17 | Storm Sewers PVC, 10" | 15 | L.F. | 930 |  |  |  |  | 62
18 | Storm Sewers PVC, 15" | 218 | L.F. | 17004 |  |  |  |  | 78
19 | Storm Sewer Pipe Removal | 15 | L.F. | 315 |  |  |  |  | 21
20 | Storm Manhole, Type A, 4' Diameter, Open Lid | 2 | Each | 6200 |  |  |  |  | 3100
21 | Storm Manhole, Type A, 6' Diameter, Open Lid | 1 | Each | 9200 |  |  |  |  | 9200
22 | Storm Inlet, Type 700 | 1 | Each | 2900 |  |  |  |  | 2900
23 | Manhole to be Removed | 1 | Each | 500 |  |  |  |  | 500
24 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 110 | L.F. | 4510 |  |  |  |  | 41
Sub Total |  |  |  | 263833.58 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, WI | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 6 - 2021 (Parking Lots)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Underground Conduit, 2" | 610 | L.F. | 10967.8 |  |  |  |  | 17.98
26 | Traffic Control and Protection | 1 | LSum | 5100 |  |  |  |  | 5100
27 | Thermoplastic Pavement Markings, 4" | 4650 | L.F. | 8137.5 |  |  |  |  | 1.75
28 | Accessible Parking Symbol Striping | 8 | Each | 2880 |  |  |  |  | 360
29 | Connect to Existing Down Spout | 5 | Each | 4125 |  |  |  |  | 825
30 | Subgrade Undercutting | 200 | C.Y. | 5000 |  |  |  |  | 25
31 | Concrete Surface Removal, 1" | 900 | S.Y. | 10350 |  |  |  |  | 11.5
Total |  |  |  | 310393.88 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
[8 empty] | DEDUCT RETAINAGE | 10% | 0
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, WI | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 6 - 2021 (Parking Lots)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 310393.88 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, WI | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 6 - 2021 (Parking Lots)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 310393.88 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Rock Road Companies
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.