## Item List
| City -Wide Street Repairs Group No. 2 - 2021 (Concrete) | [47 empty] | 1848594
Summary Of Quantities |  |  | 94003001 | 2nd Ward - 94003002 |  |  |  | 2nd Ward - 94003002 |  |  |  |  | 94003002 | 3rd Ward - 94003003 |  |  | 94003004 | 94003005 | 94003006 | 94003008 | 9th Ward - 94003009 |  | 9th Ward - 94003009 |  | 11th Ward - 94003011 |  |  | 11th Ward - 94003011 |  |  |  |  | 11th Ward - 94003011 |  |  |  | 94003012 | 94003012 | 13th Ward - 94003013 |  |  |  | Neighborhood - 2111 |  | 2155
No. | Item | Units | 1770 Sweetbriar Lane Curb and Gutter | 1400 Crosby Street | 1548 Crosby Street Sidewalk | 2001 East State Street Sidewalk | 3920 Guilford Road Curb and Gutter | 811 Lundvall Avenue Sidewalk | 832 Paris Avenue Sidewalk | 315 Regan Street Sidewalk | 304 South Chicago Avenue Sidewalk | 218 South Highland Avenue Sidewalk | 703 Tamarack Lane Sidewalk | 0100 Ellsworth Place | 2600 Green Apple Lane | Rural Street/Joslyn Street Curb | 3400/3600 Sage Drive Curb and Gutter | 0800 Sanford Street | 1700 Reed Avenue | 1700 Nixon Court | 2600/2700 Conklin Drive Sidewalk | 1727 Grant Avenue Approach | Midway Drive Sidewalk | Packard Parkway Sidewalk | 2000 18th Avenue | 1726 South 4th Street Sidewalk | 1309 South 5th Street Sidewalk | 1006 South 6th Street Sidewalk | 1527 8th Street Sidewalk | 2214-2220 9th Street Sidewalk | 833-837 10th Street Sidewalk | 612 16th Avenue Sidewalk | 2120 17th Avenue Sidewalk | 1803 17th Street Sidewalk | 811 18th Avenue Sidewalk | 828 18th Avenue Sidewalk | 2000 Clinton Street Curb and Gutter | 2600 Landstrom Road Storm Sewer | 1700 Andrews Street | 2200 Chestnut Street | 2100 Mulberry Street | 1100 Selden Street Curb and Gutter | Lindberg Drive/Lindale Road/23rd Street | 0700/0800 Westchester Drive | Glenwood Avenue Curve Recon | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Tree Removal (6 to 15 Inch Diameter) | Unit Dia | [16 empty] | 15 | [18 empty] | 64 |  | 15 | [6 empty] | 94 | 150 | 14100
2 | Tree Removal (Over 15 Inch Diameter) | Unit Dia | [16 empty] | 36 | [27 empty] | 36 | 200 | 7200
3 | Earth Excavation | C.Y. |  |  |  |  | 20 | [11 empty] | 755 |  | 60 |  | 30 | 16 | [18 empty] | 510 | 25 | 475 |  | 1891 | 30 | 56730
4 | Top Soil Furnish and Place | C.Y. | [35 empty] | 25 | [8 empty] | 25 | 200 | 5000
5 | Parkway Restoration | Lsum | 0.01 | 0.07 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.02 | 0.01 | 0.02 | 0.06 | 0.07 | 0.02 | 0.03 | 0 | 0.01 | 0.01 | 0.06 | 0.01 | 0 | 0.01 | 0 | 0.01 | 0.01 | 0.01 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.03 | 0.03 | 0.03 | 0.01 | 0.15 | 0.11 | 0.05 |  | 1 | 50000 | 50000
6 | Inlet and Pipe Protection | Each |  | 3 | [9 empty] | 2 |  |  |  | 5 |  | 4 | 2 | [17 empty] | 2 | 6 | 7 |  | 2 | 4 |  |  | 37 | 60 | 2220
7 | Stone Rip Rap | Tons | [40 empty] | 40 |  |  |  | 40 | 30 | 1200
8 | Subbase Granular Material, Type B, CA-2, 6" | Tons | [16 empty] | 425 | [25 empty] | 325 |  | 750 | 22 | 16500
9 | Aggregate Base Course, Type B, CA-6, 6" | Tons | [16 empty] | 425 | [25 empty] | 325 |  | 750 | 22 | 16500
10 | Aggregate Base Repair, 10" | S.Y. |  | 17 | [9 empty] | 11 |  |  |  | 14 |  | 4 |  |  |  |  | 15 | [13 empty] | 11 | 11 | 15 | 3 | 60 | 31 |  |  | 192 | 20 | 3840
11 | Bituminous Materials (Prime Coat) | Gal |  | 175 | [9 empty] | 110 |  |  |  | 140 | 125 | 40 |  |  |  |  | 150 | [13 empty] | 110 | 115 | 155 | 35 | 600 | 315 | 95 |  | 2165 | 3 | 6495
12 | Aggregate (Prime Coat) | Tons |  | 9 | [9 empty] | 6 |  |  |  | 7 | 6 | 2 |  |  |  |  | 7 | [13 empty] | 6 | 6 | 8 | 2 | 30 | 16 | 10 |  | 115 | 10 | 1150
13 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | [43 empty] | 500 | 500 | 65 | 32500
14 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | [16 empty] | 325 | [25 empty] | 225 |  | 550 | 65 | 35750
15 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons |  | 225 | [9 empty] | 150 |  | 25 |  | 175 | 175 | 50 |  |  |  |  | 200 | [13 empty] | 150 | 150 | 200 | 50 | 750 | 400 | 125 | 500 | 3325 | 65 | 216125
16 | Hot-Mix Asphalt, Hand Method | Tons | 5 |  |  |  | 5 |  | 3 | 3 |  |  |  |  | 15 |  | 20 |  |  |  | 10 |  | 5 | [23 empty] | 66 | 300 | 19800
17 | P.C.C. Approach Pavement, 6" | S.Y. |  | 64 | [5 empty] | 25 |  | 11 |  | 47 | 133 |  | 27 | 88 | 58 | 21 | 43 | 7 | 13 |  | 36 |  |  |  | 15 | [5 empty] | 18 |  |  | 21 | 19 | 112 | 104 | 13 | 424 | 297 | 81 | 50 | 1727 | 50 | 86350
18 | P.C.C. Approach Pavement, 8" | S.Y. |  | 102 | [13 empty] | 27 | 28 | [20 empty] | 59 |  |  |  | 54 |  | 50 | 320 | 60 | 19200
19 | P.C.C. Sidewalk, 4" | S.F. |  | 3275 | 225 | 250 |  | 250 | 425 | 675 | 650 | 325 | 350 | 350 |  | 350 | 100 | 4900 | 2725 | 450 | 3650 | 150 | 1675 | 675 | 4600 | 600 | 350 | 500 | 500 | 675 | 675 | 400 | 225 | 725 | 200 | 500 | 80 |  | 2825 | 2600 | 3975 | 225 |  | 6125 | 1150 | 5000 | 53380 | 5 | 266900
20 | Detectable Warnings, ADA Ramps | S.F. |  | 50 | [11 empty] | 10 |  | 80 | 40 | 20 | 80 |  | 80 |  | 120 | [8 empty] | 20 |  | 20 |  |  | 20 | 80 | 160 |  |  | 80 |  |  | 860 | 20 | 17200
21 | Combination Curb and Gutter Removal | L.F. | 50 | 1105 |  |  | 140 |  | 85 | 60 |  | 20 |  | 295 | 435 | 70 | 435 | 770 | 20 | 215 | 170 | 25 | 100 |  | 850 |  |  |  | 20 |  |  |  |  | 30 | 20 | 40 | 240 |  | 530 | 780 | 810 | 365 |  | 2060 | 545 | 1000 | 11285 | 10 | 112850
22 | Sidewalk Removal | S.F. |  | 3350 | 225 | 250 |  | 250 | 425 | 675 | 650 | 325 | 350 | 350 |  | 400 | 100 | 4900 |  | 450 | 975 | 150 | 375 |  | 4600 | 600 | 350 | 500 | 500 | 675 | 675 | 400 | 225 | 725 | 200 | 500 | 80 |  | 2900 | 1800 | 3975 | 225 |  | 4925 | 1150 | 5000 | 44205 | 2 | 88410
23 | Approach Pavement Removal | S.Y. |  | 166 | [5 empty] | 25 |  | 11 |  | 47 | 133 |  | 27 | 115 | 86 | 21 | 43 | 7 | 13 |  | 61 |  |  |  | 15 | [5 empty] | 18 |  |  | 21 | 19 | 171 | 122 | 13 | 424 | 351 | 81 | 100 | 2090 | 20 | 41800
24 | Surface Removal, 2" | S.Y. |  | 1750 | [9 empty] | 1100 |  | 150 |  | 1400 |  | 400 |  |  |  |  | 1500 | [13 empty] | 1100 | 1150 | 1550 | 850 | 6000 | 3150 |  | 1000 | 21100 | 3 | 63300
25 | Surface Removal, Butt Joints | S.Y. | [43 empty] | 100 | 100 | 7 | 700
26 | Storm Sewers PVC, 10" | L.F. | [17 empty] | 42 | [26 empty] | 42 | 80 | 3360
27 | Storm Sewers PVC, 18" | L.F. | [40 empty] | 914 |  |  |  | 914 | 60 | 54840
28 | Storm Sewers PVC, 24" | L.F. | [35 empty] | 194 | [8 empty] | 194 | 60 | 11640
29 | Storm Sewers PVC, 18" | L.F. | [40 empty] | 53 |  |  |  | 53 | 100 | 5300
30 | Storm Sewers Removal | L.F. | [35 empty] | 50 |  |  |  |  | 130 |  |  |  | 180 | 20 | 3600
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | [35 empty] | 2 |  |  |  |  | 2 |  |  |  | 4 | 3000 | 12000
32 | Storm Inlet, Type 700 | Each | [17 empty] | 2 | [26 empty] | 2 | 3000 | 6000
33 | Storm Inlet, Inlet Special No. 2 | Each | [40 empty] | 4 |  |  |  | 4 | 3000 | 12000
34 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [38 empty] | 1 | [5 empty] | 1 | 300 | 300
35 | Manholes to be Adjusted | Each |  | 3 | [11 empty] | 1 |  | 1 | 3 | [5 empty] | 5 | [13 empty] | 1 | 1 | 2 |  | 1 | 6 |  |  | 24 | 550 | 13200
36 | Manholes to be Adjusted with New Frame and Lid | Each | [15 empty] | 1 |  | 2 |  |  |  |  | 3 | [13 empty] | 2 |  | 2 |  |  | 3 | 2 |  | 15 | 800 | 12000
37 | Manholes to be Reconstructed | Each | [43 empty] | 1 | 1 | 1000 | 1000
38 | Manholes to be Reconstructed with New Frame and Lid | Each | [43 empty] | 1 | 1 | 1300 | 1300
39 | Inlets to be Adjusted | Each | [37 empty] | 4 | 2 |  | 1 | 4 |  |  | 11 | 1500 | 16500
40 | Inlets to be Adjusted with New Frame and Grate | Each |  | 1 | [11 empty] | 2 |  |  | 1 | 2 | [20 empty] | 1 |  | 1 |  |  |  | 8 | 1400 | 11200
41 | Inlets to be Reconstructed | Each | [43 empty] | 1 | 1 | 1500 | 1500
42 | Inlets to be Reconstructed with New Frame and Grate | Each |  | 3 | [9 empty] | 1 |  |  |  | 4 | [6 empty] | 6 | [15 empty] | 1 | [5 empty] | 15 | 1900 | 28500
43 | Inlet Special to be Repaired | Each | [43 empty] | 1 | 1 | 2200 | 2200
44 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 50 | 1105 |  |  | 140 |  | 85 | 60 |  | 20 |  | 295 | 435 | 70 | 435 | 770 | 580 | 215 | 170 | 25 | 100 |  | 850 |  |  |  | 20 |  |  |  |  | 30 | 20 | 40 | 240 |  | 530 | 780 | 810 | 365 | 4570 | 2060 | 545 | 1000 | 16415 | 25 | 410375
45 | Remove and Replace Chain Link Fence | L.F. | [40 empty] | 450 |  |  |  | 450 | 20 | 9000
46 | Traffic Control and Protection | LSum | 0.01 | 0.07 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.02 | 0.01 | 0.02 | 0.06 | 0.07 | 0.02 | 0.03 | 0 | 0.01 | 0.01 | 0.06 | 0.01 | 0 | 0.01 | 0 | 0.01 | 0.01 | 0.01 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.03 | 0.03 | 0.03 | 0.01 | 0.15 | 0.11 | 0.05 |  | 1 | 25000 | 25000
47 | Thermoplastic Pavement Markings, 4" | L.F. | [42 empty] | 530 |  | 530 | 2.5 | 1325
48 | Thermoplastic Pavement Markings, 6" | L.F. |  | 54 | [42 empty] | 54 | 4 | 216
49 | Thermoplastic Pavement Markings, 24" | L.F. | [36 empty] | 14 | [7 empty] | 14 | 12 | 168
50 | Removal and Replacement of Brick Pavers | S.F. | [34 empty] | 950 | [9 empty] | 950 | 15 | 14250
51 | Subgrade Undercutting | C.Y. | [43 empty] | 50 | 50 | 200 | 10000
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 4000 | 110616 | 1575 | 2500 | 7750 | 2500 | 7600 | 10225 | 5300 | 4495 | 3200 | 33245 | 30535 | 11375 | 25315 | 101265 | 127460 | 32715 | 37930 | 2415 | 18285 | 4605 | 106740 | 4950 | 2450 | 4250 | 5250 | 5475 | 5475 | 3550 | 1575 | 7275 | 4110 | 6050 | 23960 | 35460 | 58553 | 83295 | 97480 | 21995 | 335040 | 197400 | 91155 | 162200 | #VALUE!
1848594
|  |  | 4000 | 110616 | 1575 | 2500 | 7750 | 2500 | 7600 | 10225 | 5300 | 4495 | 3200 | 33245 | 30535 | 11375 | 25315 | 101265 | 127460 | 32715 | 37930 | 2415 | 18285 | 4605 | 106740 | 4950 | 2450 | 4250 | 5250 | 5475 | 5475 | 3550 | 1575 | 7275 | 4110 | 6050 | 23960 | 35460 | 58553 | 83295 | 97480 | 21995 | 335040 | 197400 | 91155 |  | 1848594
|  |  | 3625 | 114050 | 3625 | 5375 | 7350 | 2650 | 7650 | 2350 | 5950 | 4225 | 2950 | 36150 | 32000 | 12000 | 31100 | 107700 | 125000 | 40100 | 44525 | 5000 | 22075 | 5700 | 106000 | 6825 | 3650 | 5350 | 4925 | 6750 | 5800 | 6200 | 4175 | 8900 | 4675 | 8200 | 15650 | 31500 | 66350 | 86250 | 95600 | 28450 | 350000 | 200000 | 100000 | 0 | 1766400
#REF!
|  |  | 0.0020522 | 0.064566 | 0.0020522 | 0.0030429 | 0.004161 | 0.0015002 | 0.0043308 | 0.0013304 | 0.0033684 | 0.0023919 | 0.0016701 | 0.020465 | 0.018116 | 0.0067935 | 0.017606 | 0.060971 | 0.070765 | 0.022702 | 0.025207 | 0.0028306 | 0.012497 | 0.0032269 | 0.060009 | 0.0038638 | 0.0020663 | 0.0030288 | 0.0027882 | 0.0038213 | 0.0032835 | 0.00351 | 0.0023636 | 0.0050385 | 0.0026466 | 0.0046422 | 0.0088598 | 0.017833 | 0.037562 | 0.048828 | 0.054121 | 0.016106 | 0.19814 | 0.11322 | 0.056612 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Stenstrom Excavating |  | TCI Concrete | [7 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Rockford, il |  | Rockford, IL | [7 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete) | [5 empty] | Bid Bond |  | Bid Bond | [7 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 621-PW-044 VENDORS NOTIFIED: 129 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Tree Removal (6 to 15 Inch Diameter) | Unit Dia | 94 | 150 | 14100 | 12.34 | 1159.96 | 38 | 3572 |  | 0 |  | 0 |  | 0 | 1 | Tree Removal (6 to 15 Inch Diameter) | Unit Dia | 94 | 150 | 14100 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Tree Removal (6 to 15 Inch Diameter) | Unit Dia | 94 | 150 | 14100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Tree Removal (Over 15 Inch Diameter) | Unit Dia | 36 | 200 | 7200 | 22.5 | 810 | 45 | 1620 |  | 0 |  | 0 |  | 0 | 2 | Tree Removal (Over 15 Inch Diameter) | Unit Dia | 36 | 200 | 7200 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Tree Removal (Over 15 Inch Diameter) | Unit Dia | 36 | 200 | 7200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Earth Excavation | C.Y. | 1891 | 30 | 56730 | 24 | 45384 | 36 | 68076 |  | 0 |  | 0 |  | 0 | 3 | Earth Excavation | C.Y. | 1891 | 30 | 56730 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Earth Excavation | C.Y. | 1891 | 30 | 56730 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Top Soil Furnish and Place | C.Y. | 25 | 200 | 5000 | 65 | 1625 | 25 | 625 |  | 0 |  | 0 |  | 0 | 4 | Top Soil Furnish and Place | C.Y. | 25 | 200 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Top Soil Furnish and Place | C.Y. | 25 | 200 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Parkway Restoration | Lsum | 1 | 50000 | 50000 | 76580 | 76580 | 61000 | 61000 |  | 0 |  | 0 |  | 0 | 5 | Parkway Restoration | Lsum | 1 | 50000 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Parkway Restoration | Lsum | 1 | 50000 | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Inlet and Pipe Protection | Each | 37 | 60 | 2220 | 0.01 | 0.37 | 55 | 2035 |  | 0 |  | 0 |  | 0 | 6 | Inlet and Pipe Protection | Each | 37 | 60 | 2220 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Inlet and Pipe Protection | Each | 37 | 60 | 2220 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Stone Rip Rap | Tons | 40 | 30 | 1200 | 75 | 3000 | 52.75 | 2110 |  | 0 |  | 0 |  | 0 | 7 | Stone Rip Rap | Tons | 40 | 30 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Stone Rip Rap | Tons | 40 | 30 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 750 | 22 | 16500 | 18 | 13500 | 18.67 | 14002.5 |  | 0 |  | 0 |  | 0 | 8 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 750 | 22 | 16500 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 750 | 22 | 16500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 750 | 22 | 16500 | 22 | 16500 | 23.88 | 17910 |  | 0 |  | 0 |  | 0 | 9 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 750 | 22 | 16500 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 750 | 22 | 16500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Aggregate Base Repair, 10" | S.Y. | 192 | 20 | 3840 | 25.75 | 4944 | 38.82 | 7453.44 |  | 0 |  | 0 |  | 0 | 10 | Aggregate Base Repair, 10" | S.Y. | 192 | 20 | 3840 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Aggregate Base Repair, 10" | S.Y. | 192 | 20 | 3840 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Bituminous Materials (Prime Coat) | Gal | 2165 | 3 | 6495 | 0.01 | 21.65 | 0.01 | 21.65 |  | 0 |  | 0 |  | 0 | 11 | Bituminous Materials (Prime Coat) | Gal | 2165 | 3 | 6495 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Bituminous Materials (Prime Coat) | Gal | 2165 | 3 | 6495 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | Aggregate (Prime Coat) | Tons | 115 | 10 | 1150 | 0.01 | 1.15 | 0.01 | 1.15 |  | 0 |  | 0 |  | 0 | 12 | Aggregate (Prime Coat) | Tons | 115 | 10 | 1150 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | Aggregate (Prime Coat) | Tons | 115 | 10 | 1150 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 65 | 32500 | 65.75 | 32875 | 69.5 | 34750 |  | 0 |  | 0 |  | 0 | 13 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 65 | 32500 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 65 | 32500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 550 | 65 | 35750 | 65.75 | 36162.5 | 63 | 34650 |  | 0 |  | 0 |  | 0 | 14 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 550 | 65 | 35750 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 550 | 65 | 35750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3325 | 65 | 216125 | 68.5 | 227762.5 | 64.6 | 214795 |  | 0 |  | 0 |  | 0 | 15 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3325 | 65 | 216125 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3325 | 65 | 216125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Hot-Mix Asphalt, Hand Method | Tons | 66 | 300 | 19800 | 205 | 13530 | 500 | 33000 |  | 0 |  | 0 |  | 0 | 16 | Hot-Mix Asphalt, Hand Method | Tons | 66 | 300 | 19800 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Hot-Mix Asphalt, Hand Method | Tons | 66 | 300 | 19800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | P.C.C. Approach Pavement, 6" | S.Y. | 1727 | 50 | 86350 | 55.75 | 96280.25 | 49 | 84623 |  | 0 |  | 0 |  | 0 | 17 | P.C.C. Approach Pavement, 6" | S.Y. | 1727 | 50 | 86350 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | P.C.C. Approach Pavement, 6" | S.Y. | 1727 | 50 | 86350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | P.C.C. Approach Pavement, 8" | S.Y. | 320 | 60 | 19200 | 78.25 | 25040 | 70 | 22400 |  | 0 |  | 0 |  | 0 | 18 | P.C.C. Approach Pavement, 8" | S.Y. | 320 | 60 | 19200 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | P.C.C. Approach Pavement, 8" | S.Y. | 320 | 60 | 19200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | P.C.C. Sidewalk, 4" | S.F. | 53380 | 5 | 266900 | 5.1 | 272238 | 5 | 266900 |  | 0 |  | 0 |  | 0 | 19 | P.C.C. Sidewalk, 4" | S.F. | 53380 | 5 | 266900 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | P.C.C. Sidewalk, 4" | S.F. | 53380 | 5 | 266900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Detectable Warnings, ADA Ramps | S.F. | 860 | 20 | 17200 | 13.5 | 11610 | 25 | 21500 |  | 0 |  | 0 |  | 0 | 20 | Detectable Warnings, ADA Ramps | S.F. | 860 | 20 | 17200 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Detectable Warnings, ADA Ramps | S.F. | 860 | 20 | 17200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Combination Curb and Gutter Removal | L.F. | 11285 | 10 | 112850 | 7.5 | 84637.5 | 11.5 | 129777.5 |  | 0 |  | 0 |  | 0 | 21 | Combination Curb and Gutter Removal | L.F. | 11285 | 10 | 112850 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Combination Curb and Gutter Removal | L.F. | 11285 | 10 | 112850 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Sidewalk Removal | S.F. | 44205 | 2 | 88410 | 1.35 | 59676.75 | 1.75 | 77358.75 |  | 0 |  | 0 |  | 0 | 22 | Sidewalk Removal | S.F. | 44205 | 2 | 88410 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Sidewalk Removal | S.F. | 44205 | 2 | 88410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Approach Pavement Removal | S.Y. | 2090 | 20 | 41800 | 19.15 | 40023.5 | 17.5 | 36575 |  | 0 |  | 0 |  | 0 | 23 | Approach Pavement Removal | S.Y. | 2090 | 20 | 41800 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Approach Pavement Removal | S.Y. | 2090 | 20 | 41800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Surface Removal, 2" | S.Y. | 21100 | 3 | 63300 | 2.75 | 58025 | 2.66 | 56126 |  | 0 |  | 0 |  | 0 | 24 | Surface Removal, 2" | S.Y. | 21100 | 3 | 63300 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Surface Removal, 2" | S.Y. | 21100 | 3 | 63300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 1181120 |  | 1121387.13 |  | 1190881.99 | [7 empty] | Page 3 | Sub |  | As read | 1181120 | [9 empty] | Page 1 | Sub |  | As read | 1181120
| Award to Stenstrom Excavating | Total |  | As corrected | 1181120 |  | 1121387.13 |  | 1190881.99 | [7 empty] | Award to Stenstrom Excavating | Total |  | As corrected | 1181120 | [9 empty] | Award to Stenstrom Excavating | Total |  | As corrected | 1181120
25 | Surface Removal, Butt Joints | S.Y. | 100 | 7 | 700 | 15.5 | 1550 | 15 | 1500 |  | 0 |  | 0 |  | 0 | 25 | Surface Removal, Butt Joints | S.Y. | 100 | 7 | 700 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Surface Removal, Butt Joints | S.Y. | 100 | 7 | 700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Storm Sewers PVC, 10" | L.F. | 42 | 80 | 3360 | 84.25 | 3538.5 | 70 | 2940 |  | 0 |  | 0 |  | 0 | 26 | Storm Sewers PVC, 10" | L.F. | 42 | 80 | 3360 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Storm Sewers PVC, 10" | L.F. | 42 | 80 | 3360 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Storm Sewers PVC, 18" | L.F. | 914 | 60 | 54840 | 40 | 36560 | 70 | 63980 |  | 0 |  | 0 |  | 0 | 27 | Storm Sewers PVC, 18" | L.F. | 914 | 60 | 54840 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Storm Sewers PVC, 18" | L.F. | 914 | 60 | 54840 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Storm Sewers PVC, 24" | L.F. | 194 | 60 | 11640 | 50 | 9700 | 82 | 15908 |  | 0 |  | 0 |  | 0 | 28 | Storm Sewers PVC, 24" | L.F. | 194 | 60 | 11640 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Storm Sewers PVC, 24" | L.F. | 194 | 60 | 11640 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Storm Sewers PVC, 18" | L.F. | 53 | 100 | 5300 | 110 | 5830 | 70 | 3710 |  | 0 |  | 0 |  | 0 | 29 | Storm Sewers PVC, 18" | L.F. | 53 | 100 | 5300 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Storm Sewers PVC, 18" | L.F. | 53 | 100 | 5300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Storm Sewers Removal | L.F. | 180 | 20 | 3600 | 41 | 7380 | 29.55 | 5319 |  | 0 |  | 0 |  | 0 | 30 | Storm Sewers Removal | L.F. | 180 | 20 | 3600 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Storm Sewers Removal | L.F. | 180 | 20 | 3600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 4 | 3000 | 12000 | 1950 | 7800 | 2000 | 8000 |  | 0 |  | 0 |  | 0 | 31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 4 | 3000 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 4 | 3000 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Storm Inlet, Type 700 | Each | 2 | 3000 | 6000 | 1733 | 3466 | 1900 | 3800 |  | 0 |  | 0 |  | 0 | 32 | Storm Inlet, Type 700 | Each | 2 | 3000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Storm Inlet, Type 700 | Each | 2 | 3000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Storm Inlet, Inlet Special No. 2 | Each | 4 | 3000 | 12000 | 3100 | 12400 | 2800 | 11200 |  | 0 |  | 0 |  | 0 | 33 | Storm Inlet, Inlet Special No. 2 | Each | 4 | 3000 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Storm Inlet, Inlet Special No. 2 | Each | 4 | 3000 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 300 | 300 | 556 | 556 | 150 | 150 |  | 0 |  | 0 |  | 0 | 34 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 300 | 300 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 300 | 300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | Manholes to be Adjusted | Each | 24 | 550 | 13200 | 371 | 8904 | 450 | 10800 |  | 0 |  | 0 |  | 0 | 35 | Manholes to be Adjusted | Each | 24 | 550 | 13200 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Manholes to be Adjusted | Each | 24 | 550 | 13200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | Manholes to be Adjusted with New Frame and Lid | Each | 15 | 800 | 12000 | 622 | 9330 | 875 | 13125 |  | 0 |  | 0 |  | 0 | 36 | Manholes to be Adjusted with New Frame and Lid | Each | 15 | 800 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 | 36 | Manholes to be Adjusted with New Frame and Lid | Each | 15 | 800 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 | 1497 | 1497 | 950 | 950 |  | 0 |  | 0 |  | 0 | 37 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300 | 2257 | 2257 | 1250 | 1250 |  | 0 |  | 0 |  | 0 | 38 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300 |  | 0 |  | 0 |  | 0 |  | 0 | 38 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | Inlets to be Adjusted | Each | 11 | 1500 | 16500 | 937 | 10307 | 750 | 8250 |  | 0 |  | 0 |  | 0 | 39 | Inlets to be Adjusted | Each | 11 | 1500 | 16500 |  | 0 |  | 0 |  | 0 |  | 0 | 39 | Inlets to be Adjusted | Each | 11 | 1500 | 16500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | Inlets to be Adjusted with New Frame and Grate | Each | 8 | 1400 | 11200 | 1248 | 9984 | 1000 | 8000 |  | 0 |  | 0 |  | 0 | 40 | Inlets to be Adjusted with New Frame and Grate | Each | 8 | 1400 | 11200 |  | 0 |  | 0 |  | 0 |  | 0 | 40 | Inlets to be Adjusted with New Frame and Grate | Each | 8 | 1400 | 11200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 | 1075 | 1075 | 750 | 750 |  | 0 |  | 0 |  | 0 | 41 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 41 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
42 | Inlets to be Reconstructed with New Frame and Grate | Each | 15 | 1900 | 28500 | 1260 | 18900 | 1000 | 15000 |  | 0 |  | 0 |  | 0 | 42 | Inlets to be Reconstructed with New Frame and Grate | Each | 15 | 1900 | 28500 |  | 0 |  | 0 |  | 0 |  | 0 | 42 | Inlets to be Reconstructed with New Frame and Grate | Each | 15 | 1900 | 28500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
43 | Inlet Special to be Repaired | Each | 1 | 2200 | 2200 | 1660 | 1660 | 1100 | 1100 |  | 0 |  | 0 |  | 0 | 43 | Inlet Special to be Repaired | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 | 43 | Inlet Special to be Repaired | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
44 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 16415 | 25 | 410375 | 23.5 | 385752.5 | 25 | 410375 |  | 0 |  | 0 |  | 0 | 44 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 16415 | 25 | 410375 |  | 0 |  | 0 |  | 0 |  | 0 | 44 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 16415 | 25 | 410375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
45 | Remove and Replace Chain Link Fence | L.F. | 450 | 20 | 9000 | 17 | 7650 | 16.64 | 7488 |  | 0 |  | 0 |  | 0 | 45 | Remove and Replace Chain Link Fence | L.F. | 450 | 20 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 | 45 | Remove and Replace Chain Link Fence | L.F. | 450 | 20 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
46 | Traffic Control and Protection | LSum | 1 | 25000 | 25000 | 10000 | 10000 | 28500 | 28500 |  | 0 |  | 0 |  | 0 | 46 | Traffic Control and Protection | LSum | 1 | 25000 | 25000 |  | 0 |  | 0 |  | 0 |  | 0 | 46 | Traffic Control and Protection | LSum | 1 | 25000 | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
47 | Thermoplastic Pavement Markings, 4" | L.F. | 530 | 2.5 | 1325 | 4.65 | 2464.5 | 4.5 | 2385 |  | 0 |  | 0 |  | 0 | 47 | Thermoplastic Pavement Markings, 4" | L.F. | 530 | 2.5 | 1325 |  | 0 |  | 0 |  | 0 |  | 0 | 47 | Thermoplastic Pavement Markings, 4" | L.F. | 530 | 2.5 | 1325 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
48 | Thermoplastic Pavement Markings, 6" | L.F. | 54 | 4 | 216 | 6.95 | 375.3 | 6.75 | 364.5 |  | 0 |  | 0 |  | 0 | 48 | Thermoplastic Pavement Markings, 6" | L.F. | 54 | 4 | 216 |  | 0 |  | 0 |  | 0 |  | 0 | 48 | Thermoplastic Pavement Markings, 6" | L.F. | 54 | 4 | 216 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 1824176 |  | 1680323.93 |  | 1815726.49 | [7 empty] | Page 4 | Total |  | As read | 1824176 | [9 empty] | Page 2 | Total |  | As read | 1824176
| Award to Stenstrom Excavating | Total |  | As corrected |  |  | 1680323.93 | 0 | 1815726.49 | 0 | [6 empty] | Award to Stenstrom Excavating | Bid |  | As corrected | 1824176 | [9 empty] | Award to Stenstrom Excavating | Bid |  | As corrected | 1824176
49 | Thermoplastic Pavement Markings, 24" | L.F. | 14 | 12 | 168 | 27.75 | 388.5 | 27 | 378 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
50 | Removal and Replacement of Brick Pavers | S.F. | 950 | 15 | 14250 | 23.5 | 22325 | 1 | 950 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
51 | Subgrade Undercutting | C.Y. | 50 | 200 | 10000 | 98 | 4900 | 350 | 17500 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 1848594 |  | 1707937.43 |  | 1834554.49 | [7 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Stenstrom Excavating | Bid |  | As corrected | [12 empty] | Award to Stenstrom Excavating | Bid |  | As corrected | [10 empty] | Award to Stenstrom Excavating | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Stenstrom Excavating | Bid |  | As corrected | [12 empty] | Award to Stenstrom Excavating | Bid |  | As corrected | [10 empty] | Award to Stenstrom Excavating | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Tree Removal (6 to 15 Inch Diameter) | Unit Dia | 94 |  | 0
2 | Tree Removal (Over 15 Inch Diameter) | Unit Dia | 36 |  | 0
3 | Earth Excavation | C.Y. | 1891 |  | 0
4 | Top Soil Furnish and Place | C.Y. | 25 |  | 0
5 | Parkway Restoration | Lsum | 1 |  | 0
6 | Inlet and Pipe Protection | Each | 37 |  | 0
7 | Stone Rip Rap | Tons | 40 |  | 0
8 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 750 |  | 0
9 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 750 |  | 0
10 | Aggregate Base Repair, 10" | S.Y. | 192 |  | 0
11 | Bituminous Materials (Prime Coat) | Gal | 2165 |  | 0
12 | Aggregate (Prime Coat) | Tons | 115 |  | 0
13 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 |  | 0
14 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 550 |  | 0
15 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3325 |  | 0
16 | Hot-Mix Asphalt, Hand Method | Tons | 66 |  | 0
17 | P.C.C. Approach Pavement, 6" | S.Y. | 1727 |  | 0
18 | P.C.C. Approach Pavement, 8" | S.Y. | 320 |  | 0
19 | P.C.C. Sidewalk, 4" | S.F. | 53380 |  | 0
20 | Detectable Warnings, ADA Ramps | S.F. | 860 |  | 0
21 | Combination Curb and Gutter Removal | L.F. | 11285 |  | 0
22 | Sidewalk Removal | S.F. | 44205 |  | 0
23 | Approach Pavement Removal | S.Y. | 2090 |  | 0
24 | Surface Removal, 2" | S.Y. | 21100 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Surface Removal, Butt Joints | S.Y. | 100 |  | 0
26 | Storm Sewers PVC, 10" | L.F. | 42 |  | 0
27 | Storm Sewers PVC, 18" | L.F. | 914 |  | 0
28 | Storm Sewers PVC, 24" | L.F. | 194 |  | 0
29 | Storm Sewers PVC, 18" | L.F. | 53 |  | 0
30 | Storm Sewers Removal | L.F. | 180 |  | 0
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 4 |  | 0
32 | Storm Inlet, Type 700 | Each | 2 |  | 0
33 | Storm Inlet, Inlet Special No. 2 | Each | 4 |  | 0
34 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 |  | 0
35 | Manholes to be Adjusted | Each | 24
36 | Manholes to be Adjusted with New Frame and Lid | Each | 15
37 | Manholes to be Reconstructed | Each | 1
38 | Manholes to be Reconstructed with New Frame and Lid | Each | 1
39 | Inlets to be Adjusted | Each | 11
40 | Inlets to be Adjusted with New Frame and Grate | Each | 8
41 | Inlets to be Reconstructed | Each | 1
42 | Inlets to be Reconstructed with New Frame and Grate | Each | 15
43 | Inlet Special to be Repaired | Each | 1
44 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 16415
45 | Remove and Replace Chain Link Fence | L.F. | 450
46 | Traffic Control and Protection | LSum | 1
47 | Thermoplastic Pavement Markings, 4" | L.F. | 530
48 | Thermoplastic Pavement Markings, 6" | L.F. | 54
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected
49 | Thermoplastic Pavement Markings, 24" | L.F. | 14
50 | Removal and Replacement of Brick Pavers | S.F. | 950
51 | Subgrade Undercutting | C.Y. | 50
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Tree Removal (6 to 15 Inch Diameter) | Unit Dia | 94 | 150 | 14100
2 | Tree Removal (Over 15 Inch Diameter) | Unit Dia | 36 | 200 | 7200
3 | Earth Excavation | C.Y. | 1891 | 30 | 56730
4 | Top Soil Furnish and Place | C.Y. | 25 | 200 | 5000
5 | Parkway Restoration | Lsum | 1 | 50000 | 50000
6 | Inlet and Pipe Protection | Each | 37 | 60 | 2220
7 | Stone Rip Rap | Tons | 40 | 30 | 1200
8 | Subbase Granular Material, Type B, CA-2, 6" | Tons | 750 | 22 | 16500
9 | Aggregate Base Course, Type B, CA-6, 6" | Tons | 750 | 22 | 16500
10 | Aggregate Base Repair, 10" | S.Y. | 192 | 20 | 3840
11 | Bituminous Materials (Prime Coat) | Gal | 2165 | 3 | 6495
12 | Aggregate (Prime Coat) | Tons | 115 | 10 | 1150
13 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 65 | 32500
14 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | Tons | 550 | 65 | 35750
15 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 3325 | 65 | 216125
16 | Hot-Mix Asphalt, Hand Method | Tons | 66 | 300 | 19800
17 | P.C.C. Approach Pavement, 6" | S.Y. | 1727 | 50 | 86350
18 | P.C.C. Approach Pavement, 8" | S.Y. | 320 | 60 | 19200
19 | P.C.C. Sidewalk, 4" | S.F. | 53380 | 5 | 266900
20 | Detectable Warnings, ADA Ramps | S.F. | 860 | 20 | 17200
21 | Combination Curb and Gutter Removal | L.F. | 11285 | 10 | 112850
22 | Sidewalk Removal | S.F. | 44205 | 2 | 88410
23 | Approach Pavement Removal | S.Y. | 2090 | 20 | 41800
24 | Surface Removal, 2" | S.Y. | 21100 | 3 | 63300
|  |  |  | Sub Total | 1181120
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Surface Removal, Butt Joints | S.Y. | 100 | 7 | 700
26 | Storm Sewers PVC, 10" | L.F. | 42 | 80 | 3360
27 | Storm Sewers PVC, 18" | L.F. | 914 | 60 | 54840
28 | Storm Sewers PVC, 24" | L.F. | 194 | 60 | 11640
29 | Storm Sewers PVC, 18" | L.F. | 53 | 100 | 5300
30 | Storm Sewers Removal | L.F. | 180 | 20 | 3600
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | Each | 4 | 3000 | 12000
32 | Storm Inlet, Type 700 | Each | 2 | 3000 | 6000
33 | Storm Inlet, Inlet Special No. 2 | Each | 4 | 3000 | 12000
34 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 300 | 300
35 | Manholes to be Adjusted | Each | 24 | 550 | 13200
36 | Manholes to be Adjusted with New Frame and Lid | Each | 15 | 800 | 12000
37 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000
38 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1300 | 1300
39 | Inlets to be Adjusted | Each | 11 | 1500 | 16500
40 | Inlets to be Adjusted with New Frame and Grate | Each | 8 | 1400 | 11200
41 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500
42 | Inlets to be Reconstructed with New Frame and Grate | Each | 15 | 1900 | 28500
43 | Inlet Special to be Repaired | Each | 1 | 2200 | 2200
44 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 16415 | 25 | 410375
45 | Remove and Replace Chain Link Fence | L.F. | 450 | 20 | 9000
46 | Traffic Control and Protection | LSum | 1 | 25000 | 25000
47 | Thermoplastic Pavement Markings, 4" | L.F. | 530 | 2.5 | 1325
48 | Thermoplastic Pavement Markings, 6" | L.F. | 54 | 4 | 216
|  |  |  | Sub Total | 1824176
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | Thermoplastic Pavement Markings, 24" | L.F. | 14 | 12 | 168
50 | Removal and Replacement of Brick Pavers | S.F. | 950 | 15 | 14250
51 | Subgrade Undercutting | C.Y. | 50 | 200 | 10000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 28th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | P.O. # 19305224 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Tree Removal (6 to 15 Inch Diameter) | 94 | Unit Dia | 1159.96 | 6 |  | 100 | Unit Dia | 12.34 | 1234
2 | Tree Removal (Over 15 Inch Diameter) | 36 | Unit Dia | 810 |  | 36 |  |  | 22.5
3 | Earth Excavation | 1891 | C.Y. | 45384 |  | 1890.82 | 0.18 | C.Y. | 24 | 4.32
4 | Top Soil Furnish and Place | 25 | C.Y. | 1625 |  | 22 | 3 | C.Y. | 65 | 195
5 | Parkway Restoration | 1 | Lsum | 76580 |  | 1 |  |  | 76580
6 | Inlet and Pipe Protection | 37 | Each | 0.37 |  | 37 |  |  | 0.01
7 | Stone Rip Rap | 40 | Tons | 3000 |  | 40 |  |  | 75
8 | Subbase Granular Material, Type B, CA-2, 6" | 750 | Tons | 13500 |  | 750 |  |  | 18
9 | Aggregate Base Course, Type B, CA-6, 6" | 750 | Tons | 16500 |  | 750 |  |  | 22
10 | Aggregate Base Repair, 10" | 192 | S.Y. | 4944 |  | 192 |  |  | 25.75
11 | Bituminous Materials (Prime Coat) | 2165 | Gal | 21.65 |  | 2165 |  |  | 0.01
12 | Aggregate (Prime Coat) | 115 | Tons | 1.15 |  | 115 |  |  | 0.01
13 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | 500 | Tons | 32875 |  | 392 | 108 | Tons | 65.75 | 7101
14 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | 550 | Tons | 36162.5 |  | 525 | 25 | Tons | 65.75 | 1643.75
15 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 3325 | Tons | 227762.5 | 20525 |  | 23850 | Tons | 68.5 | 1633725
16 | Hot-Mix Asphalt, Hand Method | 66 | Tons | 13530 |  | 16 | 50 | Tons | 205 | 10250
17 | P.C.C. Approach Pavement, 6" | 1727 | S.Y. | 96280.25 |  | 1492 | 235 | S.Y. | 55.75 | 13101.25
18 | P.C.C. Approach Pavement, 8" | 320 | S.Y. | 25040 | 20530 |  | 20850 | S.Y. | 78.25 | 1631512.5
19 | P.C.C. Sidewalk, 4" | 53380 | S.F. | 272238 |  | 53247 | 133 | S.F. | 5.1 | 678.3
20 | Detectable Warnings, ADA Ramps | 860 | S.F. | 11610 |  | 860 |  |  | 13.5
21 | Combination Curb and Gutter Removal | 11285 | L.F. | 84637.5 |  | 11285 |  |  | 7.5
22 | Sidewalk Removal | 44205 | S.F. | 59676.75 |  | 44205 |  |  | 1.35
23 | Approach Pavement Removal | 2090 | S.Y. | 40023.5 |  | 2090 |  |  | 19.15
24 | Surface Removal, 2" | 21100 | S.Y. | 58025 |  | 21100 |  |  | 2.75
Sub Total |  |  |  | 1121387.13 | [5 empty] | 3299445.12
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 28th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Surface Removal, Butt Joints | 100 | S.Y. | 1550 |  | 100 |  |  | 15.5
26 | Storm Sewers PVC, 10" | 42 | L.F. | 3538.5 |  | 42 |  |  | 84.25
27 | Storm Sewers PVC, 18" | 914 | L.F. | 36560 |  | 914 |  |  | 40
28 | Storm Sewers PVC, 24" | 194 | L.F. | 9700 |  | 194 |  |  | 50
29 | Storm Sewers PVC, 18" | 53 | L.F. | 5830 |  | 53 |  |  | 110
30 | Storm Sewers Removal | 180 | L.F. | 7380 |  | 180 |  |  | 41
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | 4 | Each | 7800 |  | 4 |  |  | 1950
32 | Storm Inlet, Type 700 | 2 | Each | 3466 |  | 2 |  |  | 1733
33 | Storm Inlet, Inlet Special No. 2 | 4 | Each | 12400 |  | 4 |  |  | 3100
34 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each | 556 |  | 1 |  |  | 556
35 | Manholes to be Adjusted | 24 | Each | 8904 |  | 24 |  |  | 371
36 | Manholes to be Adjusted with New Frame and Lid | 15 | Each | 9330 |  | 15 |  |  | 622
37 | Manholes to be Reconstructed | 1 | Each | 1497 |  | 1 |  |  | 1497
38 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 2257 |  | 1 |  |  | 2257
39 | Inlets to be Adjusted | 11 | Each | 10307 |  | 11 |  |  | 937
40 | Inlets to be Adjusted with New Frame and Grate | 8 | Each | 9984 |  | 8 |  |  | 1248
41 | Inlets to be Reconstructed | 1 | Each | 1075 |  | 1 |  |  | 1075
42 | Inlets to be Reconstructed with New Frame and Grate | 15 | Each | 18900 |  | 15 |  |  | 1260
43 | Inlet Special to be Repaired | 1 | Each | 1660 | 234 |  | 235 | Each | 1660 | 390100
44 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 16415 | L.F. | 385752.5 |  | 16414.82 | 0.18 | L.F. | 23.5 | 4.23
45 | Remove and Replace Chain Link Fence | 450 | L.F. | 7650 |  | 450 |  |  | 17
46 | Traffic Control and Protection | 1 | LSum | 10000 |  | 1 |  |  | 10000
47 | Thermoplastic Pavement Markings, 4" | 530 | L.F. | 2464.5 |  | 530 |  |  | 4.65
48 | Thermoplastic Pavement Markings, 6" | 54 | L.F. | 375.3 |  | 54 |  |  | 6.95
Sub Total |  |  |  | 1680323.93 | [5 empty] | 3689549.35
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
[8 empty] | DEDUCT RETAINAGE | 10% | #VALUE!
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 28th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | Thermoplastic Pavement Markings, 24" | 14 | L.F. | 388.5 |  | 14 |  |  | 27.75
50 | Removal and Replacement of Brick Pavers | 950 | S.F. | 22325 |  | 950 |  |  | 23.5
51 | Subgrade Undercutting | 50 | C.Y. | 4900 |  | 50 |  |  | 98
Total |  |  |  | 1707937.43 | [5 empty] | 3689549.35
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 3689549.35
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 3689549.35
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 3689549.35
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 28th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 1707937.43 | [5 empty] | 3689549.35
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 3689549.35
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 3689549.35
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 3689549.35
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Pay Estimate (2)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 2 from August 28th, 2019 to September 19th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | P.O. # 19305224 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Tree Removal (6 to 15 Inch Diameter) | 94 | Unit Dia | 1159.96 | 106 |  | 200 | Unit Dia | 12.34 | 2468
2 | Tree Removal (Over 15 Inch Diameter) | 36 | Unit Dia | 810 |  | 36 |  |  | 22.5
3 | Earth Excavation | 1891 | C.Y. | 45384 |  | 1890.81 | 0.19 | C.Y. | 24 | 4.56
4 | Top Soil Furnish and Place | 25 | C.Y. | 1625 |  | 22 | 3 | C.Y. | 65 | 195
5 | Parkway Restoration | 1 | Lsum | 76580 |  | 1 |  |  | 76580
6 | Inlet and Pipe Protection | 37 | Each | 0.37 |  | 37 |  |  | 0.01
7 | Stone Rip Rap | 40 | Tons | 3000 |  | 40 |  |  | 75
8 | Subbase Granular Material, Type B, CA-2, 6" | 750 | Tons | 13500 |  | 750 |  |  | 18
9 | Aggregate Base Course, Type B, CA-6, 6" | 750 | Tons | 16500 |  | 750 |  |  | 22
10 | Aggregate Base Repair, 10" | 192 | S.Y. | 4944 |  | 192 |  |  | 25.75
11 | Bituminous Materials (Prime Coat) | 2165 | Gal | 21.65 |  | 2165 |  |  | 0.01
12 | Aggregate (Prime Coat) | 115 | Tons | 1.15 |  | 115 |  |  | 0.01
13 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | 500 | Tons | 32875 |  | 102 | 398 | Tons | 65.75 | 26168.5
14 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | 550 | Tons | 36162.5 |  | 505 | 45 | Tons | 65.75 | 2958.75
15 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 3325 | Tons | 227762.5 | 34250 |  | 37575 | Tons | 68.5 | 2573887.5
16 | Hot-Mix Asphalt, Hand Method | 66 | Tons | 13530 | 84 |  | 150 | Tons | 205 | 30750
17 | P.C.C. Approach Pavement, 6" | 1727 | S.Y. | 96280.25 | 929 |  | 2656 | S.Y. | 55.75 | 148072
18 | P.C.C. Approach Pavement, 8" | 320 | S.Y. | 25040 | 31505 |  | 31825 | S.Y. | 78.25 | 2490306.25
19 | P.C.C. Sidewalk, 4" | 53380 | S.F. | 272238 |  | 52907 | 473 | S.F. | 5.1 | 2412.3
20 | Detectable Warnings, ADA Ramps | 860 | S.F. | 11610 |  | 860 |  |  | 13.5
21 | Combination Curb and Gutter Removal | 11285 | L.F. | 84637.5 |  | 11285 |  |  | 7.5
22 | Sidewalk Removal | 44205 | S.F. | 59676.75 |  | 44205 |  |  | 1.35
23 | Approach Pavement Removal | 2090 | S.Y. | 40023.5 |  | 2090 |  |  | 19.15
24 | Surface Removal, 2" | 21100 | S.Y. | 58025 |  | 21100 |  |  | 2.75
Sub Total |  |  |  | 1121387.13 | [5 empty] | 5277222.86
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 2 from August 28th, 2019 to September 19th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Surface Removal, Butt Joints | 100 | S.Y. | 1550 |  | 100 |  |  | 15.5
26 | Storm Sewers PVC, 10" | 42 | L.F. | 3538.5 |  | 42 |  |  | 84.25
27 | Storm Sewers PVC, 18" | 914 | L.F. | 36560 |  | 914 |  |  | 40
28 | Storm Sewers PVC, 24" | 194 | L.F. | 9700 |  | 194 |  |  | 50
29 | Storm Sewers PVC, 18" | 53 | L.F. | 5830 |  | 53 |  |  | 110
30 | Storm Sewers Removal | 180 | L.F. | 7380 |  | 180 |  |  | 41
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | 4 | Each | 7800 |  | 4 |  |  | 1950
32 | Storm Inlet, Type 700 | 2 | Each | 3466 |  | 2 |  |  | 1733
33 | Storm Inlet, Inlet Special No. 2 | 4 | Each | 12400 |  | 4 |  |  | 3100
34 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each | 556 |  | 1 |  |  | 556
35 | Manholes to be Adjusted | 24 | Each | 8904 |  | 24 |  |  | 371
36 | Manholes to be Adjusted with New Frame and Lid | 15 | Each | 9330 |  | 15 |  |  | 622
37 | Manholes to be Reconstructed | 1 | Each | 1497 |  | 1 |  |  | 1497
38 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 2257 |  | 1 |  |  | 2257
39 | Inlets to be Adjusted | 11 | Each | 10307 |  | 11 |  |  | 937
40 | Inlets to be Adjusted with New Frame and Grate | 8 | Each | 9984 |  | 8 |  |  | 1248
41 | Inlets to be Reconstructed | 1 | Each | 1075 |  | 1 |  |  | 1075
42 | Inlets to be Reconstructed with New Frame and Grate | 15 | Each | 18900 |  | 15 |  |  | 1260
43 | Inlet Special to be Repaired | 1 | Each | 1660 | 2514 |  | 2515 | Each | 1660 | 4174900
44 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 16415 | L.F. | 385752.5 |  | 16414.7 | 0.3 | L.F. | 23.5 | 7.05
45 | Remove and Replace Chain Link Fence | 450 | L.F. | 7650 |  | 450 |  |  | 17
46 | Traffic Control and Protection | 1 | LSum | 10000 |  | 1 |  |  | 10000
47 | Thermoplastic Pavement Markings, 4" | 530 | L.F. | 2464.5 |  | 530 |  |  | 4.65
48 | Thermoplastic Pavement Markings, 6" | 54 | L.F. | 375.3 |  | 54 |  |  | 6.95
Sub Total |  |  |  | 1680323.93 | [5 empty] | 9452129.91
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
[8 empty] | DEDUCT RETAINAGE | 10% | #VALUE!
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
Pay Estimate No. 1 | [8 empty] | 159279.75
[8 empty] | TOTAL OF DEBITS |  | 159279.75
[8 empty] | NET AMOUNT DUE |  | #VALUE!
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 2 from August 28th, 2019 to September 19th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | Thermoplastic Pavement Markings, 24" | 14 | L.F. | 388.5 |  | 14 |  |  | 27.75
50 | Removal and Replacement of Brick Pavers | 950 | S.F. | 22325 |  | 950 |  |  | 23.5
51 | Subgrade Undercutting | 50 | C.Y. | 4900 |  | 50 |  |  | 98
Total |  |  |  | 1707937.43 | [5 empty] | 9452129.91
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 9452129.91
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 9452129.91
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 9452129.91
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 2 from August 28th, 2019 to September 19th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 1707937.43 | [5 empty] | 9452129.91
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 9452129.91
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 9452129.91
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 9452129.91
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Pay Estimate (3)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 3 from September 19th, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | P.O. # 19305224 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Tree Removal (6 to 15 Inch Diameter) | 94 | Unit Dia | 1159.96 | 606 |  | 700 | Unit Dia | 12.34 | 8638
2 | Tree Removal (Over 15 Inch Diameter) | 36 | Unit Dia | 810 |  | 36 |  |  | 22.5
3 | Earth Excavation | 1891 | C.Y. | 45384 |  | 1890.4 | 0.6 | C.Y. | 24 | 14.4
4 | Top Soil Furnish and Place | 25 | C.Y. | 1625 |  | 21 | 4 | C.Y. | 65 | 260
5 | Parkway Restoration | 1 | Lsum | 76580 |  | 1 |  |  | 76580
6 | Inlet and Pipe Protection | 37 | Each | 0.37 |  | 37 |  |  | 0.01
7 | Stone Rip Rap | 40 | Tons | 3000 |  | 40 |  |  | 75
8 | Subbase Granular Material, Type B, CA-2, 6" | 750 | Tons | 13500 |  | 750 |  |  | 18
9 | Aggregate Base Course, Type B, CA-6, 6" | 750 | Tons | 16500 |  | 750 |  |  | 22
10 | Aggregate Base Repair, 10" | 192 | S.Y. | 4944 |  | 86.82 | 105.18 | S.Y. | 25.75 | 2708.385
11 | Bituminous Materials (Prime Coat) | 2165 | Gal | 21.65 |  | 1768.42 | 396.58 | Gal | 0.01 | 3.9658
12 | Aggregate (Prime Coat) | 115 | Tons | 1.15 |  | 85 | 30 | Tons | 0.01 | 0.3
13 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | 500 | Tons | 32875 | 98 |  | 598 | Tons | 65.75 | 39318.5
14 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | 550 | Tons | 36162.5 |  | 445 | 105 | Tons | 65.75 | 6903.75
15 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 3325 | Tons | 227762.5 | 63950 |  | 67275 | Tons | 68.5 | 4608337.5
16 | Hot-Mix Asphalt, Hand Method | 66 | Tons | 13530 | 334 |  | 400 | Tons | 205 | 82000
17 | P.C.C. Approach Pavement, 6" | 1727 | S.Y. | 96280.25 | 2813 |  | 4540 | S.Y. | 55.75 | 253105
18 | P.C.C. Approach Pavement, 8" | 320 | S.Y. | 25040 | 41605 |  | 41925 | S.Y. | 78.25 | 3280631.25
19 | P.C.C. Sidewalk, 4" | 53380 | S.F. | 272238 |  | 52607 | 773 | S.F. | 5.1 | 3942.3
20 | Detectable Warnings, ADA Ramps | 860 | S.F. | 11610 |  | 860 |  |  | 13.5
21 | Combination Curb and Gutter Removal | 11285 | L.F. | 84637.5 |  | 6698 | 4587 | L.F. | 7.5 | 34402.5
22 | Sidewalk Removal | 44205 | S.F. | 59676.75 |  | 44205 |  |  | 1.35
23 | Approach Pavement Removal | 2090 | S.Y. | 40023.5 |  | 2090 |  |  | 19.15
24 | Surface Removal, 2" | 21100 | S.Y. | 58025 |  | 21100 |  |  | 2.75
Sub Total |  |  |  | 1121387.13 | [5 empty] | 8320265.8508
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 3 from September 19th, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Surface Removal, Butt Joints | 100 | S.Y. | 1550 |  | 100 |  |  | 15.5
26 | Storm Sewers PVC, 10" | 42 | L.F. | 3538.5 |  | 42 |  |  | 84.25
27 | Storm Sewers PVC, 18" | 914 | L.F. | 36560 |  | 914 |  |  | 40
28 | Storm Sewers PVC, 24" | 194 | L.F. | 9700 |  | 194 |  |  | 50
29 | Storm Sewers PVC, 18" | 53 | L.F. | 5830 |  | 53 |  |  | 110
30 | Storm Sewers Removal | 180 | L.F. | 7380 |  | 180 |  |  | 41
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | 4 | Each | 7800 |  | 4 |  |  | 1950
32 | Storm Inlet, Type 700 | 2 | Each | 3466 |  | 2 |  |  | 1733
33 | Storm Inlet, Inlet Special No. 2 | 4 | Each | 12400 |  | 4 |  |  | 3100
34 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each | 556 |  | 1 |  |  | 556
35 | Manholes to be Adjusted | 24 | Each | 8904 |  | 24 |  |  | 371
36 | Manholes to be Adjusted with New Frame and Lid | 15 | Each | 9330 |  | 15 |  |  | 622
37 | Manholes to be Reconstructed | 1 | Each | 1497 |  | 1 |  |  | 1497
38 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 2257 |  | 1 |  |  | 2257
39 | Inlets to be Adjusted | 11 | Each | 10307 |  | 11 |  |  | 937
40 | Inlets to be Adjusted with New Frame and Grate | 8 | Each | 9984 |  | 8 |  |  | 1248
41 | Inlets to be Reconstructed | 1 | Each | 1075 |  | 1 |  |  | 1075
42 | Inlets to be Reconstructed with New Frame and Grate | 15 | Each | 18900 |  | 15 |  |  | 1260
43 | Inlet Special to be Repaired | 1 | Each | 1660 | 4539 |  | 4540 | Each | 1660 | 7536400
44 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 16415 | L.F. | 385752.5 |  | 16414.25 | 0.75 | L.F. | 23.5 | 17.625
45 | Remove and Replace Chain Link Fence | 450 | L.F. | 7650 |  | 450 |  |  | 17
46 | Traffic Control and Protection | 1 | LSum | 10000 |  | 1 |  |  | 10000
47 | Thermoplastic Pavement Markings, 4" | 530 | L.F. | 2464.5 |  | 530 |  |  | 4.65
48 | Thermoplastic Pavement Markings, 6" | 54 | L.F. | 375.3 |  | 54 |  |  | 6.95
Sub Total |  |  |  | 1680323.93 | [5 empty] | 15856683.4758
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
[8 empty] | DEDUCT RETAINAGE | 5% | #VALUE!
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
Pay Estimate No. 1 | [8 empty] | 159279.75
Pay Estimate No. 2 | [8 empty] | 164789.78
[8 empty] | TOTAL OF DEBITS |  | 324069.53
[8 empty] | NET AMOUNT DUE |  | #VALUE!
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 3 from September 19th, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | Thermoplastic Pavement Markings, 24" | 14 | L.F. | 388.5 |  | 14 |  |  | 27.75
50 | Removal and Replacement of Brick Pavers | 950 | S.F. | 22325 |  | 950 |  |  | 23.5
51 | Subgrade Undercutting | 50 | C.Y. | 4900 |  | 50 |  |  | 98
Total |  |  |  | 1707937.43 | [5 empty] | 15856683.4758
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 15856683.4758
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 15856683.4758
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 15856683.4758
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 3 from September 19th, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 1707937.43 | [5 empty] | 15856683.4758
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 15856683.4758
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 15856683.4758
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 15856683.4758
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Pay Estimate (4)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 4 from October 18th, 2019 December 31st, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | P.O. # 19305224 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Tree Removal (6 to 15 Inch Diameter) | 94 | Unit Dia | 1159.96 | 875 |  | 969 | Unit Dia | 12.34 | 11957.46
2 | Tree Removal (Over 15 Inch Diameter) | 36 | Unit Dia | 810 |  | 35.85 | 0.15 | Unit Dia | 22.5 | 3.375
3 | Earth Excavation | 1891 | C.Y. | 45384 |  | 1890.4 | 0.6 | C.Y. | 24 | 14.4
4 | Top Soil Furnish and Place | 25 | C.Y. | 1625 |  | 20 | 5 | C.Y. | 65 | 325
5 | Parkway Restoration | 1 | Lsum | 76580 |  | 1 |  |  | 76580
6 | Inlet and Pipe Protection | 37 | Each | 0.37 |  | 37 |  |  | 0.01
7 | Stone Rip Rap | 40 | Tons | 3000 |  | 40 |  |  | 75
8 | Subbase Granular Material, Type B, CA-2, 6" | 750 | Tons | 13500 |  | 360 | 390 | Tons | 18 | 7020
9 | Aggregate Base Course, Type B, CA-6, 6" | 750 | Tons | 16500 |  | 750 |  |  | 22
10 | Aggregate Base Repair, 10" | 192 | S.Y. | 4944 | 2.9 |  | 194.9 | S.Y. | 25.75 | 5018.675
11 | Bituminous Materials (Prime Coat) | 2165 | Gal | 21.65 |  | 1288.33 | 876.67 | Gal | 0.01 | 8.7667
12 | Aggregate (Prime Coat) | 115 | Tons | 1.15 |  | 28 | 87 | Tons | 0.01 | 0.87
13 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | 500 | Tons | 32875 | 75 |  | 575 | Tons | 65.75 | 37806.25
14 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | 550 | Tons | 36162.5 |  | 311 | 239 | Tons | 65.75 | 15714.25
15 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 3325 | Tons | 227762.5 | 78614 |  | 81939 | Tons | 68.5 | 5612821.5
16 | Hot-Mix Asphalt, Hand Method | 66 | Tons | 13530 | 263 |  | 329 | Tons | 205 | 67445
17 | P.C.C. Approach Pavement, 6" | 1727 | S.Y. | 96280.25 | 2817 |  | 4544 | S.Y. | 55.75 | 253328
18 | P.C.C. Approach Pavement, 8" | 320 | S.Y. | 25040 | 48567 |  | 48887 | S.Y. | 78.25 | 3825407.75
19 | P.C.C. Sidewalk, 4" | 53380 | S.F. | 272238 |  | 52523 | 857 | S.F. | 5.1 | 4370.7
20 | Detectable Warnings, ADA Ramps | 860 | S.F. | 11610 |  | 860 |  |  | 13.5
21 | Combination Curb and Gutter Removal | 11285 | L.F. | 84637.5 |  | 4279 | 7006 | L.F. | 7.5 | 52545
22 | Sidewalk Removal | 44205 | S.F. | 59676.75 |  | 44205 |  |  | 1.35
23 | Approach Pavement Removal | 2090 | S.Y. | 40023.5 |  | 2090 |  |  | 19.15
24 | Surface Removal, 2" | 21100 | S.Y. | 58025 |  | 20480 | 620 | S.Y. | 2.75 | 1705
Sub Total |  |  |  | 1121387.13 | [5 empty] | 9895491.9967
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 4 from October 18th, 2019 December 31st, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Surface Removal, Butt Joints | 100 | S.Y. | 1550 |  | 100 |  |  | 15.5
26 | Storm Sewers PVC, 10" | 42 | L.F. | 3538.5 |  | 42 |  |  | 84.25
27 | Storm Sewers PVC, 18" | 914 | L.F. | 36560 |  | 914 |  |  | 40
28 | Storm Sewers PVC, 24" | 194 | L.F. | 9700 |  | 194 |  |  | 50
29 | Storm Sewers PVC, 18" | 53 | L.F. | 5830 |  | 53 |  |  | 110
30 | Storm Sewers Removal | 180 | L.F. | 7380 |  | 179 | 1 | L.F. | 41 | 41
31 | Storm Manhole, Type A, 4' Diameter, Open Lid | 4 | Each | 7800 |  | 4 |  |  | 1950
32 | Storm Inlet, Type 700 | 2 | Each | 3466 |  | 2 |  |  | 1733
33 | Storm Inlet, Inlet Special No. 2 | 4 | Each | 12400 |  | 4 |  |  | 3100
34 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each | 556 | 12 |  | 13 | Each | 556 | 7228
35 | Manholes to be Adjusted | 24 | Each | 8904 |  | 24 |  |  | 371
36 | Manholes to be Adjusted with New Frame and Lid | 15 | Each | 9330 |  | 15 |  |  | 622
37 | Manholes to be Reconstructed | 1 | Each | 1497 |  | 1 |  |  | 1497
38 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 2257 | 10 |  | 11 | Each | 2257 | 24827
39 | Inlets to be Adjusted | 11 | Each | 10307 |  | 11 |  |  | 937
40 | Inlets to be Adjusted with New Frame and Grate | 8 | Each | 9984 |  | 8 |  |  | 1248
41 | Inlets to be Reconstructed | 1 | Each | 1075 | 12 |  | 13 | Each | 1075 | 13975
42 | Inlets to be Reconstructed with New Frame and Grate | 15 | Each | 18900 | 226 |  | 241 | Each | 1260 | 303660
43 | Inlet Special to be Repaired | 1 | Each | 1660 | 4302 |  | 4303 | Each | 1660 | 7142980
44 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 16415 | L.F. | 385752.5 |  | 16414.21 | 0.79 | L.F. | 23.5 | 18.565
45 | Remove and Replace Chain Link Fence | 450 | L.F. | 7650 |  | 450 |  |  | 17
46 | Traffic Control and Protection | 1 | LSum | 10000 |  | 1 |  |  | 10000
47 | Thermoplastic Pavement Markings, 4" | 530 | L.F. | 2464.5 |  | 530 |  |  | 4.65
48 | Thermoplastic Pavement Markings, 6" | 54 | L.F. | 375.3 |  | 54 |  |  | 6.95
Sub Total |  |  |  | 1680323.93 | [5 empty] | 17388221.5617
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
Church Street Steps | [8 empty] | 65003.09
Chelsea Median | [8 empty] | 48430
East State Street and Fairview Avenue | [8 empty] | 24620
Madison Street and Market Street | [8 empty] | 26595
8th Street and 13th Avenue Sidewalk | [8 empty] | 14070
7th Ward Additional Conrete Work (Royal Avenue, North Avenue, Grant Avenue, Garrison Avenue) | [8 empty] | 78976.07
[8 empty] | TOTAL MISCELLANEOUS EXTRAS AND CREDITS |  | 257694.16
TOTAL VALUE OF COMPLETED WORK
[8 empty] | DEDUCT RETAINAGE | 5% | #VALUE!
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
Pay Estimate No. 1 | [8 empty] | 159279.75
Pay Estimate No. 2 | [8 empty] | 164789.78
Pay Estimate No. 3 | [8 empty] | 361895.06
[8 empty] | TOTAL OF DEBITS |  | 685964.59
[8 empty] | NET AMOUNT DUE |  | #VALUE!
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 4 from October 18th, 2019 December 31st, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | Thermoplastic Pavement Markings, 24" | 14 | L.F. | 388.5 |  | 14 |  |  | 27.75
50 | Removal and Replacement of Brick Pavers | 950 | S.F. | 22325 |  | 950 |  |  | 23.5
51 | Subgrade Undercutting | 50 | C.Y. | 4900 |  | 50 |  |  | 98
Total |  |  |  | 1707937.43 | [5 empty] | 17388221.5617
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 17388221.5617
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 17388221.5617
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 17388221.5617
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 4 from October 18th, 2019 December 31st, 2019 | [7 empty] | (Road District)
| Payable to: Stenstrom Excavating | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, il Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2021 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 1707937.43 | [5 empty] | 17388221.5617
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 17388221.5617
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 17388221.5617
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 17388221.5617
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Stenstrom Excavating
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.