## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 1446787.5
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 25000 | 25000
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 10000 | 10000
3 | INLET AND PIPE PROTECTION | EA | 7 | 150 | 1050
4 | CONCRETE TRUCK WASHOUT | EA | 1 | 500 | 500
5 | PAVEMENT REMOVAL | SY | 3835 | 7 | 26845
6 | APPROACH PAVEMENT REMOVAL | SY | 350 | 8 | 2800
7 | SIDEWALK REMOVAL | SF | 120 | 10 | 1200
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 125 | 25 | 3125
9 | ROCK EXCAVATION | CY | 25 | 150 | 3750
10 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 2 | 1000 | 2000
11 | REMOVE FIRE HYDRANT, COMPLETE | EA | 3 | 1250 | 3750
12 | INLETS TO BE RECONSTRUCTED | EA | 1 | 2500 | 2500
13 | PCC APPROACH PAVEMENT, 6" | SY | 155 | 150 | 23250
14 | PCC SIDEWALK, 4" | SF | 120 | 14 | 1680
15 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18(MODIFIED) | LF | 125 | 45 | 5625
16 | DETECTABLE WARNINGS | SF | 30 | 50 | 1500
17 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 3835 | 10 | 38350
18 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 3835 | 12 | 46020
19 | AGGREGATE SHOULDERS, TYPE B, 12" | SY | 345 | 12 | 4140
20 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 11 | 150 | 1650
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 1.75" | TON | 386 | 85 | 32810
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 22 | 225 | 4950
23 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 2.25" | TON | 492 | 100 | 49200
24 | HMA APPROACH PAVEMENT, 3" | SY | 195 | 45 | 8775
25 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 65 | 125 | 8125
26 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 4175 | 115 | 480125
27 | DUCTILE IRON WATER MAIN COMPLETE, 12" | LF | 25 | 450 | 11250
28 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 12" | LF | 50 | 100 | 5000
29 | GATE VALVE AND VALVE BOX, COMPLETE, 3" | EA | 1 | 82.5 | 82.5
30 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 | 2500 | 2500
31 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 17 | 3500 | 59500
32 | BUTTERFLY VALVE AND VALVE BOX, COMPLETE, 12" | EA | 1 | 5000 | 5000
33 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 7 | 6500 | 45500
34 | EXTERIOR FOUNDATION ACCESS PIT | EA | 20 | 750 | 15000
35 | WATER SERVICE (BORED), COMPLETE, 1" | LF | 3350 | 80 | 268000
36 | CONNECT TO EXISTING/RELOCATED WATER METER, COMPLETE | EA | 35 | 700 | 24500
37 | INTERIOR WATER METER RELOCATION, COMPLETE | LF | 1000 | 50 | 50000
38 | CONNECT TO EXISTING 3" WATER MAIN, COMPLETE | EA | 1 | 2000 | 2000
39 | CONNECT TO EXISTING 4" WATER MAIN, COMPLETE | EA | 1 | 2500 | 2500
40 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 3 | 3000 | 9000
41 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 1 | 3500 | 3500
42 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 2 | 4500 | 9000
43 | WATER MAIN PROTECTION, 12" | LF | 245 | 45 | 11025
44 | WATER SERVICE PROTECTION, 2" | LF | 80 | 12 | 960
45 | WATER MAIN LINE STOP, 3" | EA | 1 | 4000 | 4000
46 | WATER MAIN LINE STOP, 4" | EA | 1 | 4250 | 4250
47 | WATER MAIN LINE STOP, 6" | EA | 2 | 4500 | 9000
48 | WATER MAIN LINE STOP, 8" | EA | 1 | 6500 | 6500
49 | WATER MAIN LINE STOP,12" | EA | 1 | 7000 | 7000
50 | INSERTION VALVE, COMPLETE, 3" | EA | 1 | 5000 | 5000
51 | INSERTION VALVE, COMPLETE, 4" | EA | 1 | 5500 | 5500
52 | INSERTION VALVE, COMPLETE, 6" | EA | 1 | 5750 | 5750
53 | INSERTION VALVE, COMPLETE, 8" | EA | 1 | 8500 | 8500
54 | INSERTION VALVE, COMPLETE, 12" | EA | 1 | 13000 | 13000
55 | EXPLORATORY EXCAVATION | CY | 25 | 50 | 1250
56 | PARKWAY RESTORATION | LS | 1 | 40000 | 40000
57 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 10000 | 10000
58 | TREE AND BRUSH REMOVAL | LS | 1 | 7500 | 7500
59 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 50 | 1250
60 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 50 | 1250
61 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | EA | 1 | 2000 | 2000
62 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 2000 | 2000
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | N-Trak Group |  | Northern Illinois Services |  | Fischer Excavating
City of Rockford | [5 empty] | Loves Park, IL |  | Rockford, IL |  | Freeport, IL
Edgebrook Phase 3 WM Replacement
Bid No.: 321-W-017- VENDORS NOTIFIED: 89
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 25000 | 25000 | 8500 | 8500 | 1000 | 1000 | 57500 | 57500 |  | 0 |  | 0 |  | 0
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 10000 | 10000 | 3500 | 3500 | 5000 | 5000 | 3300 | 3300 |  | 0 |  | 0 |  | 0
3 | INLET AND PIPE PROTECTION | EA | 7 | 150 | 1050 | 100 | 700 | 100 | 700 | 150 | 1050 |  | 0 |  | 0 |  | 0
4 | CONCRETE TRUCK WASHOUT | EA | 1 | 500 | 500 | 1 | 1 | 250 | 250 | 360 | 360 |  | 0 |  | 0 |  | 0
5 | PAVEMENT REMOVAL | SY | 3835 | 7 | 26845 | 2 | 7670 | 2.5 | 9587.5 | 6.5 | 24927.5 |  | 0 |  | 0 |  | 0
6 | APPROACH PAVEMENT REMOVAL | SY | 350 | 8 | 2800 | 3 | 1050 | 3 | 1050 | 8 | 2800 |  | 0 |  | 0 |  | 0
7 | SIDEWALK REMOVAL | SF | 120 | 10 | 1200 | 1 | 120 | 1 | 120 | 3 | 360 |  | 0 |  | 0 |  | 0
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 125 | 25 | 3125 | 4 | 500 | 4 | 500 | 6 | 750 |  | 0 |  | 0 |  | 0
9 | ROCK EXCAVATION | CY | 25 | 150 | 3750 | 1 | 25 | 1 | 25 | 60 | 1500 |  | 0 |  | 0 |  | 0
10 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 2 | 1000 | 2000 | 350 | 700 | 350 | 700 | 250 | 500 |  | 0 |  | 0 |  | 0
11 | REMOVE FIRE HYDRANT, COMPLETE | EA | 3 | 1250 | 3750 | 500 | 1500 | 650 | 1950 | 460 | 1380 |  | 0 |  | 0 |  | 0
12 | INLETS TO BE RECONSTRUCTED | EA | 1 | 2500 | 2500 | 850 | 850 | 1500 | 1500 | 525 | 525 |  | 0 |  | 0 |  | 0
13 | PCC APPROACH PAVEMENT, 6" | SY | 155 | 150 | 23250 | 68 | 10540 | 80 | 12400 | 80 | 12400 |  | 0 |  | 0 |  | 0
14 | PCC SIDEWALK, 4" | SF | 120 | 14 | 1680 | 8.25 | 990 | 8 | 960 | 13 | 1560 |  | 0 |  | 0 |  | 0
15 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18(MODIFIED) | LF | 125 | 45 | 5625 | 35 | 4375 | 35 | 4375 | 53 | 6625 |  | 0 |  | 0 |  | 0
16 | DETECTABLE WARNINGS | SF | 30 | 50 | 1500 | 20 | 600 | 30 | 900 | 31 | 930 |  | 0 |  | 0 |  | 0
17 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 3835 | 10 | 38350 | 4.25 | 16298.75 | 5.5 | 21092.5 | 6 | 23010 |  | 0 |  | 0 |  | 0
18 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 3835 | 12 | 46020 | 4.25 | 16298.75 | 5.5 | 21092.5 | 7 | 26845 |  | 0 |  | 0 |  | 0
19 | AGGREGATE SHOULDERS, TYPE B, 12" | SY | 345 | 12 | 4140 | 12 | 4140 | 5 | 1725 | 9.5 | 3277.5 |  | 0 |  | 0 |  | 0
20 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 11 | 150 | 1650 | 110 | 1210 | 236.65 | 2603.15 | 164 | 1804 |  | 0 |  | 0 |  | 0
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 1.75" | TON | 386 | 85 | 32810 | 80 | 30880 | 105.99 | 40912.14 | 131 | 50566 |  | 0 |  | 0 |  | 0
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 22 | 225 | 4950 | 110 | 2420 | 150.03 | 3300.66 | 195 | 4290 |  | 0 |  | 0 |  | 0
23 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 2.25" | TON | 492 | 100 | 49200 | 78 | 38376 | 93.81 | 46154.52 | 150 | 73800 |  | 0 |  | 0 |  | 0
24 | HMA APPROACH PAVEMENT, 3" | SY | 195 | 45 | 8775 | 35 | 6825 | 43.66 | 8513.7 | 45 | 8775 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 300470 |  | 158069.5 |  | 186411.67 |  | 308835
| Award to N-Trak Group | Total |  | As corrected | 300470 |  | 158069.5 |  | 186411.67 |  | 308835
25 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 65 | 125 | 8125 | 92 | 5980 | 90 | 5850 | 100 | 6500 |  | 0 |  | 0 |  | 0
26 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 4175 | 115 | 480125 | 86 | 359050 | 89.16 | 372243 | 100 | 417500 |  | 0 |  | 0 |  | 0
27 | DUCTILE IRON WATER MAIN COMPLETE, 12" | LF | 25 | 450 | 11250 | 180 | 4500 | 175 | 4375 | 240 | 6000 |  | 0 |  | 0 |  | 0
28 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 12" | LF | 50 | 100 | 5000 | 45 | 2250 | 50 | 2500 | 125 | 6250 |  | 0 |  | 0 |  | 0
29 | GATE VALVE AND VALVE BOX, COMPLETE, 3" | EA | 1 | 82.5 | 82.5 | 750 | 750 | 1300 | 1300 | 500 | 500 |  | 0 |  | 0 |  | 0
30 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 | 2500 | 2500 | 1250 | 1250 | 1500 | 1500 | 1350 | 1350 |  | 0 |  | 0 |  | 0
31 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 17 | 3500 | 59500 | 1900 | 32300 | 1880 | 31960 | 1800 | 30600 |  | 0 |  | 0 |  | 0
32 | BUTTERFLY VALVE AND VALVE BOX, COMPLETE, 12" | EA | 1 | 5000 | 5000 | 2800 | 2800 | 2830 | 2830 | 3000 | 3000 |  | 0 |  | 0 |  | 0
33 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 7 | 6500 | 45500 | 5100 | 35700 | 4800 | 33600 | 5500 | 38500 |  | 0 |  | 0 |  | 0
34 | EXTERIOR FOUNDATION ACCESS PIT | EA | 20 | 750 | 15000 | 1 | 20 | 100 | 2000 | 400 | 8000 |  | 0 |  | 0 |  | 0
35 | WATER SERVICE (BORED), COMPLETE, 1" | LF | 3350 | 80 | 268000 | 47 | 157450 | 48 | 160800 | 33 | 110550 |  | 0 |  | 0 |  | 0
36 | CONNECT TO EXISTING/RELOCATED WATER METER, COMPLETE | EA | 35 | 700 | 24500 | 400 | 14000 | 300 | 10500 | 250 | 8750 |  | 0 |  | 0 |  | 0
37 | INTERIOR WATER METER RELOCATION, COMPLETE | LF | 1000 | 50 | 50000 | 13 | 13000 | 18 | 18000 | 22 | 22000 |  | 0 |  | 0 |  | 0
38 | CONNECT TO EXISTING 3" WATER MAIN, COMPLETE | EA | 1 | 2000 | 2000 | 1300 | 1300 | 2000 | 2000 | 2450 | 2450 |  | 0 |  | 0 |  | 0
39 | CONNECT TO EXISTING 4" WATER MAIN, COMPLETE | EA | 1 | 2500 | 2500 | 1300 | 1300 | 2000 | 2000 | 2680 | 2680 |  | 0 |  | 0 |  | 0
40 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 3 | 3000 | 9000 | 1300 | 3900 | 2000 | 6000 | 3445 | 10335 |  | 0 |  | 0 |  | 0
41 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 1 | 3500 | 3500 | 1000 | 1000 | 2000 | 2000 | 3180 | 3180 |  | 0 |  | 0 |  | 0
42 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 2 | 4500 | 9000 | 2200 | 4400 | 2000 | 4000 | 3640 | 7280 |  | 0 |  | 0 |  | 0
43 | WATER MAIN PROTECTION, 12" | LF | 245 | 45 | 11025 | 35 | 8575 | 35 | 8575 | 50 | 12250 |  | 0 |  | 0 |  | 0
44 | WATER SERVICE PROTECTION, 2" | LF | 80 | 12 | 960 | 2 | 160 | 7 | 560 | 15 | 1200 |  | 0 |  | 0 |  | 0
45 | WATER MAIN LINE STOP, 3" | EA | 1 | 4000 | 4000 | 2800 | 2800 | 3000 | 3000 | 3880 | 3880 |  | 0 |  | 0 |  | 0
46 | WATER MAIN LINE STOP, 4" | EA | 1 | 4250 | 4250 | 3000 | 3000 | 1500 | 1500 | 4350 | 4350 |  | 0 |  | 0 |  | 0
47 | WATER MAIN LINE STOP, 6" | EA | 2 | 4500 | 9000 | 3050 | 6100 | 4000 | 8000 | 4550 | 9100 |  | 0 |  | 0 |  | 0
48 | WATER MAIN LINE STOP, 8" | EA | 1 | 6500 | 6500 | 3400 | 3400 | 2500 | 2500 | 5380 | 5380 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 1336787.5 |  | 823054.5 |  | 874004.67 |  | 1030420
| Award to N-Trak Group | Total |  | As corrected | 1336787.5 |  | 823054.5 |  | 874004.67 |  | 1030420
49 | WATER MAIN LINE STOP,12" | EA | 1 | 7000 | 7000 | 5000 | 5000 | 6400 | 6400 | 7250 | 7250 |  | 0 |  | 0 |  | 0
50 | INSERTION VALVE, COMPLETE, 3" | EA | 1 | 5000 | 5000 | 4400 | 4400 | 4700 | 4700 | 6950 | 6950 |  | 0 |  | 0 |  | 0
51 | INSERTION VALVE, COMPLETE, 4" | EA | 1 | 5500 | 5500 | 4600 | 4600 | 5000 | 5000 | 6000 | 6000 |  | 0 |  | 0 |  | 0
52 | INSERTION VALVE, COMPLETE, 6" | EA | 1 | 5750 | 5750 | 4900 | 4900 | 5200 | 5200 | 6400 | 6400 |  | 0 |  | 0 |  | 0
53 | INSERTION VALVE, COMPLETE, 8" | EA | 1 | 8500 | 8500 | 5500 | 5500 | 5600 | 5600 | 6800 | 6800 |  | 0 |  | 0 |  | 0
54 | INSERTION VALVE, COMPLETE, 12" | EA | 1 | 13000 | 13000 | 8900 | 8900 | 9100 | 9100 | 12350 | 12350 |  | 0 |  | 0 |  | 0
55 | EXPLORATORY EXCAVATION | CY | 25 | 50 | 1250 | 25 | 625 | 70 | 1750 | 30 | 750 |  | 0 |  | 0 |  | 0
56 | PARKWAY RESTORATION | LS | 1 | 40000 | 40000 | 10000 | 10000 | 16700 | 16700 | 14450 | 14450 |  | 0 |  | 0 |  | 0
57 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 10000 | 10000 | 7000 | 7000 | 2500 | 2500 | 2500 | 2500 |  | 0 |  | 0 |  | 0
58 | TREE AND BRUSH REMOVAL | LS | 1 | 7500 | 7500 | 1 | 1 | 4000 | 4000 | 3800 | 3800 |  | 0 |  | 0 |  | 0
59 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 50 | 1250 | 1 | 25 | 1 | 25 | 80 | 2000 |  | 0 |  | 0 |  | 0
60 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 50 | 1250 | 1 | 25 | 1 | 25 | 75 | 1875 |  | 0 |  | 0 |  | 0
61 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | EA | 1 | 2000 | 2000 | 1 | 1 | 1 | 1 | 2400 | 2400 |  | 0 |  | 0 |  | 0
62 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 2000 | 2000 | 1 | 1 | 1500 | 1500 | 1200 | 1200 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 1446787.5 |  | 874032.5 |  | 936505.67 |  | 1105145
| Award to N-Trak Group | Bid |  | As corrected | 1446787.5 |  | 874032.5 |  | 936505.67 |  | 1105145
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Edgebrook Phase 3 WM Replacement
Item No. | Items | Units | Quantity | Unit Price | Total
1 | MOBILIZATION | LS | 1 |  | 0
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 |  | 0
3 | INLET AND PIPE PROTECTION | EA | 7 |  | 0
4 | CONCRETE TRUCK WASHOUT | EA | 1 |  | 0
5 | PAVEMENT REMOVAL | SY | 3835 |  | 0
6 | APPROACH PAVEMENT REMOVAL | SY | 350 |  | 0
7 | SIDEWALK REMOVAL | SF | 120 |  | 0
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 125 |  | 0
9 | ROCK EXCAVATION | CY | 25 |  | 0
10 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 2 |  | 0
11 | REMOVE FIRE HYDRANT, COMPLETE | EA | 3 |  | 0
12 | INLETS TO BE RECONSTRUCTED | EA | 1 |  | 0
13 | PCC APPROACH PAVEMENT, 6" | SY | 155 |  | 0
14 | PCC SIDEWALK, 4" | SF | 120 |  | 0
15 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18(MODIFIED) | LF | 125 |  | 0
16 | DETECTABLE WARNINGS | SF | 30 |  | 0
17 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 3835 |  | 0
18 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 3835 |  | 0
19 | AGGREGATE SHOULDERS, TYPE B, 12" | SY | 345 |  | 0
20 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 11 |  | 0
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 1.75" | TON | 386 |  | 0
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 22 |  | 0
23 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 2.25" | TON | 492 |  | 0
24 | HMA APPROACH PAVEMENT, 3" | SY | 195 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 65 |  | 0
26 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 4175 |  | 0
27 | DUCTILE IRON WATER MAIN COMPLETE, 12" | LF | 25 |  | 0
28 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 12" | LF | 50 |  | 0
29 | GATE VALVE AND VALVE BOX, COMPLETE, 3" | EA | 1 |  | 0
30 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 |  | 0
31 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 17 |  | 0
32 | BUTTERFLY VALVE AND VALVE BOX, COMPLETE, 12" | EA | 1 |  | 0
33 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 7 |  | 0
34 | EXTERIOR FOUNDATION ACCESS PIT | EA | 20 |  | 0
35 | WATER SERVICE (BORED), COMPLETE, 1" | LF | 3350 |  | 0
36 | CONNECT TO EXISTING/RELOCATED WATER METER, COMPLETE | EA | 35 |  | 0
37 | INTERIOR WATER METER RELOCATION, COMPLETE | LF | 1000 |  | 0
38 | CONNECT TO EXISTING 3" WATER MAIN, COMPLETE | EA | 1 |  | 0
39 | CONNECT TO EXISTING 4" WATER MAIN, COMPLETE | EA | 1 |  | 0
40 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 3 |  | 0
41 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 1 |  | 0
42 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 2 |  | 0
43 | WATER MAIN PROTECTION, 12" | LF | 245 |  | 0
44 | WATER SERVICE PROTECTION, 2" | LF | 80 |  | 0
45 | WATER MAIN LINE STOP, 3" | EA | 1 |  | 0
46 | WATER MAIN LINE STOP, 4" | EA | 1 |  | 0
47 | WATER MAIN LINE STOP, 6" | EA | 2 |  | 0
48 | WATER MAIN LINE STOP, 8" | EA | 1 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | WATER MAIN LINE STOP,12" | EA | 1 |  | 0
50 | INSERTION VALVE, COMPLETE, 3" | EA | 1 |  | 0
51 | INSERTION VALVE, COMPLETE, 4" | EA | 1 |  | 0
52 | INSERTION VALVE, COMPLETE, 6" | EA | 1 |  | 0
53 | INSERTION VALVE, COMPLETE, 8" | EA | 1 |  | 0
54 | INSERTION VALVE, COMPLETE, 12" | EA | 1 |  | 0
55 | EXPLORATORY EXCAVATION | CY | 25 |  | 0
56 | PARKWAY RESTORATION | LS | 1 |  | 0
57 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 |  | 0
58 | TREE AND BRUSH REMOVAL | LS | 1 |  | 0
59 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 |  | 0
60 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 |  | 0
61 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | EA | 1 |  | 0
62 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Edgebrook Phase 3 WM Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 25000 | 25000
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 10000 | 10000
3 | INLET AND PIPE PROTECTION | EA | 7 | 150 | 1050
4 | CONCRETE TRUCK WASHOUT | EA | 1 | 500 | 500
5 | PAVEMENT REMOVAL | SY | 3835 | 7 | 26845
6 | APPROACH PAVEMENT REMOVAL | SY | 350 | 8 | 2800
7 | SIDEWALK REMOVAL | SF | 120 | 10 | 1200
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 125 | 25 | 3125
9 | ROCK EXCAVATION | CY | 25 | 150 | 3750
10 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 2 | 1000 | 2000
11 | REMOVE FIRE HYDRANT, COMPLETE | EA | 3 | 1250 | 3750
12 | INLETS TO BE RECONSTRUCTED | EA | 1 | 2500 | 2500
13 | PCC APPROACH PAVEMENT, 6" | SY | 155 | 150 | 23250
14 | PCC SIDEWALK, 4" | SF | 120 | 14 | 1680
15 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18(MODIFIED) | LF | 125 | 45 | 5625
16 | DETECTABLE WARNINGS | SF | 30 | 50 | 1500
17 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 3835 | 10 | 38350
18 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 3835 | 12 | 46020
19 | AGGREGATE SHOULDERS, TYPE B, 12" | SY | 345 | 12 | 4140
20 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 11 | 150 | 1650
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 1.75" | TON | 386 | 85 | 32810
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 22 | 225 | 4950
23 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 2.25" | TON | 492 | 100 | 49200
24 | HMA APPROACH PAVEMENT, 3" | SY | 195 | 45 | 8775
|  |  |  | Sub Total | 300470
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Edgebrook Phase 3 WM Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 65 | 125 | 8125
26 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 4175 | 115 | 480125
27 | DUCTILE IRON WATER MAIN COMPLETE, 12" | LF | 25 | 450 | 11250
28 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 12" | LF | 50 | 100 | 5000
29 | GATE VALVE AND VALVE BOX, COMPLETE, 3" | EA | 1 | 82.5 | 82.5
30 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 | 2500 | 2500
31 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 17 | 3500 | 59500
32 | BUTTERFLY VALVE AND VALVE BOX, COMPLETE, 12" | EA | 1 | 5000 | 5000
33 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 7 | 6500 | 45500
34 | EXTERIOR FOUNDATION ACCESS PIT | EA | 20 | 750 | 15000
35 | WATER SERVICE (BORED), COMPLETE, 1" | LF | 3350 | 80 | 268000
36 | CONNECT TO EXISTING/RELOCATED WATER METER, COMPLETE | EA | 35 | 700 | 24500
37 | INTERIOR WATER METER RELOCATION, COMPLETE | LF | 1000 | 50 | 50000
38 | CONNECT TO EXISTING 3" WATER MAIN, COMPLETE | EA | 1 | 2000 | 2000
39 | CONNECT TO EXISTING 4" WATER MAIN, COMPLETE | EA | 1 | 2500 | 2500
40 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 3 | 3000 | 9000
41 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 1 | 3500 | 3500
42 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 2 | 4500 | 9000
43 | WATER MAIN PROTECTION, 12" | LF | 245 | 45 | 11025
44 | WATER SERVICE PROTECTION, 2" | LF | 80 | 12 | 960
45 | WATER MAIN LINE STOP, 3" | EA | 1 | 4000 | 4000
46 | WATER MAIN LINE STOP, 4" | EA | 1 | 4250 | 4250
47 | WATER MAIN LINE STOP, 6" | EA | 2 | 4500 | 9000
48 | WATER MAIN LINE STOP, 8" | EA | 1 | 6500 | 6500
|  |  |  | Sub Total | 1336787.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Edgebrook Phase 3 WM Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | WATER MAIN LINE STOP,12" | EA | 1 | 7000 | 7000
50 | INSERTION VALVE, COMPLETE, 3" | EA | 1 | 5000 | 5000
51 | INSERTION VALVE, COMPLETE, 4" | EA | 1 | 5500 | 5500
52 | INSERTION VALVE, COMPLETE, 6" | EA | 1 | 5750 | 5750
53 | INSERTION VALVE, COMPLETE, 8" | EA | 1 | 8500 | 8500
54 | INSERTION VALVE, COMPLETE, 12" | EA | 1 | 13000 | 13000
55 | EXPLORATORY EXCAVATION | CY | 25 | 50 | 1250
56 | PARKWAY RESTORATION | LS | 1 | 40000 | 40000
57 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 10000 | 10000
58 | TREE AND BRUSH REMOVAL | LS | 1 | 7500 | 7500
59 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 50 | 1250
60 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 50 | 1250
61 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | EA | 1 | 2000 | 2000
62 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 2000 | 2000
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1446787.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Edgebrook Phase 3 WM Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1446787.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL | [5 empty] | SECTION | Edgebrook Phase 3 WM Replacement
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | MOBILIZATION | 1 | LS | 8500 |  | 1 |  |  | 8500
2 | CONSTRUCTION LAYOUT STAKES | 1 | LS | 3500 |  | 1 |  |  | 3500
3 | INLET AND PIPE PROTECTION | 7 | EA | 700 |  | 7 |  |  | 100
4 | CONCRETE TRUCK WASHOUT | 1 | EA | 1 |  | 1 |  |  | 1
5 | PAVEMENT REMOVAL | 3835 | SY | 7670 |  | 3835 |  |  | 2
6 | APPROACH PAVEMENT REMOVAL | 350 | SY | 1050 |  | 350 |  |  | 3
7 | SIDEWALK REMOVAL | 120 | SF | 120 |  | 120 |  |  | 1
8 | COMBINATION CURB AND GUTTER REMOVAL | 125 | LF | 500 |  | 125 |  |  | 4
9 | ROCK EXCAVATION | 25 | CY | 25 |  | 25 |  |  | 1
10 | REMOVE VALVE AND VALVE BOX, COMPLETE | 2 | EA | 700 |  | 2 |  |  | 350
11 | REMOVE FIRE HYDRANT, COMPLETE | 3 | EA | 1500 |  | 3 |  |  | 500
12 | INLETS TO BE RECONSTRUCTED | 1 | EA | 850 |  | 1 |  |  | 850
13 | PCC APPROACH PAVEMENT, 6" | 155 | SY | 10540 |  | 155 |  |  | 68
14 | PCC SIDEWALK, 4" | 120 | SF | 990 |  | 120 |  |  | 8.25
15 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18(MODIFIED) | 125 | LF | 4375 |  | 125 |  |  | 35
16 | DETECTABLE WARNINGS | 30 | SF | 600 |  | 30 |  |  | 20
17 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | 3835 | SY | 16298.75 |  | 3835 |  |  | 4.25
18 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | 3835 | SY | 16298.75 |  | 3835 |  |  | 4.25
19 | AGGREGATE SHOULDERS, TYPE B, 12" | 345 | SY | 4140 |  | 345 |  |  | 12
20 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | 11 | TON | 1210 |  | 11 |  |  | 110
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 1.75" | 386 | TON | 30880 |  | 386 |  |  | 80
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | 22 | TON | 2420 |  | 22 |  |  | 110
23 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 2.25" | 492 | TON | 38376 |  | 492 |  |  | 78
24 | HMA APPROACH PAVEMENT, 3" | 195 | SY | 6825 |  | 195 |  |  | 35
Sub Total |  |  |  | 158069.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL | [5 empty] | SECTION | Edgebrook Phase 3 WM Replacement
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | 65 | LF | 5980 |  | 65 |  |  | 92
26 | DUCTILE IRON WATER MAIN COMPLETE, 8" | 4175 | LF | 359050 |  | 4175 |  |  | 86
27 | DUCTILE IRON WATER MAIN COMPLETE, 12" | 25 | LF | 4500 |  | 25 |  |  | 180
28 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 12" | 50 | LF | 2250 |  | 50 |  |  | 45
29 | GATE VALVE AND VALVE BOX, COMPLETE, 3" | 1 | EA | 750 |  | 1 |  |  | 750
30 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | 1 | EA | 1250 |  | 1 |  |  | 1250
31 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | 17 | EA | 32300 |  | 17 |  |  | 1900
32 | BUTTERFLY VALVE AND VALVE BOX, COMPLETE, 12" | 1 | EA | 2800 |  | 1 |  |  | 2800
33 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | 7 | EA | 35700 |  | 7 |  |  | 5100
34 | EXTERIOR FOUNDATION ACCESS PIT | 20 | EA | 20 |  | 20 |  |  | 1
35 | WATER SERVICE (BORED), COMPLETE, 1" | 3350 | LF | 157450 |  | 3350 |  |  | 47
36 | CONNECT TO EXISTING/RELOCATED WATER METER, COMPLETE | 35 | EA | 14000 |  | 35 |  |  | 400
37 | INTERIOR WATER METER RELOCATION, COMPLETE | 1000 | LF | 13000 |  | 1000 |  |  | 13
38 | CONNECT TO EXISTING 3" WATER MAIN, COMPLETE | 1 | EA | 1300 |  | 1 |  |  | 1300
39 | CONNECT TO EXISTING 4" WATER MAIN, COMPLETE | 1 | EA | 1300 |  | 1 |  |  | 1300
40 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | 3 | EA | 3900 |  | 3 |  |  | 1300
41 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | 1 | EA | 1000 |  | 1 |  |  | 1000
42 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | 2 | EA | 4400 |  | 2 |  |  | 2200
43 | WATER MAIN PROTECTION, 12" | 245 | LF | 8575 |  | 245 |  |  | 35
44 | WATER SERVICE PROTECTION, 2" | 80 | LF | 160 |  | 80 |  |  | 2
45 | WATER MAIN LINE STOP, 3" | 1 | EA | 2800 |  | 1 |  |  | 2800
46 | WATER MAIN LINE STOP, 4" | 1 | EA | 3000 |  | 1 |  |  | 3000
47 | WATER MAIN LINE STOP, 6" | 2 | EA | 6100 |  | 2 |  |  | 3050
48 | WATER MAIN LINE STOP, 8" | 1 | EA | 3400 |  | 1 |  |  | 3400
Sub Total |  |  |  | 823054.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL | [5 empty] | SECTION | Edgebrook Phase 3 WM Replacement
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | WATER MAIN LINE STOP,12" | 1 | EA | 5000 |  | 1 |  |  | 5000
50 | INSERTION VALVE, COMPLETE, 3" | 1 | EA | 4400 |  | 1 |  |  | 4400
51 | INSERTION VALVE, COMPLETE, 4" | 1 | EA | 4600 |  | 1 |  |  | 4600
52 | INSERTION VALVE, COMPLETE, 6" | 1 | EA | 4900 |  | 1 |  |  | 4900
53 | INSERTION VALVE, COMPLETE, 8" | 1 | EA | 5500 |  | 1 |  |  | 5500
54 | INSERTION VALVE, COMPLETE, 12" | 1 | EA | 8900 |  | 1 |  |  | 8900
55 | EXPLORATORY EXCAVATION | 25 | CY | 625 |  | 25 |  |  | 25
56 | PARKWAY RESTORATION | 1 | LS | 10000 |  | 1 |  |  | 10000
57 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | 1 | LS | 7000 |  | 1 |  |  | 7000
58 | TREE AND BRUSH REMOVAL | 1 | LS | 1 |  | 1 |  |  | 1
59 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | 25 | CY | 25 |  | 25 |  |  | 1
60 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | 25 | CY | 25 |  | 25 |  |  | 1
61 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | 1 | EA | 1 |  | 1 |  |  | 1
62 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | 1 | EA | 1 |  | 1 |  |  | 1
Total |  |  |  | 874032.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL | [5 empty] | SECTION | Edgebrook Phase 3 WM Replacement
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 874032.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Edgebrook Phase 3 WM Replacement
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | N-Trak Group
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.