## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 692260.9974
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | Mobilization | L SUM | 1 | 5000 | 5000
2 | Building Removal, 5111 Carter Court | L SUM | 1 | 15400 | 15400
3 | Building Removal, 1214 Fieldcrest Drive | L SUM | 1 | 10000 | 10000
4 | Building Removal, 1218 Fieldcrest Drive | L SUM | 1 | 10500 | 10500
5 | Building Removal, 1218 Esmond Drive | L SUM | 1 | 13000 | 13000
6 | Asbestos Removal, 5111 Carter Court | L SUM | 1 | 800 | 800
7 | Asbestos Removal, 1218 Fieldcrest Drive | L SUM | 1 | 2000 | 2000
8 | Asbestos Removal, 1218 Esmond Drive | L SUM | 1 | 1200 | 1200
9 | Tree Removal, Under 6 Units Diameter | UNIT | 5 | 120 | 600
10 | Tree Removal, 6 to 15 Units Diameter | UNIT | 214 | 30 | 6420
11 | Tree Removal, Over 15 Units Diameter | UNIT | 135 | 43 | 5805
12 | Earth Excavation | CU YD | 6122 | 30 | 183660
13 | Trench Backfill | CU YD | 242 | 55 | 13310
14 | Parkway Restoration | L SUM | 1 | 27628 | 27628
15 | Perimeter Erosion Barrier | FOOT | 1067 | 2 | 2134
16 | Inlet and Pipe Protection | EACH | 7 | 150 | 1050
17 | Aggregate Base Course, Type B, CA-6, 4" | SQ YD | 20 | 8 | 160
18 | Aggregate Base Course, Type B, CA-6, 6" | SQ YD | 252 | 10 | 2520
19 | Subbase Granular Material, Type B, 6" | SQ YD | 199 | 17 | 3383
20 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 2.5" | TON | 20 | 100 | 2000
21 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | TON | 13 | 115 | 1495
22 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | TON | 12 | 130 | 1560
23 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | TON | 7 | 130 | 910
24 | P.C.C Approach Pavement, 8" | SQ YD | 20 | 80 | 1600
25 | Portland Cement Concrete Sidewalk, 4" | SQ FT | 441 | 12 | 5292
26 | Portland Cement Concrete Sidewalk, 6" | SQ FT | 23 | 18 | 414
27 | Combination Curb and Gutter Removal | FOOT | 164 | 10 | 1640
28 | Sidewalk Removal | SQ FT | 464 | 5 | 2320
29 | Pavement Removal | SQ YD | 199 | 12 | 2388
30 | Approach Pavement Removal | SQ FT | 783 | 1.3333 | 1043.9974
31 | Aggregate Base Course Removal | SQ YD | 252 | 12 | 3024
32 | Reinforced Concrete End Section, 30" Dual Pipes | EACH | 6 | 4000 | 24000
33 | Connection to Existing Drainage Structure | EACH | 1 | 1500 | 1500
34 | Storm Sewers, Class A, Type 1, 30" (RCP) | FOOT | 690 | 65 | 44850
35 | Storm Sewers, Class B, Type 1, 30" (HDPE) | FOOT | 769 | 65 | 49985
36 | Storm Sewers, Water Main Quality, 30" Complete | FOOT | 51 | 80 | 4080
37 | Storm Sewer Removal, 36" | FOOT | 521 | 27 | 14067
38 | Connect to Existing 6" Water Main, Complete | EACH | 2 | 2000 | 4000
39 | Remove Existing 6" Watermain | FOOT | 52 | 20 | 1040
40 | Ductile Iron Water Main Complete, 6" | FOOT | 52 | 110 | 5720
41 | Water Main Protection, 12" | FOOT | 27.5 | 35 | 962.5
42 | Water Main Line Stop, 6" | EACH | 2 | 4000 | 8000
43 | Water Service Connection, Complete, 1" | EACH | 1 | 1500 | 1500
44 | Pipe Underdrains, Type I, 4" | FOOT | 175 | 0.5 | 87.5
45 | Pipe Underdrain, Cleanout | EACH | 2 | 50 | 100
46 | Manholes, Type A, 9' Dia., Inlet 700 | EACH | 1 | 17250 | 17250
47 | Manholes, Type A, 9' Dia., Type 1 Frame, Closed Lid | EACH | 1 | 15750 | 15750
48 | Manholes, Type A, 9' Dia., Type 1 Frame, Open Lid | EACH | 3 | 15750 | 47250
49 | Manholes, Type A, 9' Dia., Type 1 Frame, Curb Inlet | EACH | 3 | 17500 | 52500
50 | Removing Inlets | EACH | 4 | 1000 | 4000
51 | Removing Manholes | EACH | 4 | 1200 | 4800
52 | Combination Curb and Gutter, Type M-6.18 (Modified) | FOOT | 164 | 45 | 7380
53 | Paved Ditch, Type B-15 | FOOT | 283 | 50 | 14150
54 | Fence Removal | FOOT | 304 | 3 | 912
55 | Fence | FOOT | 304 | 30 | 9120
56 | Non-Special Waste Disposal | CY YD | 200 | 25 | 5000
57 | Special Waste Disposal | CU YD | 200 | 30 | 6000
58 | Soil Disposal Analysis | EACH | 10 | 1000 | 10000
59 | Special Waste Plans and Reports (Special) | L SUM | 1 | 5000 | 5000
60 | Traffic Control and Protection, Special | L SUM | 1 | 5000 | 5000
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | N-TRAK Group |  | Northern Illinois Service |  | Fischer Excavating
City of Rockford | [5 empty] | Loves Park, IL |  | Rockford, IL |  | Freeport, IL
Bid No.: 821-PW-062
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Mobilization | L SUM | 1 | 5000 | 5000 | 20000 | 20000 | 16145 | 16145 | 11400 | 11400 |  | 0 |  | 0 |  | 0
2 | Building Removal, 5111 Carter Court | L SUM | 1 | 15400 | 15400 | 8000 | 8000 | 8100 | 8100 | 18700 | 18700 |  | 0 |  | 0 |  | 0
3 | Building Removal, 1214 Fieldcrest Drive | L SUM | 1 | 10000 | 10000 | 8000 | 8000 | 8550 | 8550 | 18700 | 18700 |  | 0 |  | 0 |  | 0
4 | Building Removal, 1218 Fieldcrest Drive | L SUM | 1 | 10500 | 10500 | 8000 | 8000 | 8650 | 8650 | 19100 | 19100 |  | 0 |  | 0 |  | 0
5 | Building Removal, 1218 Esmond Drive | L SUM | 1 | 13000 | 13000 | 8000 | 8000 | 8650 | 8650 | 20100 | 20100 |  | 0 |  | 0 |  | 0
6 | Asbestos Removal, 5111 Carter Court | L SUM | 1 | 800 | 800 | 1000 | 1000 | 950 | 950 | 950 | 950 |  | 0 |  | 0 |  | 0
7 | Asbestos Removal, 1218 Fieldcrest Drive | L SUM | 1 | 2000 | 2000 | 5000 | 5000 | 4950 | 4950 | 4950 | 4950 |  | 0 |  | 0 |  | 0
8 | Asbestos Removal, 1218 Esmond Drive | L SUM | 1 | 1200 | 1200 | 1000 | 1000 | 950 | 950 | 950 | 950 |  | 0 |  | 0 |  | 0
9 | Tree Removal, Under 6 Units Diameter | UNIT | 5 | 120 | 600 | 13 | 65 | 12 | 60 | 12 | 60 |  | 0 |  | 0 |  | 0
10 | Tree Removal, 6 to 15 Units Diameter | UNIT | 214 | 30 | 6420 | 19 | 4066 | 18 | 3852 | 18 | 3852 |  | 0 |  | 0 |  | 0
11 | Tree Removal, Over 15 Units Diameter | UNIT | 135 | 43 | 5805 | 29 | 3915 | 28 | 3780 | 28 | 3780 |  | 0 |  | 0 |  | 0
12 | Earth Excavation | CU YD | 6122 | 30 | 183660 | 15 | 91830 | 39.31 | 240655.82 | 20 | 122440 |  | 0 |  | 0 |  | 0
13 | Trench Backfill | CU YD | 242 | 55 | 13310 | 20 | 4840 | 0.01 | 2.42 | 53 | 12826 |  | 0 |  | 0 |  | 0
14 | Parkway Restoration | L SUM | 1 | 27628 | 27628 | 65000 | 65000 | 35000 | 35000 | 40100 | 40100 |  | 0 |  | 0 |  | 0
15 | Perimeter Erosion Barrier | FOOT | 1067 | 2 | 2134 | 3 | 3201 | 3 | 3201 | 3 | 3201 |  | 0 |  | 0 |  | 0
16 | Inlet and Pipe Protection | EACH | 7 | 150 | 1050 | 75 | 525 | 150 | 1050 | 160 | 1120 |  | 0 |  | 0 |  | 0
17 | Aggregate Base Course, Type B, CA-6, 4" | SQ YD | 20 | 8 | 160 | 15 | 300 | 18 | 360 | 4 | 80 |  | 0 |  | 0 |  | 0
18 | Aggregate Base Course, Type B, CA-6, 6" | SQ YD | 252 | 10 | 2520 | 15 | 3780 | 18 | 4536 | 6 | 1512 |  | 0 |  | 0 |  | 0
19 | Subbase Granular Material, Type B, 6" | SQ YD | 199 | 17 | 3383 | 15 | 2985 | 18 | 3582 | 6 | 1194 |  | 0 |  | 0 |  | 0
20 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 2.5" | TON | 20 | 100 | 2000 | 180 | 3600 | 174 | 3480 | 174 | 3480 |  | 0 |  | 0 |  | 0
21 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | TON | 13 | 115 | 1495 | 180 | 2340 | 139.85 | 1818.05 | 140 | 1820 |  | 0 |  | 0 |  | 0
22 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | TON | 12 | 130 | 1560 | 180 | 2160 | 179.25 | 2151 | 180 | 2160 |  | 0 |  | 0 |  | 0
23 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | TON | 7 | 130 | 910 | 180 | 1260 | 270.25 | 1891.75 | 270 | 1890 |  | 0 |  | 0 |  | 0
24 | P.C.C Approach Pavement, 8" | SQ YD | 20 | 80 | 1600 | 98 | 1960 | 85.5 | 1710 | 178 | 3560 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 312135 |  | 250827 |  | 364075.04 |  | 297925
| Award to N-TRAK Group | Total |  | As corrected | 312135 |  | 250827 |  | 364075.04 |  | 297925
25 | Portland Cement Concrete Sidewalk, 4" | SQ FT | 441 | 12 | 5292 | 5 | 2205 | 6.1 | 2690.1 | 9.5 | 4189.5 |  | 0 |  | 0 |  | 0
26 | Portland Cement Concrete Sidewalk, 6" | SQ FT | 23 | 18 | 414 | 6.5 | 149.5 | 7.5 | 172.5 | 10.5 | 241.5 |  | 0 |  | 0 |  | 0
27 | Combination Curb and Gutter Removal | FOOT | 164 | 10 | 1640 | 6 | 984 | 4 | 656 | 3 | 492 |  | 0 |  | 0 |  | 0
28 | Sidewalk Removal | SQ FT | 464 | 5 | 2320 | 2 | 928 | 0.3 | 139.2 | 2.3 | 1067.2 |  | 0 |  | 0 |  | 0
29 | Pavement Removal | SQ YD | 199 | 12 | 2388 | 9 | 1791 | 1 | 199 | 10.6 | 2109.4 |  | 0 |  | 0 |  | 0
30 | Approach Pavement Removal | SQ FT | 783 | 1.3333 | 1043.9974 | 1 | 783 | 0.3 | 234.9 | 7.75 | 6068.25 |  | 0 |  | 0 |  | 0
31 | Aggregate Base Course Removal | SQ YD | 252 | 12 | 3024 | 5 | 1260 | 0.5 | 126 | 3.5 | 882 |  | 0 |  | 0 |  | 0
32 | Reinforced Concrete End Section, 30" Dual Pipes | EACH | 6 | 4000 | 24000 | 7500 | 45000 | 10000 | 60000 | 8102 | 48612 |  | 0 |  | 0 |  | 0
33 | Connection to Existing Drainage Structure | EACH | 1 | 1500 | 1500 | 2500 | 2500 | 1500 | 1500 | 1963 | 1963 |  | 0 |  | 0 |  | 0
34 | Storm Sewers, Class A, Type 1, 30" (RCP) | FOOT | 690 | 65 | 44850 | 90 | 62100 | 124 | 85560 | 127 | 87630 |  | 0 |  | 0 |  | 0
35 | Storm Sewers, Class B, Type 1, 30" (HDPE) | FOOT | 769 | 65 | 49985 | 100 | 76900 | 124 | 95356 | 155 | 119195 |  | 0 |  | 0 |  | 0
36 | Storm Sewers, Water Main Quality, 30" Complete | FOOT | 51 | 80 | 4080 | 330 | 16830 | 330 | 16830 | 399 | 20349 |  | 0 |  | 0 |  | 0
37 | Storm Sewer Removal, 36" | FOOT | 521 | 27 | 14067 | 10 | 5210 | 15 | 7815 | 30 | 15630 |  | 0 |  | 0 |  | 0
38 | Connect to Existing 6" Water Main, Complete | EACH | 2 | 2000 | 4000 | 3000 | 6000 | 2500 | 5000 | 2820 | 5640 |  | 0 |  | 0 |  | 0
39 | Remove Existing 6" Watermain | FOOT | 52 | 20 | 1040 | 20 | 1040 | 20 | 1040 | 15 | 780 |  | 0 |  | 0 |  | 0
40 | Ductile Iron Water Main Complete, 6" | FOOT | 52 | 110 | 5720 | 180 | 9360 | 150 | 7800 | 142 | 7384 |  | 0 |  | 0 |  | 0
41 | Water Main Protection, 12" | FOOT | 27.5 | 35 | 962.5 | 65 | 1787.5 | 80 | 2200 | 88 | 2420 |  | 0 |  | 0 |  | 0
42 | Water Main Line Stop, 6" | EACH | 2 | 4000 | 8000 | 4500 | 9000 | 4000 | 8000 | 3900 | 7800 |  | 0 |  | 0 |  | 0
43 | Water Service Connection, Complete, 1" | EACH | 1 | 1500 | 1500 | 1700 | 1700 | 3000 | 3000 | 1789 | 1789 |  | 0 |  | 0 |  | 0
44 | Pipe Underdrains, Type I, 4" | FOOT | 175 | 0.5 | 87.5 | 22 | 3850 | 25 | 4375 | 17 | 2975 |  | 0 |  | 0 |  | 0
45 | Pipe Underdrain, Cleanout | EACH | 2 | 50 | 100 | 150 | 300 | 750 | 1500 | 350 | 700 |  | 0 |  | 0 |  | 0
46 | Manholes, Type A, 9' Dia., Inlet 700 | EACH | 1 | 17250 | 17250 | 10500 | 10500 | 15000 | 15000 | 17000 | 17000 |  | 0 |  | 0 |  | 0
47 | Manholes, Type A, 9' Dia., Type 1 Frame, Closed Lid | EACH | 1 | 15750 | 15750 | 10500 | 10500 | 15000 | 15000 | 17100 | 17100 |  | 0 |  | 0 |  | 0
48 | Manholes, Type A, 9' Dia., Type 1 Frame, Open Lid | EACH | 3 | 15750 | 47250 | 10500 | 31500 | 15000 | 45000 | 16500 | 49500 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 568398.9974 |  | 553005 |  | 743268.74 |  | 719441.85
| Award to N-TRAK Group | Total |  | As corrected | 568398.9974 |  | 553005 |  | 743268.74 |  | 719441.85
49 | Manholes, Type A, 9' Dia., Type 1 Frame, Curb Inlet | EACH | 3 | 17500 | 52500 | 10500 | 31500 | 15000 | 45000 | 16850 | 50550 |  | 0 |  | 0 |  | 0
50 | Removing Inlets | EACH | 4 | 1000 | 4000 | 500 | 2000 | 750 | 3000 | 333 | 1332 |  | 0 |  | 0 |  | 0
51 | Removing Manholes | EACH | 4 | 1200 | 4800 | 700 | 2800 | 750 | 3000 | 453 | 1812 |  | 0 |  | 0 |  | 0
52 | Combination Curb and Gutter, Type M-6.18 (Modified) | FOOT | 164 | 45 | 7380 | 30 | 4920 | 34.5 | 5658 | 39 | 6396 |  | 0 |  | 0 |  | 0
53 | Paved Ditch, Type B-15 | FOOT | 283 | 50 | 14150 | 75 | 21225 | 42 | 11886 | 43 | 12169 |  | 0 |  | 0 |  | 0
54 | Fence Removal | FOOT | 304 | 3 | 912 | 10 | 3040 | 10 | 3040 | 5.7 | 1732.8 |  | 0 |  | 0 |  | 0
55 | Fence | FOOT | 304 | 30 | 9120 | 61 | 18544 | 58 | 17632 | 58 | 17632 |  | 0 |  | 0 |  | 0
56 | Non-Special Waste Disposal | CY YD | 200 | 25 | 5000 | 0.01 | 2 | 1 | 200 | 59 | 11800 |  | 0 |  | 0 |  | 0
57 | Special Waste Disposal | CU YD | 200 | 30 | 6000 | 0.01 | 2 | 1 | 200 | 71 | 14200 |  | 0 |  | 0 |  | 0
58 | Soil Disposal Analysis | EACH | 10 | 1000 | 10000 | 0.01 | 0.1 | 150 | 1500 | 1200 | 12000 |  | 0 |  | 0 |  | 0
59 | Special Waste Plans and Reports (Special) | L SUM | 1 | 5000 | 5000 | 0.01 | 0.01 | 1 | 1 | 2900 | 2900 |  | 0 |  | 0 |  | 0
60 | Traffic Control and Protection, Special | L SUM | 1 | 5000 | 5000 | 2500 | 2500 | 3500 | 3500 | 2375 | 2375 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 692260.9974 |  | 639538.11 |  | 837885.74 |  | 854340.65
| Award to N-TRAK Group | Bid |  | As corrected | 692260.9974 |  | 639538.11 |  | 837885.74 |  | 854340.65
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to N-TRAK Group | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
0
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Mobilization | L SUM | 1 |  | 0
2 | Building Removal, 5111 Carter Court | L SUM | 1 |  | 0
3 | Building Removal, 1214 Fieldcrest Drive | L SUM | 1 |  | 0
4 | Building Removal, 1218 Fieldcrest Drive | L SUM | 1 |  | 0
5 | Building Removal, 1218 Esmond Drive | L SUM | 1 |  | 0
6 | Asbestos Removal, 5111 Carter Court | L SUM | 1 |  | 0
7 | Asbestos Removal, 1218 Fieldcrest Drive | L SUM | 1 |  | 0
8 | Asbestos Removal, 1218 Esmond Drive | L SUM | 1 |  | 0
9 | Tree Removal, Under 6 Units Diameter | UNIT | 5 |  | 0
10 | Tree Removal, 6 to 15 Units Diameter | UNIT | 214 |  | 0
11 | Tree Removal, Over 15 Units Diameter | UNIT | 135 |  | 0
12 | Earth Excavation | CU YD | 6122 |  | 0
13 | Trench Backfill | CU YD | 242 |  | 0
14 | Parkway Restoration | L SUM | 1 |  | 0
15 | Perimeter Erosion Barrier | FOOT | 1067 |  | 0
16 | Inlet and Pipe Protection | EACH | 7 |  | 0
17 | Aggregate Base Course, Type B, CA-6, 4" | SQ YD | 20 |  | 0
18 | Aggregate Base Course, Type B, CA-6, 6" | SQ YD | 252 |  | 0
19 | Subbase Granular Material, Type B, 6" | SQ YD | 199 |  | 0
20 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 2.5" | TON | 20 |  | 0
21 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | TON | 13 |  | 0
22 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | TON | 12 |  | 0
23 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | TON | 7 |  | 0
24 | P.C.C Approach Pavement, 8" | SQ YD | 20 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Portland Cement Concrete Sidewalk, 4" | SQ FT | 441 |  | 0
26 | Portland Cement Concrete Sidewalk, 6" | SQ FT | 23 |  | 0
27 | Combination Curb and Gutter Removal | FOOT | 164 |  | 0
28 | Sidewalk Removal | SQ FT | 464 |  | 0
29 | Pavement Removal | SQ YD | 199 |  | 0
30 | Approach Pavement Removal | SQ FT | 783 |  | 0
31 | Aggregate Base Course Removal | SQ YD | 252 |  | 0
32 | Reinforced Concrete End Section, 30" Dual Pipes | EACH | 6 |  | 0
33 | Connection to Existing Drainage Structure | EACH | 1 |  | 0
34 | Storm Sewers, Class A, Type 1, 30" (RCP) | FOOT | 690 |  | 0
35 | Storm Sewers, Class B, Type 1, 30" (HDPE) | FOOT | 769 |  | 0
36 | Storm Sewers, Water Main Quality, 30" Complete | FOOT | 51 |  | 0
37 | Storm Sewer Removal, 36" | FOOT | 521 |  | 0
38 | Connect to Existing 6" Water Main, Complete | EACH | 2 |  | 0
39 | Remove Existing 6" Watermain | FOOT | 52 |  | 0
40 | Ductile Iron Water Main Complete, 6" | FOOT | 52 |  | 0
41 | Water Main Protection, 12" | FOOT | 27.5 |  | 0
42 | Water Main Line Stop, 6" | EACH | 2 |  | 0
43 | Water Service Connection, Complete, 1" | EACH | 1 |  | 0
44 | Pipe Underdrains, Type I, 4" | FOOT | 175 |  | 0
45 | Pipe Underdrain, Cleanout | EACH | 2 |  | 0
46 | Manholes, Type A, 9' Dia., Inlet 700 | EACH | 1 |  | 0
47 | Manholes, Type A, 9' Dia., Type 1 Frame, Closed Lid | EACH | 1 |  | 0
48 | Manholes, Type A, 9' Dia., Type 1 Frame, Open Lid | EACH | 3 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | Manholes, Type A, 9' Dia., Type 1 Frame, Curb Inlet | EACH | 3 |  | 0
50 | Removing Inlets | EACH | 4 |  | 0
51 | Removing Manholes | EACH | 4 |  | 0
52 | Combination Curb and Gutter, Type M-6.18 (Modified) | FOOT | 164 |  | 0
53 | Paved Ditch, Type B-15 | FOOT | 283 |  | 0
54 | Fence Removal | FOOT | 304 |  | 0
55 | Fence | FOOT | 304 |  | 0
56 | Non-Special Waste Disposal | CY YD | 200 |  | 0
57 | Special Waste Disposal | CU YD | 200 |  | 0
58 | Soil Disposal Analysis | EACH | 10 |  | 0
59 | Special Waste Plans and Reports (Special) | L SUM | 1 |  | 0
60 | Traffic Control and Protection, Special | L SUM | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Mobilization | L SUM | 1 | 5000 | 5000
2 | Building Removal, 5111 Carter Court | L SUM | 1 | 15400 | 15400
3 | Building Removal, 1214 Fieldcrest Drive | L SUM | 1 | 10000 | 10000
4 | Building Removal, 1218 Fieldcrest Drive | L SUM | 1 | 10500 | 10500
5 | Building Removal, 1218 Esmond Drive | L SUM | 1 | 13000 | 13000
6 | Asbestos Removal, 5111 Carter Court | L SUM | 1 | 800 | 800
7 | Asbestos Removal, 1218 Fieldcrest Drive | L SUM | 1 | 2000 | 2000
8 | Asbestos Removal, 1218 Esmond Drive | L SUM | 1 | 1200 | 1200
9 | Tree Removal, Under 6 Units Diameter | UNIT | 5 | 120 | 600
10 | Tree Removal, 6 to 15 Units Diameter | UNIT | 214 | 30 | 6420
11 | Tree Removal, Over 15 Units Diameter | UNIT | 135 | 43 | 5805
12 | Earth Excavation | CU YD | 6122 | 30 | 183660
13 | Trench Backfill | CU YD | 242 | 55 | 13310
14 | Parkway Restoration | L SUM | 1 | 27628 | 27628
15 | Perimeter Erosion Barrier | FOOT | 1067 | 2 | 2134
16 | Inlet and Pipe Protection | EACH | 7 | 150 | 1050
17 | Aggregate Base Course, Type B, CA-6, 4" | SQ YD | 20 | 8 | 160
18 | Aggregate Base Course, Type B, CA-6, 6" | SQ YD | 252 | 10 | 2520
19 | Subbase Granular Material, Type B, 6" | SQ YD | 199 | 17 | 3383
20 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 2.5" | TON | 20 | 100 | 2000
21 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | TON | 13 | 115 | 1495
22 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | TON | 12 | 130 | 1560
23 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | TON | 7 | 130 | 910
24 | P.C.C Approach Pavement, 8" | SQ YD | 20 | 80 | 1600
|  |  |  | Sub Total | 312135
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Portland Cement Concrete Sidewalk, 4" | SQ FT | 441 | 12 | 5292
26 | Portland Cement Concrete Sidewalk, 6" | SQ FT | 23 | 18 | 414
27 | Combination Curb and Gutter Removal | FOOT | 164 | 10 | 1640
28 | Sidewalk Removal | SQ FT | 464 | 5 | 2320
29 | Pavement Removal | SQ YD | 199 | 12 | 2388
30 | Approach Pavement Removal | SQ FT | 783 | 1.3333 | 1043.9974
31 | Aggregate Base Course Removal | SQ YD | 252 | 12 | 3024
32 | Reinforced Concrete End Section, 30" Dual Pipes | EACH | 6 | 4000 | 24000
33 | Connection to Existing Drainage Structure | EACH | 1 | 1500 | 1500
34 | Storm Sewers, Class A, Type 1, 30" (RCP) | FOOT | 690 | 65 | 44850
35 | Storm Sewers, Class B, Type 1, 30" (HDPE) | FOOT | 769 | 65 | 49985
36 | Storm Sewers, Water Main Quality, 30" Complete | FOOT | 51 | 80 | 4080
37 | Storm Sewer Removal, 36" | FOOT | 521 | 27 | 14067
38 | Connect to Existing 6" Water Main, Complete | EACH | 2 | 2000 | 4000
39 | Remove Existing 6" Watermain | FOOT | 52 | 20 | 1040
40 | Ductile Iron Water Main Complete, 6" | FOOT | 52 | 110 | 5720
41 | Water Main Protection, 12" | FOOT | 27.5 | 35 | 962.5
42 | Water Main Line Stop, 6" | EACH | 2 | 4000 | 8000
43 | Water Service Connection, Complete, 1" | EACH | 1 | 1500 | 1500
44 | Pipe Underdrains, Type I, 4" | FOOT | 175 | 0.5 | 87.5
45 | Pipe Underdrain, Cleanout | EACH | 2 | 50 | 100
46 | Manholes, Type A, 9' Dia., Inlet 700 | EACH | 1 | 17250 | 17250
47 | Manholes, Type A, 9' Dia., Type 1 Frame, Closed Lid | EACH | 1 | 15750 | 15750
48 | Manholes, Type A, 9' Dia., Type 1 Frame, Open Lid | EACH | 3 | 15750 | 47250
|  |  |  | Sub Total | 568398.9974
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | Manholes, Type A, 9' Dia., Type 1 Frame, Curb Inlet | EACH | 3 | 17500 | 52500
50 | Removing Inlets | EACH | 4 | 1000 | 4000
51 | Removing Manholes | EACH | 4 | 1200 | 4800
52 | Combination Curb and Gutter, Type M-6.18 (Modified) | FOOT | 164 | 45 | 7380
53 | Paved Ditch, Type B-15 | FOOT | 283 | 50 | 14150
54 | Fence Removal | FOOT | 304 | 3 | 912
55 | Fence | FOOT | 304 | 30 | 9120
56 | Non-Special Waste Disposal | CY YD | 200 | 25 | 5000
57 | Special Waste Disposal | CU YD | 200 | 30 | 6000
58 | Soil Disposal Analysis | EACH | 10 | 1000 | 10000
59 | Special Waste Plans and Reports (Special) | L SUM | 1 | 5000 | 5000
60 | Traffic Control and Protection, Special | L SUM | 1 | 5000 | 5000
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 692260.9974
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | 0
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 692260.9974
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Mobilization | 1 | L SUM | 20000 |  | 1 |  |  | 20000
2 | Building Removal, 5111 Carter Court | 1 | L SUM | 8000 |  | 1 |  |  | 8000
3 | Building Removal, 1214 Fieldcrest Drive | 1 | L SUM | 8000 |  | 1 |  |  | 8000
4 | Building Removal, 1218 Fieldcrest Drive | 1 | L SUM | 8000 |  | 1 |  |  | 8000
5 | Building Removal, 1218 Esmond Drive | 1 | L SUM | 8000 |  | 1 |  |  | 8000
6 | Asbestos Removal, 5111 Carter Court | 1 | L SUM | 1000 |  | 1 |  |  | 1000
7 | Asbestos Removal, 1218 Fieldcrest Drive | 1 | L SUM | 5000 |  | 1 |  |  | 5000
8 | Asbestos Removal, 1218 Esmond Drive | 1 | L SUM | 1000 |  | 1 |  |  | 1000
9 | Tree Removal, Under 6 Units Diameter | 5 | UNIT | 65 |  | 5 |  |  | 13
10 | Tree Removal, 6 to 15 Units Diameter | 214 | UNIT | 4066 |  | 214 |  |  | 19
11 | Tree Removal, Over 15 Units Diameter | 135 | UNIT | 3915 |  | 135 |  |  | 29
12 | Earth Excavation | 6122 | CU YD | 91830 |  | 6122 |  |  | 15
13 | Trench Backfill | 242 | CU YD | 4840 |  | 242 |  |  | 20
14 | Parkway Restoration | 1 | L SUM | 65000 |  | 1 |  |  | 65000
15 | Perimeter Erosion Barrier | 1067 | FOOT | 3201 |  | 1067 |  |  | 3
16 | Inlet and Pipe Protection | 7 | EACH | 525 |  | 7 |  |  | 75
17 | Aggregate Base Course, Type B, CA-6, 4" | 20 | SQ YD | 300 |  | 20 |  |  | 15
18 | Aggregate Base Course, Type B, CA-6, 6" | 252 | SQ YD | 3780 |  | 252 |  |  | 15
19 | Subbase Granular Material, Type B, 6" | 199 | SQ YD | 2985 |  | 199 |  |  | 15
20 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 2.5" | 20 | TON | 3600 |  | 20 |  |  | 180
21 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 4" | 13 | TON | 2340 |  | 13 |  |  | 180
22 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | 12 | TON | 2160 |  | 12 |  |  | 180
23 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 7 | TON | 1260 |  | 7 |  |  | 180
24 | P.C.C Approach Pavement, 8" | 20 | SQ YD | 1960 |  | 20 |  |  | 98
Sub Total |  |  |  | 250827 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Portland Cement Concrete Sidewalk, 4" | 441 | SQ FT | 2205 |  | 441 |  |  | 5
26 | Portland Cement Concrete Sidewalk, 6" | 23 | SQ FT | 149.5 |  | 23 |  |  | 6.5
27 | Combination Curb and Gutter Removal | 164 | FOOT | 984 |  | 164 |  |  | 6
28 | Sidewalk Removal | 464 | SQ FT | 928 |  | 464 |  |  | 2
29 | Pavement Removal | 199 | SQ YD | 1791 |  | 199 |  |  | 9
30 | Approach Pavement Removal | 783 | SQ FT | 783 |  | 783 |  |  | 1
31 | Aggregate Base Course Removal | 252 | SQ YD | 1260 |  | 252 |  |  | 5
32 | Reinforced Concrete End Section, 30" Dual Pipes | 6 | EACH | 45000 |  | 6 |  |  | 7500
33 | Connection to Existing Drainage Structure | 1 | EACH | 2500 |  | 1 |  |  | 2500
34 | Storm Sewers, Class A, Type 1, 30" (RCP) | 690 | FOOT | 62100 |  | 690 |  |  | 90
35 | Storm Sewers, Class B, Type 1, 30" (HDPE) | 769 | FOOT | 76900 |  | 769 |  |  | 100
36 | Storm Sewers, Water Main Quality, 30" Complete | 51 | FOOT | 16830 |  | 51 |  |  | 330
37 | Storm Sewer Removal, 36" | 521 | FOOT | 5210 |  | 521 |  |  | 10
38 | Connect to Existing 6" Water Main, Complete | 2 | EACH | 6000 |  | 2 |  |  | 3000
39 | Remove Existing 6" Watermain | 52 | FOOT | 1040 |  | 52 |  |  | 20
40 | Ductile Iron Water Main Complete, 6" | 52 | FOOT | 9360 |  | 52 |  |  | 180
41 | Water Main Protection, 12" | 27.5 | FOOT | 1787.5 |  | 27.5 |  |  | 65
42 | Water Main Line Stop, 6" | 2 | EACH | 9000 |  | 2 |  |  | 4500
43 | Water Service Connection, Complete, 1" | 1 | EACH | 1700 |  | 1 |  |  | 1700
44 | Pipe Underdrains, Type I, 4" | 175 | FOOT | 3850 |  | 175 |  |  | 22
45 | Pipe Underdrain, Cleanout | 2 | EACH | 300 |  | 2 |  |  | 150
46 | Manholes, Type A, 9' Dia., Inlet 700 | 1 | EACH | 10500 |  | 1 |  |  | 10500
47 | Manholes, Type A, 9' Dia., Type 1 Frame, Closed Lid | 1 | EACH | 10500 |  | 1 |  |  | 10500
48 | Manholes, Type A, 9' Dia., Type 1 Frame, Open Lid | 3 | EACH | 31500 |  | 3 |  |  | 10500
Sub Total |  |  |  | 553005 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | Manholes, Type A, 9' Dia., Type 1 Frame, Curb Inlet | 3 | EACH | 31500 |  | 3 |  |  | 10500
50 | Removing Inlets | 4 | EACH | 2000 |  | 4 |  |  | 500
51 | Removing Manholes | 4 | EACH | 2800 |  | 4 |  |  | 700
52 | Combination Curb and Gutter, Type M-6.18 (Modified) | 164 | FOOT | 4920 |  | 164 |  |  | 30
53 | Paved Ditch, Type B-15 | 283 | FOOT | 21225 |  | 283 |  |  | 75
54 | Fence Removal | 304 | FOOT | 3040 |  | 304 |  |  | 10
55 | Fence | 304 | FOOT | 18544 |  | 304 |  |  | 61
56 | Non-Special Waste Disposal | 200 | CY YD | 2 |  | 200 |  |  | 0.01
57 | Special Waste Disposal | 200 | CU YD | 2 |  | 200 |  |  | 0.01
58 | Soil Disposal Analysis | 10 | EACH | 0.1 |  | 10 |  |  | 0.01
59 | Special Waste Plans and Reports (Special) | 1 | L SUM | 0.01 |  | 1 |  |  | 0.01
60 | Traffic Control and Protection, Special | 1 | L SUM | 2500 |  | 1 |  |  | 2500
Total |  |  |  | 639538.11 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Park, IL | [5 empty] | SECTION | 0
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 639538.11 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | 0
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | N-TRAK Group
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.