## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 2303354.7
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | TREE REMOVAL, ACRES | ACRE | 0.1 | 10000 | 1000
2 | EARTH EXCAVATION | CU YD | 6330 | 45 | 284850
3 | TRENCH BACKFILL | CU YD | 133 | 40 | 5320
4 | TOPSOIL FURNISH AND PLACE, 4" | SQ YD | 7858 | 6 | 47148
5 | GRADING AND SHAPING DITCHES | FOOT | 611 | 15 | 9165
6 | SEEDING, CLASS 1A | ACRE | 1.6 | 3600 | 5760
7 | NITROGEN FERTILZER NUTRIENT | POUND | 144 | 3.6 | 518.4
8 | PHOSPHOROUS FERTILIZER NUTRIENT | POUND | 144 | 3.6 | 518.4
9 | POTASSIUM FERTILZER NUTRIENT | POUND | 144 | 3.6 | 518.4
10 | EROSION CONTROL BLANKET | SQ YD | 7858 | 2 | 15716
11 | TEMPORARY DITCH CHECKS | FOOT | 100 | 15 | 1500
12 | PERIMETER EROSION BARRIER | FOOT | 6019 | 3.25 | 19561.75
13 | INLET AND PIPE PROTECTION | EACH | 45 | 160 | 7200
14 | STONE RIPRAP, CLASS A3 | SQ YD | 1272 | 60 | 76320
15 | FILTER FABRIC | SQ YD | 1272 | 3.5 | 4452
16 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 3913 | 25 | 97825
17 | AGGREGATE BASE COURSE, TYPE B | TON | 5375 | 50 | 268750
18 | BITUMINOUS MATERIALS (PRIME COAT) | POUND | 26228 | 0.7 | 18359.6
19 | BITUMINOUS MATERIALS (TACK COAT) | POUND | 3299 | 1 | 3299
20 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N90 | TON | 3860 | 65 | 250900
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N70 | TON | 1808 | 65 | 117520
22 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 12559 | 8.5 | 106751.5
23 | PAVEMENT REMOVAL | SQ YD | 14697 | 16 | 235152
24 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 5479 | 12 | 65748
25 | SIDEWALK REMOVAL | SQ FT | 39 | 2.5 | 97.5
26 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 12" | EACH | 4 | 700 | 2800
27 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 15" | EACH | 2 | 800 | 1600
28 | REMOVING INLETS | EACH | 17 | 475 | 8075
29 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 5615 | 40 | 224600
30 | STEEL PLATE BEAM GUARDRAIL, TYPE A, 9 FOOT POSTS | FOOT | 412.5 | 40 | 16500
31 | TRAFFIC BARRIER TERMINAL, TYPE 1B | EACH | 1 | 2400 | 2400
32 | TRAFFIC BARRIER TERMINAL, TYPE 6A | EACH | 1 | 3600 | 3600
33 | GUARDRAIL REMOVAL | FOOT | 477 | 6.5 | 3100.5
34 | REMOVE AND REERECT RAIL ELEMENT OF EXISTING GUARDRAIL | FOOT | 12.5 | 33 | 412.5
35 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 60 | 12000
36 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 50 | 10000
37 | SOIL DISPOSAL ANALYSIS | EACH | 1 | 1500 | 1500
38 | MOBILIZATION | L SUM | 1 | 25000 | 25000
39 | CHANGEABLE MESSAGE SIGN | CAL DA | 28 | 75 | 2100
40 | SIGN PANEL - TYPE 1 | SQ FT | 9.25 | 50 | 462.5
41 | METAL POST - TYPE A | FOOT | 26 | 21 | 546
42 | THERMOPLASTIC PAVEMENT MARKING - LETTERS AND SYMBOLS | SQ FT | 436.8 | 6 | 2620.8
43 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" | FOOT | 7005 | 1.2 | 8406
44 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | FOOT | 708 | 2 | 1416
45 | THERMOPLASTIC PAVEMENT MARKING - LINE 8" | FOOT | 800 | 1.7 | 1360
46 | THERMOPLASTIC PAVEMENT MARKING - LINE 12" | FOOT | 219 | 2.95 | 646.05
47 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" | FOOT | 139 | 7 | 973
48 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 5C | FOOT | 280.5 | 1.6 | 448.8
49 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, MAST ARM MOUNTED | EACH | 1 | 965 | 965
50 | RELOCATE EXISTING SIGNAL HEAD | EACH | 1 | 650 | 650
51 | MODIFY EXISTING CONTROLLER | EACH | 1 | 2400 | 2400
52 | STORM SEWERS, CLASS A, TYPE 1 12" | FOOT | 812 | 70 | 56840
53 | STORM SEWERS, CLASS A, TYPE 1 15" | FOOT | 47 | 70 | 3290
54 | STORM SEWERS, CLASS A, TYPE 2 12" | FOOT | 125 | 80 | 10000
55 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 | 3500 | 3500
56 | RELOCATE EXISTING MAILBOX | EACH | 10 | 200 | 2000
57 | RAILROAD FLAGGER | L SUM | 1 | 10000 | 10000
58 | PAVEMENT MARKING REMOVAL - WATER BLASTING | SQ FT | 216 | 3 | 648
59 | REMOVE AND RELOCATE SIGN PANEL AND POLE ASSEMBLY | EACH | 15 | 550 | 8250
60 | STORM SEWER REMOVAL | FOOT | 704 | 15 | 10560
61 | INLETS, SPECIAL | EACH | 26 | 2600 | 67600
62 | SANITARY MANHOLES TO BE ADJUSTED | EACH | 4 | 850 | 3400
63 | SANITARY MANHOLES TO BE RECONSTRUCTED WITH NEW TYPE 1 FRAME, CLOSED LID | EACH | 1 | 3000 | 3000
64 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 | 30000 | 30000
65 | SIGN REMOVAL | EACH | 2 | 265 | 530
66 | HANDHOLE TO BE ADJUSTED | EACH | 1 | 1400 | 1400
67 | CONCRETE TRUCK WASHOUT | L SUM | 1 | 1800 | 1800
68 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT REMOVAL | SQ YD | 790 | 18 | 14220
69 | CONSTRUCTION LAYOUT | L SUM | 1 | 28500 | 28500
70 | VIDEO VEHICLE DETECTION SYSTEM | EACH | 1 | 9000 | 9000
71 | RAILROAD PROTECTIVE LIABILITY INSURANCE | L SUM | 1 | 11500 | 11500
72 | SUBGRADE UNDERCUTTING | CU YD | 573 | 48 | 27504
73 | ADA CURB RAMP, STD 424001 | EACH | 12 | 1540 | 18480
74 | ADA CURB RAMP, STD 424026 | EACH | 4 | 700 | 2800
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | William Charles Construction |  | N-TRAK Group |  | Northern Illinois Service |  | Stenstrom Excavation |  | Fischer Excavating
City of Rockford | [5 empty] | Rockford, IL |  | Loves Park, IL |  | Rockford, IL |  | Rockford, IL |  | Freeport, IL
VENDORS NOTIFIED: 89 | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond
Bid No.: 521-PW-042
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | TREE REMOVAL, ACRES | ACRE | 0.1 | 10000 | 1000 | 55000 | 5500 | 55000 | 5500 | 55000 | 5500 | 41345 | 4134.5 | 55000 | 5500 |  | 0
2 | EARTH EXCAVATION | CU YD | 6330 | 45 | 284850 | 22.25 | 140842.5 | 18 | 113940 | 26 | 164580 | 16.2 | 102546 | 20 | 126600 |  | 0
3 | TRENCH BACKFILL | CU YD | 133 | 40 | 5320 | 40 | 5320 | 0.01 | 1.33 | 28 | 3724 | 0.01 | 1.33 | 24.5 | 3258.5 |  | 0
4 | TOPSOIL FURNISH AND PLACE, 4" | SQ YD | 7858 | 6 | 47148 | 2.7 | 21216.6 | 2.5 | 19645 | 2.85 | 22395.3 | 2.9 | 22788.2 | 3.7 | 29074.6 |  | 0
5 | GRADING AND SHAPING DITCHES | FOOT | 611 | 15 | 9165 | 7.95 | 4857.45 | 10 | 6110 | 18 | 10998 | 12.6 | 7698.6 | 8.7 | 5315.7 |  | 0
6 | SEEDING, CLASS 1A | ACRE | 1.6 | 3600 | 5760 | 5000 | 8000 | 3700 | 5920 | 3700 | 5920 | 5440 | 8704 | 5000 | 8000 |  | 0
7 | NITROGEN FERTILZER NUTRIENT | POUND | 144 | 3.6 | 518.4 | 1 | 144 | 4 | 576 | 4 | 576 | 1.1 | 158.4 | 1 | 144 |  | 0
8 | PHOSPHOROUS FERTILIZER NUTRIENT | POUND | 144 | 3.6 | 518.4 | 1 | 144 | 4 | 576 | 4 | 576 | 1.1 | 158.4 | 1 | 144 |  | 0
9 | POTASSIUM FERTILZER NUTRIENT | POUND | 144 | 3.6 | 518.4 | 1 | 144 | 4 | 576 | 4 | 576 | 1.1 | 158.4 | 1 | 144 |  | 0
10 | EROSION CONTROL BLANKET | SQ YD | 7858 | 2 | 15716 | 1.1 | 8643.8 | 1 | 7858 | 1 | 7858 | 1.2 | 9429.6 | 1.1 | 8643.8 |  | 0
11 | TEMPORARY DITCH CHECKS | FOOT | 100 | 15 | 1500 | 22 | 2200 | 14 | 1400 | 10 | 1000 | 24 | 2400 | 22 | 2200 |  | 0
12 | PERIMETER EROSION BARRIER | FOOT | 6019 | 3.25 | 19561.75 | 3.5 | 21066.5 | 1.7 | 10232.3 | 2 | 12038 | 3.8 | 22872.2 | 3.5 | 21066.5 |  | 0
13 | INLET AND PIPE PROTECTION | EACH | 45 | 160 | 7200 | 75 | 3375 | 75 | 3375 | 100 | 4500 | 82 | 3690 | 75 | 3375 |  | 0
14 | STONE RIPRAP, CLASS A3 | SQ YD | 1272 | 60 | 76320 | 0.01 | 12.72 | 45 | 57240 | 60 | 76320 | 0.01 | 12.72 | 15.75 | 20034 |  | 0
15 | FILTER FABRIC | SQ YD | 1272 | 3.5 | 4452 | 2.65 | 3370.8 | 2.5 | 3180 | 3 | 3816 | 1 | 1272 | 2.45 | 3116.4 |  | 0
16 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 3913 | 25 | 97825 | 12.4 | 48521.2 | 14 | 54782 | 14 | 54782 | 14.7 | 57521.1 | 17.75 | 69455.75 |  | 0
17 | AGGREGATE BASE COURSE, TYPE B | TON | 5375 | 50 | 268750 | 16.05 | 86268.75 | 18 | 96750 | 14 | 75250 | 15.6 | 83850 | 17.8 | 95675 |  | 0
18 | BITUMINOUS MATERIALS (PRIME COAT) | POUND | 26228 | 0.7 | 18359.6 | 0.5 | 13114 | 0.01 | 262.28 | 0.01 | 262.28 | 0.01 | 262.28 | 0.01 | 262.28 |  | 0
19 | BITUMINOUS MATERIALS (TACK COAT) | POUND | 3299 | 1 | 3299 | 0.5 | 1649.5 | 0.01 | 32.99 | 0.35 | 1154.65 | 0.4 | 1319.6 | 0.35 | 1154.65 |  | 0
20 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N90 | TON | 3860 | 65 | 250900 | 64 | 247040 | 70 | 270200 | 58 | 223880 | 63.95 | 246847 | 58 | 223880 |  | 0
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N70 | TON | 1808 | 65 | 117520 | 70 | 126560 | 77 | 139216 | 65 | 117520 | 84.5 | 152776 | 65 | 117520 |  | 0
22 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 12559 | 8.5 | 106751.5 | 6.1 | 76609.9 | 6.25 | 78493.75 | 6.5 | 81633.5 | 5.4 | 67818.6 | 6 | 75354 |  | 0
23 | PAVEMENT REMOVAL | SQ YD | 14697 | 16 | 235152 | 5.4 | 79363.8 | 7.25 | 106553.25 | 9 | 132273 | 9 | 132273 | 8.75 | 128598.75 |  | 0
24 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 5479 | 12 | 65748 | 2.85 | 15615.15 | 2.5 | 13697.5 | 2 | 10958 | 4.4 | 24107.6 | 4 | 21916 |  | 0
| Page 1 | Sub |  | As read | 1643853.05 |  | 919579.67 |  | 996117.4 |  | 1018090.73 |  | 952799.53 |  | 970432.93
| Award to William Charles Construction | Total |  | As corrected | 1643853.05 |  | 919579.67 |  | 996117.4 |  | 1018090.73 |  | 952799.53 |  | 970432.93
25 | SIDEWALK REMOVAL | SQ FT | 39 | 2.5 | 97.5 | 2.2 | 85.8 | 4 | 156 | 1 | 39 | 7.5 | 292.5 | 2.5 | 97.5 |  | 0
26 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 12" | EACH | 4 | 700 | 2800 | 950 | 3800 | 1150 | 4600 | 650 | 2600 | 710 | 2840 | 555 | 2220 |  | 0
27 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 15" | EACH | 2 | 800 | 1600 | 980 | 1960 | 1150 | 2300 | 800 | 1600 | 740 | 1480 | 620 | 1240 |  | 0
28 | REMOVING INLETS | EACH | 17 | 475 | 8075 | 460 | 7820 | 500 | 8500 | 150 | 2550 | 250 | 4250 | 383 | 6511 |  | 0
29 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 5615 | 40 | 224600 | 16.75 | 94051.25 | 22 | 123530 | 16.75 | 94051.25 | 20.25 | 113703.75 | 20.25 | 113703.75 |  | 0
30 | STEEL PLATE BEAM GUARDRAIL, TYPE A, 9 FOOT POSTS | FOOT | 412.5 | 40 | 16500 | 30.6 | 12622.5 | 31 | 12787.5 | 30.58 | 12614.25 | 33.25 | 13715.625 | 30.6 | 12622.5 |  | 0
31 | TRAFFIC BARRIER TERMINAL, TYPE 1B | EACH | 1 | 2400 | 2400 | 1984.6 | 1984.6 | 2000 | 2000 | 1963 | 1963 | 2135 | 2135 | 1960 | 1960 |  | 0
32 | TRAFFIC BARRIER TERMINAL, TYPE 6A | EACH | 1 | 3600 | 3600 | 3501.1 | 3501.1 | 3500 | 3500 | 3463 | 3463 | 3770 | 3770 | 3463 | 3463 |  | 0
33 | GUARDRAIL REMOVAL | FOOT | 477 | 6.5 | 3100.5 | 5.95 | 2838.15 | 6 | 2862 | 4 | 1908 | 6.5 | 3100.5 | 5.95 | 2838.15 |  | 0
34 | REMOVE AND REERECT RAIL ELEMENT OF EXISTING GUARDRAIL | FOOT | 12.5 | 33 | 412.5 | 15 | 187.5 | 15 | 187.5 | 15 | 187.5 | 16.3 | 203.75 | 15 | 187.5 |  | 0
35 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 60 | 12000 | 29.33 | 5866 | 0.01 | 2 | 15 | 3000 | 62 | 12400 | 72 | 14400 |  | 0
36 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 50 | 10000 | 43.73 | 8746 | 0.01 | 2 | 15 | 3000 | 70 | 14000 | 82 | 16400 |  | 0
37 | SOIL DISPOSAL ANALYSIS | EACH | 1 | 1500 | 1500 | 1250 | 1250 | 1250 | 1250 | 4000 | 4000 | 1360 | 1360 | 1250 | 1250 |  | 0
38 | MOBILIZATION | L SUM | 1 | 25000 | 25000 | 54000 | 54000 | 33000 | 33000 | 7500 | 7500 | 19000.1 | 19000.1 | 7000 | 7000 |  | 0
39 | CHANGEABLE MESSAGE SIGN | CAL DA | 28 | 75 | 2100 | 40 | 1120 | 45 | 1260 | 40 | 1120 | 43 | 1204 | 45 | 1260 |  | 0
40 | SIGN PANEL - TYPE 1 | SQ FT | 9.25 | 50 | 462.5 | 30 | 277.5 | 30 | 277.5 | 30 | 277.5 | 32 | 296 | 30 | 277.5 |  | 0
41 | METAL POST - TYPE A | FOOT | 26 | 21 | 546 | 15 | 390 | 15 | 390 | 15 | 390 | 16 | 416 | 15 | 390 |  | 0
42 | THERMOPLASTIC PAVEMENT MARKING - LETTERS AND SYMBOLS | SQ FT | 436.8 | 6 | 2620.8 | 5 | 2184 | 5 | 2184 | 5 | 2184 | 5.45 | 2380.56 | 5 | 2184 |  | 0
43 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" | FOOT | 7005 | 1.2 | 8406 | 0.6 | 4203 | 0.6 | 4203 | 0.6 | 4203 | 0.65 | 4553.25 | 0.6 | 4203 |  | 0
44 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | FOOT | 708 | 2 | 1416 | 0.9 | 637.2 | 0.9 | 637.2 | 0.9 | 637.2 | 1 | 708 | 0.9 | 637.2 |  | 0
45 | THERMOPLASTIC PAVEMENT MARKING - LINE 8" | FOOT | 800 | 1.7 | 1360 | 1.2 | 960 | 1.2 | 960 | 1.2 | 960 | 1.3 | 1040 | 1.2 | 960 |  | 0
46 | THERMOPLASTIC PAVEMENT MARKING - LINE 12" | FOOT | 219 | 2.95 | 646.05 | 1.8 | 394.2 | 1.8 | 394.2 | 1.8 | 394.2 | 2 | 438 | 1.8 | 394.2 |  | 0
47 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" | FOOT | 139 | 7 | 973 | 3.6 | 500.4 | 3.6 | 500.4 | 3.6 | 500.4 | 3.95 | 549.05 | 3.6 | 500.4 |  | 0
48 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 5C | FOOT | 280.5 | 1.6 | 448.8 | 2.15 | 603.075 | 2.8 | 785.4 | 4.94 | 1385.67 | 5.4 | 1514.7 | 2.3 | 645.15 |  | 0
| Page 2 | Sub |  | As read | 1974517.7 |  | 1129561.945 |  | 1202386.1 |  | 1168618.7 |  | 1158150.315 |  | 1165777.78
| Award to William Charles Construction | Total |  | As corrected | 1974517.7 |  | 1129561.945 |  | 1202386.1 |  | 1168618.7 |  | 1158150.315 |  | 1165777.78
49 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, MAST ARM MOUNTED | EACH | 1 | 965 | 965 | 819.3 | 819.3 | 695 | 695 | 1180 | 1180 | 1290 | 1290 | 877 | 877 |  | 0
50 | RELOCATE EXISTING SIGNAL HEAD | EACH | 1 | 650 | 650 | 477.5 | 477.5 | 1000 | 1000 | 963 | 963 | 1050 | 1050 | 507 | 507 |  | 0
51 | MODIFY EXISTING CONTROLLER | EACH | 1 | 2400 | 2400 | 1231.2 | 1231.2 | 1300 | 1300 | 200 | 200 | 220 | 220 | 1303 | 1303 |  | 0
52 | STORM SEWERS, CLASS A, TYPE 1 12" | FOOT | 812 | 70 | 56840 | 52.95 | 42995.4 | 58 | 47096 | 60 | 48720 | 60 | 48720 | 52 | 42224 |  | 0
53 | STORM SEWERS, CLASS A, TYPE 1 15" | FOOT | 47 | 70 | 3290 | 99.05 | 4655.35 | 58 | 2726 | 65 | 3055 | 72 | 3384 | 56 | 2632 |  | 0
54 | STORM SEWERS, CLASS A, TYPE 2 12" | FOOT | 125 | 80 | 10000 | 51.2 | 6400 | 65 | 8125 | 60 | 7500 | 73.75 | 9218.75 | 52 | 6500 |  | 0
55 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 | 3500 | 3500 | 2224.2 | 2224.2 | 0.01 | 0.01 | 2000 | 2000 | 2395 | 2395 | 2000 | 2000 |  | 0
56 | RELOCATE EXISTING MAILBOX | EACH | 10 | 200 | 2000 | 338.6 | 3386 | 250 | 2500 | 150 | 1500 | 325 | 3250 | 156 | 1560 |  | 0
57 | RAILROAD FLAGGER | L SUM | 1 | 10000 | 10000 | 8846.3 | 8846.3 | 15000 | 15000 | 5000 | 5000 | 6965 | 6965 | 7500 | 7500 |  | 0
58 | PAVEMENT MARKING REMOVAL - WATER BLASTING | SQ FT | 216 | 3 | 648 | 7.1 | 1533.6 | 7 | 1512 | 7 | 1512 | 15 | 3240 | 13.9 | 3002.4 |  | 0
59 | REMOVE AND RELOCATE SIGN PANEL AND POLE ASSEMBLY | EACH | 15 | 550 | 8250 | 212.3 | 3184.5 | 210 | 3150 | 210 | 3150 | 230 | 3450 | 210 | 3150 |  | 0
60 | STORM SEWER REMOVAL | FOOT | 704 | 15 | 10560 | 43.4 | 30553.6 | 20 | 14080 | 20 | 14080 | 18.15 | 12777.6 | 17 | 11968 |  | 0
61 | INLETS, SPECIAL | EACH | 26 | 2600 | 67600 | 2524.2 | 65629.2 | 1900 | 49400 | 3000 | 78000 | 2265 | 58890 | 2280 | 59280 |  | 0
62 | SANITARY MANHOLES TO BE ADJUSTED | EACH | 4 | 850 | 3400 | 980.8 | 3923.2 | 1000 | 4000 | 1250 | 5000 | 1850 | 7400 | 1050 | 4200 |  | 0
63 | SANITARY MANHOLES TO BE RECONSTRUCTED WITH NEW TYPE 1 FRAME, CLOSED LID | EACH | 1 | 3000 | 3000 | 3018.6 | 3018.6 | 1800 | 1800 | 4500 | 4500 | 7000 | 7000 | 1450 | 1450 |  | 0
64 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 | 30000 | 30000 | 23000 | 23000 | 25000 | 25000 | 18000 | 18000 | 58300.33 | 58300.33 | 20900 | 20900 |  | 0
65 | SIGN REMOVAL | EACH | 2 | 265 | 530 | 60.65 | 121.3 | 60 | 120 | 120 | 240 | 50 | 100 | 60 | 120 |  | 0
66 | HANDHOLE TO BE ADJUSTED | EACH | 1 | 1400 | 1400 | 2076.3 | 2076.3 | 1900 | 1900 | 2208.4 | 2208.4 | 2400 | 2400 | 2208 | 2208 |  | 0
67 | CONCRETE TRUCK WASHOUT | L SUM | 1 | 1800 | 1800 | 750 | 750 | 500 | 500 | 750 | 750 | 1100 | 1100 | 1150 | 1150 |  | 0
68 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT REMOVAL | SQ YD | 790 | 18 | 14220 | 3.95 | 3120.5 | 4 | 3160 | 2 | 1580 | 5.15 | 4068.5 | 2.85 | 2251.5 |  | 0
69 | CONSTRUCTION LAYOUT | L SUM | 1 | 28500 | 28500 | 15500 | 15500 | 10000 | 10000 | 11000 | 11000 | 9060 | 9060 | 8325 | 8325 |  | 0
70 | VIDEO VEHICLE DETECTION SYSTEM | EACH | 1 | 9000 | 9000 | 23933 | 23933 | 19880 | 19880 | 24265 | 24265 | 26400 | 26400 | 25757 | 25757 |  | 0
71 | RAILROAD PROTECTIVE LIABILITY INSURANCE | L SUM | 1 | 11500 | 11500 | 4100 | 4100 | 5000 | 5000 | 3000 | 3000 | 6555 | 6555 | 9350 | 9350 |  | 0
72 | SUBGRADE UNDERCUTTING | CU YD | 573 | 48 | 27504 | 0.01 | 5.73 | 35 | 20055 | 58 | 33234 | 42.5 | 24352.5 | 55 | 31515 |  | 0
| Page 3 | Sub |  | As read | 2282074.7 |  | 1381046.725 |  | 1440385.11 |  | 1439256.1 |  | 1459736.995 |  | 1415507.68
| Award to William Charles Construction | Total |  | As corrected | 2282074.7 |  | 1381046.725 |  | 1440385.11 |  | 1439256.1 |  | 1459736.995 |  | 1415507.68
73 | ADA CURB RAMP, STD 424001 | EACH | 12 | 1540 | 18480 | 810 | 9720 | 1500 | 18000 | 705 | 8460 | 1600 | 19200 | 1690 | 20280 |  | 0
74 | ADA CURB RAMP, STD 424026 | EACH | 4 | 700 | 2800 | 516 | 2064 | 725 | 2900 | 415 | 1660 | 780 | 3120 | 845 | 3380 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | 2303354.7 |  | 1392830.725 |  | 1461285.11 |  | 1449376.1 |  | 1482056.995 |  | 1439167.68
| Award to William Charles Construction | Bid |  | As corrected | 2303354.7 |  | 1392830.725 |  | 1461285.11 |  | 1449376.1 |  | 1482056.995 |  | 1439167.68

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
VENDORS NOTIFIED: 89
Item No. | Items | Units | Quantity | Unit Price | Total
1 | TREE REMOVAL, ACRES | ACRE | 0.1 |  | 0
2 | EARTH EXCAVATION | CU YD | 6330 |  | 0
3 | TRENCH BACKFILL | CU YD | 133 |  | 0
4 | TOPSOIL FURNISH AND PLACE, 4" | SQ YD | 7858 |  | 0
5 | GRADING AND SHAPING DITCHES | FOOT | 611 |  | 0
6 | SEEDING, CLASS 1A | ACRE | 1.6 |  | 0
7 | NITROGEN FERTILZER NUTRIENT | POUND | 144 |  | 0
8 | PHOSPHOROUS FERTILIZER NUTRIENT | POUND | 144 |  | 0
9 | POTASSIUM FERTILZER NUTRIENT | POUND | 144 |  | 0
10 | EROSION CONTROL BLANKET | SQ YD | 7858 |  | 0
11 | TEMPORARY DITCH CHECKS | FOOT | 100 |  | 0
12 | PERIMETER EROSION BARRIER | FOOT | 6019 |  | 0
13 | INLET AND PIPE PROTECTION | EACH | 45 |  | 0
14 | STONE RIPRAP, CLASS A3 | SQ YD | 1272 |  | 0
15 | FILTER FABRIC | SQ YD | 1272 |  | 0
16 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 3913 |  | 0
17 | AGGREGATE BASE COURSE, TYPE B | TON | 5375 |  | 0
18 | BITUMINOUS MATERIALS (PRIME COAT) | POUND | 26228 |  | 0
19 | BITUMINOUS MATERIALS (TACK COAT) | POUND | 3299 |  | 0
20 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N90 | TON | 3860 |  | 0
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N70 | TON | 1808 |  | 0
22 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 12559 |  | 0
23 | PAVEMENT REMOVAL | SQ YD | 14697 |  | 0
24 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 5479 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | SIDEWALK REMOVAL | SQ FT | 39 |  | 0
26 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 12" | EACH | 4 |  | 0
27 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 15" | EACH | 2 |  | 0
28 | REMOVING INLETS | EACH | 17 |  | 0
29 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 5615 |  | 0
30 | STEEL PLATE BEAM GUARDRAIL, TYPE A, 9 FOOT POSTS | FOOT | 412.5 |  | 0
31 | TRAFFIC BARRIER TERMINAL, TYPE 1B | EACH | 1 |  | 0
32 | TRAFFIC BARRIER TERMINAL, TYPE 6A | EACH | 1 |  | 0
33 | GUARDRAIL REMOVAL | FOOT | 477 |  | 0
34 | REMOVE AND REERECT RAIL ELEMENT OF EXISTING GUARDRAIL | FOOT | 12.5 |  | 0
35 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 |  | 0
36 | SPECIAL WASTE DISPOSAL | CU YD | 200 |  | 0
37 | SOIL DISPOSAL ANALYSIS | EACH | 1 |  | 0
38 | MOBILIZATION | L SUM | 1 |  | 0
39 | CHANGEABLE MESSAGE SIGN | CAL DA | 28 |  | 0
40 | SIGN PANEL - TYPE 1 | SQ FT | 9.25 |  | 0
41 | METAL POST - TYPE A | FOOT | 26 |  | 0
42 | THERMOPLASTIC PAVEMENT MARKING - LETTERS AND SYMBOLS | SQ FT | 436.8 |  | 0
43 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" | FOOT | 7005 |  | 0
44 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | FOOT | 708 |  | 0
45 | THERMOPLASTIC PAVEMENT MARKING - LINE 8" | FOOT | 800 |  | 0
46 | THERMOPLASTIC PAVEMENT MARKING - LINE 12" | FOOT | 219 |  | 0
47 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" | FOOT | 139 |  | 0
48 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 5C | FOOT | 280.5 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, MAST ARM MOUNTED | EACH | 1 |  | 0
50 | RELOCATE EXISTING SIGNAL HEAD | EACH | 1 |  | 0
51 | MODIFY EXISTING CONTROLLER | EACH | 1 |  | 0
52 | STORM SEWERS, CLASS A, TYPE 1 12" | FOOT | 812 |  | 0
53 | STORM SEWERS, CLASS A, TYPE 1 15" | FOOT | 47 |  | 0
54 | STORM SEWERS, CLASS A, TYPE 2 12" | FOOT | 125 |  | 0
55 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 |  | 0
56 | RELOCATE EXISTING MAILBOX | EACH | 10 |  | 0
57 | RAILROAD FLAGGER | L SUM | 1 |  | 0
58 | PAVEMENT MARKING REMOVAL - WATER BLASTING | SQ FT | 216 |  | 0
59 | REMOVE AND RELOCATE SIGN PANEL AND POLE ASSEMBLY | EACH | 15 |  | 0
60 | STORM SEWER REMOVAL | FOOT | 704 |  | 0
61 | INLETS, SPECIAL | EACH | 26 |  | 0
62 | SANITARY MANHOLES TO BE ADJUSTED | EACH | 4 |  | 0
63 | SANITARY MANHOLES TO BE RECONSTRUCTED WITH NEW TYPE 1 FRAME, CLOSED LID | EACH | 1 |  | 0
64 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 |  | 0
65 | SIGN REMOVAL | EACH | 2 |  | 0
66 | HANDHOLE TO BE ADJUSTED | EACH | 1 |  | 0
67 | CONCRETE TRUCK WASHOUT | L SUM | 1 |  | 0
68 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT REMOVAL | SQ YD | 790 |  | 0
69 | CONSTRUCTION LAYOUT | L SUM | 1 |  | 0
70 | VIDEO VEHICLE DETECTION SYSTEM | EACH | 1 |  | 0
71 | RAILROAD PROTECTIVE LIABILITY INSURANCE | L SUM | 1 |  | 0
72 | SUBGRADE UNDERCUTTING | CU YD | 573 |  | 0
| Page 3 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
73 | ADA CURB RAMP, STD 424001 | EACH | 12 |  | 0
74 | ADA CURB RAMP, STD 424026 | EACH | 4 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | VENDORS NOTIFIED: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | TREE REMOVAL, ACRES | ACRE | 0.1 | 10000 | 1000
2 | EARTH EXCAVATION | CU YD | 6330 | 45 | 284850
3 | TRENCH BACKFILL | CU YD | 133 | 40 | 5320
4 | TOPSOIL FURNISH AND PLACE, 4" | SQ YD | 7858 | 6 | 47148
5 | GRADING AND SHAPING DITCHES | FOOT | 611 | 15 | 9165
6 | SEEDING, CLASS 1A | ACRE | 1.6 | 3600 | 5760
7 | NITROGEN FERTILZER NUTRIENT | POUND | 144 | 3.6 | 518.4
8 | PHOSPHOROUS FERTILIZER NUTRIENT | POUND | 144 | 3.6 | 518.4
9 | POTASSIUM FERTILZER NUTRIENT | POUND | 144 | 3.6 | 518.4
10 | EROSION CONTROL BLANKET | SQ YD | 7858 | 2 | 15716
11 | TEMPORARY DITCH CHECKS | FOOT | 100 | 15 | 1500
12 | PERIMETER EROSION BARRIER | FOOT | 6019 | 3.25 | 19561.75
13 | INLET AND PIPE PROTECTION | EACH | 45 | 160 | 7200
14 | STONE RIPRAP, CLASS A3 | SQ YD | 1272 | 60 | 76320
15 | FILTER FABRIC | SQ YD | 1272 | 3.5 | 4452
16 | SUBBASE GRANULAR MATERIAL, TYPE B | TON | 3913 | 25 | 97825
17 | AGGREGATE BASE COURSE, TYPE B | TON | 5375 | 50 | 268750
18 | BITUMINOUS MATERIALS (PRIME COAT) | POUND | 26228 | 0.7 | 18359.6
19 | BITUMINOUS MATERIALS (TACK COAT) | POUND | 3299 | 1 | 3299
20 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N90 | TON | 3860 | 65 | 250900
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N70 | TON | 1808 | 65 | 117520
22 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | SQ FT | 12559 | 8.5 | 106751.5
23 | PAVEMENT REMOVAL | SQ YD | 14697 | 16 | 235152
24 | COMBINATION CURB AND GUTTER REMOVAL | FOOT | 5479 | 12 | 65748
|  |  |  | Sub Total | 1643853.05
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | VENDORS NOTIFIED: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | SIDEWALK REMOVAL | SQ FT | 39 | 2.5 | 97.5
26 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 12" | EACH | 4 | 700 | 2800
27 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 15" | EACH | 2 | 800 | 1600
28 | REMOVING INLETS | EACH | 17 | 475 | 8075
29 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | FOOT | 5615 | 40 | 224600
30 | STEEL PLATE BEAM GUARDRAIL, TYPE A, 9 FOOT POSTS | FOOT | 412.5 | 40 | 16500
31 | TRAFFIC BARRIER TERMINAL, TYPE 1B | EACH | 1 | 2400 | 2400
32 | TRAFFIC BARRIER TERMINAL, TYPE 6A | EACH | 1 | 3600 | 3600
33 | GUARDRAIL REMOVAL | FOOT | 477 | 6.5 | 3100.5
34 | REMOVE AND REERECT RAIL ELEMENT OF EXISTING GUARDRAIL | FOOT | 12.5 | 33 | 412.5
35 | NON-SPECIAL WASTE DISPOSAL | CU YD | 200 | 60 | 12000
36 | SPECIAL WASTE DISPOSAL | CU YD | 200 | 50 | 10000
37 | SOIL DISPOSAL ANALYSIS | EACH | 1 | 1500 | 1500
38 | MOBILIZATION | L SUM | 1 | 25000 | 25000
39 | CHANGEABLE MESSAGE SIGN | CAL DA | 28 | 75 | 2100
40 | SIGN PANEL - TYPE 1 | SQ FT | 9.25 | 50 | 462.5
41 | METAL POST - TYPE A | FOOT | 26 | 21 | 546
42 | THERMOPLASTIC PAVEMENT MARKING - LETTERS AND SYMBOLS | SQ FT | 436.8 | 6 | 2620.8
43 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" | FOOT | 7005 | 1.2 | 8406
44 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | FOOT | 708 | 2 | 1416
45 | THERMOPLASTIC PAVEMENT MARKING - LINE 8" | FOOT | 800 | 1.7 | 1360
46 | THERMOPLASTIC PAVEMENT MARKING - LINE 12" | FOOT | 219 | 2.95 | 646.05
47 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" | FOOT | 139 | 7 | 973
48 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 5C | FOOT | 280.5 | 1.6 | 448.8
|  |  |  | Sub Total | 1974517.7
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | VENDORS NOTIFIED: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, MAST ARM MOUNTED | EACH | 1 | 965 | 965
50 | RELOCATE EXISTING SIGNAL HEAD | EACH | 1 | 650 | 650
51 | MODIFY EXISTING CONTROLLER | EACH | 1 | 2400 | 2400
52 | STORM SEWERS, CLASS A, TYPE 1 12" | FOOT | 812 | 70 | 56840
53 | STORM SEWERS, CLASS A, TYPE 1 15" | FOOT | 47 | 70 | 3290
54 | STORM SEWERS, CLASS A, TYPE 2 12" | FOOT | 125 | 80 | 10000
55 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | L SUM | 1 | 3500 | 3500
56 | RELOCATE EXISTING MAILBOX | EACH | 10 | 200 | 2000
57 | RAILROAD FLAGGER | L SUM | 1 | 10000 | 10000
58 | PAVEMENT MARKING REMOVAL - WATER BLASTING | SQ FT | 216 | 3 | 648
59 | REMOVE AND RELOCATE SIGN PANEL AND POLE ASSEMBLY | EACH | 15 | 550 | 8250
60 | STORM SEWER REMOVAL | FOOT | 704 | 15 | 10560
61 | INLETS, SPECIAL | EACH | 26 | 2600 | 67600
62 | SANITARY MANHOLES TO BE ADJUSTED | EACH | 4 | 850 | 3400
63 | SANITARY MANHOLES TO BE RECONSTRUCTED WITH NEW TYPE 1 FRAME, CLOSED LID | EACH | 1 | 3000 | 3000
64 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | L SUM | 1 | 30000 | 30000
65 | SIGN REMOVAL | EACH | 2 | 265 | 530
66 | HANDHOLE TO BE ADJUSTED | EACH | 1 | 1400 | 1400
67 | CONCRETE TRUCK WASHOUT | L SUM | 1 | 1800 | 1800
68 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT REMOVAL | SQ YD | 790 | 18 | 14220
69 | CONSTRUCTION LAYOUT | L SUM | 1 | 28500 | 28500
70 | VIDEO VEHICLE DETECTION SYSTEM | EACH | 1 | 9000 | 9000
71 | RAILROAD PROTECTIVE LIABILITY INSURANCE | L SUM | 1 | 11500 | 11500
72 | SUBGRADE UNDERCUTTING | CU YD | 573 | 48 | 27504
|  |  |  | Sub Total | 2282074.7
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | VENDORS NOTIFIED: 89
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
73 | ADA CURB RAMP, STD 424001 | EACH | 12 | 1540 | 18480
74 | ADA CURB RAMP, STD 424026 | EACH | 4 | 700 | 2800
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 2303354.7
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: William Charles Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | VENDORS NOTIFIED: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | TREE REMOVAL, ACRES | 0.1 | ACRE | 5500 |  | 0.1 |  |  | 55000
2 | EARTH EXCAVATION | 6330 | CU YD | 140842.5 |  | 6330 |  |  | 22.25
3 | TRENCH BACKFILL | 133 | CU YD | 5320 |  | 133 |  |  | 40
4 | TOPSOIL FURNISH AND PLACE, 4" | 7858 | SQ YD | 21216.6 |  | 7858 |  |  | 2.7
5 | GRADING AND SHAPING DITCHES | 611 | FOOT | 4857.45 |  | 611 |  |  | 7.95
6 | SEEDING, CLASS 1A | 1.6 | ACRE | 8000 |  | 1.6 |  |  | 5000
7 | NITROGEN FERTILZER NUTRIENT | 144 | POUND | 144 |  | 144 |  |  | 1
8 | PHOSPHOROUS FERTILIZER NUTRIENT | 144 | POUND | 144 |  | 144 |  |  | 1
9 | POTASSIUM FERTILZER NUTRIENT | 144 | POUND | 144 |  | 144 |  |  | 1
10 | EROSION CONTROL BLANKET | 7858 | SQ YD | 8643.8 |  | 7858 |  |  | 1.1
11 | TEMPORARY DITCH CHECKS | 100 | FOOT | 2200 |  | 100 |  |  | 22
12 | PERIMETER EROSION BARRIER | 6019 | FOOT | 21066.5 |  | 6019 |  |  | 3.5
13 | INLET AND PIPE PROTECTION | 45 | EACH | 3375 |  | 45 |  |  | 75
14 | STONE RIPRAP, CLASS A3 | 1272 | SQ YD | 12.72 |  | 1272 |  |  | 0.01
15 | FILTER FABRIC | 1272 | SQ YD | 3370.8 |  | 1272 |  |  | 2.65
16 | SUBBASE GRANULAR MATERIAL, TYPE B | 3913 | TON | 48521.2 |  | 3913 |  |  | 12.4
17 | AGGREGATE BASE COURSE, TYPE B | 5375 | TON | 86268.75 |  | 5375 |  |  | 16.05
18 | BITUMINOUS MATERIALS (PRIME COAT) | 26228 | POUND | 13114 |  | 26228 |  |  | 0.5
19 | BITUMINOUS MATERIALS (TACK COAT) | 3299 | POUND | 1649.5 |  | 3299 |  |  | 0.5
20 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N90 | 3860 | TON | 247040 |  | 3860 |  |  | 64
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N70 | 1808 | TON | 126560 |  | 1808 |  |  | 70
22 | PORTLAND CEMENT CONCRETE SIDEWALK 4 INCH | 12559 | SQ FT | 76609.9 |  | 12559 |  |  | 6.1
23 | PAVEMENT REMOVAL | 14697 | SQ YD | 79363.8 |  | 14697 |  |  | 5.4
24 | COMBINATION CURB AND GUTTER REMOVAL | 5479 | FOOT | 15615.15 |  | 5479 |  |  | 2.85
Sub Total |  |  |  | 919579.67 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: William Charles Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | VENDORS NOTIFIED: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | SIDEWALK REMOVAL | 39 | SQ FT | 85.8 |  | 39 |  |  | 2.2
26 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 12" | 4 | EACH | 3800 |  | 4 |  |  | 950
27 | PRECAST REINFORCED CONCRETE FLARED END SECTIONS 15" | 2 | EACH | 1960 |  | 2 |  |  | 980
28 | REMOVING INLETS | 17 | EACH | 7820 |  | 17 |  |  | 460
29 | COMBINATION CONCRETE CURB AND GUTTER, TYPE M-6.18 (MODIFIED) | 5615 | FOOT | 94051.25 |  | 5615 |  |  | 16.75
30 | STEEL PLATE BEAM GUARDRAIL, TYPE A, 9 FOOT POSTS | 412.5 | FOOT | 12622.5 |  | 412.5 |  |  | 30.6
31 | TRAFFIC BARRIER TERMINAL, TYPE 1B | 1 | EACH | 1984.6 |  | 1 |  |  | 1984.6
32 | TRAFFIC BARRIER TERMINAL, TYPE 6A | 1 | EACH | 3501.1 |  | 1 |  |  | 3501.1
33 | GUARDRAIL REMOVAL | 477 | FOOT | 2838.15 |  | 477 |  |  | 5.95
34 | REMOVE AND REERECT RAIL ELEMENT OF EXISTING GUARDRAIL | 12.5 | FOOT | 187.5 |  | 12.5 |  |  | 15
35 | NON-SPECIAL WASTE DISPOSAL | 200 | CU YD | 5866 |  | 200 |  |  | 29.33
36 | SPECIAL WASTE DISPOSAL | 200 | CU YD | 8746 |  | 200 |  |  | 43.73
37 | SOIL DISPOSAL ANALYSIS | 1 | EACH | 1250 |  | 1 |  |  | 1250
38 | MOBILIZATION | 1 | L SUM | 54000 |  | 1 |  |  | 54000
39 | CHANGEABLE MESSAGE SIGN | 28 | CAL DA | 1120 |  | 28 |  |  | 40
40 | SIGN PANEL - TYPE 1 | 9.25 | SQ FT | 277.5 |  | 9.25 |  |  | 30
41 | METAL POST - TYPE A | 26 | FOOT | 390 |  | 26 |  |  | 15
42 | THERMOPLASTIC PAVEMENT MARKING - LETTERS AND SYMBOLS | 436.8 | SQ FT | 2184 |  | 436.8 |  |  | 5
43 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" | 7005 | FOOT | 4203 |  | 7005 |  |  | 0.6
44 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | 708 | FOOT | 637.2 |  | 708 |  |  | 0.9
45 | THERMOPLASTIC PAVEMENT MARKING - LINE 8" | 800 | FOOT | 960 |  | 800 |  |  | 1.2
46 | THERMOPLASTIC PAVEMENT MARKING - LINE 12" | 219 | FOOT | 394.2 |  | 219 |  |  | 1.8
47 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" | 139 | FOOT | 500.4 |  | 139 |  |  | 3.6
48 | ELECTRIC CABLE IN CONDUIT, SIGNAL NO. 14 5C | 280.5 | FOOT | 603.075 |  | 280.5 |  |  | 2.15
Sub Total |  |  |  | 1129561.945 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: William Charles Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | VENDORS NOTIFIED: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | SIGNAL HEAD, POLYCARBONATE, LED, 1-FACE, 3-SECTION, MAST ARM MOUNTED | 1 | EACH | 819.3 |  | 1 |  |  | 819.3
50 | RELOCATE EXISTING SIGNAL HEAD | 1 | EACH | 477.5 |  | 1 |  |  | 477.5
51 | MODIFY EXISTING CONTROLLER | 1 | EACH | 1231.2 |  | 1 |  |  | 1231.2
52 | STORM SEWERS, CLASS A, TYPE 1 12" | 812 | FOOT | 42995.4 |  | 812 |  |  | 52.95
53 | STORM SEWERS, CLASS A, TYPE 1 15" | 47 | FOOT | 4655.35 |  | 47 |  |  | 99.05
54 | STORM SEWERS, CLASS A, TYPE 2 12" | 125 | FOOT | 6400 |  | 125 |  |  | 51.2
55 | SPECIAL WASTE PLANS AND REPORTS (SPECIAL) | 1 | L SUM | 2224.2 |  | 1 |  |  | 2224.2
56 | RELOCATE EXISTING MAILBOX | 10 | EACH | 3386 |  | 10 |  |  | 338.6
57 | RAILROAD FLAGGER | 1 | L SUM | 8846.3 |  | 1 |  |  | 8846.3
58 | PAVEMENT MARKING REMOVAL - WATER BLASTING | 216 | SQ FT | 1533.6 |  | 216 |  |  | 7.1
59 | REMOVE AND RELOCATE SIGN PANEL AND POLE ASSEMBLY | 15 | EACH | 3184.5 |  | 15 |  |  | 212.3
60 | STORM SEWER REMOVAL | 704 | FOOT | 30553.6 |  | 704 |  |  | 43.4
61 | INLETS, SPECIAL | 26 | EACH | 65629.2 |  | 26 |  |  | 2524.2
62 | SANITARY MANHOLES TO BE ADJUSTED | 4 | EACH | 3923.2 |  | 4 |  |  | 980.8
63 | SANITARY MANHOLES TO BE RECONSTRUCTED WITH NEW TYPE 1 FRAME, CLOSED LID | 1 | EACH | 3018.6 |  | 1 |  |  | 3018.6
64 | TRAFFIC CONTROL AND PROTECTION, (SPECIAL) | 1 | L SUM | 23000 |  | 1 |  |  | 23000
65 | SIGN REMOVAL | 2 | EACH | 121.3 |  | 2 |  |  | 60.65
66 | HANDHOLE TO BE ADJUSTED | 1 | EACH | 2076.3 |  | 1 |  |  | 2076.3
67 | CONCRETE TRUCK WASHOUT | 1 | L SUM | 750 |  | 1 |  |  | 750
68 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT REMOVAL | 790 | SQ YD | 3120.5 |  | 790 |  |  | 3.95
69 | CONSTRUCTION LAYOUT | 1 | L SUM | 15500 |  | 1 |  |  | 15500
70 | VIDEO VEHICLE DETECTION SYSTEM | 1 | EACH | 23933 |  | 1 |  |  | 23933
71 | RAILROAD PROTECTIVE LIABILITY INSURANCE | 1 | L SUM | 4100 |  | 1 |  |  | 4100
72 | SUBGRADE UNDERCUTTING | 573 | CU YD | 5.73 |  | 573 |  |  | 0.01
Sub Total |  |  |  | 1381046.725 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: William Charles Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | VENDORS NOTIFIED: 89
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
73 | ADA CURB RAMP, STD 424001 | 12 | EACH | 9720 |  | 12 |  |  | 810
74 | ADA CURB RAMP, STD 424026 | 4 | EACH | 2064 |  | 4 |  |  | 516
Total |  |  |  | 1392830.725 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | VENDORS NOTIFIED: 89
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | William Charles Construction
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.