## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 1308833
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 55500 | 55500
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 27700 | 27700
3 | INLET FILTERS | EA | 23 | 175 | 4025
4 | SEDIMENT CONTROL, SILT FENCE | LF | 1449 | 5 | 7245
5 | CONCRETE TRUCK WASHOUT | EA | 3 | 1200 | 3600
6 | HMA SURFACE REMOVAL, 2" | SY | 294 | 10 | 2940
7 | DRIVEWAY PAVEMENT REMOVAL | SY | 163 | 15 | 2445
8 | SIDEWALK REMOVAL | SF | 2265 | 2 | 4530
9 | COMBINATION CURB AND GUTTER REMOVAL | LF | 183 | 10 | 1830
10 | ROCK EXCAVATION | CY | 25 | 230 | 5750
11 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 4 | 300 | 1200
12 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 17 | 500 | 8500
13 | REMOVE FIRE HYDRANT, COMPLETE | EA | 9 | 500 | 4500
14 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | SY | 163 | 75 | 12225
15 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SF | 2265 | 8 | 18120
16 | DETECTABLE WARNINGS | SF | 26 | 36 | 936
17 | COMBINATION CONCRETE CURB AND GUTTER,TYPE B6.18(MODIFIED) | LF | 183 | 38 | 6954
18 | CONCRETE SIDEWALK STEPS | CY | 11 | 500 | 5500
19 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 1271 | 12 | 15252
20 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 1271 | 11 | 13981
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 167 | 180 | 30060
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 6" | TON | 285 | 160 | 45600
23 | BITUMINOUS MATERIALS (PRIME COAT) | GAL | 706 | 5 | 3530
24 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | LF | 386 | 5 | 1930
25 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 165 | 85 | 14025
26 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 2643 | 105 | 277515
27 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 14 | 3500 | 49000
28 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 9 | 6250 | 56250
29 | BOUNDARY VALVE VAULT W/ 1.5" BYPASS SERVICE | EA | 2 | 6000 | 12000
30 | WATER SERVICE (LONG), COMPLETE, 1" | EA | 6 | 4000 | 24000
31 | WATER SERVICE (SHORT), COMPLETE 1" | EA | 13 | 2600 | 33800
32 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 12 | 2200 | 26400
33 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 1 | 3600 | 3600
34 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 1 | 4100 | 4100
35 | WATER MAIN PROTECTION, 15" | LF | 383 | 300 | 114900
36 | WATER SERVICE PROTECTION, 2" | LF | 126 | 250 | 31500
37 | WATER MAIN REMOVAL, 6" | LF | 148 | 25 | 3700
38 | WATER MAIN TO BE ABANDONED, 6" | CY | 34 | 1370 | 46580
39 | WATER MAIN LINE STOP, 6" | EA | 13 | 5200 | 67600
40 | WATER MAIN LINE STOP, 8" | EA | 2 | 5250 | 10500
41 | WATER MAIN LINE STOP, 12" | EA | 1 | 5400 | 5400
42 | INSERTION VALVE, COMPLETE, 6" | EA | 2 | 9000 | 18000
43 | INSERTION VALVE, COMPLETE, 8" | EA | 2 | 9400 | 18800
44 | EXPLORATORY EXCAVATION ALLOWANCE | CY | 120 | 20 | 2400
45 | PARKWAY RESTORATION | LS | 1 | 28930 | 28930
46 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 28000 | 28000
47 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 50 | 1750 | 87500
48 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 50 | 1200 | 60000
49 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 | 230 | 230
50 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 250 | 250
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | N-TRAK Group |  | Northern Illinois Service |  | Fischer Excavating
City of Rockford | [5 empty] | Loves Par, IL |  | Rockford, IL |  | Rockford, IL
West State St. Water Main Relocation
Bid No.: 721-W-055 VENDORS NOTIFIED: 89
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 55500 | 55500 | 20000 | 20000 | 14600 | 14600 | 9000 | 9000 |  | 0 |  | 0 |  | 0
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 27700 | 27700 | 8500 | 8500 | 5500 | 5500 | 8425 | 8425 |  | 0 |  | 0 |  | 0
3 | INLET FILTERS | EA | 23 | 175 | 4025 | 100 | 2300 | 125 | 2875 | 120 | 2760 |  | 0 |  | 0 |  | 0
4 | SEDIMENT CONTROL, SILT FENCE | LF | 1449 | 5 | 7245 | 3 | 4347 | 2 | 2898 | 2.7 | 3912.3 |  | 0 |  | 0 |  | 0
5 | CONCRETE TRUCK WASHOUT | EA | 3 | 1200 | 3600 | 1 | 3 | 150 | 450 | 225 | 675 |  | 0 |  | 0 |  | 0
6 | HMA SURFACE REMOVAL, 2" | SY | 294 | 10 | 2940 | 3 | 882 | 12 | 3528 | 21 | 6174 |  | 0 |  | 0 |  | 0
7 | DRIVEWAY PAVEMENT REMOVAL | SY | 163 | 15 | 2445 | 7 | 1141 | 5 | 815 | 8.6 | 1401.8 |  | 0 |  | 0 |  | 0
8 | SIDEWALK REMOVAL | SF | 2265 | 2 | 4530 | 1 | 2265 | 1.5 | 3397.5 | 2.9 | 6568.5 |  | 0 |  | 0 |  | 0
9 | COMBINATION CURB AND GUTTER REMOVAL | LF | 183 | 10 | 1830 | 4 | 732 | 5 | 915 | 4.3 | 786.9 |  | 0 |  | 0 |  | 0
10 | ROCK EXCAVATION | CY | 25 | 230 | 5750 | 100 | 2500 | 50 | 1250 | 70 | 1750 |  | 0 |  | 0 |  | 0
11 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 4 | 300 | 1200 | 400 | 1600 | 400 | 1600 | 190 | 760 |  | 0 |  | 0 |  | 0
12 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 17 | 500 | 8500 | 500 | 8500 | 600 | 10200 | 300 | 5100 |  | 0 |  | 0 |  | 0
13 | REMOVE FIRE HYDRANT, COMPLETE | EA | 9 | 500 | 4500 | 750 | 6750 | 700 | 6300 | 602 | 5418 |  | 0 |  | 0 |  | 0
14 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | SY | 163 | 75 | 12225 | 76 | 12388 | 73 | 11899 | 79 | 12877 |  | 0 |  | 0 |  | 0
15 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SF | 2265 | 8 | 18120 | 7.5 | 16987.5 | 6.65 | 15062.25 | 8 | 18120 |  | 0 |  | 0 |  | 0
16 | DETECTABLE WARNINGS | SF | 26 | 36 | 936 | 25 | 650 | 28 | 728 | 28 | 728 |  | 0 |  | 0 |  | 0
17 | COMBINATION CONCRETE CURB AND GUTTER,TYPE B6.18(MODIFIED) | LF | 183 | 38 | 6954 | 37 | 6771 | 29.5 | 5398.5 | 38 | 6954 |  | 0 |  | 0 |  | 0
18 | CONCRETE SIDEWALK STEPS | CY | 11 | 500 | 5500 | 225 | 2475 | 475 | 5225 | 475 | 5225 |  | 0 |  | 0 |  | 0
19 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 1271 | 12 | 15252 | 5.5 | 6990.5 | 7 | 8897 | 40 | 50840 |  | 0 |  | 0 |  | 0
20 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 1271 | 11 | 13981 | 5.5 | 6990.5 | 7 | 8897 | 11.5 | 14616.5 |  | 0 |  | 0 |  | 0
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 167 | 180 | 30060 | 104.5 | 17451.5 | 145 | 24215 | 302 | 50434 |  | 0 |  | 0 |  | 0
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 6" | TON | 285 | 160 | 45600 | 104.5 | 29782.5 | 170 | 48450 | 561 | 159885 |  | 0 |  | 0 |  | 0
23 | BITUMINOUS MATERIALS (PRIME COAT) | GAL | 706 | 5 | 3530 | 0.01 | 7.06 | 5 | 3530 | 0.02 | 14.12 |  | 0 |  | 0 |  | 0
24 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | LF | 386 | 5 | 1930 | 8 | 3088 | 8 | 3088 | 8 | 3088 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 283853 |  | 163101.56 |  | 189718.25 |  | 375513.12
| Award to N-TRAK Group | Total |  | As corrected | 283853 |  | 163101.56 |  | 189718.25 |  | 375513.12
25 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 165 | 85 | 14025 | 120 | 19800 | 150 | 24750 | 142 | 23430 |  | 0 |  | 0 |  | 0
26 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 2643 | 105 | 277515 | 125 | 330375 | 150 | 396450 | 146 | 385878 |  | 0 |  | 0 |  | 0
27 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 14 | 3500 | 49000 | 2300 | 32200 | 2500 | 35000 | 2225 | 31150 |  | 0 |  | 0 |  | 0
28 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 9 | 6250 | 56250 | 5600 | 50400 | 6000 | 54000 | 5900 | 53100 |  | 0 |  | 0 |  | 0
29 | BOUNDARY VALVE VAULT W/ 1.5" BYPASS SERVICE | EA | 2 | 6000 | 12000 | 3200 | 6400 | 8000 | 16000 | 4414 | 8828 |  | 0 |  | 0 |  | 0
30 | WATER SERVICE (LONG), COMPLETE, 1" | EA | 6 | 4000 | 24000 | 4200 | 25200 | 4000 | 24000 | 2953 | 17718 |  | 0 |  | 0 |  | 0
31 | WATER SERVICE (SHORT), COMPLETE 1" | EA | 13 | 2600 | 33800 | 2600 | 33800 | 2500 | 32500 | 2596 | 33748 |  | 0 |  | 0 |  | 0
32 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 12 | 2200 | 26400 | 3500 | 42000 | 2500 | 30000 | 2627 | 31524 |  | 0 |  | 0 |  | 0
33 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 1 | 3600 | 3600 | 3600 | 3600 | 2500 | 2500 | 3430 | 3430 |  | 0 |  | 0 |  | 0
34 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 1 | 4100 | 4100 | 4000 | 4000 | 2500 | 2500 | 5300 | 5300 |  | 0 |  | 0 |  | 0
35 | WATER MAIN PROTECTION, 15" | LF | 383 | 300 | 114900 | 50 | 19150 | 70 | 26810 | 107 | 40981 |  | 0 |  | 0 |  | 0
36 | WATER SERVICE PROTECTION, 2" | LF | 126 | 250 | 31500 | 7 | 882 | 10 | 1260 | 10 | 1260 |  | 0 |  | 0 |  | 0
37 | WATER MAIN REMOVAL, 6" | LF | 148 | 25 | 3700 | 20 | 2960 | 15 | 2220 | 23 | 3404 |  | 0 |  | 0 |  | 0
38 | WATER MAIN TO BE ABANDONED, 6" | CY | 34 | 1370 | 46580 | 350 | 11900 | 350 | 11900 | 900 | 30600 |  | 0 |  | 0 |  | 0
39 | WATER MAIN LINE STOP, 6" | EA | 13 | 5200 | 67600 | 4000 | 52000 | 3500 | 45500 | 4210 | 54730 |  | 0 |  | 0 |  | 0
40 | WATER MAIN LINE STOP, 8" | EA | 2 | 5250 | 10500 | 4300 | 8600 | 4000 | 8000 | 4736 | 9472 |  | 0 |  | 0 |  | 0
41 | WATER MAIN LINE STOP, 12" | EA | 1 | 5400 | 5400 | 5900 | 5900 | 7000 | 7000 | 7034 | 7034 |  | 0 |  | 0 |  | 0
42 | INSERTION VALVE, COMPLETE, 6" | EA | 2 | 9000 | 18000 | 5600 | 11200 | 5300 | 10600 | 6228 | 12456 |  | 0 |  | 0 |  | 0
43 | INSERTION VALVE, COMPLETE, 8" | EA | 2 | 9400 | 18800 | 6000 | 12000 | 5700 | 11400 | 11300 | 22600 |  | 0 |  | 0 |  | 0
44 | EXPLORATORY EXCAVATION ALLOWANCE | CY | 120 | 20 | 2400 | 83 | 9960 | 50 | 6000 | 155 | 18600 |  | 0 |  | 0 |  | 0
45 | PARKWAY RESTORATION | LS | 1 | 28930 | 28930 | 15000 | 15000 | 7500 | 7500 | 24450 | 24450 |  | 0 |  | 0 |  | 0
46 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 28000 | 28000 | 7500 | 7500 | 5000 | 5000 | 6950 | 6950 |  | 0 |  | 0 |  | 0
47 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 50 | 1750 | 87500 | 51.55 | 2577.5 | 50 | 2500 | 84 | 4200 |  | 0 |  | 0 |  | 0
48 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 50 | 1200 | 60000 | 64.5 | 3225 | 50 | 2500 | 100 | 5000 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 1308353 |  | 873731.06 |  | 955608.25 |  | 1211356.12
| Award to N-TRAK Group | Total |  | As corrected | 1308353 |  | 873731.06 |  | 955608.25 |  | 1211356.12
49 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 | 230 | 230 | 1 | 1 | 2000 | 2000 | 2600 | 2600 |  | 0 |  | 0 |  | 0
50 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 250 | 250 | 1200 | 1200 | 2000 | 2000 | 1200 | 1200 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 1308833 |  | 874932.06 |  | 959608.25 |  | 1215156.12
| Award to N-TRAK Group | Bid |  | As corrected | 1308833 |  | 874932.06 |  | 959608.25 |  | 1215156.12
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to N-TRAK Group | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
West State St. Water Main Relocation
Item No. | Items | Units | Quantity | Unit Price | Total
1 | MOBILIZATION | LS | 1 |  | 0
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 |  | 0
3 | INLET FILTERS | EA | 23 |  | 0
4 | SEDIMENT CONTROL, SILT FENCE | LF | 1449 |  | 0
5 | CONCRETE TRUCK WASHOUT | EA | 3 |  | 0
6 | HMA SURFACE REMOVAL, 2" | SY | 294 |  | 0
7 | DRIVEWAY PAVEMENT REMOVAL | SY | 163 |  | 0
8 | SIDEWALK REMOVAL | SF | 2265 |  | 0
9 | COMBINATION CURB AND GUTTER REMOVAL | LF | 183 |  | 0
10 | ROCK EXCAVATION | CY | 25 |  | 0
11 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 4 |  | 0
12 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 17 |  | 0
13 | REMOVE FIRE HYDRANT, COMPLETE | EA | 9 |  | 0
14 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | SY | 163 |  | 0
15 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SF | 2265 |  | 0
16 | DETECTABLE WARNINGS | SF | 26 |  | 0
17 | COMBINATION CONCRETE CURB AND GUTTER,TYPE B6.18(MODIFIED) | LF | 183 |  | 0
18 | CONCRETE SIDEWALK STEPS | CY | 11 |  | 0
19 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 1271 |  | 0
20 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 1271 |  | 0
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 167 |  | 0
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 6" | TON | 285 |  | 0
23 | BITUMINOUS MATERIALS (PRIME COAT) | GAL | 706 |  | 0
24 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | LF | 386 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 165 |  | 0
26 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 2643 |  | 0
27 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 14 |  | 0
28 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 9 |  | 0
29 | BOUNDARY VALVE VAULT W/ 1.5" BYPASS SERVICE | EA | 2 |  | 0
30 | WATER SERVICE (LONG), COMPLETE, 1" | EA | 6 |  | 0
31 | WATER SERVICE (SHORT), COMPLETE 1" | EA | 13 |  | 0
32 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 12 |  | 0
33 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 1 |  | 0
34 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 1 |  | 0
35 | WATER MAIN PROTECTION, 15" | LF | 383 |  | 0
36 | WATER SERVICE PROTECTION, 2" | LF | 126 |  | 0
37 | WATER MAIN REMOVAL, 6" | LF | 148 |  | 0
38 | WATER MAIN TO BE ABANDONED, 6" | CY | 34 |  | 0
39 | WATER MAIN LINE STOP, 6" | EA | 13 |  | 0
40 | WATER MAIN LINE STOP, 8" | EA | 2 |  | 0
41 | WATER MAIN LINE STOP, 12" | EA | 1 |  | 0
42 | INSERTION VALVE, COMPLETE, 6" | EA | 2 |  | 0
43 | INSERTION VALVE, COMPLETE, 8" | EA | 2 |  | 0
44 | EXPLORATORY EXCAVATION ALLOWANCE | CY | 120 |  | 0
45 | PARKWAY RESTORATION | LS | 1 |  | 0
46 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 |  | 0
47 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 50 |  | 0
48 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 50 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 |  | 0
50 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | West State St. Water Main Relocation
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 55500 | 55500
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 27700 | 27700
3 | INLET FILTERS | EA | 23 | 175 | 4025
4 | SEDIMENT CONTROL, SILT FENCE | LF | 1449 | 5 | 7245
5 | CONCRETE TRUCK WASHOUT | EA | 3 | 1200 | 3600
6 | HMA SURFACE REMOVAL, 2" | SY | 294 | 10 | 2940
7 | DRIVEWAY PAVEMENT REMOVAL | SY | 163 | 15 | 2445
8 | SIDEWALK REMOVAL | SF | 2265 | 2 | 4530
9 | COMBINATION CURB AND GUTTER REMOVAL | LF | 183 | 10 | 1830
10 | ROCK EXCAVATION | CY | 25 | 230 | 5750
11 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 4 | 300 | 1200
12 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 17 | 500 | 8500
13 | REMOVE FIRE HYDRANT, COMPLETE | EA | 9 | 500 | 4500
14 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | SY | 163 | 75 | 12225
15 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SF | 2265 | 8 | 18120
16 | DETECTABLE WARNINGS | SF | 26 | 36 | 936
17 | COMBINATION CONCRETE CURB AND GUTTER,TYPE B6.18(MODIFIED) | LF | 183 | 38 | 6954
18 | CONCRETE SIDEWALK STEPS | CY | 11 | 500 | 5500
19 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 1271 | 12 | 15252
20 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 1271 | 11 | 13981
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | TON | 167 | 180 | 30060
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 6" | TON | 285 | 160 | 45600
23 | BITUMINOUS MATERIALS (PRIME COAT) | GAL | 706 | 5 | 3530
24 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | LF | 386 | 5 | 1930
|  |  |  | Sub Total | 283853
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | West State St. Water Main Relocation
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 165 | 85 | 14025
26 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 2643 | 105 | 277515
27 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 14 | 3500 | 49000
28 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 9 | 6250 | 56250
29 | BOUNDARY VALVE VAULT W/ 1.5" BYPASS SERVICE | EA | 2 | 6000 | 12000
30 | WATER SERVICE (LONG), COMPLETE, 1" | EA | 6 | 4000 | 24000
31 | WATER SERVICE (SHORT), COMPLETE 1" | EA | 13 | 2600 | 33800
32 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 12 | 2200 | 26400
33 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 1 | 3600 | 3600
34 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | EA | 1 | 4100 | 4100
35 | WATER MAIN PROTECTION, 15" | LF | 383 | 300 | 114900
36 | WATER SERVICE PROTECTION, 2" | LF | 126 | 250 | 31500
37 | WATER MAIN REMOVAL, 6" | LF | 148 | 25 | 3700
38 | WATER MAIN TO BE ABANDONED, 6" | CY | 34 | 1370 | 46580
39 | WATER MAIN LINE STOP, 6" | EA | 13 | 5200 | 67600
40 | WATER MAIN LINE STOP, 8" | EA | 2 | 5250 | 10500
41 | WATER MAIN LINE STOP, 12" | EA | 1 | 5400 | 5400
42 | INSERTION VALVE, COMPLETE, 6" | EA | 2 | 9000 | 18000
43 | INSERTION VALVE, COMPLETE, 8" | EA | 2 | 9400 | 18800
44 | EXPLORATORY EXCAVATION ALLOWANCE | CY | 120 | 20 | 2400
45 | PARKWAY RESTORATION | LS | 1 | 28930 | 28930
46 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 28000 | 28000
47 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 50 | 1750 | 87500
48 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 50 | 1200 | 60000
|  |  |  | Sub Total | 1308353
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | West State St. Water Main Relocation
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 | 230 | 230
50 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 250 | 250
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1308833
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | West State St. Water Main Relocation
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1308833
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Par, IL | [5 empty] | SECTION | West State St. Water Main Relocation
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | MOBILIZATION | 1 | LS | 20000 |  | 1 |  |  | 20000
2 | CONSTRUCTION LAYOUT STAKES | 1 | LS | 8500 |  | 1 |  |  | 8500
3 | INLET FILTERS | 23 | EA | 2300 |  | 23 |  |  | 100
4 | SEDIMENT CONTROL, SILT FENCE | 1449 | LF | 4347 |  | 1449 |  |  | 3
5 | CONCRETE TRUCK WASHOUT | 3 | EA | 3 |  | 3 |  |  | 1
6 | HMA SURFACE REMOVAL, 2" | 294 | SY | 882 |  | 294 |  |  | 3
7 | DRIVEWAY PAVEMENT REMOVAL | 163 | SY | 1141 |  | 163 |  |  | 7
8 | SIDEWALK REMOVAL | 2265 | SF | 2265 |  | 2265 |  |  | 1
9 | COMBINATION CURB AND GUTTER REMOVAL | 183 | LF | 732 |  | 183 |  |  | 4
10 | ROCK EXCAVATION | 25 | CY | 2500 |  | 25 |  |  | 100
11 | REMOVE VALVE AND VALVE BOX, COMPLETE | 4 | EA | 1600 |  | 4 |  |  | 400
12 | REMOVE VALVE AND VALVE VAULT, COMPLETE | 17 | EA | 8500 |  | 17 |  |  | 500
13 | REMOVE FIRE HYDRANT, COMPLETE | 9 | EA | 6750 |  | 9 |  |  | 750
14 | PORTLAND CEMENT CONCRETE DRIVEWAY PAVEMENT, 6" | 163 | SY | 12388 |  | 163 |  |  | 76
15 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | 2265 | SF | 16987.5 |  | 2265 |  |  | 7.5
16 | DETECTABLE WARNINGS | 26 | SF | 650 |  | 26 |  |  | 25
17 | COMBINATION CONCRETE CURB AND GUTTER,TYPE B6.18(MODIFIED) | 183 | LF | 6771 |  | 183 |  |  | 37
18 | CONCRETE SIDEWALK STEPS | 11 | CY | 2475 |  | 11 |  |  | 225
19 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | 1271 | SY | 6990.5 |  | 1271 |  |  | 5.5
20 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | 1271 | SY | 6990.5 |  | 1271 |  |  | 5.5
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX C, N50, 2" | 167 | TON | 17451.5 |  | 167 |  |  | 104.5
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 6" | 285 | TON | 29782.5 |  | 285 |  |  | 104.5
23 | BITUMINOUS MATERIALS (PRIME COAT) | 706 | GAL | 7.06 |  | 706 |  |  | 0.01
24 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" | 386 | LF | 3088 |  | 386 |  |  | 8
Sub Total |  |  |  | 163101.56 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Par, IL | [5 empty] | SECTION | West State St. Water Main Relocation
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | 165 | LF | 19800 |  | 165 |  |  | 120
26 | DUCTILE IRON WATER MAIN COMPLETE, 8" | 2643 | LF | 330375 |  | 2643 |  |  | 125
27 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | 14 | EA | 32200 |  | 14 |  |  | 2300
28 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | 9 | EA | 50400 |  | 9 |  |  | 5600
29 | BOUNDARY VALVE VAULT W/ 1.5" BYPASS SERVICE | 2 | EA | 6400 |  | 2 |  |  | 3200
30 | WATER SERVICE (LONG), COMPLETE, 1" | 6 | EA | 25200 |  | 6 |  |  | 4200
31 | WATER SERVICE (SHORT), COMPLETE 1" | 13 | EA | 33800 |  | 13 |  |  | 2600
32 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | 12 | EA | 42000 |  | 12 |  |  | 3500
33 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | 1 | EA | 3600 |  | 1 |  |  | 3600
34 | CONNECT TO EXISTING 12" WATER MAIN, COMPLETE | 1 | EA | 4000 |  | 1 |  |  | 4000
35 | WATER MAIN PROTECTION, 15" | 383 | LF | 19150 |  | 383 |  |  | 50
36 | WATER SERVICE PROTECTION, 2" | 126 | LF | 882 |  | 126 |  |  | 7
37 | WATER MAIN REMOVAL, 6" | 148 | LF | 2960 |  | 148 |  |  | 20
38 | WATER MAIN TO BE ABANDONED, 6" | 34 | CY | 11900 |  | 34 |  |  | 350
39 | WATER MAIN LINE STOP, 6" | 13 | EA | 52000 |  | 13 |  |  | 4000
40 | WATER MAIN LINE STOP, 8" | 2 | EA | 8600 |  | 2 |  |  | 4300
41 | WATER MAIN LINE STOP, 12" | 1 | EA | 5900 |  | 1 |  |  | 5900
42 | INSERTION VALVE, COMPLETE, 6" | 2 | EA | 11200 |  | 2 |  |  | 5600
43 | INSERTION VALVE, COMPLETE, 8" | 2 | EA | 12000 |  | 2 |  |  | 6000
44 | EXPLORATORY EXCAVATION ALLOWANCE | 120 | CY | 9960 |  | 120 |  |  | 83
45 | PARKWAY RESTORATION | 1 | LS | 15000 |  | 1 |  |  | 15000
46 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | 1 | LS | 7500 |  | 1 |  |  | 7500
47 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | 50 | CY | 2577.5 |  | 50 |  |  | 51.55
48 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | 50 | CY | 3225 |  | 50 |  |  | 64.5
Sub Total |  |  |  | 873731.06 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Par, IL | [5 empty] | SECTION | West State St. Water Main Relocation
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | 1 | LS | 1 |  | 1 |  |  | 1
50 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | 1 | EA | 1200 |  | 1 |  |  | 1200
Total |  |  |  | 874932.06 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: N-TRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Loves Par, IL | [5 empty] | SECTION | West State St. Water Main Relocation
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 874932.06 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | West State St. Water Main Relocation
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | N-TRAK Group
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.