## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 756110
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 7500 | 7500
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 5000 | 5000
3 | INLET AND PIPE PROTECTION | EA | 10 | 250 | 2500
4 | CONCRETE TRUCK WASHOUT | EA | 1 | 500 | 500
5 | PAVEMENT REMOVAL | SY | 1790 | 12.5 | 22375
6 | APPROACH PAVEMENT REMOVAL | SY | 65 | 12 | 780
7 | SIDEWALK REMOVAL | SF | 3235 | 3 | 9705
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 1610 | 17.5 | 28175
9 | ROCK EXCAVATION | CY | 25 | 200 | 5000
10 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 1 | 950 | 950
11 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 3 | 1000 | 3000
12 | REMOVE FIRE HYDRANT, COMPLETE | EA | 4 | 1000 | 4000
13 | PCC APPROACH PAVEMENT, 6" | SY | 50 | 150 | 7500
14 | PCC SIDEWALK, 4" | SF | 3235 | 10 | 32350
15 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18(MODIFIED) | LF | 1610 | 35 | 56350
16 | DETECTABLE WARNINGS | SF | 50 | 85 | 4250
17 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 1790 | 7.5 | 13425
18 | AGGREGATE BASE COURSE, TYPE B, 4" (CA-6) | SY | 30 | 7.5 | 225
19 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 1790 | 7.5 | 13425
20 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N50, 2" | TON | 200 | 100 | 20000
21 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 400 | 115 | 46000
22 | P.C.C. PAVEMENT, 9.5" (JOINTED) | SY | 30 | 200 | 6000
23 | HMA APPROACH PAVEMENT, 3" | SY | 15 | 50 | 750
24 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 20 | 125 | 2500
25 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 1375 | 110 | 151250
26 | DUCTILE IRON WATER MAIN COMPLETE, 10" | LF | 45 | 140 | 6300
27 | MANHOLES, TYPE A, 5' DIAMETER, WITH SALVAGED FRAME AND LID | EA | 1 | 3500 | 3500
28 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 12" | LF | 60 | 90 | 5400
29 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 15" | LF | 20 | 95 | 1900
30 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 18" | LF | 25 | 100 | 2500
31 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 | 2000 | 2000
32 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 6 | 2500 | 15000
33 | GATE VALVE AND VALVE BOX, COMPLETE, 10" | EA | 1 | 3000 | 3000
34 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 4 | 6000 | 24000
35 | WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 42 | 2500 | 105000
36 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 2 | 4500 | 9000
37 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 3 | 5500 | 16500
38 | CONNECT TO EXISTING 10" WATER MAIN, COMPLETE | EA | 2 | 6500 | 13000
39 | WATER MAIN PROTECTION, 12" | LF | 50 | 50 | 2500
40 | WATER SERVICE PROTECTION, 2" | LF | 500 | 10 | 5000
41 | WATER MAIN LINE STOP, 6" | EA | 2 | 4500 | 9000
42 | WATER MAIN LINE STOP, 8" | EA | 2 | 4500 | 9000
43 | WATER MAIN LINE STOP,10" | EA | 2 | 5500 | 11000
44 | INSERTION VALVE, COMPLETE, 6" | EA | 1 | 4500 | 4500
45 | INSERTION VALVE, COMPLETE, 8" | EA | 1 | 6500 | 6500
46 | INSERTION VALVE, COMPLETE, 10" | EA | 1 | 8500 | 8500
47 | EXPLORATORY EXCAVATION | CY | 25 | 50 | 1250
48 | TREE REMOVAL (6-15" UNITS DIAMETER) | UD | 15 | 50 | 750
49 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UD | 220 | 60 | 13200
50 | PARKWAY RESTORATION | LS | 1 | 15000 | 15000
51 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 7500 | 7500
52 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 50 | 1250
53 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 50 | 1250
54 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | EA | 1 | 2000 | 2000
55 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 2000 | 2000
56 | KENTUCKY COFFEETREE / Gymnocladus Dioicus, 2.5" CALIPER | EA | 3 | 500 | 1500
57 | SUGAR MAPLE / Acer Saccharum, 2.5" CALIPER | EA | 3 | 600 | 1800
58 | EASTERN REDBUD / Cercis canadenis, 2" CALIPER | EA | 2 | 450 | 900
59 | AUTUMN BRILLIANCE SERVICE BERRY / Amelanchier x grandiflora 'Autumn Brilliance', 2" CALIPER | EA | 2 | 550 | 1100
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Northern Illinois Service |  | Stenstrom Excavation |  | Fischer Excavating |  | N-TRAK Group
City of Rockford | [5 empty] | Rockford, IL |  | Rockford, IL |  | Freeport, IL |  | Loves Park, IL
Welty Ave Watermain Replacement | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond
Bid No.:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 7500 | 7500 | 13400 | 13400 | 11610 | 11610 | 6650 | 6650 | 30000 | 30000 |  | 0 |  | 0
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 5000 | 5000 | 3000 | 3000 | 5000 | 5000 | 4475 | 4475 | 5000 | 5000 |  | 0 |  | 0
3 | INLET AND PIPE PROTECTION | EA | 10 | 250 | 2500 | 100 | 1000 | 100 | 1000 | 100 | 1000 | 75 | 750 |  | 0 |  | 0
4 | CONCRETE TRUCK WASHOUT | EA | 1 | 500 | 500 | 300 | 300 | 600 | 600 | 850 | 850 | 1 | 1 |  | 0 |  | 0
5 | PAVEMENT REMOVAL | SY | 1790 | 12.5 | 22375 | 5 | 8950 | 7.5 | 13425 | 6.5 | 11635 | 6 | 10740 |  | 0 |  | 0
6 | APPROACH PAVEMENT REMOVAL | SY | 65 | 12 | 780 | 5 | 325 | 23.5 | 1527.5 | 7.7 | 500.5 | 6 | 390 |  | 0 |  | 0
7 | SIDEWALK REMOVAL | SF | 3235 | 3 | 9705 | 1.5 | 4852.5 | 1.25 | 4043.75 | 2 | 6470 | 1 | 3235 |  | 0 |  | 0
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 1610 | 17.5 | 28175 | 4 | 6440 | 5.5 | 8855 | 3 | 4830 | 3 | 4830 |  | 0 |  | 0
9 | ROCK EXCAVATION | CY | 25 | 200 | 5000 | 50 | 1250 | 0.01 | 0.25 | 60 | 1500 | 1 | 25 |  | 0 |  | 0
10 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 1 | 950 | 950 | 400 | 400 | 1100 | 1100 | 120 | 120 | 500 | 500 |  | 0 |  | 0
11 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 3 | 1000 | 3000 | 600 | 1800 | 1450 | 4350 | 321 | 963 | 500 | 1500 |  | 0 |  | 0
12 | REMOVE FIRE HYDRANT, COMPLETE | EA | 4 | 1000 | 4000 | 700 | 2800 | 1390 | 5560 | 480 | 1920 | 750 | 3000 |  | 0 |  | 0
13 | PCC APPROACH PAVEMENT, 6" | SY | 50 | 150 | 7500 | 68.5 | 3425 | 77.5 | 3875 | 83 | 4150 | 65 | 3250 |  | 0 |  | 0
14 | PCC SIDEWALK, 4" | SF | 3235 | 10 | 32350 | 5.5 | 17792.5 | 7.1 | 22968.5 | 7.5 | 24262.5 | 6.5 | 21027.5 |  | 0 |  | 0
15 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18(MODIFIED) | LF | 1610 | 35 | 56350 | 25.75 | 41457.5 | 25.25 | 40652.5 | 34 | 54740 | 28.5 | 45885 |  | 0 |  | 0
16 | DETECTABLE WARNINGS | SF | 50 | 85 | 4250 | 25 | 1250 | 26 | 1300 | 28 | 1400 | 30 | 1500 |  | 0 |  | 0
17 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 1790 | 7.5 | 13425 | 5.5 | 9845 | 8 | 14320 | 6 | 10740 | 6 | 10740 |  | 0 |  | 0
18 | AGGREGATE BASE COURSE, TYPE B, 4" (CA-6) | SY | 30 | 7.5 | 225 | 5.5 | 165 | 21.9 | 657 | 6 | 180 | 30 | 900 |  | 0 |  | 0
19 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 1790 | 7.5 | 13425 | 5.5 | 9845 | 8 | 14320 | 6.9 | 12351 | 9 | 16110 |  | 0 |  | 0
20 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N50, 2" | TON | 200 | 100 | 20000 | 108 | 21600 | 105 | 21000 | 110 | 22000 | 140 | 28000 |  | 0 |  | 0
21 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 400 | 115 | 46000 | 103.7 | 41480 | 99.5 | 39800 | 140 | 56000 | 91 | 36400 |  | 0 |  | 0
22 | P.C.C. PAVEMENT, 9.5" (JOINTED) | SY | 30 | 200 | 6000 | 115.5 | 3465 | 116.75 | 3502.5 | 144 | 4320 | 78 | 2340 |  | 0 |  | 0
23 | HMA APPROACH PAVEMENT, 3" | SY | 15 | 50 | 750 | 103.8 | 1557 | 105 | 1575 | 73 | 1095 | 100 | 1500 |  | 0 |  | 0
24 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 20 | 125 | 2500 | 110 | 2200 | 225 | 4500 | 80 | 1600 | 100 | 2000 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 292260 |  | 198599.5 |  | 225542 |  | 233752 |  | 229623.5
| Award to Northern Illinois Service | Total |  | As corrected | 292260 |  | 198599.5 |  | 225542 |  | 233752 |  | 229623.5
25 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 1375 | 110 | 151250 | 100 | 137500 | 131.85 | 181293.75 | 92 | 126500 | 115 | 158125 |  | 0 |  | 0
26 | DUCTILE IRON WATER MAIN COMPLETE, 10" | LF | 45 | 140 | 6300 | 120 | 5400 | 167.65 | 7544.25 | 147 | 6615 | 118 | 5310 |  | 0 |  | 0
27 | MANHOLES, TYPE A, 5' DIAMETER, WITH SALVAGED FRAME AND LID | EA | 1 | 3500 | 3500 | 3000 | 3000 | 3580 | 3580 | 3137 | 3137 | 3000 | 3000 |  | 0 |  | 0
28 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 12" | LF | 60 | 90 | 5400 | 60 | 3600 | 143 | 8580 | 147 | 8820 | 90 | 5400 |  | 0 |  | 0
29 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 15" | LF | 20 | 95 | 1900 | 120 | 2400 | 166.5 | 3330 | 152 | 3040 | 100 | 2000 |  | 0 |  | 0
30 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 18" | LF | 25 | 100 | 2500 | 170 | 4250 | 191 | 4775 | 319 | 7975 | 155 | 3875 |  | 0 |  | 0
31 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 | 2000 | 2000 | 1500 | 1500 | 1500 | 1500 | 1380 | 1380 | 1700 | 1700 |  | 0 |  | 0
32 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 6 | 2500 | 15000 | 1900 | 11400 | 1900 | 11400 | 1658 | 9948 | 2200 | 13200 |  | 0 |  | 0
33 | GATE VALVE AND VALVE BOX, COMPLETE, 10" | EA | 1 | 3000 | 3000 | 2700 | 2700 | 2580 | 2580 | 2647 | 2647 | 2800 | 2800 |  | 0 |  | 0
34 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 4 | 6000 | 24000 | 5500 | 22000 | 5885 | 23540 | 5078 | 20312 | 5200 | 20800 |  | 0 |  | 0
35 | WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 42 | 2500 | 105000 | 2600 | 109200 | 2950 | 123900 | 2200 | 92400 | 3000 | 126000 |  | 0 |  | 0
36 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 2 | 4500 | 9000 | 2000 | 4000 | 1910 | 3820 | 2556 | 5112 | 2500 | 5000 |  | 0 |  | 0
37 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 3 | 5500 | 16500 | 2000 | 6000 | 1940 | 5820 | 2971 | 8913 | 2500 | 7500 |  | 0 |  | 0
38 | CONNECT TO EXISTING 10" WATER MAIN, COMPLETE | EA | 2 | 6500 | 13000 | 2000 | 4000 | 2020 | 4040 | 3256 | 6512 | 2500 | 5000 |  | 0 |  | 0
39 | WATER MAIN PROTECTION, 12" | LF | 50 | 50 | 2500 | 100 | 5000 | 48.5 | 2425 | 20 | 1000 | 50 | 2500 |  | 0 |  | 0
40 | WATER SERVICE PROTECTION, 2" | LF | 500 | 10 | 5000 | 10 | 5000 | 10 | 5000 | 12 | 6000 | 4 | 2000 |  | 0 |  | 0
41 | WATER MAIN LINE STOP, 6" | EA | 2 | 4500 | 9000 | 2600 | 5200 | 5000 | 10000 | 3715 | 7430 | 3500 | 7000 |  | 0 |  | 0
42 | WATER MAIN LINE STOP, 8" | EA | 2 | 4500 | 9000 | 3000 | 6000 | 5425 | 10850 | 4530 | 9060 | 4000 | 8000 |  | 0 |  | 0
43 | WATER MAIN LINE STOP,10" | EA | 2 | 5500 | 11000 | 6000 | 12000 | 6675 | 13350 | 6254 | 12508 | 5000 | 10000 |  | 0 |  | 0
44 | INSERTION VALVE, COMPLETE, 6" | EA | 1 | 4500 | 4500 | 5300 | 5300 | 6815 | 6815 | 6246 | 6246 | 5700 | 5700 |  | 0 |  | 0
45 | INSERTION VALVE, COMPLETE, 8" | EA | 1 | 6500 | 6500 | 5700 | 5700 | 7645 | 7645 | 7100 | 7100 | 6200 | 6200 |  | 0 |  | 0
46 | INSERTION VALVE, COMPLETE, 10" | EA | 1 | 8500 | 8500 | 8700 | 8700 | 10240 | 10240 | 11116 | 11116 | 9500 | 9500 |  | 0 |  | 0
47 | EXPLORATORY EXCAVATION | CY | 25 | 50 | 1250 | 50 | 1250 | 65 | 1625 | 18 | 450 | 45 | 1125 |  | 0 |  | 0
48 | TREE REMOVAL (6-15" UNITS DIAMETER) | UD | 15 | 50 | 750 | 15 | 225 | 15.75 | 236.25 | 15 | 225 | 15 | 225 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 708610 |  | 569924.5 |  | 679431.25 |  | 598198 |  | 641583.5
| Award to Northern Illinois Service | Total |  | As corrected | 708610 |  | 569924.5 |  | 679431.25 |  | 598198 |  | 641583.5
49 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UD | 220 | 60 | 13200 | 25 | 5500 | 26 | 5720 | 25 | 5500 | 25 | 5500 |  | 0 |  | 0
50 | PARKWAY RESTORATION | LS | 1 | 15000 | 15000 | 6400 | 6400 | 6645 | 6645 | 6400 | 6400 | 15000 | 15000 |  | 0 |  | 0
51 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 7500 | 7500 | 5000 | 5000 | 4100 | 4100 | 3950 | 3950 | 10000 | 10000 |  | 0 |  | 0
52 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 50 | 1250 | 1 | 25 | 1 | 25 | 84 | 2100 | 1 | 25 |  | 0 |  | 0
53 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 50 | 1250 | 1 | 25 | 1 | 25 | 94 | 2350 | 1 | 25 |  | 0 |  | 0
54 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | EA | 1 | 2000 | 2000 | 1 | 1 | 1 | 1 | 2000 | 2000 | 1 | 1 |  | 0 |  | 0
55 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 2000 | 2000 | 2000 | 2000 | 1200 | 1200 | 1250 | 1250 | 1250 | 1250 |  | 0 |  | 0
56 | KENTUCKY COFFEETREE / Gymnocladus Dioicus, 2.5" CALIPER | EA | 3 | 500 | 1500 | 550 | 1650 | 575 | 1725 | 550 | 1650 | 550 | 1650 |  | 0 |  | 0
57 | SUGAR MAPLE / Acer Saccharum, 2.5" CALIPER | EA | 3 | 600 | 1800 | 550 | 1650 | 575 | 1725 | 550 | 1650 | 550 | 1650 |  | 0 |  | 0
58 | EASTERN REDBUD / Cercis canadenis, 2" CALIPER | EA | 2 | 450 | 900 | 450 | 900 | 470 | 940 | 550 | 1100 | 450 | 900 |  | 0 |  | 0
59 | AUTUMN BRILLIANCE SERVICE BERRY / Amelanchier x grandiflora 'Autumn Brilliance', 2" CALIPER | EA | 2 | 550 | 1100 | 550 | 1100 | 575 | 1150 | 550 | 1100 | 550 | 1100 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 756110 |  | 594175.5 |  | 702687.25 |  | 627248 |  | 678684.5
| Award to Northern Illinois Service | Bid |  | As corrected | 756110 |  | 594175.5 |  | 702687.25 |  | 627248 |  | 678684.5
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to Northern Illinois Service | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Welty Ave Watermain Replacement
Item No. | Items | Units | Quantity | Unit Price | Total
1 | MOBILIZATION | LS | 1 |  | 0
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 |  | 0
3 | INLET AND PIPE PROTECTION | EA | 10 |  | 0
4 | CONCRETE TRUCK WASHOUT | EA | 1 |  | 0
5 | PAVEMENT REMOVAL | SY | 1790 |  | 0
6 | APPROACH PAVEMENT REMOVAL | SY | 65 |  | 0
7 | SIDEWALK REMOVAL | SF | 3235 |  | 0
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 1610 |  | 0
9 | ROCK EXCAVATION | CY | 25 |  | 0
10 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 1 |  | 0
11 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 3 |  | 0
12 | REMOVE FIRE HYDRANT, COMPLETE | EA | 4 |  | 0
13 | PCC APPROACH PAVEMENT, 6" | SY | 50 |  | 0
14 | PCC SIDEWALK, 4" | SF | 3235 |  | 0
15 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18(MODIFIED) | LF | 1610 |  | 0
16 | DETECTABLE WARNINGS | SF | 50 |  | 0
17 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 1790 |  | 0
18 | AGGREGATE BASE COURSE, TYPE B, 4" (CA-6) | SY | 30 |  | 0
19 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 1790 |  | 0
20 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N50, 2" | TON | 200 |  | 0
21 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 400 |  | 0
22 | P.C.C. PAVEMENT, 9.5" (JOINTED) | SY | 30 |  | 0
23 | HMA APPROACH PAVEMENT, 3" | SY | 15 |  | 0
24 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 20 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 1375 |  | 0
26 | DUCTILE IRON WATER MAIN COMPLETE, 10" | LF | 45 |  | 0
27 | MANHOLES, TYPE A, 5' DIAMETER, WITH SALVAGED FRAME AND LID | EA | 1 |  | 0
28 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 12" | LF | 60 |  | 0
29 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 15" | LF | 20 |  | 0
30 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 18" | LF | 25 |  | 0
31 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 |  | 0
32 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 6 |  | 0
33 | GATE VALVE AND VALVE BOX, COMPLETE, 10" | EA | 1 |  | 0
34 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 4 |  | 0
35 | WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 42 |  | 0
36 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 2 |  | 0
37 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 3 |  | 0
38 | CONNECT TO EXISTING 10" WATER MAIN, COMPLETE | EA | 2 |  | 0
39 | WATER MAIN PROTECTION, 12" | LF | 50 |  | 0
40 | WATER SERVICE PROTECTION, 2" | LF | 500 |  | 0
41 | WATER MAIN LINE STOP, 6" | EA | 2 |  | 0
42 | WATER MAIN LINE STOP, 8" | EA | 2 |  | 0
43 | WATER MAIN LINE STOP,10" | EA | 2 |  | 0
44 | INSERTION VALVE, COMPLETE, 6" | EA | 1 |  | 0
45 | INSERTION VALVE, COMPLETE, 8" | EA | 1 |  | 0
46 | INSERTION VALVE, COMPLETE, 10" | EA | 1 |  | 0
47 | EXPLORATORY EXCAVATION | CY | 25 |  | 0
48 | TREE REMOVAL (6-15" UNITS DIAMETER) | UD | 15 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UD | 220 |  | 0
50 | PARKWAY RESTORATION | LS | 1 |  | 0
51 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 |  | 0
52 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 |  | 0
53 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 |  | 0
54 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | EA | 1 |  | 0
55 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 |  | 0
56 | KENTUCKY COFFEETREE / Gymnocladus Dioicus, 2.5" CALIPER | EA | 3 |  | 0
57 | SUGAR MAPLE / Acer Saccharum, 2.5" CALIPER | EA | 3 |  | 0
58 | EASTERN REDBUD / Cercis canadenis, 2" CALIPER | EA | 2 |  | 0
59 | AUTUMN BRILLIANCE SERVICE BERRY / Amelanchier x grandiflora 'Autumn Brilliance', 2" CALIPER | EA | 2 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Welty Ave Watermain Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 7500 | 7500
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 5000 | 5000
3 | INLET AND PIPE PROTECTION | EA | 10 | 250 | 2500
4 | CONCRETE TRUCK WASHOUT | EA | 1 | 500 | 500
5 | PAVEMENT REMOVAL | SY | 1790 | 12.5 | 22375
6 | APPROACH PAVEMENT REMOVAL | SY | 65 | 12 | 780
7 | SIDEWALK REMOVAL | SF | 3235 | 3 | 9705
8 | COMBINATION CURB AND GUTTER REMOVAL | LF | 1610 | 17.5 | 28175
9 | ROCK EXCAVATION | CY | 25 | 200 | 5000
10 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 1 | 950 | 950
11 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 3 | 1000 | 3000
12 | REMOVE FIRE HYDRANT, COMPLETE | EA | 4 | 1000 | 4000
13 | PCC APPROACH PAVEMENT, 6" | SY | 50 | 150 | 7500
14 | PCC SIDEWALK, 4" | SF | 3235 | 10 | 32350
15 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18(MODIFIED) | LF | 1610 | 35 | 56350
16 | DETECTABLE WARNINGS | SF | 50 | 85 | 4250
17 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | SY | 1790 | 7.5 | 13425
18 | AGGREGATE BASE COURSE, TYPE B, 4" (CA-6) | SY | 30 | 7.5 | 225
19 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | SY | 1790 | 7.5 | 13425
20 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N50, 2" | TON | 200 | 100 | 20000
21 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 400 | 115 | 46000
22 | P.C.C. PAVEMENT, 9.5" (JOINTED) | SY | 30 | 200 | 6000
23 | HMA APPROACH PAVEMENT, 3" | SY | 15 | 50 | 750
24 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | LF | 20 | 125 | 2500
|  |  |  | Sub Total | 292260
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Welty Ave Watermain Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 1375 | 110 | 151250
26 | DUCTILE IRON WATER MAIN COMPLETE, 10" | LF | 45 | 140 | 6300
27 | MANHOLES, TYPE A, 5' DIAMETER, WITH SALVAGED FRAME AND LID | EA | 1 | 3500 | 3500
28 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 12" | LF | 60 | 90 | 5400
29 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 15" | LF | 20 | 95 | 1900
30 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 18" | LF | 25 | 100 | 2500
31 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | EA | 1 | 2000 | 2000
32 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 6 | 2500 | 15000
33 | GATE VALVE AND VALVE BOX, COMPLETE, 10" | EA | 1 | 3000 | 3000
34 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 4 | 6000 | 24000
35 | WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 42 | 2500 | 105000
36 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | EA | 2 | 4500 | 9000
37 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 3 | 5500 | 16500
38 | CONNECT TO EXISTING 10" WATER MAIN, COMPLETE | EA | 2 | 6500 | 13000
39 | WATER MAIN PROTECTION, 12" | LF | 50 | 50 | 2500
40 | WATER SERVICE PROTECTION, 2" | LF | 500 | 10 | 5000
41 | WATER MAIN LINE STOP, 6" | EA | 2 | 4500 | 9000
42 | WATER MAIN LINE STOP, 8" | EA | 2 | 4500 | 9000
43 | WATER MAIN LINE STOP,10" | EA | 2 | 5500 | 11000
44 | INSERTION VALVE, COMPLETE, 6" | EA | 1 | 4500 | 4500
45 | INSERTION VALVE, COMPLETE, 8" | EA | 1 | 6500 | 6500
46 | INSERTION VALVE, COMPLETE, 10" | EA | 1 | 8500 | 8500
47 | EXPLORATORY EXCAVATION | CY | 25 | 50 | 1250
48 | TREE REMOVAL (6-15" UNITS DIAMETER) | UD | 15 | 50 | 750
|  |  |  | Sub Total | 708610
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Welty Ave Watermain Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UD | 220 | 60 | 13200
50 | PARKWAY RESTORATION | LS | 1 | 15000 | 15000
51 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 7500 | 7500
52 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 50 | 1250
53 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 50 | 1250
54 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | EA | 1 | 2000 | 2000
55 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 2000 | 2000
56 | KENTUCKY COFFEETREE / Gymnocladus Dioicus, 2.5" CALIPER | EA | 3 | 500 | 1500
57 | SUGAR MAPLE / Acer Saccharum, 2.5" CALIPER | EA | 3 | 600 | 1800
58 | EASTERN REDBUD / Cercis canadenis, 2" CALIPER | EA | 2 | 450 | 900
59 | AUTUMN BRILLIANCE SERVICE BERRY / Amelanchier x grandiflora 'Autumn Brilliance', 2" CALIPER | EA | 2 | 550 | 1100
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 756110
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Welty Ave Watermain Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 756110
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Welty Ave Watermain Replacement
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | MOBILIZATION | 1 | LS | 13400 |  | 1 |  |  | 13400
2 | CONSTRUCTION LAYOUT STAKES | 1 | LS | 3000 |  | 1 |  |  | 3000
3 | INLET AND PIPE PROTECTION | 10 | EA | 1000 |  | 10 |  |  | 100
4 | CONCRETE TRUCK WASHOUT | 1 | EA | 300 |  | 1 |  |  | 300
5 | PAVEMENT REMOVAL | 1790 | SY | 8950 |  | 1790 |  |  | 5
6 | APPROACH PAVEMENT REMOVAL | 65 | SY | 325 |  | 65 |  |  | 5
7 | SIDEWALK REMOVAL | 3235 | SF | 4852.5 |  | 3235 |  |  | 1.5
8 | COMBINATION CURB AND GUTTER REMOVAL | 1610 | LF | 6440 |  | 1610 |  |  | 4
9 | ROCK EXCAVATION | 25 | CY | 1250 |  | 25 |  |  | 50
10 | REMOVE VALVE AND VALVE BOX, COMPLETE | 1 | EA | 400 |  | 1 |  |  | 400
11 | REMOVE VALVE AND VALVE VAULT, COMPLETE | 3 | EA | 1800 |  | 3 |  |  | 600
12 | REMOVE FIRE HYDRANT, COMPLETE | 4 | EA | 2800 |  | 4 |  |  | 700
13 | PCC APPROACH PAVEMENT, 6" | 50 | SY | 3425 |  | 50 |  |  | 68.5
14 | PCC SIDEWALK, 4" | 3235 | SF | 17792.5 |  | 3235 |  |  | 5.5
15 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18(MODIFIED) | 1610 | LF | 41457.5 |  | 1610 |  |  | 25.75
16 | DETECTABLE WARNINGS | 50 | SF | 1250 |  | 50 |  |  | 25
17 | SUBBASE GRANULAR MATERIAL, TYPE B, 6" (CA-2) | 1790 | SY | 9845 |  | 1790 |  |  | 5.5
18 | AGGREGATE BASE COURSE, TYPE B, 4" (CA-6) | 30 | SY | 165 |  | 30 |  |  | 5.5
19 | AGGREGATE BASE COURSE, TYPE B, 6" (CA-6) | 1790 | SY | 9845 |  | 1790 |  |  | 5.5
20 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N50, 2" | 200 | TON | 21600 |  | 200 |  |  | 108
21 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | 400 | TON | 41480 |  | 400 |  |  | 103.7
22 | P.C.C. PAVEMENT, 9.5" (JOINTED) | 30 | SY | 3465 |  | 30 |  |  | 115.5
23 | HMA APPROACH PAVEMENT, 3" | 15 | SY | 1557 |  | 15 |  |  | 103.8
24 | DUCTILE IRON WATER MAIN, COMPLETE, 6" | 20 | LF | 2200 |  | 20 |  |  | 110
Sub Total |  |  |  | 198599.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Welty Ave Watermain Replacement
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | DUCTILE IRON WATER MAIN COMPLETE, 8" | 1375 | LF | 137500 |  | 1375 |  |  | 100
26 | DUCTILE IRON WATER MAIN COMPLETE, 10" | 45 | LF | 5400 |  | 45 |  |  | 120
27 | MANHOLES, TYPE A, 5' DIAMETER, WITH SALVAGED FRAME AND LID | 1 | EA | 3000 |  | 1 |  |  | 3000
28 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 12" | 60 | LF | 3600 |  | 60 |  |  | 60
29 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 15" | 20 | LF | 2400 |  | 20 |  |  | 120
30 | STORM SEWER, WATER MAIN QUALITY, COMPLETE, 18" | 25 | LF | 4250 |  | 25 |  |  | 170
31 | GATE VALVE AND VALVE BOX, COMPLETE, 6" | 1 | EA | 1500 |  | 1 |  |  | 1500
32 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | 6 | EA | 11400 |  | 6 |  |  | 1900
33 | GATE VALVE AND VALVE BOX, COMPLETE, 10" | 1 | EA | 2700 |  | 1 |  |  | 2700
34 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | 4 | EA | 22000 |  | 4 |  |  | 5500
35 | WATER SERVICE (OPEN-CUT), COMPLETE, 1" | 42 | EA | 109200 |  | 42 |  |  | 2600
36 | CONNECT TO EXISTING 6" WATER MAIN, COMPLETE | 2 | EA | 4000 |  | 2 |  |  | 2000
37 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | 3 | EA | 6000 |  | 3 |  |  | 2000
38 | CONNECT TO EXISTING 10" WATER MAIN, COMPLETE | 2 | EA | 4000 |  | 2 |  |  | 2000
39 | WATER MAIN PROTECTION, 12" | 50 | LF | 5000 |  | 50 |  |  | 100
40 | WATER SERVICE PROTECTION, 2" | 500 | LF | 5000 |  | 500 |  |  | 10
41 | WATER MAIN LINE STOP, 6" | 2 | EA | 5200 |  | 2 |  |  | 2600
42 | WATER MAIN LINE STOP, 8" | 2 | EA | 6000 |  | 2 |  |  | 3000
43 | WATER MAIN LINE STOP,10" | 2 | EA | 12000 |  | 2 |  |  | 6000
44 | INSERTION VALVE, COMPLETE, 6" | 1 | EA | 5300 |  | 1 |  |  | 5300
45 | INSERTION VALVE, COMPLETE, 8" | 1 | EA | 5700 |  | 1 |  |  | 5700
46 | INSERTION VALVE, COMPLETE, 10" | 1 | EA | 8700 |  | 1 |  |  | 8700
47 | EXPLORATORY EXCAVATION | 25 | CY | 1250 |  | 25 |  |  | 50
48 | TREE REMOVAL (6-15" UNITS DIAMETER) | 15 | UD | 225 |  | 15 |  |  | 15
Sub Total |  |  |  | 569924.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Welty Ave Watermain Replacement
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | 220 | UD | 5500 |  | 220 |  |  | 25
50 | PARKWAY RESTORATION | 1 | LS | 6400 |  | 1 |  |  | 6400
51 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | 1 | LS | 5000 |  | 1 |  |  | 5000
52 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | 25 | CY | 25 |  | 25 |  |  | 1
53 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | 25 | CY | 25 |  | 25 |  |  | 1
54 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | 1 | EA | 1 |  | 1 |  |  | 1
55 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | 1 | EA | 2000 |  | 1 |  |  | 2000
56 | KENTUCKY COFFEETREE / Gymnocladus Dioicus, 2.5" CALIPER | 3 | EA | 1650 |  | 3 |  |  | 550
57 | SUGAR MAPLE / Acer Saccharum, 2.5" CALIPER | 3 | EA | 1650 |  | 3 |  |  | 550
58 | EASTERN REDBUD / Cercis canadenis, 2" CALIPER | 2 | EA | 900 |  | 2 |  |  | 450
59 | AUTUMN BRILLIANCE SERVICE BERRY / Amelanchier x grandiflora 'Autumn Brilliance', 2" CALIPER | 2 | EA | 1100 |  | 2 |  |  | 550
Total |  |  |  | 594175.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Welty Ave Watermain Replacement
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 594175.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Welty Ave Watermain Replacement
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Northern Illinois Service
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.