## Item List
| City -Wide Street Repairs Group No. 2 - 2023 (Residential) | [40 empty] | 2390209
Summary Of Quantities |  |  | 5th Ward | 6th Ward |  |  | 7th Ward |  |  |  | 7th Ward |  |  |  | 7th Ward | 9th Ward |  |  | 10th Ward |  |  |  | 10th Ward |  |  |  | 10th Ward |  | 12th Ward |  | 12th Ward |  |  | 13th Ward | 13th Ward |  |  | Neighborhood
No. | Item | Units | 2400/2600 Forsythia Drive | 2800 18th Street | 2800 Bildahl Street | 1900/2000 3400/3500 Jamestown Drive | 2100/2400 Arthur Avenue Patching | 2000 Ashland Avenue | 3200/3300 Blackstone Avenue | 3400 Garfield Drive Patching | 0500/0700 John Street | 2800 Kenmore Avenue | 0600 Napoleon Street | 2500/2600 Prial Avenue Patching | 2400/2500 Rockwell Street | 1300/1400 Quincy Street | 3200/3300 Sablewood Drive | 1300 Wagner Avenue | 2700 12th Avenue Patching | 2600/2700 Brighton Road | 3800 Hemlock Court | 0200/0300 Kenilworth Drive | 0400/0500 Laurel Drive Patching | 0300 Ridgeview Avenue | 0200/0300 Rockcliff Drive | 1200 Shenandoah Avenue | 0500 Skylark Drive Patching | 0400 Westchester Drive | 1200 Belmont Boulevard | 1500 Belmont Boulevard | 3400/3500 Fremont Street | 3200 Latham Street | 4100/4400 Marsh Avenue | 1700 Elm Street | 2000/2400 Elm Steet | 3500 Elm Street | 2800/3000 Mulberry Street | 6600/6900 Garret Lane | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. | [29 empty] | 40 | [6 empty] | 100 | 140 | 30 | 4200
2 | Parkway Restoration | Lsum | 0.08 | 0 | 0.03 | 0.05 | 0 | 0.01 | 0.06 | 0.02 | 0.04 | 0.04 | 0.03 | 0 | 0 | 0.05 | 0.05 | 0.03 | 0 | 0.03 | 0.03 | 0.05 | 0.03 | 0 | 0 | 0 | 0.02 | 0 | 0.04 | 0.03 | 0.02 | 0.05 | 0.02 | 0 | 0.08 | 0 | 0.06 | 0.05 |  | 1 | 60000 | 60000
3 | Inlet and Pipe Protection | Each | 11 |  | 4 | 12 |  |  | 4 | 1 | 9 | 2 |  |  |  | 5 | 6 | 2 |  | 3 | 2 | 5 | 4 |  | 1 | 2 | 1 |  |  |  | 2 | 5 | 7 |  | 13 |  |  | 9 |  | 110 | 75 | 8250
4 | Aggregate Base Repair, 10" | S.Y. | 44 | 21 | 18 | 75 | 12 | 7 | 25 | 11 | 36 | 9 | 15 | 11 | 26 | 19 | 22 | 8 | 7 | 14 | 12 | 29 | 20 | 15 | 23 | 23 | 10 | 25 | 8 | 7 | 33 | 13 | 55 | 10 | 65 | 20 | 32 | 90 |  | 870 | 20 | 17400
5 | Bituminous Materials (Prime Coat) | Gal | 440 | 210 | 180 | 750 | 127 | 75 | 250 | 115 | 365 | 95 | 155 | 115 | 260 | 190 | 222 | 87 | 75 | 140 | 120 | 295 | 200 | 150 | 230 | 230 | 100 | 250 | 85 | 70 | 330 | 135 | 550 | 100 | 655 | 200 | 320 | 905 |  | 8776 | 3 | 26328
6 | Aggregate (Prime Coat) | Tons | 44 | 21 | 18 | 75 | 12 | 7 | 25 | 11 | 36 | 9 | 15 | 11 | 26 | 19 | 22 | 8 | 7 | 14 | 12 | 29 | 20 | 15 | 23 | 23 | 10 | 25 | 8 | 7 | 33 | 13 | 55 | 10 | 65 | 20 | 32 | 90 |  | 870 | 10 | 8700
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | [36 empty] | 500 | 500 | 80 | 40000
8 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | [35 empty] | 650 |  | 650 | 80 | 52000
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 525 | 250 | 225 | 900 | 175 | 100 | 300 | 150 | 450 | 125 | 200 | 150 | 325 | 225 | 275 | 125 | 100 | 175 | 175 | 350 | 250 | 175 | 275 | 275 | 125 | 300 | 100 | 100 | 400 | 175 | 675 | 125 | 800 | 250 | 400 | 1100 | 500 | 11325 | 80 | 906000
10 | Hot-Mix Asphalt, Hand Method | Tons | [30 empty] | 20 | [5 empty] | 10 | 30 | 300 | 9000
11 | P.C.C. Approach Pavement, 6" | S.Y. | 73 |  | 90 | 707 | [10 empty] | 121 | 32 |  | 80 | 62 | 24 | [6 empty] | 12 | 17 | 28 |  |  |  | 54 |  |  |  | 25 | 1325 | 65 | 86125
12 | P.C.C. Approach Pavement, 8" | S.Y. | [32 empty] | 126 |  |  |  | 25 | 151 | 80 | 12080
13 | P.C.C. Sidewalk, 4" | S.F. | 4850 |  | 875 | 1975 |  |  | 3250 | 400 | 1000 | 1450 | 575 |  |  | 1600 | 1825 | 650 |  | 725 |  | 1875 | 600 |  |  |  | 450 |  | 1050 | 700 | 475 | 2175 |  |  | 4100 |  | 2675 | 2000 | 1000 | 36275 | 6 | 217650
14 | Detectable Warnings, ADA Ramps | S.F. | 60 |  |  | 40 |  |  |  | 20 | 120 |  |  |  |  | 120 | 60 |  |  | 20 |  | 20 | 10 |  |  |  | 20 |  |  |  |  | 40 |  |  | 160 |  | 160 | 90 |  | 940 | 30 | 28200
15 | Combination Curb and Gutter Removal | L.F. | 255 |  | 155 | 1140 |  | 10 |  | 60 | 180 | 60 |  |  |  | 145 | 435 | 65 |  | 300 | 130 | 90 | 140 |  |  |  | 20 |  | 30 | 55 | 90 | 115 | 375 |  | 480 |  | 260 | 225 | 500 | 5315 | 15 | 79725
16 | Sidewalk Removal | S.F. | 5000 |  | 875 | 1975 |  |  | 3250 | 500 | 1000 | 1450 | 575 |  |  | 1600 | 1975 | 650 |  | 825 |  | 1975 | 650 |  |  |  | 450 |  | 1050 | 700 | 475 | 250 |  |  | 4100 |  | 2675 | 2000 | 1000 | 35000 | 2 | 70000
17 | Approach Pavement Removal | S.Y. | 73 |  | 90 | 707 | [10 empty] | 121 | 32 |  | 80 | 62 | 24 | [6 empty] | 12 | 17 | 28 |  |  |  | 188 |  |  |  | 50 | 1484 | 25 | 37100
18 | Surface Removal, 2" | S.Y. | 4400 | 2100 | 1800 | 7500 | 1275 | 775 | 2500 | 1150 | 3650 | 950 | 1550 | 1150 | 2600 | 1900 | 2225 | 875 | 750 | 1400 | 1200 | 2950 | 2000 | 1500 | 2300 | 2300 | 1000 | 2500 | 850 | 700 | 3300 | 1350 | 5500 | 1000 | 6550 | 2000 | 3200 | 4800 | 1000 | 84550 | 3 | 253650
19 | Surface Removal, 4.5" | S.Y. | [35 empty] | 4250 |  | 4250 | 5 | 21250
20 | Surface Removal, Butt Joints | S.Y. | [36 empty] | 100 | 100 | 7 | 700
21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [19 empty] | 1 | [5 empty] | 1 | [6 empty] | 1 |  |  |  |  | 3 | 500 | 1500
22 | Manholes to be Adjusted | Each | 6 | 1 | 2 | 4 | 1 |  | 4 | 1 | 5 | 3 | 2 | 2 | 4 | 2 | 5 | 1 |  | 2 | 1 | 5 | 3 | 1 | 5 | 3 |  | 5 | 1 |  |  | 1 | 11 | 1 | 8 | 1 | 4 | 9 |  | 104 | 650 | 67600
23 | Manholes to be Adjusted with New Frame and Lid | Each | 3 |  |  | 1 |  |  |  |  | 2 |  | 1 |  | 2 | 1 | 2 | [7 empty] | 1 | 1 | 1 | 1 |  |  |  | 2 | 1 |  |  |  |  | 1 |  | 20 | 1000 | 20000
24 | Manholes to be Reconstructed | Each | [36 empty] | 1 | 1 | 1200 | 1200
25 | Manholes to be Reconstructed with New Frame and Lid | Each | [36 empty] | 1 | 1 | 1600 | 1600
26 | Inlets to be Adjusted | Each |  |  |  | 8 |  |  |  |  | 3 |  |  |  | 1 | 2 | 1 | [7 empty] | 1 | [9 empty] | 3 |  |  |  |  | 19 | 1100 | 20900
27 | Inlets to be Adjusted with New Frame and Grate | Each | 1 |  | 2 | 3 | [8 empty] | 1 |  | 1 |  |  |  | 2 | 3 | 2 |  |  | 2 | [5 empty] | 2 |  |  | 2 |  |  |  |  | 21 | 1600 | 33600
28 | Inlets to be Reconstructed | Each | [36 empty] | 1 | 1 | 1500 | 1500
29 | Inlets to be Reconstructed with New Frame and Grate | Each | [15 empty] | 2 | [20 empty] | 1 | 3 | 1800 | 5400
30 | Inlet Specials to be Repaired | Each | [36 empty] | 1 | 1 | 2200 | 2200
31 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 255 |  | 155 | 1140 |  | 10 |  | 60 | 180 | 60 |  |  |  | 145 | 435 | 65 |  | 300 | 130 | 90 | 140 |  |  |  | 20 |  | 30 | 55 | 90 | 115 | 375 |  | 480 |  | 260 | 225 | 500 | 5315 | 40 | 212600
32 | Traffic Control and Protection | Lsum | 0.06 | 0.01 | 0.03 | 0.12 | 0.01 | 0.01 | 0.03 | 0.01 | 0.04 | 0.01 | 0.01 | 0.01 | 0.02 | 0.03 | 0.04 | 0.01 | 0.01 | 0.02 | 0.02 | 0.03 | 0.02 | 0.01 | 0.02 | 0.02 | 0.01 | 0.02 | 0.02 | 0.01 | 0.03 | 0.02 | 0.05 | 0.01 | 0.08 | 0.01 | 0.04 | 0.1 |  | 1 | 75000 | 75000
33 | Thermoplastic Pavement Markings, 4" | L.F. | [31 empty] | 70 | 370 |  |  |  |  | 440 | 2 | 880
34 | Thermoplastic Pavement Markings, 6" | L.F. | [14 empty] | 79 | [20 empty] | 100 |  | 179 | 3 | 537
35 | Thermoplastic Pavement Markings, 12" | L.F. | [35 empty] | 162 |  | 162 | 4 | 648
36 | Thermoplastic Pavement Markings, 24" | L.F. | [14 empty] | 13 | [20 empty] | 18 |  | 31 | 6 | 186
37 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | [36 empty] | 50 | 50 | 10 | 500
38 | Detector Loops | L.F. | [36 empty] | 200 | 200 | 30 | 6000
39
40
41
42 | [40 empty] | 0
43 | [40 empty] | 0
44 | [40 empty] | 0
45 | [40 empty] | 0
46 | [40 empty] | 0
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 137960 | 28960 | 56955 | 272430 | 19966 | 12660 | 67750 | 26100 | 85250 | 33555 | 31015 | 18175 | 44160 | 59340 | 96231 | 31731 | 11435 | 54165 | 38350 | 75690 | 48850 | 20800 | 37205 | 38080 | 21925 | 39250 | 26725 | 23225 | 58750 | 51845 | 114050 | 15140 | 194570 | 28600 | 93220 | 231221 | 144875 | #VALUE!
|  |  | 8260.9981 | 1775.8294 | 4313.169 | 17280.4234 | 1558.4753 | 1025.1099 | 4354.79 | 1664.8401 | 5606.5031 | 2145.7939 | 1925.3567 | 1045.1496 | 2791.6902 | 3810.634 | 5947.1787 | 1909.9415 | 704.474 | 3397.507 | 2139.6278 | 4362.4976 | 2887.2643 | 1567.7244 | 2290.6966 | 2392.4368 | 1233.2149 | 2435.5994 | 2861.0585 | 1586.2226 | 4421.0753 | 3543.9512 | 7874.077 | 1353.4533 | 12142.5419 | 1800.4937 | 5050.0149 | 15415.1859 |  | 2390209
|  |  | 146220.9981 | 30735.8294 | 61268.169 | 289710.4234 | 21524.4753 | 13685.1099 | 72104.79 | 27764.8401 | 90856.5031 | 35700.7939 | 32940.3567 | 19220.1496 | 46951.6902 | 63150.634 | 102178.1787 | 33640.9415 | 12139.474 | 57562.507 | 40489.6278 | 80052.4976 | 51737.2643 | 22367.7244 | 39495.6966 | 40472.4368 | 23158.2149 | 41685.5994 | 29586.0585 | 24811.2226 | 63171.0753 | 55388.9512 | 121924.077 | 16493.4533 | 206712.5419 | 30400.4937 | 98270.0149 | 246636.1859 |  | 2390209
|  |  | 133975 | 28800 | 69950 | 280250 | 25275 | 16625 | 70625 | 27000 | 90925 | 34800 | 31225 | 16950 | 45275 | 61800 | 96450 | 30975 | 11425 | 55100 | 34700 | 70750 | 46825 | 25425 | 37150 | 38800 | 20000 | 39500 | 46400 | 25725 | 71700 | 57475 | 127700 | 21950 | 196925 | 29200 | 81900 | 250000 | 0 | 2349550
#REF!
|  |  | 0.057022 | 0.012258 | 0.029772 | 0.11928 | 0.010757 | 0.0070758 | 0.030059 | 0.011492 | 0.038699 | 0.014811 | 0.01329 | 0.0072141 | 0.01927 | 0.026303 | 0.04105 | 0.013183 | 0.0048626 | 0.023451 | 0.014769 | 0.030112 | 0.019929 | 0.010821 | 0.015812 | 0.016514 | 0.0085123 | 0.016812 | 0.019748 | 0.010949 | 0.030516 | 0.024462 | 0.054351 | 0.0093422 | 0.083814 | 0.012428 | 0.034858 | 0.1064 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | ROCK ROAD CO. |  | CURRAN CONTRACTING | [7 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | JANESVILLE, WI |  | CRYSTAL LAKE, IL | [7 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 2 - 2023 (Residential) | [5 empty] | BID BOND |  | BID BOND | [7 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 423-PW-042 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 140 | 30 | 4200 | 73 | 10220 | 60 | 8400 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 140 | 30 | 4200 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 140 | 30 | 4200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 60000 | 60000 | 30300 | 30300 | 50000 | 50000 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 60000 | 60000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 60000 | 60000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 110 | 75 | 8250 | 59 | 6490 | 75 | 8250 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 110 | 75 | 8250 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 110 | 75 | 8250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Aggregate Base Repair, 10" | S.Y. | 870 | 20 | 17400 | 0.01 | 8.7 | 14 | 12180 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Repair, 10" | S.Y. | 870 | 20 | 17400 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Repair, 10" | S.Y. | 870 | 20 | 17400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Bituminous Materials (Prime Coat) | Gal | 8776 | 3 | 26328 | 0.01 | 87.76 | 2.5 | 21940 |  | 0 |  | 0 |  | 0 | 5 | Bituminous Materials (Prime Coat) | Gal | 8776 | 3 | 26328 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Bituminous Materials (Prime Coat) | Gal | 8776 | 3 | 26328 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Aggregate (Prime Coat) | Tons | 870 | 10 | 8700 | 0.01 | 8.7 | 0.01 | 8.7 |  | 0 |  | 0 |  | 0 | 6 | Aggregate (Prime Coat) | Tons | 870 | 10 | 8700 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate (Prime Coat) | Tons | 870 | 10 | 8700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000 | 76 | 38000 | 88 | 44000 |  | 0 |  | 0 |  | 0 | 7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 650 | 80 | 52000 | 76 | 49400 | 73 | 47450 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 650 | 80 | 52000 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 650 | 80 | 52000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 11325 | 80 | 906000 | 79.25 | 897506.25 | 76 | 860700 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 11325 | 80 | 906000 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 11325 | 80 | 906000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt, Hand Method | Tons | 30 | 300 | 9000 | 80 | 2400 | 250 | 7500 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt, Hand Method | Tons | 30 | 300 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt, Hand Method | Tons | 30 | 300 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | P.C.C. Approach Pavement, 6" | S.Y. | 1325 | 65 | 86125 | 94 | 124550 | 75 | 99375 |  | 0 |  | 0 |  | 0 | 11 | P.C.C. Approach Pavement, 6" | S.Y. | 1325 | 65 | 86125 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | P.C.C. Approach Pavement, 6" | S.Y. | 1325 | 65 | 86125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | P.C.C. Approach Pavement, 8" | S.Y. | 151 | 80 | 12080 | 108 | 16308 | 85 | 12835 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 8" | S.Y. | 151 | 80 | 12080 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 8" | S.Y. | 151 | 80 | 12080 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | P.C.C. Sidewalk, 4" | S.F. | 36275 | 6 | 217650 | 6.7 | 243042.5 | 8 | 290200 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Sidewalk, 4" | S.F. | 36275 | 6 | 217650 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Sidewalk, 4" | S.F. | 36275 | 6 | 217650 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | Detectable Warnings, ADA Ramps | S.F. | 940 | 30 | 28200 | 30 | 28200 | 29 | 27260 |  | 0 |  | 0 |  | 0 | 14 | Detectable Warnings, ADA Ramps | S.F. | 940 | 30 | 28200 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | Detectable Warnings, ADA Ramps | S.F. | 940 | 30 | 28200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Combination Curb and Gutter Removal | L.F. | 5315 | 15 | 79725 | 10.8 | 57402 | 10 | 53150 |  | 0 |  | 0 |  | 0 | 15 | Combination Curb and Gutter Removal | L.F. | 5315 | 15 | 79725 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Combination Curb and Gutter Removal | L.F. | 5315 | 15 | 79725 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Sidewalk Removal | S.F. | 35000 | 2 | 70000 | 1.5 | 52500 | 2.5 | 87500 |  | 0 |  | 0 |  | 0 | 16 | Sidewalk Removal | S.F. | 35000 | 2 | 70000 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Sidewalk Removal | S.F. | 35000 | 2 | 70000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Approach Pavement Removal | S.Y. | 1484 | 25 | 37100 | 15.7 | 23298.8 | 26 | 38584 |  | 0 |  | 0 |  | 0 | 17 | Approach Pavement Removal | S.Y. | 1484 | 25 | 37100 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Approach Pavement Removal | S.Y. | 1484 | 25 | 37100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Surface Removal, 2" | S.Y. | 84550 | 3 | 253650 | 2.6 | 219830 | 3 | 253650 |  | 0 |  | 0 |  | 0 | 18 | Surface Removal, 2" | S.Y. | 84550 | 3 | 253650 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Surface Removal, 2" | S.Y. | 84550 | 3 | 253650 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Surface Removal, 4.5" | S.Y. | 4250 | 5 | 21250 | 4.58 | 19465 | 4.25 | 18062.5 |  | 0 |  | 0 |  | 0 | 19 | Surface Removal, 4.5" | S.Y. | 4250 | 5 | 21250 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Surface Removal, 4.5" | S.Y. | 4250 | 5 | 21250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Surface Removal, Butt Joints | S.Y. | 100 | 7 | 700 | 10.58 | 1058 | 9.05 | 905 |  | 0 |  | 0 |  | 0 | 20 | Surface Removal, Butt Joints | S.Y. | 100 | 7 | 700 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Surface Removal, Butt Joints | S.Y. | 100 | 7 | 700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 3 | 500 | 1500 | 252 | 756 | 500 | 1500 |  | 0 |  | 0 |  | 0 | 21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 3 | 500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 3 | 500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Manholes to be Adjusted | Each | 104 | 650 | 67600 | 584 | 60736 | 800 | 83200 |  | 0 |  | 0 |  | 0 | 22 | Manholes to be Adjusted | Each | 104 | 650 | 67600 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Manholes to be Adjusted | Each | 104 | 650 | 67600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Manholes to be Adjusted with New Frame and Lid | Each | 20 | 1000 | 20000 | 1262 | 25240 | 1200 | 24000 |  | 0 |  | 0 |  | 0 | 23 | Manholes to be Adjusted with New Frame and Lid | Each | 20 | 1000 | 20000 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Manholes to be Adjusted with New Frame and Lid | Each | 20 | 1000 | 20000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Manholes to be Reconstructed | Each | 1 | 1200 | 1200 | 1606 | 1606 | 1400 | 1400 |  | 0 |  | 0 |  | 0 | 24 | Manholes to be Reconstructed | Each | 1 | 1200 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Manholes to be Reconstructed | Each | 1 | 1200 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 2028658 |  | 1908413.71 |  | 2052050.2 | [7 empty] | Page 3 | Sub |  | As read | 2028658 | [9 empty] | Page 1 | Sub |  | As read | 2028658
| Award to ROCK ROAD CO. | Total |  | As corrected | 2028658 |  | 1908413.71 |  | 2052050.2 | [7 empty] | Award to ROCK ROAD CO. | Total |  | As corrected | 2028658 | [9 empty] | Award to ROCK ROAD CO. | Total |  | As corrected | 2028658
25 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600 | 2205 | 2205 | 1800 | 1800 |  | 0 |  | 0 |  | 0 | 25 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Inlets to be Adjusted | Each | 19 | 1100 | 20900 | 1150 | 21850 | 1100 | 20900 |  | 0 |  | 0 |  | 0 | 26 | Inlets to be Adjusted | Each | 19 | 1100 | 20900 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Inlets to be Adjusted | Each | 19 | 1100 | 20900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Inlets to be Adjusted with New Frame and Grate | Each | 21 | 1600 | 33600 | 1640 | 34440 | 1800 | 37800 |  | 0 |  | 0 |  | 0 | 27 | Inlets to be Adjusted with New Frame and Grate | Each | 21 | 1600 | 33600 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Inlets to be Adjusted with New Frame and Grate | Each | 21 | 1600 | 33600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 | 1840 | 1840 | 1800 | 1800 |  | 0 |  | 0 |  | 0 | 28 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Inlets to be Reconstructed with New Frame and Grate | Each | 3 | 1800 | 5400 | 2240 | 6720 | 2200 | 6600 |  | 0 |  | 0 |  | 0 | 29 | Inlets to be Reconstructed with New Frame and Grate | Each | 3 | 1800 | 5400 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Inlets to be Reconstructed with New Frame and Grate | Each | 3 | 1800 | 5400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Inlet Specials to be Repaired | Each | 1 | 2200 | 2200 | 2000 | 2000 | 2000 | 2000 |  | 0 |  | 0 |  | 0 | 30 | Inlet Specials to be Repaired | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Inlet Specials to be Repaired | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 5315 | 40 | 212600 | 43.5 | 231202.5 | 40 | 212600 |  | 0 |  | 0 |  | 0 | 31 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 5315 | 40 | 212600 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 5315 | 40 | 212600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Traffic Control and Protection | Lsum | 1 | 75000 | 75000 | 71395.17 | 71395.17 | 100000 | 100000 |  | 0 |  | 0 |  | 0 | 32 | Traffic Control and Protection | Lsum | 1 | 75000 | 75000 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Traffic Control and Protection | Lsum | 1 | 75000 | 75000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Thermoplastic Pavement Markings, 4" | L.F. | 440 | 2 | 880 | 2.6 | 1144 | 2.6 | 1144 |  | 0 |  | 0 |  | 0 | 33 | Thermoplastic Pavement Markings, 4" | L.F. | 440 | 2 | 880 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Thermoplastic Pavement Markings, 4" | L.F. | 440 | 2 | 880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | Thermoplastic Pavement Markings, 6" | L.F. | 179 | 3 | 537 | 3.9 | 698.1 | 3.9 | 698.1 |  | 0 |  | 0 |  | 0 | 34 | Thermoplastic Pavement Markings, 6" | L.F. | 179 | 3 | 537 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Thermoplastic Pavement Markings, 6" | L.F. | 179 | 3 | 537 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | Thermoplastic Pavement Markings, 12" | L.F. | 162 | 4 | 648 | 7.8 | 1263.6 | 7.8 | 1263.6 |  | 0 |  | 0 |  | 0 | 35 | Thermoplastic Pavement Markings, 12" | L.F. | 162 | 4 | 648 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Thermoplastic Pavement Markings, 12" | L.F. | 162 | 4 | 648 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | Thermoplastic Pavement Markings, 24" | L.F. | 31 | 6 | 186 | 15.6 | 483.6 | 15.6 | 483.6 |  | 0 |  | 0 |  | 0 | 36 | Thermoplastic Pavement Markings, 24" | L.F. | 31 | 6 | 186 |  | 0 |  | 0 |  | 0 |  | 0 | 36 | Thermoplastic Pavement Markings, 24" | L.F. | 31 | 6 | 186 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 50 | 10 | 500 | 15.6 | 780 | 15.6 | 780 |  | 0 |  | 0 |  | 0 | 37 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 50 | 10 | 500 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 50 | 10 | 500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | Detector Loops | L.F. | 200 | 30 | 6000 | 35.75 | 7150 | 35.75 | 7150 |  | 0 |  | 0 |  | 0 | 38 | Detector Loops | L.F. | 200 | 30 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 38 | Detector Loops | L.F. | 200 | 30 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 2390209 |  | 2291585.68 |  | 2447069.5 | [7 empty] | Page 4 | Total |  | As read | 2390209 | [9 empty] | Page 2 | Total |  | As read | 2390209
| Award to ROCK ROAD CO. | Bid |  | As corrected |  |  | 2291585.68 | 0 | 2447069.5 | 0 | [6 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected | #VALUE! | [9 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to ROCK ROAD CO. | Bid |  | As corrected | [12 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected | [10 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to ROCK ROAD CO. | Bid |  | As corrected | [12 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected | [10 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 2 - 2023 (Residential)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 140 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 110 |  | 0
4 | Aggregate Base Repair, 10" | S.Y. | 870 |  | 0
5 | Bituminous Materials (Prime Coat) | Gal | 8776 |  | 0
6 | Aggregate (Prime Coat) | Tons | 870 |  | 0
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 650 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 11325 |  | 0
10 | Hot-Mix Asphalt, Hand Method | Tons | 30 |  | 0
11 | P.C.C. Approach Pavement, 6" | S.Y. | 1325 |  | 0
12 | P.C.C. Approach Pavement, 8" | S.Y. | 151 |  | 0
13 | P.C.C. Sidewalk, 4" | S.F. | 36275 |  | 0
14 | Detectable Warnings, ADA Ramps | S.F. | 940 |  | 0
15 | Combination Curb and Gutter Removal | L.F. | 5315 |  | 0
16 | Sidewalk Removal | S.F. | 35000 |  | 0
17 | Approach Pavement Removal | S.Y. | 1484 |  | 0
18 | Surface Removal, 2" | S.Y. | 84550 |  | 0
19 | Surface Removal, 4.5" | S.Y. | 4250 |  | 0
20 | Surface Removal, Butt Joints | S.Y. | 100 |  | 0
21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 3 |  | 0
22 | Manholes to be Adjusted | Each | 104 |  | 0
23 | Manholes to be Adjusted with New Frame and Lid | Each | 20 |  | 0
24 | Manholes to be Reconstructed | Each | 1 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 |  | 0
26 | Inlets to be Adjusted | Each | 19 |  | 0
27 | Inlets to be Adjusted with New Frame and Grate | Each | 21 |  | 0
28 | Inlets to be Reconstructed | Each | 1 |  | 0
29 | Inlets to be Reconstructed with New Frame and Grate | Each | 3 |  | 0
30 | Inlet Specials to be Repaired | Each | 1 |  | 0
31 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 5315 |  | 0
32 | Traffic Control and Protection | Lsum | 1 |  | 0
33 | Thermoplastic Pavement Markings, 4" | L.F. | 440 |  | 0
34 | Thermoplastic Pavement Markings, 6" | L.F. | 179 |  | 0
35 | Thermoplastic Pavement Markings, 12" | L.F. | 162
36 | Thermoplastic Pavement Markings, 24" | L.F. | 31
37 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 50
38 | Detector Loops | L.F. | 200
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 140 | 30 | 4200
2 | Parkway Restoration | Lsum | 1 | 60000 | 60000
3 | Inlet and Pipe Protection | Each | 110 | 75 | 8250
4 | Aggregate Base Repair, 10" | S.Y. | 870 | 20 | 17400
5 | Bituminous Materials (Prime Coat) | Gal | 8776 | 3 | 26328
6 | Aggregate (Prime Coat) | Tons | 870 | 10 | 8700
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000
8 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | Tons | 650 | 80 | 52000
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 11325 | 80 | 906000
10 | Hot-Mix Asphalt, Hand Method | Tons | 30 | 300 | 9000
11 | P.C.C. Approach Pavement, 6" | S.Y. | 1325 | 65 | 86125
12 | P.C.C. Approach Pavement, 8" | S.Y. | 151 | 80 | 12080
13 | P.C.C. Sidewalk, 4" | S.F. | 36275 | 6 | 217650
14 | Detectable Warnings, ADA Ramps | S.F. | 940 | 30 | 28200
15 | Combination Curb and Gutter Removal | L.F. | 5315 | 15 | 79725
16 | Sidewalk Removal | S.F. | 35000 | 2 | 70000
17 | Approach Pavement Removal | S.Y. | 1484 | 25 | 37100
18 | Surface Removal, 2" | S.Y. | 84550 | 3 | 253650
19 | Surface Removal, 4.5" | S.Y. | 4250 | 5 | 21250
20 | Surface Removal, Butt Joints | S.Y. | 100 | 7 | 700
21 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 3 | 500 | 1500
22 | Manholes to be Adjusted | Each | 104 | 650 | 67600
23 | Manholes to be Adjusted with New Frame and Lid | Each | 20 | 1000 | 20000
24 | Manholes to be Reconstructed | Each | 1 | 1200 | 1200
|  |  |  | Sub Total | 2028658
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600
26 | Inlets to be Adjusted | Each | 19 | 1100 | 20900
27 | Inlets to be Adjusted with New Frame and Grate | Each | 21 | 1600 | 33600
28 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500
29 | Inlets to be Reconstructed with New Frame and Grate | Each | 3 | 1800 | 5400
30 | Inlet Specials to be Repaired | Each | 1 | 2200 | 2200
31 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 5315 | 40 | 212600
32 | Traffic Control and Protection | Lsum | 1 | 75000 | 75000
33 | Thermoplastic Pavement Markings, 4" | L.F. | 440 | 2 | 880
34 | Thermoplastic Pavement Markings, 6" | L.F. | 179 | 3 | 537
35 | Thermoplastic Pavement Markings, 12" | L.F. | 162 | 4 | 648
36 | Thermoplastic Pavement Markings, 24" | L.F. | 31 | 6 | 186
37 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 50 | 10 | 500
38 | Detector Loops | L.F. | 200 | 30 | 6000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 2 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: ROCK ROAD CO. | P.O. # 19305222 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: JANESVILLE, WI BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 140 | C.Y. | 10220 |  |  |  |  | 73
2 | Parkway Restoration | 1 | Lsum | 30300 |  |  |  |  | 30300
3 | Inlet and Pipe Protection | 110 | Each | 6490 |  |  | 35 | Each | 59 | 2065
4 | Aggregate Base Repair, 10" | 870 | S.Y. | 8.7 |  |  |  |  | 0.01
5 | Bituminous Materials (Prime Coat) | 8776 | Gal | 87.76 |  |  |  |  | 0.01
6 | Aggregate (Prime Coat) | 870 | Tons | 8.7 |  |  |  |  | 0.01
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | 500 | Tons | 38000 |  |  |  |  | 76
8 | Hot-Mix Asphalt Binder Course, IL-19.0, N50, 2.5" | 650 | Tons | 49400 |  |  |  |  | 76
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 11325 | Tons | 897506.25 |  |  |  |  | 79.25
10 | Hot-Mix Asphalt, Hand Method | 30 | Tons | 2400 | 1370 |  | 1400 | Tons | 80 | 112000
11 | P.C.C. Approach Pavement, 6" | 1325 | S.Y. | 124550 |  |  |  |  | 94
12 | P.C.C. Approach Pavement, 8" | 151 | S.Y. | 16308 |  |  |  |  | 108
13 | P.C.C. Sidewalk, 4" | 36275 | S.F. | 243042.5 |  |  | 2030 | S.F. | 6.7 | 13601
14 | Detectable Warnings, ADA Ramps | 940 | S.F. | 28200 |  |  |  |  | 30
15 | Combination Curb and Gutter Removal | 5315 | L.F. | 57402 |  |  | 292 | L.F. | 10.8 | 3153.6
16 | Sidewalk Removal | 35000 | S.F. | 52500 |  |  |  |  | 1.5
17 | Approach Pavement Removal | 1484 | S.Y. | 23298.8 | 13610 |  | 15094 | S.Y. | 15.7 | 236975.8
18 | Surface Removal, 2" | 84550 | S.Y. | 219830 |  |  | 500 | S.Y. | 2.6 | 1300
19 | Surface Removal, 4.5" | 4250 | S.Y. | 19465 |  |  | 1498 | S.Y. | 4.58 | 6860.84
20 | Surface Removal, Butt Joints | 100 | S.Y. | 1058 | 15144 |  | 15244 | S.Y. | 10.58 | 161281.52
21 | Sanitary Riser/Valve Boxes to be Adjusted | 3 | Each | 756 | 289 |  | 292 | Each | 252 | 73584
22 | Manholes to be Adjusted | 104 | Each | 60736 |  |  |  |  | 584
23 | Manholes to be Adjusted with New Frame and Lid | 20 | Each | 25240 | 18185 |  | 18205 | Each | 1262 | 22974710
24 | Manholes to be Reconstructed | 1 | Each | 1606 | 712 |  | 713 | Each | 1606 | 1145078
Sub Total |  |  |  | 1908413.71 | [5 empty] | 24730609.76
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: ROCK ROAD CO. | [5 empty] | MUNICIPALITY | City of Rockford
| Address: JANESVILLE, WI BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 2205 |  |  |  |  | 2205
26 | Inlets to be Adjusted | 19 | Each | 21850 |  |  |  |  | 1150
27 | Inlets to be Adjusted with New Frame and Grate | 21 | Each | 34440 |  |  |  |  | 1640
28 | Inlets to be Reconstructed | 1 | Each | 1840 |  |  |  |  | 1840
29 | Inlets to be Reconstructed with New Frame and Grate | 3 | Each | 6720 |  |  |  |  | 2240
30 | Inlet Specials to be Repaired | 1 | Each | 2000 | 9 |  | 10 | Each | 2000 | 20000
31 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 5315 | L.F. | 231202.5 |  |  |  |  | 43.5
32 | Traffic Control and Protection | 1 | Lsum | 71395.17 |  |  |  |  | 71395.17
33 | Thermoplastic Pavement Markings, 4" | 440 | L.F. | 1144 |  |  |  |  | 2.6
34 | Thermoplastic Pavement Markings, 6" | 179 | L.F. | 698.1 |  |  | 8 | L.F. | 3.9 | 31.2
35 | Thermoplastic Pavement Markings, 12" | 162 | L.F. | 1263.6 |  |  |  |  | 7.8
36 | Thermoplastic Pavement Markings, 24" | 31 | L.F. | 483.6 |  |  |  |  | 15.6
37 | Thermoplastic Pavement Markings, Letters and Symbols | 50 | S.F. | 780 |  |  |  |  | 15.6
38 | Detector Loops | 200 | L.F. | 7150 |  |  | 1 | L.F. | 35.75 | 35.75
[7 empty] | 1318 |  |  | #VALUE!
[7 empty] | 0.5 |  |  | #VALUE!
Total |  |  |  | 2291585.68 | [5 empty] | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | #VALUE!
[8 empty] | DEDUCT RETAINAGE | 10%
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | #VALUE!
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | #VALUE!
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: ROCK ROAD CO. | [5 empty] | MUNICIPALITY | City of Rockford
| Address: JANESVILLE, WI BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 2291585.68 | [5 empty] | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | #VALUE!
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | #VALUE!
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | #VALUE!
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: ROCK ROAD CO. | [5 empty] | MUNICIPALITY | City of Rockford
| Address: JANESVILLE, WI BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 2 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 2291585.68 | [5 empty] | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | #VALUE!
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | #VALUE!
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | #VALUE!
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | ROCK ROAD CO.
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.