## Item List
| City -Wide Street Repairs Group No. 3 - 2022 (Concrete) | [44 empty] | 1871039.5
Summary Of Quantities |  |  | 2nd Ward |  |  |  |  | 2nd Ward |  |  |  | 2nd Ward |  | 3rd Ward | 4th Ward | 5th Ward |  | 9th Ward |  | 11th Ward |  |  |  | 11th Ward |  |  |  | 11th Ward |  |  |  | 11th Ward | 14th Ward | Neighborhood Allocation |  | Neighborhood | Winter Repair | City Wide Sidewalk |  | City Wide Sidewalk |  | Traffic Safety
No. | Item | Units | 1716 2nd Avenue Sidewalk | 7th Avenue Sidewalk/Approach | 1025 12th Street Sidewalk | 1012-1016 18th Street Sidewalk | 1316 18th Street Sidewalk | 1104-1126 Arden Avenue Sidewalk | 1537 Crosby Street Curb and Gutte | 2111 Hutchins Avenue Curb and Gutter | 314 Paris Avenue Sidewalk | 116 Robert Avenue Sidewalk | 615 Rome Avenue Sidewalk | 3008 Barrington Place Sidewalk/Approach | 2651 Bordeaux Drive Curb and Gutter | 0300 Bremer Street | 0400 Catlin Street | 1500/1600 Burton Street | 3424 Packard Parkway Approach | 1437-1443 7th Avenue Sidewalk | 1522 7th Street Sidewalks | 2334 7th Street Sidewalks | 1411 9th Street Sidewalks | 1409 11th Avenue Sidewalk | 1911-1925 15th Street Sidewalk | 1820 16th Street Sidewalk | 1908 16th Avenue Sidewalk | 1715 17th Street Sidewalk | 1100 21st Avenue | 1616 Columbia Avenue Sidewalk | 2200 South 4th Street | 2200 South 4th Street | 5110-5114 Carter Court Approaches | 2800/2900 Brendenwood Road | 1700/2400 Mulberry Street | 1500 South 4th Street | Spring Creek Road/ Mulford Road Median Repairs | 0400 Cedar Street Sidewalk | 0400 Chestnut Street Sidewalk | 0300/0400 South Church Street Sidewalk | 1710 Rural Street Approach | Harrison Avenue Median Repairs | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. | [40 empty] | 50 | 50 | 30 | 1500
2 | Parkway Restoration | Lsum | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0.08 | 0.04 | 0.09 | 0.01 | 0.01 | 0.01 | 0 | 0.01 | 0 | 0.01 | 0.01 | 0 | 0.01 | 0.07 | 0 | 0.01 | 0.04 | 0.01 | 0.09 | 0.3 | 0.08 | 0.01 | 0.01 | 0.01 | 0 | 0.01 | 0.01 |  | 1 | 100000 | 100000
3 | Inlet and Pipe Protection | Each | [13 empty] | 3 | 2 | 9 | [10 empty] | 3 |  |  | 2 |  | 4 | 25 | 3 | [7 empty] | 51 | 60 | 3060
4 | Aggregate Base Repair, 10" | S.Y. | [13 empty] | 13 | 9 | 22 | [10 empty] | 16 |  |  | 12 |  | 27 | 78 | 13 | [7 empty] | 190 | 20 | 3800
5 | Bituminous Materials (Prime Coat) | Gal | [13 empty] | 135 | 95 | 220 | [10 empty] | 165 |  |  | 125 |  | 270 | 780 | 135 | [7 empty] | 1925 | 3 | 5775
6 | Aggregate (Prime Coat) | Tons | [13 empty] | 13 | 9 | 22 | [10 empty] | 16 |  |  | 12 |  | 27 | 78 | 13 | [7 empty] | 190 | 10 | 1900
7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | [26 empty] | 100 | [14 empty] | 100 | 115 | 11500
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | [13 empty] | 100 | 50 | [17 empty] | 450 | [8 empty] | 600 | 80 | 48000
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | [26 empty] | 150 | [14 empty] | 150 | 80 | 12000
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | [13 empty] | 175 | 125 | 275 | [13 empty] | 150 |  | 325 | 1000 | 175 | [6 empty] | 500 | 2725 | 80 | 218000
11 | Hot-Mix Asphalt, Hand Method | Tons |  | 5 | 2 |  |  |  | 2 | 10 | [24 empty] | 5 | [5 empty] | 2 |  |  | 26 | 300 | 7800
12 | P.C.C. Approach Pavement, 6" | S.Y. |  | 66 | 27 |  |  |  |  | 12 |  |  |  | 11 | 18 | 150 | 42 | 88 | 16 |  |  |  | 13 | [5 empty] | 241 |  |  | 91 | 40 | 46 | 526 | 222 | [6 empty] | 50 | 1659 | 65 | 107835
13 | P.C.C. Approach Pavement, 8" | S.Y. | [15 empty] | 19 |  |  | 20 | [19 empty] | 42 |  | 50 | 131 | 80 | 10480
14 | P.C.C. Sidewalk, 4" | S.F. | 150 | 625 | 700 | 650 | 1150 | 575 |  | 400 | 250 | 475 | 250 | 225 | 100 | 4300 | 2700 | 2950 | 425 | 700 | 475 | 275 | 425 | 200 | 600 | 1400 | 325 | 475 | 3275 | 325 | 675 | 1675 | 250 | 3075 | 14150 | 3325 |  | 350 | 120 | 180 | 150 |  | 5000 | 53350 | 6 | 320100
15 | Detectable Warnings, ADA Ramps | S.F. |  |  | 10 | [12 empty] | 160 | [10 empty] | 40 |  |  |  |  | 160 | 160 | 40 | [7 empty] | 570 | 30 | 17100
16 | Class B Patch, Type IV, 10" | S.Y. | [34 empty] | 120 | [6 empty] | 120 | 150 | 18000
17 | Dowel Bars | Each | [34 empty] | 30 | [6 empty] | 30 | 20 | 600
18 | No. 6 Transverse Tie Bars | Each | [34 empty] | 30 | [6 empty] | 30 | 15 | 450
19 | Welded Wire Reinforcement | S.Y. | [34 empty] | 120 | [6 empty] | 120 | 10 | 1200
20 | Combination Curb and Gutter Removal | L.F. |  | 140 | 100 |  |  |  | 30 | 125 |  |  |  | 30 | 40 | 1205 | 520 | 1520 | 25 |  | 55 | [7 empty] | 1000 |  |  | 860 | 50 | 1525 | 3585 | 915 | 220 |  |  |  | 50 |  | 1000 | 12995 | 15 | 194925
21 | Sidewalk Removal | S.F. | 150 | 625 | 900 | 650 | 1150 | 575 |  | 400 | 250 | 475 | 250 | 225 | 100 | 4800 | 2700 | 2950 | 425 | 700 | 550 | 275 | 425 | 200 | 600 | 1400 | 325 | 475 | 3275 | 325 | 675 | 1675 | 250 | 3100 | 14275 | 3375 |  | 350 | 120 | 180 | 150 |  | 5000 | 54325 | 2.5 | 135812.5
22 | Approach Pavement Removal | S.Y. |  | 66 | 27 |  |  |  |  | 12 |  |  |  |  | 18 | 150 | 76 | 107 | 16 |  | 20 |  | 30 | [5 empty] | 241 |  |  | 91 | 40 | 46 | 526 | 222 |  |  |  |  | 42 |  | 100 | 1830 | 25 | 45750
23 | Median Removal | S.Y. | [34 empty] | 650 |  |  |  |  | 370 |  | 1020 | 5 | 5100
24 | Surface Removal, 2" | S.Y. | [13 empty] | 1350 | 950 | 2200 | [13 empty] | 1250 |  | 2700 | 7800 | 1350 | [6 empty] | 1000 | 18600 | 3 | 55800
25 | Surface Removal, Butt Joints | S.Y. | [26 empty] | 160 | [14 empty] | 160 | 7 | 1120
26 | Concrete Surface Removal, 1.5" | S.Y. | [26 empty] | 1300 | [14 empty] | 1300 | 7 | 9100
27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [15 empty] | 3 | [15 empty] | 1 | 2 | [8 empty] | 6 | 500 | 3000
28 | Manholes to be Adjusted | Each | [13 empty] | 3 |  | 1 | [10 empty] | 2 |  |  | 1 |  | 3 | 7 | 1 | [7 empty] | 18 | 650 | 11700
29 | Manholes to be Adjusted with New Frame and Lid | Each | [31 empty] | 1 | 2 | [8 empty] | 3 | 1000 | 3000
30 | Manholes to be Reconstructed | Each | [40 empty] | 1 | 1 | 1000 | 1000
31 | Manholes to be Reconstructed with New Frame and Lid | Each | [40 empty] | 1 | 1 | 1600 | 1600
32 | Inlets to be Adjusted | Each | [15 empty] | 5 | [10 empty] | 2 |  |  |  |  | 4 | 10 | 2 | [7 empty] | 23 | 1100 | 25300
33 | Inlets to be Adjusted with New Frame and Grate | Each |  |  | 1 | [10 empty] | 1 | [18 empty] | 2 | [8 empty] | 4 | 1600 | 6400
34 | Inlets to be Reconstructed | Each | [40 empty] | 1 | 1 | 1500 | 1500
35 | Inlets to be Reconstructed with New Frame and Grate | Each |  |  | 1 | [12 empty] | 3 | [25 empty] | 4 | 1800 | 7200
36 | Inlet Special to be Repaired | Each | [40 empty] | 1 | 1 | 2200 | 2200
37 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. |  | 140 | 100 |  |  |  | 30 | 125 |  |  |  | 30 | 40 | 1205 | 520 | 1520 | 25 |  | 55 | [7 empty] | 1000 |  |  | 860 | 50 | 1525 | 3585 | 915 | 220 |  |  |  | 50 |  | 1000 | 12995 | 30 | 389850
38 | Concrete Median, 4" | S.F. | [34 empty] | 650 | [6 empty] | 650 | 30 | 19500
39 | Concrete Corrugated Median, 10" | S.F. | [39 empty] | 370 |  | 370 | 30 | 11100
40 | Traffic Control and Protection | Lsum | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0.08 | 0.04 | 0.09 | 0.01 | 0.01 | 0.01 | 0 | 0.01 | 0 | 0.01 | 0.01 | 0 | 0.01 | 0.07 | 0 | 0.01 | 0.04 | 0.01 | 0.09 | 0.3 | 0.08 | 0.01 | 0.01 | 0.01 | 0 | 0.01 | 0.01 |  | 1 | 30000 | 30000
41 | Thermoplastic Pavement Markings, 4" | L.F. | [40 empty] | 500 | 500 | 2.5 | 1250
42 | Thermoplastic Pavement Markings, 6" | L.F. | [31 empty] | 435 | 391 | [8 empty] | 826 | 4 | 3304
43 | Thermoplastic Pavement Markings, 24" | L.F. | [31 empty] | 52 | 67 | [8 empty] | 119 | 12 | 1428
44 | Subgrade Undercutting | C.Y. | [40 empty] | 50 | 50 | 300 | 15000
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 1275 | 20352.5 | 18980 | 6825 | 11075 | 6187.5 | 1950 | 14405 | 2125 | 4037.5 | 2125 | 3977.5 | 5570 | 146500 | 73705 | 163400 | 7477.5 | 7250 | 10100 | 2337.5 | 6507.5 | 1700 | 6400 | 13200 | 2762.5 | 5337.5 | 143202.5 | 2762.5 | 7037.5 | 83582.5 | 9275 | 161639 | 544250.5 | 123017.5 | 54200 | 4275 | 2320 | 1530 | 9835 | 14250 | 164300 | #VALUE!
|  |  | 340.6856 | 1926.184 | 1834.4609 | 598.3837 | 980.5631 | 543.7866 | 388.731 | 2177.3304 | 292.6402 | 480.4541 | 0 | 670.4518 | 388.731 | 13572.8271 | 6632.4499 | 15245.6808 | 583.0965 | 659.5324 | 1177.1124 | 312.2951 | 814.588 | 218.3882 | 569.9932 | 1207.6868 | 331.9501 | 412.7537 | 12461.2311 | 674.8196 | 650.7969 | 7934.0436 | 1159.6414 | 15287.1745 | 52413.1698 | 13103.2924 | 5241.317 | 305.7435 | 131.0329 | 174.7106 | 1091.941 | 1310.3292 |  | 1871039.5
|  |  | 1615.6856 | 22278.684 | 20814.4609 | 7423.3837 | 12055.5631 | 6731.2866 | 2338.731 | 16582.3304 | 2417.6402 | 4517.9541 | 2125 | 4647.9518 | 5958.731 | 160072.8271 | 80337.4499 | 178645.6808 | 8060.5965 | 7909.5324 | 11277.1124 | 2649.7951 | 7322.088 | 1918.3882 | 6969.9932 | 14407.6868 | 3094.4501 | 5750.2537 | 155663.7311 | 3437.3196 | 7688.2969 | 91516.5436 | 10434.6414 | 176926.1745 | 596663.6698 | 136120.7924 | 59441.317 | 4580.7435 | 2451.0329 | 1704.7106 | 10926.941 | 15560.3292 |  | 1871039.5
|  |  | 3900 | 22050 | 21000 | 6850 | 11225 | 6225 | 4450 | 24925 | 3350 | 5500 | 0 | 7675 | 4450 | 155375 | 75925 | 174525 | 6675 | 7550 | 13475 | 3575 | 9325 | 2500 | 6525 | 13825 | 3800 | 4725 | 142650 | 7725 | 7450 | 90825 | 13275 | 175000 | 600000 | 150000 | 60000 | 3500 | 1500 | 2000 | 12500 | 15000 | 0 | 1880825
#REF!
|  |  | 0.0020736 | 0.011724 | 0.011165 | 0.003642 | 0.0059681 | 0.0033097 | 0.002366 | 0.013252 | 0.0017811 | 0.0029242 | 0 | 0.0040807 | 0.002366 | 0.08261 | 0.040368 | 0.092792 | 0.003549 | 0.0040142 | 0.0071644 | 0.0019008 | 0.0049579 | 0.0013292 | 0.0034692 | 0.0073505 | 0.0020204 | 0.0025122 | 0.075844 | 0.0041072 | 0.003961 | 0.04829 | 0.0070581 | 0.093044 | 0.31901 | 0.079752 | 0.031901 | 0.0018609 | 0.00079752 | 0.0010634 | 0.006646 | 0.0079752 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | TCI CONCRETE |  | STENSTROM EXCAVATION | [7 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | ROCKFORD,IL |  | ROCKFORD, IL | [7 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 3 - 2023 (Concrete) | [5 empty] | BID BOND |  | BID BOND | [7 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 423-PW-043 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 50 | 30 | 1500 | 320 | 16000 | 150 | 7500 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 50 | 30 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 50 | 30 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 100000 | 100000 | 10000 | 10000 | 82500 | 82500 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 100000 | 100000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 100000 | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 51 | 60 | 3060 | 0.01 | 0.51 | 110 | 5610 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 51 | 60 | 3060 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 51 | 60 | 3060 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Aggregate Base Repair, 10" | S.Y. | 190 | 20 | 3800 | 20 | 3800 | 56.5 | 10735 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Repair, 10" | S.Y. | 190 | 20 | 3800 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Repair, 10" | S.Y. | 190 | 20 | 3800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Bituminous Materials (Prime Coat) | Gal | 1925 | 3 | 5775 | 2.93 | 5640.25 | 3 | 5775 |  | 0 |  | 0 |  | 0 | 5 | Bituminous Materials (Prime Coat) | Gal | 1925 | 3 | 5775 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Bituminous Materials (Prime Coat) | Gal | 1925 | 3 | 5775 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Aggregate (Prime Coat) | Tons | 190 | 10 | 1900 | 0.01 | 1.9 | 0.01 | 1.9 |  | 0 |  | 0 |  | 0 | 6 | Aggregate (Prime Coat) | Tons | 190 | 10 | 1900 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate (Prime Coat) | Tons | 190 | 10 | 1900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | 100 | 115 | 11500 | 99.51 | 9951 | 104.5 | 10450 |  | 0 |  | 0 |  | 0 | 7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | 100 | 115 | 11500 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | 100 | 115 | 11500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 600 | 80 | 48000 | 75.36 | 45216 | 80 | 48000 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 600 | 80 | 48000 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 600 | 80 | 48000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 150 | 80 | 12000 | 86.48 | 12972 | 91 | 13650 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 150 | 80 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 150 | 80 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 2725 | 80 | 218000 | 78.53 | 213994.25 | 82 | 223450 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 2725 | 80 | 218000 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 2725 | 80 | 218000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Hot-Mix Asphalt, Hand Method | Tons | 26 | 300 | 7800 | 600 | 15600 | 250 | 6500 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt, Hand Method | Tons | 26 | 300 | 7800 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt, Hand Method | Tons | 26 | 300 | 7800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 1659 | 65 | 107835 | 45 | 74655 | 69.75 | 115715.25 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 1659 | 65 | 107835 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 1659 | 65 | 107835 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 131 | 80 | 10480 | 50 | 6550 | 84.25 | 11036.75 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 131 | 80 | 10480 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 131 | 80 | 10480 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 53350 | 6 | 320100 | 9.5 | 506825 | 7.55 | 402792.5 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 53350 | 6 | 320100 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 53350 | 6 | 320100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Detectable Warnings, ADA Ramps | S.F. | 570 | 30 | 17100 | 10 | 5700 | 35 | 19950 |  | 0 |  | 0 |  | 0 | 15 | Detectable Warnings, ADA Ramps | S.F. | 570 | 30 | 17100 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Detectable Warnings, ADA Ramps | S.F. | 570 | 30 | 17100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Class B Patch, Type IV, 10" | S.Y. | 120 | 150 | 18000 | 110 | 13200 | 111 | 13320 |  | 0 |  | 0 |  | 0 | 16 | Class B Patch, Type IV, 10" | S.Y. | 120 | 150 | 18000 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Class B Patch, Type IV, 10" | S.Y. | 120 | 150 | 18000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Dowel Bars | Each | 30 | 20 | 600 | 10 | 300 | 12 | 360 |  | 0 |  | 0 |  | 0 | 17 | Dowel Bars | Each | 30 | 20 | 600 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Dowel Bars | Each | 30 | 20 | 600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | No. 6 Transverse Tie Bars | Each | 30 | 15 | 450 | 3 | 90 | 18.75 | 562.5 |  | 0 |  | 0 |  | 0 | 18 | No. 6 Transverse Tie Bars | Each | 30 | 15 | 450 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | No. 6 Transverse Tie Bars | Each | 30 | 15 | 450 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Welded Wire Reinforcement | S.Y. | 120 | 10 | 1200 | 43 | 5160 | 5.15 | 618 |  | 0 |  | 0 |  | 0 | 19 | Welded Wire Reinforcement | S.Y. | 120 | 10 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Welded Wire Reinforcement | S.Y. | 120 | 10 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Combination Curb and Gutter Removal | L.F. | 12995 | 15 | 194925 | 7 | 90965 | 22.5 | 292387.5 |  | 0 |  | 0 |  | 0 | 20 | Combination Curb and Gutter Removal | L.F. | 12995 | 15 | 194925 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Combination Curb and Gutter Removal | L.F. | 12995 | 15 | 194925 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Sidewalk Removal | S.F. | 54325 | 2.5 | 135812.5 | 2.75 | 149393.75 | 2.2 | 119515 |  | 0 |  | 0 |  | 0 | 21 | Sidewalk Removal | S.F. | 54325 | 2.5 | 135812.5 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Sidewalk Removal | S.F. | 54325 | 2.5 | 135812.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Approach Pavement Removal | S.Y. | 1830 | 25 | 45750 | 18 | 32940 | 25 | 45750 |  | 0 |  | 0 |  | 0 | 22 | Approach Pavement Removal | S.Y. | 1830 | 25 | 45750 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Approach Pavement Removal | S.Y. | 1830 | 25 | 45750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Median Removal | S.Y. | 1020 | 5 | 5100 | 10 | 10200 | 25 | 25500 |  | 0 |  | 0 |  | 0 | 23 | Median Removal | S.Y. | 1020 | 5 | 5100 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Median Removal | S.Y. | 1020 | 5 | 5100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Surface Removal, 2" | S.Y. | 18600 | 3 | 55800 | 2.35 | 43710 | 3.45 | 64170 |  | 0 |  | 0 |  | 0 | 24 | Surface Removal, 2" | S.Y. | 18600 | 3 | 55800 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Surface Removal, 2" | S.Y. | 18600 | 3 | 55800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 1326487.5 |  | 1272864.66 |  | 1525849.4 | [7 empty] | Page 3 | Sub |  | As read | 1326487.5 | [9 empty] | Page 1 | Sub |  | As read | 1326487.5
| Award to TCI CONCRETE | Total |  | As corrected | 1326487.5 |  | 1272864.66 |  | 1525849.4 | [7 empty] | Award to TCI CONCRETE | Total |  | As corrected | 1326487.5 | [9 empty] | Award to TCI CONCRETE | Total |  | As corrected | 1326487.5
25 | Surface Removal, Butt Joints | S.Y. | 160 | 7 | 1120 | 5.3 | 848 | 11.5 | 1840 |  | 0 |  | 0 |  | 0 | 25 | Surface Removal, Butt Joints | S.Y. | 160 | 7 | 1120 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Surface Removal, Butt Joints | S.Y. | 160 | 7 | 1120 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Concrete Surface Removal, 1.5" | S.Y. | 1300 | 7 | 9100 | 5.3 | 6890 | 7 | 9100 |  | 0 |  | 0 |  | 0 | 26 | Concrete Surface Removal, 1.5" | S.Y. | 1300 | 7 | 9100 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Concrete Surface Removal, 1.5" | S.Y. | 1300 | 7 | 9100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 6 | 500 | 3000 | 250 | 1500 | 425 | 2550 |  | 0 |  | 0 |  | 0 | 27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 6 | 500 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 6 | 500 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Manholes to be Adjusted | Each | 18 | 650 | 11700 | 350 | 6300 | 610 | 10980 |  | 0 |  | 0 |  | 0 | 28 | Manholes to be Adjusted | Each | 18 | 650 | 11700 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Manholes to be Adjusted | Each | 18 | 650 | 11700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Manholes to be Adjusted with New Frame and Lid | Each | 3 | 1000 | 3000 | 1400 | 4200 | 1046 | 3138 |  | 0 |  | 0 |  | 0 | 29 | Manholes to be Adjusted with New Frame and Lid | Each | 3 | 1000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Manholes to be Adjusted with New Frame and Lid | Each | 3 | 1000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 | 500 | 500 | 1426 | 1426 |  | 0 |  | 0 |  | 0 | 30 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600 | 1900 | 1900 | 1822 | 1822 |  | 0 |  | 0 |  | 0 | 31 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Inlets to be Adjusted | Each | 23 | 1100 | 25300 | 550 | 12650 | 993 | 22839 |  | 0 |  | 0 |  | 0 | 32 | Inlets to be Adjusted | Each | 23 | 1100 | 25300 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Inlets to be Adjusted | Each | 23 | 1100 | 25300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Inlets to be Adjusted with New Frame and Grate | Each | 4 | 1600 | 6400 | 900 | 3600 | 1650 | 6600 |  | 0 |  | 0 |  | 0 | 33 | Inlets to be Adjusted with New Frame and Grate | Each | 4 | 1600 | 6400 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Inlets to be Adjusted with New Frame and Grate | Each | 4 | 1600 | 6400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 | 750 | 750 | 1432 | 1432 |  | 0 |  | 0 |  | 0 | 34 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | Inlets to be Reconstructed with New Frame and Grate | Each | 4 | 1800 | 7200 | 1200 | 4800 | 1919 | 7676 |  | 0 |  | 0 |  | 0 | 35 | Inlets to be Reconstructed with New Frame and Grate | Each | 4 | 1800 | 7200 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Inlets to be Reconstructed with New Frame and Grate | Each | 4 | 1800 | 7200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | Inlet Special to be Repaired | Each | 1 | 2200 | 2200 | 1500 | 1500 | 2864 | 2864 |  | 0 |  | 0 |  | 0 | 36 | Inlet Special to be Repaired | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 | 36 | Inlet Special to be Repaired | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 12995 | 30 | 389850 | 22 | 285890 | 29.5 | 383352.5 |  | 0 |  | 0 |  | 0 | 37 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 12995 | 30 | 389850 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 12995 | 30 | 389850 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | Concrete Median, 4" | S.F. | 650 | 30 | 19500 | 10 | 6500 | 8.25 | 5362.5 |  | 0 |  | 0 |  | 0 | 38 | Concrete Median, 4" | S.F. | 650 | 30 | 19500 |  | 0 |  | 0 |  | 0 |  | 0 | 38 | Concrete Median, 4" | S.F. | 650 | 30 | 19500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | Concrete Corrugated Median, 10" | S.F. | 370 | 30 | 11100 | 10 | 3700 | 11.75 | 4347.5 |  | 0 |  | 0 |  | 0 | 39 | Concrete Corrugated Median, 10" | S.F. | 370 | 30 | 11100 |  | 0 |  | 0 |  | 0 |  | 0 | 39 | Concrete Corrugated Median, 10" | S.F. | 370 | 30 | 11100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | Traffic Control and Protection | Lsum | 1 | 30000 | 30000 | 15000 | 15000 | 50000 | 50000 |  | 0 |  | 0 |  | 0 | 40 | Traffic Control and Protection | Lsum | 1 | 30000 | 30000 |  | 0 |  | 0 |  | 0 |  | 0 | 40 | Traffic Control and Protection | Lsum | 1 | 30000 | 30000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | Thermoplastic Pavement Markings, 4" | L.F. | 500 | 2.5 | 1250 | 2 | 1000 | 2.1 | 1050 |  | 0 |  | 0 |  | 0 | 41 | Thermoplastic Pavement Markings, 4" | L.F. | 500 | 2.5 | 1250 |  | 0 |  | 0 |  | 0 |  | 0 | 41 | Thermoplastic Pavement Markings, 4" | L.F. | 500 | 2.5 | 1250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
42 | Thermoplastic Pavement Markings, 6" | L.F. | 826 | 4 | 3304 | 3 | 2478 | 3.15 | 2601.9 |  | 0 |  | 0 |  | 0 | 42 | Thermoplastic Pavement Markings, 6" | L.F. | 826 | 4 | 3304 |  | 0 |  | 0 |  | 0 |  | 0 | 42 | Thermoplastic Pavement Markings, 6" | L.F. | 826 | 4 | 3304 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
43 | Thermoplastic Pavement Markings, 24" | L.F. | 119 | 12 | 1428 | 12 | 1428 | 12.58 | 1497.02 |  | 0 |  | 0 |  | 0 | 43 | Thermoplastic Pavement Markings, 24" | L.F. | 119 | 12 | 1428 |  | 0 |  | 0 |  | 0 |  | 0 | 43 | Thermoplastic Pavement Markings, 24" | L.F. | 119 | 12 | 1428 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
44 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000 | 200 | 10000 | 200 | 10000 |  | 0 |  | 0 |  | 0 | 44 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 | 44 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 1871039.5 |  | 1644298.66 |  | 2056327.82 | [7 empty] | Page 4 | Total |  | As read | 1871039.5 | [9 empty] | Page 2 | Total |  | As read | 1871039.5
| Award to TCI CONCRETE | Bid |  | As corrected |  |  | 1644298.66 |  | 2056327.82 | 0 | [6 empty] | Award to TCI CONCRETE | Bid |  | As corrected | #VALUE! | [9 empty] | Award to TCI CONCRETE | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to TCI CONCRETE | Bid |  | As corrected | [12 empty] | Award to TCI CONCRETE | Bid |  | As corrected | [10 empty] | Award to TCI CONCRETE | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to TCI CONCRETE | Bid |  | As corrected | [12 empty] | Award to TCI CONCRETE | Bid |  | As corrected | [10 empty] | Award to TCI CONCRETE | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 3 - 2023 (Concrete)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 50 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 51 |  | 0
4 | Aggregate Base Repair, 10" | S.Y. | 190 |  | 0
5 | Bituminous Materials (Prime Coat) | Gal | 1925 |  | 0
6 | Aggregate (Prime Coat) | Tons | 190 |  | 0
7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | 100 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 600 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 150 |  | 0
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 2725 |  | 0
11 | Hot-Mix Asphalt, Hand Method | Tons | 26 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 1659 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 131 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 53350 |  | 0
15 | Detectable Warnings, ADA Ramps | S.F. | 570 |  | 0
16 | Class B Patch, Type IV, 10" | S.Y. | 120 |  | 0
17 | Dowel Bars | Each | 30 |  | 0
18 | No. 6 Transverse Tie Bars | Each | 30 |  | 0
19 | Welded Wire Reinforcement | S.Y. | 120 |  | 0
20 | Combination Curb and Gutter Removal | L.F. | 12995 |  | 0
21 | Sidewalk Removal | S.F. | 54325 |  | 0
22 | Approach Pavement Removal | S.Y. | 1830 |  | 0
23 | Median Removal | S.Y. | 1020 |  | 0
24 | Surface Removal, 2" | S.Y. | 18600 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Surface Removal, Butt Joints | S.Y. | 160 |  | 0
26 | Concrete Surface Removal, 1.5" | S.Y. | 1300 |  | 0
27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 6 |  | 0
28 | Manholes to be Adjusted | Each | 18 |  | 0
29 | Manholes to be Adjusted with New Frame and Lid | Each | 3 |  | 0
30 | Manholes to be Reconstructed | Each | 1 |  | 0
31 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 |  | 0
32 | Inlets to be Adjusted | Each | 23 |  | 0
33 | Inlets to be Adjusted with New Frame and Grate | Each | 4 |  | 0
34 | Inlets to be Reconstructed | Each | 1 |  | 0
35 | Inlets to be Reconstructed with New Frame and Grate | Each | 4
36 | Inlet Special to be Repaired | Each | 1
37 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 12995
38 | Concrete Median, 4" | S.F. | 650
39 | Concrete Corrugated Median, 10" | S.F. | 370
40 | Traffic Control and Protection | Lsum | 1
41 | Thermoplastic Pavement Markings, 4" | L.F. | 500
42 | Thermoplastic Pavement Markings, 6" | L.F. | 826
43 | Thermoplastic Pavement Markings, 24" | L.F. | 119
44 | Subgrade Undercutting | C.Y. | 50
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2023 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 50 | 30 | 1500
2 | Parkway Restoration | Lsum | 1 | 100000 | 100000
3 | Inlet and Pipe Protection | Each | 51 | 60 | 3060
4 | Aggregate Base Repair, 10" | S.Y. | 190 | 20 | 3800
5 | Bituminous Materials (Prime Coat) | Gal | 1925 | 3 | 5775
6 | Aggregate (Prime Coat) | Tons | 190 | 10 | 1900
7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | 100 | 115 | 11500
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 600 | 80 | 48000
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 150 | 80 | 12000
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 2725 | 80 | 218000
11 | Hot-Mix Asphalt, Hand Method | Tons | 26 | 300 | 7800
12 | P.C.C. Approach Pavement, 6" | S.Y. | 1659 | 65 | 107835
13 | P.C.C. Approach Pavement, 8" | S.Y. | 131 | 80 | 10480
14 | P.C.C. Sidewalk, 4" | S.F. | 53350 | 6 | 320100
15 | Detectable Warnings, ADA Ramps | S.F. | 570 | 30 | 17100
16 | Class B Patch, Type IV, 10" | S.Y. | 120 | 150 | 18000
17 | Dowel Bars | Each | 30 | 20 | 600
18 | No. 6 Transverse Tie Bars | Each | 30 | 15 | 450
19 | Welded Wire Reinforcement | S.Y. | 120 | 10 | 1200
20 | Combination Curb and Gutter Removal | L.F. | 12995 | 15 | 194925
21 | Sidewalk Removal | S.F. | 54325 | 2.5 | 135812.5
22 | Approach Pavement Removal | S.Y. | 1830 | 25 | 45750
23 | Median Removal | S.Y. | 1020 | 5 | 5100
24 | Surface Removal, 2" | S.Y. | 18600 | 3 | 55800
|  |  |  | Sub Total | 1326487.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2023 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Surface Removal, Butt Joints | S.Y. | 160 | 7 | 1120
26 | Concrete Surface Removal, 1.5" | S.Y. | 1300 | 7 | 9100
27 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 6 | 500 | 3000
28 | Manholes to be Adjusted | Each | 18 | 650 | 11700
29 | Manholes to be Adjusted with New Frame and Lid | Each | 3 | 1000 | 3000
30 | Manholes to be Reconstructed | Each | 1 | 1000 | 1000
31 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600
32 | Inlets to be Adjusted | Each | 23 | 1100 | 25300
33 | Inlets to be Adjusted with New Frame and Grate | Each | 4 | 1600 | 6400
34 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500
35 | Inlets to be Reconstructed with New Frame and Grate | Each | 4 | 1800 | 7200
36 | Inlet Special to be Repaired | Each | 1 | 2200 | 2200
37 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 12995 | 30 | 389850
38 | Concrete Median, 4" | S.F. | 650 | 30 | 19500
39 | Concrete Corrugated Median, 10" | S.F. | 370 | 30 | 11100
40 | Traffic Control and Protection | Lsum | 1 | 30000 | 30000
41 | Thermoplastic Pavement Markings, 4" | L.F. | 500 | 2.5 | 1250
42 | Thermoplastic Pavement Markings, 6" | L.F. | 826 | 4 | 3304
43 | Thermoplastic Pavement Markings, 24" | L.F. | 119 | 12 | 1428
44 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2023 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2023 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from June 20, 2022 to July 7, 2022 | [7 empty] | (Road District)
| Payable to: TCI CONCRETE | P.O. # 22305291 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: ROCKFORD,IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2023 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 50 | C.Y. | 16000 |  |  |  |  | 320
2 | Parkway Restoration | 1 | Lsum | 10000 |  |  |  |  | 10000
3 | Inlet and Pipe Protection | 51 | Each | 0.51 |  |  |  |  | 0.01
4 | Aggregate Base Repair, 10" | 190 | S.Y. | 3800 |  |  |  |  | 20
5 | Bituminous Materials (Prime Coat) | 1925 | Gal | 5640.25 |  |  |  |  | 2.93
6 | Aggregate (Prime Coat) | 190 | Tons | 1.9 |  |  |  |  | 0.01
7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | 100 | Tons | 9951 |  |  |  |  | 99.51
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | 600 | Tons | 45216 |  |  |  |  | 75.36
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | 150 | Tons | 12972 |  |  |  |  | 86.48
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 2725 | Tons | 213994.25 |  |  |  |  | 78.53
11 | Hot-Mix Asphalt, Hand Method | 26 | Tons | 15600 |  |  |  |  | 600
12 | P.C.C. Approach Pavement, 6" | 1659 | S.Y. | 74655 |  |  |  |  | 45
13 | P.C.C. Approach Pavement, 8" | 131 | S.Y. | 6550 |  |  |  |  | 50
14 | P.C.C. Sidewalk, 4" | 53350 | S.F. | 506825 |  |  |  |  | 9.5
15 | Detectable Warnings, ADA Ramps | 570 | S.F. | 5700 |  |  |  |  | 10
16 | Class B Patch, Type IV, 10" | 120 | S.Y. | 13200 |  |  |  |  | 110
17 | Dowel Bars | 30 | Each | 300 |  |  |  |  | 10
18 | No. 6 Transverse Tie Bars | 30 | Each | 90 |  |  |  |  | 3
19 | Welded Wire Reinforcement | 120 | S.Y. | 5160 |  |  |  |  | 43
20 | Combination Curb and Gutter Removal | 12995 | L.F. | 90965 |  |  |  |  | 7
21 | Sidewalk Removal | 54325 | S.F. | 149393.75 |  |  |  |  | 2.75
22 | Approach Pavement Removal | 1830 | S.Y. | 32940 |  |  |  |  | 18
23 | Median Removal | 1020 | S.Y. | 10200 |  |  |  |  | 10
24 | Surface Removal, 2" | 18600 | S.Y. | 43710 |  |  |  |  | 2.35
Sub Total |  |  |  | 1272864.66 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from June 20, 2022 to July 7, 2022 | [7 empty] | (Road District)
| Payable to: TCI CONCRETE | [5 empty] | MUNICIPALITY | City of Rockford
| Address: ROCKFORD,IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2023 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Surface Removal, Butt Joints | 160 | S.Y. | 848 |  |  |  |  | 5.3
26 | Concrete Surface Removal, 1.5" | 1300 | S.Y. | 6890 |  |  |  |  | 5.3
27 | Sanitary Riser/Valve Boxes to be Adjusted | 6 | Each | 1500 |  |  |  |  | 250
28 | Manholes to be Adjusted | 18 | Each | 6300 |  |  |  |  | 350
29 | Manholes to be Adjusted with New Frame and Lid | 3 | Each | 4200 |  |  |  |  | 1400
30 | Manholes to be Reconstructed | 1 | Each | 500 |  |  |  |  | 500
31 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 1900 |  |  |  |  | 1900
32 | Inlets to be Adjusted | 23 | Each | 12650 |  |  |  |  | 550
33 | Inlets to be Adjusted with New Frame and Grate | 4 | Each | 3600 |  |  |  |  | 900
34 | Inlets to be Reconstructed | 1 | Each | 750 |  |  |  |  | 750
35 | Inlets to be Reconstructed with New Frame and Grate | 4 | Each | 4800 |  |  |  |  | 1200
36 | Inlet Special to be Repaired | 1 | Each | 1500 |  |  |  |  | 1500
37 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 12995 | L.F. | 285890 |  |  |  |  | 22
38 | Concrete Median, 4" | 650 | S.F. | 6500 |  |  |  |  | 10
39 | Concrete Corrugated Median, 10" | 370 | S.F. | 3700 |  |  |  |  | 10
40 | Traffic Control and Protection | 1 | Lsum | 15000 |  |  |  |  | 15000
41 | Thermoplastic Pavement Markings, 4" | 500 | L.F. | 1000 |  |  |  |  | 2
42 | Thermoplastic Pavement Markings, 6" | 826 | L.F. | 2478 |  |  |  |  | 3
43 | Thermoplastic Pavement Markings, 24" | 119 | L.F. | 1428 |  |  |  |  | 12
44 | Subgrade Undercutting | 50 | C.Y. | 10000 |  |  |  |  | 200
Total |  |  |  | 1644298.66 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
[8 empty] | DEDUCT RETAINAGE | 10% | 0
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from June 20, 2022 to July 7, 2022 | [7 empty] | (Road District)
| Payable to: TCI CONCRETE | [5 empty] | MUNICIPALITY | City of Rockford
| Address: ROCKFORD,IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2023 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 1644298.66 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from June 20, 2022 to July 7, 2022 | [7 empty] | (Road District)
| Payable to: TCI CONCRETE | [5 empty] | MUNICIPALITY | City of Rockford
| Address: ROCKFORD,IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2023 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 1644298.66 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | TCI CONCRETE
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.