## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 667255
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 7500 | 7500
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 1500 | 1500
3 | INLET AND PIPE PROTECTION | EA | 7 | 250 | 1750
4 | CONCRETE TRUCK WASHOUT | LS | 1 | 750 | 750
5 | PAVEMENT REMOVAL | SY | 2030 | 25 | 50750
6 | PAVEMENT SURFACE REMOVAL, 2" | SY | 730 | 12.5 | 9125
7 | APPROACH PAVEMENT REMOVAL | SY | 185 | 15 | 2775
8 | SIDEWALK REMOVAL | SF | 1800 | 1 | 1800
9 | COMBINATION CURB AND GUTTER REMOVAL | LF | 605 | 15 | 9075
10 | ROCK EXCAVATION | CY | 25 | 100 | 2500
11 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 2 | 1250 | 2500
12 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 2 | 500 | 1000
13 | REMOVE FIRE HYDRANT AND AUXILIARY VALVE, COMPLETE | EA | 1 | 1250 | 1250
14 | SANITARY MANHOLES TO BE ADJUSTED | EA | 1 | 1200 | 1200
15 | STORM MANHOLES TO BE ADJUSTED | EA | 3 | 1750 | 5250
16 | PCC APPROACH PAVEMENT, 6" | SY | 105 | 100 | 10500
17 | PCC SIDEWALK, 4" | SF | 1800 | 10 | 18000
18 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18 (MODIFIED) | LF | 890 | 35 | 31150
19 | DETECTABLE WARNINGS | SF | 30 | 50 | 1500
20 | AGGREGATE BASE COURSE, TYPE B, 12" (CA-6) | SY | 1180 | 15 | 17700
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N50, 2" | TON | 335 | 108 | 36180
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 485 | 95 | 46075
23 | HMA APPROACH PAVEMENT, 3" | SY | 78 | 75 | 5850
24 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 85 | 125 | 10625
25 | DUCTILE IRON WATER MAIN COMPLETE, 16" | LF | 595 | 225 | 133875
26 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 3 | 3250 | 9750
27 | GATE VALVE AND VALVE BOX, COMPLETE, 16" | EA | 3 | 8500 | 25500
28 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 3 | 7500 | 22500
29 | EXTERIOR FOUNDATION ACCESS PIT | EA | 1 | 750 | 750
30 | PUBLIC WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 7 | 2000 | 14000
31 | PUBLIC WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 | 2500 | 2500
32 | PRIVATE WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 | 2500 | 2500
33 | PRIVATE WATER SERVICE (BORED OR PULLED), COMPLETE, 1" | LF | 140 | 105 | 14700
34 | CONNECT TO EXISTING/RELOCATED WATER METER (BASEMENT/CRAWLSPACE), COMPLETE | EA | 8 | 1000 | 8000
35 | CONNECT TO EXISTING/RELOCATED WATER METER (SLAB ON GRADE), COMPLETE | EA | 1 | 1250 | 1250
36 | INTERIOR WATER METER RELOCATION, COMPLETE | LF | 110 | 50 | 5500
37 | RECONNECTION OF WATER SERVICE ELECTRICAL JUMPER CABLE | EA | 9 | 500 | 4500
38 | PRIMARY ELECTRICAL GROUNDING SYSTEM INSTALLATION | EA | 9 | 1250 | 11250
39 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 3 | 3000 | 9000
40 | CONNECT TO EXISTING 16" WATER MAIN, COMPLETE | EA | 2 | 4500 | 9000
41 | WATER MAIN PROTECTION, 24" | LF | 65 | 80 | 5200
42 | WATER SERVICE PROTECTION, 2" | LF | 50 | 15 | 750
43 | WATER SERVICE PROTECTION, 4" | LF | 50 | 25 | 1250
44 | WATER MAIN LINE STOP, 8" | EA | 3 | 7500 | 22500
45 | WATER MAIN LINE STOP,16" | EA | 1 | 15500 | 15500
46 | INSERTION VALVE, COMPLETE, 8" | EA | 1 | 8500 | 8500
47 | INSERTION VALVE, COMPLETE, 16" | EA | 1 | 24500 | 24500
48 | WATER MAIN QUALITY STORM SEWER, COMPLETE, 12" | LF | 35 | 75 | 2625
49 | WATER MAIN QUALITY STORM SEWER, COMPLETE, 15" | LF | 15 | 85 | 1275
50 | EXPLORATORY EXCAVATION | SY | 25 | 75 | 1875
51 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UD | 40 | 60 | 2400
52 | PARKWAY RESTORATION | LS | 1 | 12500 | 12500
53 | PAINT PAVEMENT MARKINGS | LS | 1 | 4250 | 4250
54 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 5500 | 5500
55 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 75 | 1875
56 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 75 | 1875
57 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 | 2000 | 2000
58 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 2000 | 2000
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Northern Illinois Service |  | DPI Construction |  | N-Trak Group
City of Rockford | [5 empty] | Rockford, IL |  | Pecatonica, IL |  | Loves Park, IL
Corbin St Water Main Bid No.: 723-W-066 | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond
Vendors Notified: 112
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 7500 | 7500 | 29800 | 29800 | 50000 | 50000 | 75000 | 75000 |  | 0 |  | 0 |  | 0
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 1500 | 1500 | 4500 | 4500 | 8000 | 8000 | 10000 | 10000 |  | 0 |  | 0 |  | 0
3 | INLET AND PIPE PROTECTION | EA | 7 | 250 | 1750 | 250 | 1750 | 100 | 700 | 101 | 707 |  | 0 |  | 0 |  | 0
4 | CONCRETE TRUCK WASHOUT | LS | 1 | 750 | 750 | 850 | 850 | 650 | 650 | 506 | 506 |  | 0 |  | 0 |  | 0
5 | PAVEMENT REMOVAL | SY | 2030 | 25 | 50750 | 10 | 20300 | 3.2 | 6496 | 10 | 20300 |  | 0 |  | 0 |  | 0
6 | PAVEMENT SURFACE REMOVAL, 2" | SY | 730 | 12.5 | 9125 | 16 | 11680 | 16 | 11680 | 10 | 7300 |  | 0 |  | 0 |  | 0
7 | APPROACH PAVEMENT REMOVAL | SY | 185 | 15 | 2775 | 18 | 3330 | 45 | 8325 | 10 | 1850 |  | 0 |  | 0 |  | 0
8 | SIDEWALK REMOVAL | SF | 1800 | 1 | 1800 | 2 | 3600 | 2.6 | 4680 | 3 | 5400 |  | 0 |  | 0 |  | 0
9 | COMBINATION CURB AND GUTTER REMOVAL | LF | 605 | 15 | 9075 | 5 | 3025 | 11 | 6655 | 9 | 5445 |  | 0 |  | 0 |  | 0
10 | ROCK EXCAVATION | CY | 25 | 100 | 2500 | 250 | 6250 | 180 | 4500 | 125 | 3125 |  | 0 |  | 0 |  | 0
11 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 2 | 1250 | 2500 | 750 | 1500 | 2800 | 5600 | 1000 | 2000 |  | 0 |  | 0 |  | 0
12 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 2 | 500 | 1000 | 750 | 1500 | 2700 | 5400 | 750 | 1500 |  | 0 |  | 0 |  | 0
13 | REMOVE FIRE HYDRANT AND AUXILIARY VALVE, COMPLETE | EA | 1 | 1250 | 1250 | 750 | 750 | 2700 | 2700 | 1200 | 1200 |  | 0 |  | 0 |  | 0
14 | SANITARY MANHOLES TO BE ADJUSTED | EA | 1 | 1200 | 1200 | 1500 | 1500 | 1200 | 1200 | 1200 | 1200 |  | 0 |  | 0 |  | 0
15 | STORM MANHOLES TO BE ADJUSTED | EA | 3 | 1750 | 5250 | 1500 | 4500 | 590 | 1770 | 1000 | 3000 |  | 0 |  | 0 |  | 0
16 | PCC APPROACH PAVEMENT, 6" | SY | 105 | 100 | 10500 | 90 | 9450 | 91 | 9555 | 89 | 9345 |  | 0 |  | 0 |  | 0
17 | PCC SIDEWALK, 4" | SF | 1800 | 10 | 18000 | 11 | 19800 | 9.75 | 17550 | 9.5 | 17100 |  | 0 |  | 0 |  | 0
18 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18 (MODIFIED) | LF | 890 | 35 | 31150 | 42 | 37380 | 37 | 32930 | 35 | 31150 |  | 0 |  | 0 |  | 0
19 | DETECTABLE WARNINGS | SF | 30 | 50 | 1500 | 45 | 1350 | 46 | 1380 | 30 | 900 |  | 0 |  | 0 |  | 0
20 | AGGREGATE BASE COURSE, TYPE B, 12" (CA-6) | SY | 1180 | 15 | 17700 | 15 | 17700 | 22 | 25960 | 15 | 17700 |  | 0 |  | 0 |  | 0
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N50, 2" | TON | 335 | 108 | 36180 | 112 | 37520 | 112 | 37520 | 130 | 43550 |  | 0 |  | 0 |  | 0
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 485 | 95 | 46075 | 112 | 54320 | 122 | 59170 | 130 | 63050 |  | 0 |  | 0 |  | 0
23 | HMA APPROACH PAVEMENT, 3" | SY | 78 | 75 | 5850 | 60 | 4680 | 39 | 3042 | 60 | 4680 |  | 0 |  | 0 |  | 0
24 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 85 | 125 | 10625 | 200 | 17000 | 240 | 20400 | 265 | 22525 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 276305 |  | 294035 |  | 325863 |  | 348533
| Award to Northern Illinois Service | Total |  | As corrected | 276305 |  | 294035 |  | 325863 |  | 348533
25 | DUCTILE IRON WATER MAIN COMPLETE, 16" | LF | 595 | 225 | 133875 | 365 | 217175 | 295 | 175525 | 400 | 238000 |  | 0 |  | 0 |  | 0
26 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 3 | 3250 | 9750 | 3500 | 10500 | 4500 | 13500 | 5000 | 15000 |  | 0 |  | 0 |  | 0
27 | GATE VALVE AND VALVE BOX, COMPLETE, 16" | EA | 3 | 8500 | 25500 | 11500 | 34500 | 14500 | 43500 | 17000 | 51000 |  | 0 |  | 0 |  | 0
28 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 3 | 7500 | 22500 | 9000 | 27000 | 9250 | 27750 | 12500 | 37500 |  | 0 |  | 0 |  | 0
29 | EXTERIOR FOUNDATION ACCESS PIT | EA | 1 | 750 | 750 | 1000 | 1000 | 1400 | 1400 | 500 | 500 |  | 0 |  | 0 |  | 0
30 | PUBLIC WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 7 | 2000 | 14000 | 4500 | 31500 | 3850 | 26950 | 4000 | 28000 |  | 0 |  | 0 |  | 0
31 | PUBLIC WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 | 2500 | 2500 | 6300 | 6300 | 4250 | 4250 | 6800 | 6800 |  | 0 |  | 0 |  | 0
32 | PRIVATE WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 | 2500 | 2500 | 3500 | 3500 | 3500 | 3500 | 5300 | 5300 |  | 0 |  | 0 |  | 0
33 | PRIVATE WATER SERVICE (BORED OR PULLED), COMPLETE, 1" | LF | 140 | 105 | 14700 | 110 | 15400 | 130 | 18200 | 200 | 28000 |  | 0 |  | 0 |  | 0
34 | CONNECT TO EXISTING/RELOCATED WATER METER (BASEMENT/CRAWLSPACE), COMPLETE | EA | 8 | 1000 | 8000 | 2000 | 16000 | 670 | 5360 | 900 | 7200 |  | 0 |  | 0 |  | 0
35 | CONNECT TO EXISTING/RELOCATED WATER METER (SLAB ON GRADE), COMPLETE | EA | 1 | 1250 | 1250 | 2000 | 2000 | 900 | 900 | 1000 | 1000 |  | 0 |  | 0 |  | 0
36 | INTERIOR WATER METER RELOCATION, COMPLETE | LF | 110 | 50 | 5500 | 20 | 2200 | 50 | 5500 | 100 | 11000 |  | 0 |  | 0 |  | 0
37 | RECONNECTION OF WATER SERVICE ELECTRICAL JUMPER CABLE | EA | 9 | 500 | 4500 | 750 | 6750 | 200 | 1800 | 750 | 6750 |  | 0 |  | 0 |  | 0
38 | PRIMARY ELECTRICAL GROUNDING SYSTEM INSTALLATION | EA | 9 | 1250 | 11250 | 2125 | 19125 | 500 | 4500 | 1000 | 9000 |  | 0 |  | 0 |  | 0
39 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 3 | 3000 | 9000 | 8000 | 24000 | 2700 | 8100 | 5000 | 15000 |  | 0 |  | 0 |  | 0
40 | CONNECT TO EXISTING 16" WATER MAIN, COMPLETE | EA | 2 | 4500 | 9000 | 9500 | 19000 | 5100 | 10200 | 10000 | 20000 |  | 0 |  | 0 |  | 0
41 | WATER MAIN PROTECTION, 24" | LF | 65 | 80 | 5200 | 200 | 13000 | 295 | 19175 | 225 | 14625 |  | 0 |  | 0 |  | 0
42 | WATER SERVICE PROTECTION, 2" | LF | 50 | 15 | 750 | 20 | 1000 | 3 | 150 | 5 | 250 |  | 0 |  | 0 |  | 0
43 | WATER SERVICE PROTECTION, 4" | LF | 50 | 25 | 1250 | 25 | 1250 | 7 | 350 | 9 | 450 |  | 0 |  | 0 |  | 0
44 | WATER MAIN LINE STOP, 8" | EA | 3 | 7500 | 22500 | 4000 | 12000 | 8000 | 24000 | 6500 | 19500 |  | 0 |  | 0 |  | 0
45 | WATER MAIN LINE STOP,16" | EA | 1 | 15500 | 15500 | 12000 | 12000 | 40000 | 40000 | 25000 | 25000 |  | 0 |  | 0 |  | 0
46 | INSERTION VALVE, COMPLETE, 8" | EA | 1 | 8500 | 8500 | 5000 | 5000 | 8000 | 8000 | 10000 | 10000 |  | 0 |  | 0 |  | 0
47 | INSERTION VALVE, COMPLETE, 16" | EA | 1 | 24500 | 24500 | 27000 | 27000 | 40000 | 40000 | 50000 | 50000 |  | 0 |  | 0 |  | 0
48 | WATER MAIN QUALITY STORM SEWER, COMPLETE, 12" | LF | 35 | 75 | 2625 | 150 | 5250 | 160 | 5600 | 200 | 7000 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 631705 |  | 806485 |  | 814073 |  | 955408
| Award to Northern Illinois Service | Total |  | As corrected | 631705 |  | 806485 |  | 814073 |  | 955408
49 | WATER MAIN QUALITY STORM SEWER, COMPLETE, 15" | LF | 15 | 85 | 1275 | 200 | 3000 | 270 | 4050 | 275 | 4125 |  | 0 |  | 0 |  | 0
50 | EXPLORATORY EXCAVATION | SY | 25 | 75 | 1875 | 0.01 | 0.25 | 262 | 6550 | 100 | 2500 |  | 0 |  | 0 |  | 0
51 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UD | 40 | 60 | 2400 | 62 | 2480 | 190 | 7600 | 120 | 4800 |  | 0 |  | 0 |  | 0
52 | PARKWAY RESTORATION | LS | 1 | 12500 | 12500 | 15000 | 15000 | 6000 | 6000 | 20000 | 20000 |  | 0 |  | 0 |  | 0
53 | PAINT PAVEMENT MARKINGS | LS | 1 | 4250 | 4250 | 4500 | 4500 | 2800 | 2800 | 3500 | 3500 |  | 0 |  | 0 |  | 0
54 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 5500 | 5500 | 10000 | 10000 | 8500 | 8500 | 5000 | 5000 |  | 0 |  | 0 |  | 0
55 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 75 | 1875 | 0.01 | 0.25 | 68 | 1700 | 50 | 1250 |  | 0 |  | 0 |  | 0
56 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 75 | 1875 | 0.01 | 0.25 | 68 | 1700 | 50 | 1250 |  | 0 |  | 0 |  | 0
57 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 | 2000 | 2000 | 0.01 | 0.01 | 3500 | 3500 | 3000 | 3000 |  | 0 |  | 0 |  | 0
58 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 2000 | 2000 | 0.01 | 0.01 | 1200 | 1200 | 1500 | 1500 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 667255 |  | 841465.77 |  | 857673 |  | 1002333
| Award to Northern Illinois Service | Bid |  | As corrected | 667255 |  | 841465.77 |  | 857673 |  | 1002333
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to Northern Illinois Service | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Corbin St Water Main Bid No.: 723-W-066
Item No. | Items | Units | Quantity | Unit Price | Total
1 | MOBILIZATION | LS | 1 |  | 0
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 |  | 0
3 | INLET AND PIPE PROTECTION | EA | 7 |  | 0
4 | CONCRETE TRUCK WASHOUT | LS | 1 |  | 0
5 | PAVEMENT REMOVAL | SY | 2030 |  | 0
6 | PAVEMENT SURFACE REMOVAL, 2" | SY | 730 |  | 0
7 | APPROACH PAVEMENT REMOVAL | SY | 185 |  | 0
8 | SIDEWALK REMOVAL | SF | 1800 |  | 0
9 | COMBINATION CURB AND GUTTER REMOVAL | LF | 605 |  | 0
10 | ROCK EXCAVATION | CY | 25 |  | 0
11 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 2 |  | 0
12 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 2 |  | 0
13 | REMOVE FIRE HYDRANT AND AUXILIARY VALVE, COMPLETE | EA | 1 |  | 0
14 | SANITARY MANHOLES TO BE ADJUSTED | EA | 1 |  | 0
15 | STORM MANHOLES TO BE ADJUSTED | EA | 3 |  | 0
16 | PCC APPROACH PAVEMENT, 6" | SY | 105 |  | 0
17 | PCC SIDEWALK, 4" | SF | 1800 |  | 0
18 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18 (MODIFIED) | LF | 890 |  | 0
19 | DETECTABLE WARNINGS | SF | 30 |  | 0
20 | AGGREGATE BASE COURSE, TYPE B, 12" (CA-6) | SY | 1180 |  | 0
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N50, 2" | TON | 335 |  | 0
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 485 |  | 0
23 | HMA APPROACH PAVEMENT, 3" | SY | 78 |  | 0
24 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 85 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | DUCTILE IRON WATER MAIN COMPLETE, 16" | LF | 595 |  | 0
26 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 3 |  | 0
27 | GATE VALVE AND VALVE BOX, COMPLETE, 16" | EA | 3 |  | 0
28 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 3 |  | 0
29 | EXTERIOR FOUNDATION ACCESS PIT | EA | 1 |  | 0
30 | PUBLIC WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 7 |  | 0
31 | PUBLIC WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 |  | 0
32 | PRIVATE WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 |  | 0
33 | PRIVATE WATER SERVICE (BORED OR PULLED), COMPLETE, 1" | LF | 140 |  | 0
34 | CONNECT TO EXISTING/RELOCATED WATER METER (BASEMENT/CRAWLSPACE), COMPLETE | EA | 8 |  | 0
35 | CONNECT TO EXISTING/RELOCATED WATER METER (SLAB ON GRADE), COMPLETE | EA | 1 |  | 0
36 | INTERIOR WATER METER RELOCATION, COMPLETE | LF | 110 |  | 0
37 | RECONNECTION OF WATER SERVICE ELECTRICAL JUMPER CABLE | EA | 9 |  | 0
38 | PRIMARY ELECTRICAL GROUNDING SYSTEM INSTALLATION | EA | 9 |  | 0
39 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 3 |  | 0
40 | CONNECT TO EXISTING 16" WATER MAIN, COMPLETE | EA | 2 |  | 0
41 | WATER MAIN PROTECTION, 24" | LF | 65 |  | 0
42 | WATER SERVICE PROTECTION, 2" | LF | 50 |  | 0
43 | WATER SERVICE PROTECTION, 4" | LF | 50 |  | 0
44 | WATER MAIN LINE STOP, 8" | EA | 3 |  | 0
45 | WATER MAIN LINE STOP,16" | EA | 1 |  | 0
46 | INSERTION VALVE, COMPLETE, 8" | EA | 1 |  | 0
47 | INSERTION VALVE, COMPLETE, 16" | EA | 1 |  | 0
48 | WATER MAIN QUALITY STORM SEWER, COMPLETE, 12" | LF | 35 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | WATER MAIN QUALITY STORM SEWER, COMPLETE, 15" | LF | 15 |  | 0
50 | EXPLORATORY EXCAVATION | SY | 25 |  | 0
51 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UD | 40 |  | 0
52 | PARKWAY RESTORATION | LS | 1 |  | 0
53 | PAINT PAVEMENT MARKINGS | LS | 1 |  | 0
54 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 |  | 0
55 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 |  | 0
56 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 |  | 0
57 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 |  | 0
58 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Corbin St Water Main Bid No.: 723-W-066
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | MOBILIZATION | LS | 1 | 7500 | 7500
2 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 1500 | 1500
3 | INLET AND PIPE PROTECTION | EA | 7 | 250 | 1750
4 | CONCRETE TRUCK WASHOUT | LS | 1 | 750 | 750
5 | PAVEMENT REMOVAL | SY | 2030 | 25 | 50750
6 | PAVEMENT SURFACE REMOVAL, 2" | SY | 730 | 12.5 | 9125
7 | APPROACH PAVEMENT REMOVAL | SY | 185 | 15 | 2775
8 | SIDEWALK REMOVAL | SF | 1800 | 1 | 1800
9 | COMBINATION CURB AND GUTTER REMOVAL | LF | 605 | 15 | 9075
10 | ROCK EXCAVATION | CY | 25 | 100 | 2500
11 | REMOVE VALVE AND VALVE VAULT, COMPLETE | EA | 2 | 1250 | 2500
12 | REMOVE VALVE AND VALVE BOX, COMPLETE | EA | 2 | 500 | 1000
13 | REMOVE FIRE HYDRANT AND AUXILIARY VALVE, COMPLETE | EA | 1 | 1250 | 1250
14 | SANITARY MANHOLES TO BE ADJUSTED | EA | 1 | 1200 | 1200
15 | STORM MANHOLES TO BE ADJUSTED | EA | 3 | 1750 | 5250
16 | PCC APPROACH PAVEMENT, 6" | SY | 105 | 100 | 10500
17 | PCC SIDEWALK, 4" | SF | 1800 | 10 | 18000
18 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18 (MODIFIED) | LF | 890 | 35 | 31150
19 | DETECTABLE WARNINGS | SF | 30 | 50 | 1500
20 | AGGREGATE BASE COURSE, TYPE B, 12" (CA-6) | SY | 1180 | 15 | 17700
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N50, 2" | TON | 335 | 108 | 36180
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 485 | 95 | 46075
23 | HMA APPROACH PAVEMENT, 3" | SY | 78 | 75 | 5850
24 | DUCTILE IRON WATER MAIN COMPLETE, 8" | LF | 85 | 125 | 10625
|  |  |  | Sub Total | 276305
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Corbin St Water Main Bid No.: 723-W-066
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | DUCTILE IRON WATER MAIN COMPLETE, 16" | LF | 595 | 225 | 133875
26 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | EA | 3 | 3250 | 9750
27 | GATE VALVE AND VALVE BOX, COMPLETE, 16" | EA | 3 | 8500 | 25500
28 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | EA | 3 | 7500 | 22500
29 | EXTERIOR FOUNDATION ACCESS PIT | EA | 1 | 750 | 750
30 | PUBLIC WATER SERVICE (OPEN-CUT), COMPLETE, 1" | EA | 7 | 2000 | 14000
31 | PUBLIC WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 | 2500 | 2500
32 | PRIVATE WATER SERVICE (OPEN-CUT), COMPLETE, 2" | EA | 1 | 2500 | 2500
33 | PRIVATE WATER SERVICE (BORED OR PULLED), COMPLETE, 1" | LF | 140 | 105 | 14700
34 | CONNECT TO EXISTING/RELOCATED WATER METER (BASEMENT/CRAWLSPACE), COMPLETE | EA | 8 | 1000 | 8000
35 | CONNECT TO EXISTING/RELOCATED WATER METER (SLAB ON GRADE), COMPLETE | EA | 1 | 1250 | 1250
36 | INTERIOR WATER METER RELOCATION, COMPLETE | LF | 110 | 50 | 5500
37 | RECONNECTION OF WATER SERVICE ELECTRICAL JUMPER CABLE | EA | 9 | 500 | 4500
38 | PRIMARY ELECTRICAL GROUNDING SYSTEM INSTALLATION | EA | 9 | 1250 | 11250
39 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | EA | 3 | 3000 | 9000
40 | CONNECT TO EXISTING 16" WATER MAIN, COMPLETE | EA | 2 | 4500 | 9000
41 | WATER MAIN PROTECTION, 24" | LF | 65 | 80 | 5200
42 | WATER SERVICE PROTECTION, 2" | LF | 50 | 15 | 750
43 | WATER SERVICE PROTECTION, 4" | LF | 50 | 25 | 1250
44 | WATER MAIN LINE STOP, 8" | EA | 3 | 7500 | 22500
45 | WATER MAIN LINE STOP,16" | EA | 1 | 15500 | 15500
46 | INSERTION VALVE, COMPLETE, 8" | EA | 1 | 8500 | 8500
47 | INSERTION VALVE, COMPLETE, 16" | EA | 1 | 24500 | 24500
48 | WATER MAIN QUALITY STORM SEWER, COMPLETE, 12" | LF | 35 | 75 | 2625
|  |  |  | Sub Total | 631705
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Corbin St Water Main Bid No.: 723-W-066
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | WATER MAIN QUALITY STORM SEWER, COMPLETE, 15" | LF | 15 | 85 | 1275
50 | EXPLORATORY EXCAVATION | SY | 25 | 75 | 1875
51 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | UD | 40 | 60 | 2400
52 | PARKWAY RESTORATION | LS | 1 | 12500 | 12500
53 | PAINT PAVEMENT MARKINGS | LS | 1 | 4250 | 4250
54 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 5500 | 5500
55 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | CY | 25 | 75 | 1875
56 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | CY | 25 | 75 | 1875
57 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | LS | 1 | 2000 | 2000
58 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | EA | 1 | 2000 | 2000
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 667255
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Corbin St Water Main Bid No.: 723-W-066
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 667255
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Corbin St Water Main Bid No.: 723-W-066
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | MOBILIZATION | 1 | LS | 29800 |  | 1 |  |  | 29800
2 | CONSTRUCTION LAYOUT STAKES | 1 | LS | 4500 |  | 1 |  |  | 4500
3 | INLET AND PIPE PROTECTION | 7 | EA | 1750 |  | 7 |  |  | 250
4 | CONCRETE TRUCK WASHOUT | 1 | LS | 850 |  | 1 |  |  | 850
5 | PAVEMENT REMOVAL | 2030 | SY | 20300 |  | 2030 |  |  | 10
6 | PAVEMENT SURFACE REMOVAL, 2" | 730 | SY | 11680 |  | 730 |  |  | 16
7 | APPROACH PAVEMENT REMOVAL | 185 | SY | 3330 |  | 185 |  |  | 18
8 | SIDEWALK REMOVAL | 1800 | SF | 3600 |  | 1800 |  |  | 2
9 | COMBINATION CURB AND GUTTER REMOVAL | 605 | LF | 3025 |  | 605 |  |  | 5
10 | ROCK EXCAVATION | 25 | CY | 6250 |  | 25 |  |  | 250
11 | REMOVE VALVE AND VALVE VAULT, COMPLETE | 2 | EA | 1500 |  | 2 |  |  | 750
12 | REMOVE VALVE AND VALVE BOX, COMPLETE | 2 | EA | 1500 |  | 2 |  |  | 750
13 | REMOVE FIRE HYDRANT AND AUXILIARY VALVE, COMPLETE | 1 | EA | 750 |  | 1 |  |  | 750
14 | SANITARY MANHOLES TO BE ADJUSTED | 1 | EA | 1500 |  | 1 |  |  | 1500
15 | STORM MANHOLES TO BE ADJUSTED | 3 | EA | 4500 |  | 3 |  |  | 1500
16 | PCC APPROACH PAVEMENT, 6" | 105 | SY | 9450 |  | 105 |  |  | 90
17 | PCC SIDEWALK, 4" | 1800 | SF | 19800 |  | 1800 |  |  | 11
18 | COMBINATION CONCRETE CURB AND GUTTER,TYPE M6.18 (MODIFIED) | 890 | LF | 37380 |  | 890 |  |  | 42
19 | DETECTABLE WARNINGS | 30 | SF | 1350 |  | 30 |  |  | 45
20 | AGGREGATE BASE COURSE, TYPE B, 12" (CA-6) | 1180 | SY | 17700 |  | 1180 |  |  | 15
21 | HOT-MIX ASPHALT SURFACE COURSE, MIX D, N50, 2" | 335 | TON | 37520 |  | 335 |  |  | 112
22 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | 485 | TON | 54320 |  | 485 |  |  | 112
23 | HMA APPROACH PAVEMENT, 3" | 78 | SY | 4680 |  | 78 |  |  | 60
24 | DUCTILE IRON WATER MAIN COMPLETE, 8" | 85 | LF | 17000 |  | 85 |  |  | 200
Sub Total |  |  |  | 294035 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Corbin St Water Main Bid No.: 723-W-066
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | DUCTILE IRON WATER MAIN COMPLETE, 16" | 595 | LF | 217175 |  | 595 |  |  | 365
26 | GATE VALVE AND VALVE BOX, COMPLETE, 8" | 3 | EA | 10500 |  | 3 |  |  | 3500
27 | GATE VALVE AND VALVE BOX, COMPLETE, 16" | 3 | EA | 34500 |  | 3 |  |  | 11500
28 | FIRE HYDRANT WITH 6" VALVE AND VALVE BOX, COMPLETE | 3 | EA | 27000 |  | 3 |  |  | 9000
29 | EXTERIOR FOUNDATION ACCESS PIT | 1 | EA | 1000 |  | 1 |  |  | 1000
30 | PUBLIC WATER SERVICE (OPEN-CUT), COMPLETE, 1" | 7 | EA | 31500 |  | 7 |  |  | 4500
31 | PUBLIC WATER SERVICE (OPEN-CUT), COMPLETE, 2" | 1 | EA | 6300 |  | 1 |  |  | 6300
32 | PRIVATE WATER SERVICE (OPEN-CUT), COMPLETE, 2" | 1 | EA | 3500 |  | 1 |  |  | 3500
33 | PRIVATE WATER SERVICE (BORED OR PULLED), COMPLETE, 1" | 140 | LF | 15400 |  | 140 |  |  | 110
34 | CONNECT TO EXISTING/RELOCATED WATER METER (BASEMENT/CRAWLSPACE), COMPLETE | 8 | EA | 16000 |  | 8 |  |  | 2000
35 | CONNECT TO EXISTING/RELOCATED WATER METER (SLAB ON GRADE), COMPLETE | 1 | EA | 2000 |  | 1 |  |  | 2000
36 | INTERIOR WATER METER RELOCATION, COMPLETE | 110 | LF | 2200 |  | 110 |  |  | 20
37 | RECONNECTION OF WATER SERVICE ELECTRICAL JUMPER CABLE | 9 | EA | 6750 |  | 9 |  |  | 750
38 | PRIMARY ELECTRICAL GROUNDING SYSTEM INSTALLATION | 9 | EA | 19125 |  | 9 |  |  | 2125
39 | CONNECT TO EXISTING 8" WATER MAIN, COMPLETE | 3 | EA | 24000 |  | 3 |  |  | 8000
40 | CONNECT TO EXISTING 16" WATER MAIN, COMPLETE | 2 | EA | 19000 |  | 2 |  |  | 9500
41 | WATER MAIN PROTECTION, 24" | 65 | LF | 13000 |  | 65 |  |  | 200
42 | WATER SERVICE PROTECTION, 2" | 50 | LF | 1000 |  | 50 |  |  | 20
43 | WATER SERVICE PROTECTION, 4" | 50 | LF | 1250 |  | 50 |  |  | 25
44 | WATER MAIN LINE STOP, 8" | 3 | EA | 12000 |  | 3 |  |  | 4000
45 | WATER MAIN LINE STOP,16" | 1 | EA | 12000 |  | 1 |  |  | 12000
46 | INSERTION VALVE, COMPLETE, 8" | 1 | EA | 5000 |  | 1 |  |  | 5000
47 | INSERTION VALVE, COMPLETE, 16" | 1 | EA | 27000 |  | 1 |  |  | 27000
48 | WATER MAIN QUALITY STORM SEWER, COMPLETE, 12" | 35 | LF | 5250 |  | 35 |  |  | 150
Sub Total |  |  |  | 806485 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Corbin St Water Main Bid No.: 723-W-066
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | WATER MAIN QUALITY STORM SEWER, COMPLETE, 15" | 15 | LF | 3000 |  | 15 |  |  | 200
50 | EXPLORATORY EXCAVATION | 25 | SY | 0.25 |  | 25 |  |  | 0.01
51 | TREE REMOVAL (OVER 15 UNITS DIAMETER) | 40 | UD | 2480 |  | 40 |  |  | 62
52 | PARKWAY RESTORATION | 1 | LS | 15000 |  | 1 |  |  | 15000
53 | PAINT PAVEMENT MARKINGS | 1 | LS | 4500 |  | 1 |  |  | 4500
54 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | 1 | LS | 10000 |  | 1 |  |  | 10000
55 | NON-SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900200) | 25 | CY | 0.25 |  | 25 |  |  | 0.01
56 | SPECIAL WASTE DISPOSAL (IDOT PAY ITEM 66900205) | 25 | CY | 0.25 |  | 25 |  |  | 0.01
57 | SPECIAL WASTE PLANS AND REPORTS (IDOT PAY ITEM 66900450) | 1 | LS | 0.01 |  | 1 |  |  | 0.01
58 | SOIL DISPOSAL ANALYSIS (IDOT PAY ITEM 66900530) | 1 | EA | 0.01 |  | 1 |  |  | 0.01
Total |  |  |  | 841465.77 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: Northern Illinois Service | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Rockford, IL Bid Bond | [5 empty] | SECTION | Corbin St Water Main Bid No.: 723-W-066
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 841465.77 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Corbin St Water Main Bid No.: 723-W-066
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Northern Illinois Service
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.