## Item List
| City -Wide Street Repairs Group No. 1 - 2023 (Residential) | [41 empty] | 2021843
Summary Of Quantities |  |  | 1st Ward |  |  | 2nd Ward | 2nd Ward |  |  |  | 3rd Ward |  |  |  | 3rd Ward |  | 4th Ward |  | 8th Ward |  |  |  | 8th Ward |  |  |  | 8th Ward |  |  |  | 8th Ward |  | 11th Ward | 14th Ward | 14th Ward |  |  | Neighborhood Allocation
No. | Item | Units | 5900 Gale Lane | 2100/2200 Granchester Place | 6700/6900 Rote Road | 1600/1700 10th Avenue | 1900 10th Avenue | 1100/1200 17th Street | 2100/200 Princeton Avenue Patching | 4200/4300 Villa Wood Circle Patching | 0800/1000 B Street | 0800 Brown Hills Court | 1200/1400 Camp Avenue | 0900/1100 Luther Avenue | 0400 Napoleon Street Patching | 1900 Stoneview Trail | 3800 Badger Road | 3800 Calderwood Drive Patching | 3300/3400 Balsam Lane Patching | Bavarian Lane/ Balsam Lane Patch | 2700/2800 Colorado Avenue Patching | 3900 Dakota Lane | 3200 Darthmouth Drive | 4000 Florida Drive | 3100 Foliage Lane Patching | 3300 Holiday Drive Patching | 3500/3600 Louisiana Road | 1800 Raismore Road | 1700 Remington Way | 1500 Sexton Drive Patching | 2100 Wyoming Drive Patching | 2500 Wyoming Drive Patching | 1600 Herbert Avenue | 5800 Meadowlark Court | 1500/1700 Meadowlark Lane | 5100 Valentine Place | 2400 Eastrock Drive | 0900/1400 Easton Parkway | 1000/1400 Stony Creek Way | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. | [16 empty] | 5 | [9 empty] | 50 | [10 empty] | 100 | 155 | 30 | 4650
2 | Parkway Restoration | Lsum | 0.02 | 0.04 | 0 | 0.07 | 0.05 | 0.06 | 0 | 0 | 0.02 | 0 | 0.07 | 0.04 | 0 | 0 | 0.02 | 0.02 | 0.02 | 0.02 | 0 | 0.03 | 0.02 | 0.02 | 0 | 0 | 0.03 | 0.04 | 0.01 | 0 | 0 | 0 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.15 | 0.15 |  | 1 | 60000 | 60000
3 | Inlet and Pipe Protection | Each | 2 | 8 |  | 9 | 3 |  |  |  | 1 |  | 9 |  |  |  | 4 | 1 | 2 | 5 |  | 6 | 3 | 5 |  |  | 3 | 2 | 4 |  |  |  | 3 | 2 |  |  | 2 |  | 21 |  | 95 | 75 | 7125
4 | Aggregate Base Repair, 10" | S.Y. | 7 | 33 | 46 | 35 | 10 | 18 | 8 | 8 | 24 | 11 | 51 | 35 | 5 | 13 | 17 |  | 2 | 4 | 3 | 11 | 32 | 14 |  | 9 | 30 | 19 | 15 | 3 | 3 | 3 | 13 | 12 | 32 | 6 | 15 | 121 | 92 |  | 760 | 20 | 15200
5 | Bituminous Materials (Prime Coat) | Gal | 75 | 335 | 465 | 353 | 109 | 183 | 85 | 80 | 247 | 110 | 510 | 350 | 52 | 130 | 170 | 15 | 25 | 42 | 30 | 110 | 325 | 145 | 15 | 97 | 305 | 195 | 150 | 35 | 35 | 35 | 130 | 120 | 320 | 65 | 150 | 1210 | 920 |  | 7728 | 3 | 23184
6 | Aggregate (Prime Coat) | Tons | 7 | 33 | 46 | 35 | 10 | 18 | 8 | 8 | 24 | 11 | 51 | 35 | 5 | 13 | 17 |  | 2 | 4 | 3 | 11 | 32 | 14 |  | 9 | 30 | 19 | 15 | 3 | 3 | 3 | 13 | 12 | 32 | 6 | 15 | 121 | 92 |  | 760 | 10 | 7600
7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons |  |  |  | 150 |  | 125 | [32 empty] | 275 | 115 | 31625
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | [37 empty] | 500 | 500 | 80 | 40000
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons |  |  |  | 225 |  | 175 | [32 empty] | 400 | 80 | 32000
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 100 | 400 | 550 | 150 | 150 |  | 100 | 100 | 300 | 150 | 600 | 425 | 75 | 175 | 200 | 25 | 35 | 50 | 40 | 150 | 400 | 175 | 25 | 125 | 375 | 250 | 175 | 50 | 50 | 50 | 175 | 150 | 375 | 90 | 175 | 1500 | 1100 | 500 | 9515 | 80 | 761200
11 | Hot-Mix Asphalt, Hand Method | Tons | [36 empty] | 10 | 10 | 20 | 300 | 6000
12 | P.C.C. Approach Pavement, 6" | S.Y. |  |  |  | 52 | [7 empty] | 50 | [7 empty] | 25 |  |  |  |  | 18 | [5 empty] | 30 |  |  |  |  | 37 |  |  | 212 | 65 | 13780
13 | P.C.C. Approach Pavement, 8" | S.Y. |  |  |  |  | 28 | [32 empty] | 50 | 78 | 80 | 6240
14 | P.C.C. Sidewalk, 4" | S.F. | 450 | 1050 |  | 3125 | 1850 | 2275 |  |  | 750 |  | 7075 | 1600 |  |  | 350 | 325 | 175 | 350 |  | 875 | 350 | 550 |  |  | 950 | 1500 | 700 |  |  |  | 475 | 300 | 125 | 175 | 350 | 2750 | 2525 | 1000 | 32000 | 6 | 192000
15 | Detectable Warnings, ADA Ramps | S.F. | 30 | 60 |  | 100 | 40 |  |  |  | 10 |  | 220 | 80 |  |  | 20 | 20 | 20 | 50 |  | 80 | 20 | 40 |  |  | 100 | 100 |  |  |  |  | 20 | 20 | 10 | 20 | 20 | 130 | 60 |  | 1270 | 30 | 38100
16 | Combination Curb and Gutter Removal | L.F. | 45 | 125 |  | 190 | 110 |  |  |  | 38 |  | 350 | 200 |  |  | 50 | 45 | 45 | 70 |  | 135 | 20 | 110 |  |  | 165 | 140 | 18 |  |  |  | 100 | 60 |  | 20 | 60 | 390 | 490 | 500 | 3476 | 15 | 52140
17 | Sidewalk Removal | S.F. | 450 | 1300 |  | 3125 | 1850 | 2275 |  |  | 750 |  | 7125 | 1600 |  |  | 450 | 375 | 150 | 350 |  | 875 | 350 | 650 |  |  | 950 | 1550 |  |  |  |  | 575 | 500 | 125 | 325 | 350 | 2750 | 2525 | 1000 | 32325 | 2.5 | 80812.5
18 | Approach Pavement Removal | S.Y. |  |  |  | 52 | 28 | [6 empty] | 50 | [7 empty] | 25 |  |  |  |  | 18 | [5 empty] | 30 | [6 empty] | 50 | 253 | 25 | 6325
19 | Surface Removal, 2" | S.Y. | 750 | 3350 | 4650 | 900 | 1000 |  | 850 | 800 | 2475 | 1100 | 5100 | 3500 | 550 | 1300 | 1700 | 150 | 250 | 425 | 300 | 1100 | 3250 | 1450 | 150 | 975 | 3050 | 1950 | 1500 | 350 | 350 | 350 | 1300 | 1200 | 3200 | 650 | 1500 | 12100 | 9200 | 1000 | 73775 | 3 | 221325
20 | Surface Removal, Butt Joints | S.Y. |  |  |  | 185 | 90 | 130 | [32 empty] | 405 | 7 | 2835
21 | Concrete Surface Removal, 1.5" | S.Y. |  |  |  | 2450 |  | 1700 | [32 empty] | 4150 | 9 | 37350
22 | Hand Holes to be Adjusted | Each | [37 empty] | 1 | 1 | 2500 | 2500
23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [35 empty] | 1 |  |  | 1 | 500 | 500
24 | Manholes to be Adjusted | Each |  | 6 | 2 | 3 |  | 2 | 3 | 1 | 6 |  | 8 | 4 |  |  | 1 |  |  |  |  | 2 | 4 | 3 | 1 |  | 6 | 4 | 1 | 1 |  | 1 |  | 2 | 6 | 2 |  | 11 | 3 |  | 83 | 650 | 53950
25 | Manholes to be Adjusted with New Frame and Lid | Each | 2 |  | 1 | 2 | 2 | [5 empty] | 1 | 2 |  |  | 2 |  | 1 |  |  |  | 1 | [9 empty] | 1 |  |  |  |  | 2 |  |  | 17 | 1000 | 17000
26 | Manholes to be Reconstructed | Each | [37 empty] | 1 | 1 | 1200 | 1200
27 | Manholes to be Reconstructed with New Frame and Lid | Each | [37 empty] | 1 | 1 | 1600 | 1600
28 | Inlets to be Adjusted | Each | 2 |  |  | 3 | [7 empty] | 1 |  |  | 2 |  |  | 2 |  | 1 | [15 empty] | 2 | 1 |  | 14 | 1100 | 15400
29 | Inlets to be Adjusted with New Frame and Grate | Each |  |  |  | 1 | [6 empty] | 1 | 1 | [7 empty] | 1 | 1 |  |  |  | 1 | 2 | 4 |  |  |  | 1 | [7 empty] | 13 | 1600 | 20800
30 | Inlets to be Reconstructed | Each | [37 empty] | 1 | 1 | 1500 | 1500
31 | Inlets to be Reconstructed with New Frame and Grate | Each |  |  |  |  | 1 | [25 empty] | 1 | [7 empty] | 2 | 1800 | 3600
32 | Inlet Speicals to be Repaired | Each |  |  | 2 | [7 empty] | 1 | [25 empty] | 2 |  | 5 | 2200 | 11000
33 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 45 | 125 |  | 190 | 110 |  |  |  | 38 |  | 350 | 200 |  |  | 50 | 45 | 45 | 70 |  | 135 | 20 | 110 |  |  | 165 | 140 | 18 |  |  |  | 100 | 60 |  | 20 | 60 | 390 | 490 | 500 | 3476 | 40 | 139040
34 | Traffic Control and Protection | Lsum | 0.01 | 0.04 | 0.04 | 0.07 | 0.02 | 0.04 | 0.01 | 0.01 | 0.04 | 0.01 | 0.08 | 0.05 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.03 | 0.02 | 0.01 | 0.01 | 0.04 | 0.03 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.03 | 0.01 | 0.01 | 0.12 | 0.11 |  | 1 | 75000 | 75000
35 | Thermoplastic Pavement Markings, 4" | L.F. |  |  | 2580 | [32 empty] | 1385 |  |  | 3965 | 1.5 | 5947.5
36 | Thermoplastic Pavement Markings, 6" | L.F. |  |  | 302 | [21 empty] | 300 | [11 empty] | 288 |  | 890 | 2 | 1780
37 | Thermoplastic Pavement Markings, 12" | L.F. |  |  | 284 | [21 empty] | 228 | [13 empty] | 512 | 4 | 2048
38 | Thermoplastic Pavement Markings, 24" | L.F. |  |  | 29 | [21 empty] | 14 | [10 empty] | 66 |  |  | 109 | 6 | 654
39 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. |  |  | 229 | [35 empty] | 229 | 8 | 1832
40 | Detector Loops | L.F. |  |  | 500 | [35 empty] | 500 | 30 | 15000
41 | Speed Hump | Each | [36 empty] | 4 |  | 4 | 3000 | 12000
42 | [41 empty] | 0
43 | [41 empty] | 0
44 | [41 empty] | 0
45 | [41 empty] | 0
46 | [41 empty] | 0
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 24185 | 72170 | 93041 | 139071.5 | 50697 | 72911.5 | 13745 | 12280 | 49826 | 16710 | 173347.5 | 91550 | 8706 | 19430 | 36545 | 10482.5 | 11435 | 18371 | 5030 | 42472.5 | 57235 | 36405 | 3895 | 14236 | 74856 | 61180 | 34790 | 6645 | 5995 | 6645 | 39092.5 | 26670 | 50232.5 | 16337.5 | 28375 | 247013.5 | 213183.5 | 137050 | #VALUE!
|  |  | 2090.0102 | 6132.432 | 6054.3355 | 10040.9742 | 3259.5977 | 5031.6437 | 1199.3386 | 1132.3988 | 5539.2707 | 1177.0253 | 11290.5176 | 7006.3686 | 712.1654 | 1567.5076 | 2835.6455 | 760.5108 | 743.7759 | 1487.5517 | 477.876 | 1500.5678 | 4332.4944 | 2971.3846 | 327.2614 | 1156.5715 | 5730.793 | 3609.1724 | 2227.6087 | 544.8158 | 500.1893 | 502.0487 | 2818.9105 | 2210.8738 | 3754.2087 | 1366.6881 | 2231.3276 | 17106.8449 | 15619.2931 |  | 2021843
|  |  | 26275.0102 | 78302.432 | 99095.3355 | 149112.4742 | 53956.5977 | 77943.1437 | 14944.3386 | 13412.3988 | 55365.2707 | 17887.0253 | 184638.0176 | 98556.3686 | 9418.1654 | 20997.5076 | 39380.6455 | 11243.0108 | 12178.7759 | 19858.5517 | 5507.876 | 43973.0678 | 61567.4944 | 39376.3846 | 4222.2614 | 15392.5715 | 80586.793 | 64789.1724 | 37017.6087 | 7189.8158 | 6495.1893 | 7147.0487 | 41911.4105 | 28880.8738 | 53986.7087 | 17704.1881 | 30606.3276 | 264120.3449 | 228802.7931 |  | 2021843
|  |  | 28100 | 82450 | 81400 | 135000 | 43825 | 67650 | 16125 | 15225 | 74475 | 15825 | 151800 | 94200 | 9575 | 21075 | 38125 | 10225 | 10000 | 20000 | 6425 | 20175 | 58250 | 39950 | 4400 | 15550 | 77050 | 48525 | 29950 | 7325 | 6725 | 6750 | 37900 | 29725 | 50475 | 18375 | 30000 | 230000 | 210000 | 0 | 1842625
#REF!
|  |  | 0.01525 | 0.044746 | 0.044176 | 0.073265 | 0.023784 | 0.036714 | 0.0087511 | 0.0082627 | 0.040418 | 0.0085883 | 0.082382 | 0.051123 | 0.0051964 | 0.011437 | 0.020691 | 0.0055491 | 0.005427 | 0.010854 | 0.0034869 | 0.010949 | 0.031613 | 0.021681 | 0.0023879 | 0.008439 | 0.041815 | 0.026335 | 0.016254 | 0.0039753 | 0.0036497 | 0.0036633 | 0.020568 | 0.016132 | 0.027393 | 0.0099722 | 0.016281 | 0.12482 | 0.11397 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Rock Road Co. |  | Curran Contracting | [7 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Janesville, WI |  | Crystal Lake, IL | [7 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 1 - 2023 (Residential) | [5 empty] | Bid Bond |  | Bid Bond | [7 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 323-PW-024 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 155 | 30 | 4650 | 66 | 10230 | 65 | 10075 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 155 | 30 | 4650 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 155 | 30 | 4650 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 60000 | 60000 | 37935.5 | 37935.5 | 35000 | 35000 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 60000 | 60000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 60000 | 60000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 95 | 75 | 7125 | 58.99 | 5604.05 | 70 | 6650 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 95 | 75 | 7125 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 95 | 75 | 7125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Aggregate Base Repair, 10" | S.Y. | 760 | 20 | 15200 | 0.01 | 7.6 | 16 | 12160 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Repair, 10" | S.Y. | 760 | 20 | 15200 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Repair, 10" | S.Y. | 760 | 20 | 15200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Bituminous Materials (Prime Coat) | Gal | 7728 | 3 | 23184 | 0.01 | 77.28 | 3.65 | 28207.2 |  | 0 |  | 0 |  | 0 | 5 | Bituminous Materials (Prime Coat) | Gal | 7728 | 3 | 23184 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Bituminous Materials (Prime Coat) | Gal | 7728 | 3 | 23184 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Aggregate (Prime Coat) | Tons | 760 | 10 | 7600 | 0.01 | 7.6 | 0.01 | 7.6 |  | 0 |  | 0 |  | 0 | 6 | Aggregate (Prime Coat) | Tons | 760 | 10 | 7600 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate (Prime Coat) | Tons | 760 | 10 | 7600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | 275 | 115 | 31625 | 97.21 | 26732.75 | 125 | 34375 |  | 0 |  | 0 |  | 0 | 7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | 275 | 115 | 31625 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | 275 | 115 | 31625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000 | 78 | 39000 | 95 | 47500 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 400 | 80 | 32000 | 78 | 31200 | 90 | 36000 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 400 | 80 | 32000 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 400 | 80 | 32000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 9515 | 80 | 761200 | 78 | 742170 | 90 | 856350 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 9515 | 80 | 761200 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 9515 | 80 | 761200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Hot-Mix Asphalt, Hand Method | Tons | 20 | 300 | 6000 | 80 | 1600 | 300 | 6000 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt, Hand Method | Tons | 20 | 300 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt, Hand Method | Tons | 20 | 300 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 212 | 65 | 13780 | 85.36 | 18096.32 | 67 | 14204 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 212 | 65 | 13780 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 212 | 65 | 13780 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 78 | 80 | 6240 | 95.53 | 7451.34 | 77 | 6006 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 78 | 80 | 6240 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 78 | 80 | 6240 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 32000 | 6 | 192000 | 5.95 | 190400 | 9.5 | 304000 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 32000 | 6 | 192000 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 32000 | 6 | 192000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Detectable Warnings, ADA Ramps | S.F. | 1270 | 30 | 38100 | 28.5 | 36195 | 20 | 25400 |  | 0 |  | 0 |  | 0 | 15 | Detectable Warnings, ADA Ramps | S.F. | 1270 | 30 | 38100 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Detectable Warnings, ADA Ramps | S.F. | 1270 | 30 | 38100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Combination Curb and Gutter Removal | L.F. | 3476 | 15 | 52140 | 12.67 | 44040.92 | 10 | 34760 |  | 0 |  | 0 |  | 0 | 16 | Combination Curb and Gutter Removal | L.F. | 3476 | 15 | 52140 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Combination Curb and Gutter Removal | L.F. | 3476 | 15 | 52140 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Sidewalk Removal | S.F. | 32325 | 2.5 | 80812.5 | 1.98 | 64003.5 | 4 | 129300 |  | 0 |  | 0 |  | 0 | 17 | Sidewalk Removal | S.F. | 32325 | 2.5 | 80812.5 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Sidewalk Removal | S.F. | 32325 | 2.5 | 80812.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Approach Pavement Removal | S.Y. | 253 | 25 | 6325 | 26.24 | 6638.72 | 25 | 6325 |  | 0 |  | 0 |  | 0 | 18 | Approach Pavement Removal | S.Y. | 253 | 25 | 6325 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Approach Pavement Removal | S.Y. | 253 | 25 | 6325 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Surface Removal, 2" | S.Y. | 73775 | 3 | 221325 | 2.24 | 165256 | 4.45 | 328298.75 |  | 0 |  | 0 |  | 0 | 19 | Surface Removal, 2" | S.Y. | 73775 | 3 | 221325 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Surface Removal, 2" | S.Y. | 73775 | 3 | 221325 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Surface Removal, Butt Joints | S.Y. | 405 | 7 | 2835 | 7.3 | 2956.5 | 20 | 8100 |  | 0 |  | 0 |  | 0 | 20 | Surface Removal, Butt Joints | S.Y. | 405 | 7 | 2835 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Surface Removal, Butt Joints | S.Y. | 405 | 7 | 2835 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Concrete Surface Removal, 1.5" | S.Y. | 4150 | 9 | 37350 | 4 | 16600 | 4.45 | 18467.5 |  | 0 |  | 0 |  | 0 | 21 | Concrete Surface Removal, 1.5" | S.Y. | 4150 | 9 | 37350 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Concrete Surface Removal, 1.5" | S.Y. | 4150 | 9 | 37350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Hand Holes to be Adjusted | Each | 1 | 2500 | 2500 | 3558 | 3558 | 800 | 800 |  | 0 |  | 0 |  | 0 | 22 | Hand Holes to be Adjusted | Each | 1 | 2500 | 2500 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Hand Holes to be Adjusted | Each | 1 | 2500 | 2500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 | 271.28 | 271.28 | 275 | 275 |  | 0 |  | 0 |  | 0 | 23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Manholes to be Adjusted | Each | 83 | 650 | 53950 | 512.48 | 42535.84 | 800 | 66400 |  | 0 |  | 0 |  | 0 | 24 | Manholes to be Adjusted | Each | 83 | 650 | 53950 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Manholes to be Adjusted | Each | 83 | 650 | 53950 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 1696441.5 |  | 1492568.2 |  | 2014661.05 | [7 empty] | Page 3 | Sub |  | As read | 1696441.5 | [9 empty] | Page 1 | Sub |  | As read | 1696441.5
| Award to Rock Road Co. | Total |  | As corrected | 1696441.5 |  | 1492568.2 |  | 2014661.05 | [7 empty] | Award to Rock Road Co. | Total |  | As corrected | 1696441.5 | [9 empty] | Award to Rock Road Co. | Total |  | As corrected | 1696441.5
25 | Manholes to be Adjusted with New Frame and Lid | Each | 17 | 1000 | 17000 | 1059.75 | 18015.75 | 1100 | 18700 |  | 0 |  | 0 |  | 0 | 25 | Manholes to be Adjusted with New Frame and Lid | Each | 17 | 1000 | 17000 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Manholes to be Adjusted with New Frame and Lid | Each | 17 | 1000 | 17000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Manholes to be Reconstructed | Each | 1 | 1200 | 1200 | 1546.67 | 1546.67 | 1500 | 1500 |  | 0 |  | 0 |  | 0 | 26 | Manholes to be Reconstructed | Each | 1 | 1200 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Manholes to be Reconstructed | Each | 1 | 1200 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600 | 2123.74 | 2123.74 | 2200 | 2200 |  | 0 |  | 0 |  | 0 | 27 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Inlets to be Adjusted | Each | 14 | 1100 | 15400 | 1116.56 | 15631.84 | 1100 | 15400 |  | 0 |  | 0 |  | 0 | 28 | Inlets to be Adjusted | Each | 14 | 1100 | 15400 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Inlets to be Adjusted | Each | 14 | 1100 | 15400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Inlets to be Adjusted with New Frame and Grate | Each | 13 | 1600 | 20800 | 1581.6 | 20560.8 | 2000 | 26000 |  | 0 |  | 0 |  | 0 | 29 | Inlets to be Adjusted with New Frame and Grate | Each | 13 | 1600 | 20800 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Inlets to be Adjusted with New Frame and Grate | Each | 13 | 1600 | 20800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 | 1778.43 | 1778.43 | 2000 | 2000 |  | 0 |  | 0 |  | 0 | 30 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Inlets to be Reconstructed with New Frame and Grate | Each | 2 | 1800 | 3600 | 2158.92 | 4317.84 | 2500 | 5000 |  | 0 |  | 0 |  | 0 | 31 | Inlets to be Reconstructed with New Frame and Grate | Each | 2 | 1800 | 3600 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Inlets to be Reconstructed with New Frame and Grate | Each | 2 | 1800 | 3600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Inlet Speicals to be Repaired | Each | 5 | 2200 | 11000 | 2274.28 | 11371.4 | 2000 | 10000 |  | 0 |  | 0 |  | 0 | 32 | Inlet Speicals to be Repaired | Each | 5 | 2200 | 11000 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Inlet Speicals to be Repaired | Each | 5 | 2200 | 11000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 3476 | 40 | 139040 | 39.73 | 138101.48 | 42 | 145992 |  | 0 |  | 0 |  | 0 | 33 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 3476 | 40 | 139040 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 3476 | 40 | 139040 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | Traffic Control and Protection | Lsum | 1 | 75000 | 75000 | 34972 | 34972 | 240000 | 240000 |  | 0 |  | 0 |  | 0 | 34 | Traffic Control and Protection | Lsum | 1 | 75000 | 75000 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Traffic Control and Protection | Lsum | 1 | 75000 | 75000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | Thermoplastic Pavement Markings, 4" | L.F. | 3965 | 1.5 | 5947.5 | 1 | 3965 | 1 | 3965 |  | 0 |  | 0 |  | 0 | 35 | Thermoplastic Pavement Markings, 4" | L.F. | 3965 | 1.5 | 5947.5 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Thermoplastic Pavement Markings, 4" | L.F. | 3965 | 1.5 | 5947.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | Thermoplastic Pavement Markings, 6" | L.F. | 890 | 2 | 1780 | 1.5 | 1335 | 1.5 | 1335 |  | 0 |  | 0 |  | 0 | 36 | Thermoplastic Pavement Markings, 6" | L.F. | 890 | 2 | 1780 |  | 0 |  | 0 |  | 0 |  | 0 | 36 | Thermoplastic Pavement Markings, 6" | L.F. | 890 | 2 | 1780 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | Thermoplastic Pavement Markings, 12" | L.F. | 512 | 4 | 2048 | 3 | 1536 | 3 | 1536 |  | 0 |  | 0 |  | 0 | 37 | Thermoplastic Pavement Markings, 12" | L.F. | 512 | 4 | 2048 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | Thermoplastic Pavement Markings, 12" | L.F. | 512 | 4 | 2048 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | Thermoplastic Pavement Markings, 24" | L.F. | 109 | 6 | 654 | 6 | 654 | 6 | 654 |  | 0 |  | 0 |  | 0 | 38 | Thermoplastic Pavement Markings, 24" | L.F. | 109 | 6 | 654 |  | 0 |  | 0 |  | 0 |  | 0 | 38 | Thermoplastic Pavement Markings, 24" | L.F. | 109 | 6 | 654 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 229 | 8 | 1832 | 6 | 1374 | 6 | 1374 |  | 0 |  | 0 |  | 0 | 39 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 229 | 8 | 1832 |  | 0 |  | 0 |  | 0 |  | 0 | 39 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 229 | 8 | 1832 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | Detector Loops | L.F. | 500 | 30 | 15000 | 26.5 | 13250 | 19.69 | 9845 |  | 0 |  | 0 |  | 0 | 40 | Detector Loops | L.F. | 500 | 30 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 | 40 | Detector Loops | L.F. | 500 | 30 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | Speed Hump | Each | 4 | 3000 | 12000 | 1380.15 | 5520.6 | 4000 | 16000 |  | 0 |  | 0 |  | 0 | 41 | Speed Hump | Each | 4 | 3000 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 | 41 | Speed Hump | Each | 4 | 3000 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 2021843 |  | 1768622.75 |  | 2516162.05 | [7 empty] | Page 4 | Total |  | As read | 2021843 | [9 empty] | Page 2 | Total |  | As read | 2021843
| Award to Rock Road Co. | Bid |  | As corrected |  |  | 1768622.75 | 0 | 2516162.05 | 0 | [6 empty] | Award to Rock Road Co. | Bid |  | As corrected | #VALUE! | [9 empty] | Award to Rock Road Co. | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Rock Road Co. | Bid |  | As corrected | [12 empty] | Award to Rock Road Co. | Bid |  | As corrected | [10 empty] | Award to Rock Road Co. | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Rock Road Co. | Bid |  | As corrected | [12 empty] | Award to Rock Road Co. | Bid |  | As corrected | [10 empty] | Award to Rock Road Co. | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 1 - 2023 (Residential)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 155 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 95 |  | 0
4 | Aggregate Base Repair, 10" | S.Y. | 760 |  | 0
5 | Bituminous Materials (Prime Coat) | Gal | 7728 |  | 0
6 | Aggregate (Prime Coat) | Tons | 760 |  | 0
7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | 275 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 400 |  | 0
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 9515 |  | 0
11 | Hot-Mix Asphalt, Hand Method | Tons | 20 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 212 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 78 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 32000 |  | 0
15 | Detectable Warnings, ADA Ramps | S.F. | 1270 |  | 0
16 | Combination Curb and Gutter Removal | L.F. | 3476 |  | 0
17 | Sidewalk Removal | S.F. | 32325 |  | 0
18 | Approach Pavement Removal | S.Y. | 253 |  | 0
19 | Surface Removal, 2" | S.Y. | 73775 |  | 0
20 | Surface Removal, Butt Joints | S.Y. | 405 |  | 0
21 | Concrete Surface Removal, 1.5" | S.Y. | 4150 |  | 0
22 | Hand Holes to be Adjusted | Each | 1 |  | 0
23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 |  | 0
24 | Manholes to be Adjusted | Each | 83 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Manholes to be Adjusted with New Frame and Lid | Each | 17 |  | 0
26 | Manholes to be Reconstructed | Each | 1 |  | 0
27 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 |  | 0
28 | Inlets to be Adjusted | Each | 14 |  | 0
29 | Inlets to be Adjusted with New Frame and Grate | Each | 13 |  | 0
30 | Inlets to be Reconstructed | Each | 1 |  | 0
31 | Inlets to be Reconstructed with New Frame and Grate | Each | 2 |  | 0
32 | Inlet Speicals to be Repaired | Each | 5 |  | 0
33 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 3476 |  | 0
34 | Traffic Control and Protection | Lsum | 1 |  | 0
35 | Thermoplastic Pavement Markings, 4" | L.F. | 3965
36 | Thermoplastic Pavement Markings, 6" | L.F. | 890
37 | Thermoplastic Pavement Markings, 12" | L.F. | 512
38 | Thermoplastic Pavement Markings, 24" | L.F. | 109
39 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 229
40 | Detector Loops | L.F. | 500
41 | Speed Hump | Each | 4
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 155 | 30 | 4650
2 | Parkway Restoration | Lsum | 1 | 60000 | 60000
3 | Inlet and Pipe Protection | Each | 95 | 75 | 7125
4 | Aggregate Base Repair, 10" | S.Y. | 760 | 20 | 15200
5 | Bituminous Materials (Prime Coat) | Gal | 7728 | 3 | 23184
6 | Aggregate (Prime Coat) | Tons | 760 | 10 | 7600
7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | Tons | 275 | 115 | 31625
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 400 | 80 | 32000
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 9515 | 80 | 761200
11 | Hot-Mix Asphalt, Hand Method | Tons | 20 | 300 | 6000
12 | P.C.C. Approach Pavement, 6" | S.Y. | 212 | 65 | 13780
13 | P.C.C. Approach Pavement, 8" | S.Y. | 78 | 80 | 6240
14 | P.C.C. Sidewalk, 4" | S.F. | 32000 | 6 | 192000
15 | Detectable Warnings, ADA Ramps | S.F. | 1270 | 30 | 38100
16 | Combination Curb and Gutter Removal | L.F. | 3476 | 15 | 52140
17 | Sidewalk Removal | S.F. | 32325 | 2.5 | 80812.5
18 | Approach Pavement Removal | S.Y. | 253 | 25 | 6325
19 | Surface Removal, 2" | S.Y. | 73775 | 3 | 221325
20 | Surface Removal, Butt Joints | S.Y. | 405 | 7 | 2835
21 | Concrete Surface Removal, 1.5" | S.Y. | 4150 | 9 | 37350
22 | Hand Holes to be Adjusted | Each | 1 | 2500 | 2500
23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500
24 | Manholes to be Adjusted | Each | 83 | 650 | 53950
|  |  |  | Sub Total | 1696441.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Manholes to be Adjusted with New Frame and Lid | Each | 17 | 1000 | 17000
26 | Manholes to be Reconstructed | Each | 1 | 1200 | 1200
27 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 1600 | 1600
28 | Inlets to be Adjusted | Each | 14 | 1100 | 15400
29 | Inlets to be Adjusted with New Frame and Grate | Each | 13 | 1600 | 20800
30 | Inlets to be Reconstructed | Each | 1 | 1500 | 1500
31 | Inlets to be Reconstructed with New Frame and Grate | Each | 2 | 1800 | 3600
32 | Inlet Speicals to be Repaired | Each | 5 | 2200 | 11000
33 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 3476 | 40 | 139040
34 | Traffic Control and Protection | Lsum | 1 | 75000 | 75000
35 | Thermoplastic Pavement Markings, 4" | L.F. | 3965 | 1.5 | 5947.5
36 | Thermoplastic Pavement Markings, 6" | L.F. | 890 | 2 | 1780
37 | Thermoplastic Pavement Markings, 12" | L.F. | 512 | 4 | 2048
38 | Thermoplastic Pavement Markings, 24" | L.F. | 109 | 6 | 654
39 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 229 | 8 | 1832
40 | Detector Loops | L.F. | 500 | 30 | 15000
41 | Speed Hump | Each | 4 | 3000 | 12000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Co. | P.O. # 19305222 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: Janesville, WI Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 155 | C.Y. | 10230 |  |  |  |  | 66
2 | Parkway Restoration | 1 | Lsum | 37935.5 |  |  |  |  | 37935.5
3 | Inlet and Pipe Protection | 95 | Each | 5604.05 |  |  | 35 | Each | 58.99 | 2064.65
4 | Aggregate Base Repair, 10" | 760 | S.Y. | 7.6 |  |  |  |  | 0.01
5 | Bituminous Materials (Prime Coat) | 7728 | Gal | 77.28 |  |  |  |  | 0.01
6 | Aggregate (Prime Coat) | 760 | Tons | 7.6 |  |  |  |  | 0.01
7 | Polymerized Leveling Binder, IL-4.75, N50, 1" | 275 | Tons | 26732.75 |  |  |  |  | 97.21
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | 500 | Tons | 39000 |  |  |  |  | 78
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | 400 | Tons | 31200 |  |  |  |  | 78
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 9515 | Tons | 742170 |  |  | 1400 | Tons | 78 | 109200
11 | Hot-Mix Asphalt, Hand Method | 20 | Tons | 1600 |  |  |  |  | 80
12 | P.C.C. Approach Pavement, 6" | 212 | S.Y. | 18096.32 |  |  |  |  | 85.36
13 | P.C.C. Approach Pavement, 8" | 78 | S.Y. | 7451.34 | 1952 |  | 2030 | S.Y. | 95.53 | 193925.9
14 | P.C.C. Sidewalk, 4" | 32000 | S.F. | 190400 |  |  |  |  | 5.95
15 | Detectable Warnings, ADA Ramps | 1270 | S.F. | 36195 |  |  | 292 | S.F. | 28.5 | 8322
16 | Combination Curb and Gutter Removal | 3476 | L.F. | 44040.92 |  |  |  |  | 12.67
17 | Sidewalk Removal | 32325 | S.F. | 64003.5 |  |  | 15094 | S.F. | 1.98 | 29886.12
18 | Approach Pavement Removal | 253 | S.Y. | 6638.72 | 247 |  | 500 | S.Y. | 26.24 | 13120
19 | Surface Removal, 2" | 73775 | S.Y. | 165256 |  |  | 1498 | S.Y. | 2.24 | 3355.52
20 | Surface Removal, Butt Joints | 405 | S.Y. | 2956.5 | 14839 |  | 15244 | S.Y. | 7.3 | 111281.2
21 | Concrete Surface Removal, 1.5" | 4150 | S.Y. | 16600 |  |  | 292 | S.Y. | 4 | 1168
22 | Hand Holes to be Adjusted | 1 | Each | 3558 |  |  |  |  | 3558
23 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each | 271.28 | 18204 |  | 18205 | Each | 271.28 | 4938652.4
24 | Manholes to be Adjusted | 83 | Each | 42535.84 | 630 |  | 713 | Each | 512.48 | 365398.24
Sub Total |  |  |  | 1492568.2 | [5 empty] | 5776374.03
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Co. | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, WI Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Manholes to be Adjusted with New Frame and Lid | 17 | Each | 18015.75 |  |  |  |  | 1059.75
26 | Manholes to be Reconstructed | 1 | Each | 1546.67 |  |  |  |  | 1546.67
27 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 2123.74 |  |  |  |  | 2123.74
28 | Inlets to be Adjusted | 14 | Each | 15631.84 |  |  |  |  | 1116.56
29 | Inlets to be Adjusted with New Frame and Grate | 13 | Each | 20560.8 |  |  |  |  | 1581.6
30 | Inlets to be Reconstructed | 1 | Each | 1778.43 | 9 |  | 10 | Each | 1778.43 | 17784.3
31 | Inlets to be Reconstructed with New Frame and Grate | 2 | Each | 4317.84 |  |  |  |  | 2158.92
32 | Inlet Speicals to be Repaired | 5 | Each | 11371.4 |  |  |  |  | 2274.28
33 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 3476 | L.F. | 138101.48 |  |  |  |  | 39.73
34 | Traffic Control and Protection | 1 | Lsum | 34972 | 7 |  | 8 | Lsum | 34972 | 279776
35 | Thermoplastic Pavement Markings, 4" | 3965 | L.F. | 3965 |  |  |  |  | 1
36 | Thermoplastic Pavement Markings, 6" | 890 | L.F. | 1335 |  |  |  |  | 1.5
37 | Thermoplastic Pavement Markings, 12" | 512 | L.F. | 1536 |  |  |  |  | 3
38 | Thermoplastic Pavement Markings, 24" | 109 | L.F. | 654 |  |  | 1 | L.F. | 6 | 6
39 | Thermoplastic Pavement Markings, Letters and Symbols | 229 | S.F. | 1374 | 1089 |  | 1318 | S.F. | 6 | 7908
40 | Detector Loops | 500 | L.F. | 13250 |  |  | 0.5 | L.F. | 26.5 | 13.25
41 | Speed Hump | 4 | Each | 5520.6 |  |  |  |  | 1380.15
Total |  |  |  | 1768622.75 | [5 empty] | 6081861.58
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 6081861.58
[8 empty] | DEDUCT RETAINAGE | 10% | 608186.158
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 5473675.422
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 5473675.422
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Co. | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, WI Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 1768622.75 | [5 empty] | 6081861.58
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 6081861.58
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 6081861.58
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 6081861.58
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Co. | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, WI Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 1768622.75 | [5 empty] | 6081861.58
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 6081861.58
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 6081861.58
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 6081861.58
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Rock Road Co.
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.