## Item List
| City -Wide Street Repairs Group No. 4 - 2023 (Alleys) | [21 empty] | 477444
Summary Of Quantities |  |  | 2nd Ward |  | 3rd Ward | 5th Ward | 7th Ward |  | 11th Ward |  |  | 11th Ward | 12th Ward | 13th Ward | 13th Ward | Bike Path |  | Bike Path | Parking
No. | Item | Units | Alley 107 | Alley 688 | Alley 761 | Alley 209 | Alley 1043 | Alley 1066 | Alley 288 | Alley 463 | Alley 464 | Alley 493 | Alley 570 | Alley 1011 | Alley 1021 | Com Ed Multi-Use Path | Hulin Street Bike Path | Riverside Bike Path | West State Street/Kilburn Avenue | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. |  |  | 175 | [7 empty] | 300 | 400 |  | 50 |  | 25 | 15 |  | 965 | 40 | 38600
2 | Parkway Restoration | Lsum | 0.06 | 0.06 | 0.05 | 0.06 | 0.06 | 0.02 | 0.04 | 0.02 | 0.02 | 0.03 | 0.13 | 0.16 | 0.05 | 0.17 | 0.03 | 0.02 | 0.02 |  | 1 | 10000 | 10000
3 | Inlet and Pipe Protection | Each | [17 empty] | 1 | 1 | 100 | 100
4 | Perimeter Erosion Barrier | L.F. | [13 empty] | 685 |  |  |  |  | 685 | 3.5 | 2397.5
5 | Aggregate Base Course, Type B, CA-6, 8" | Tons | [13 empty] | 75 |  | 35 |  |  | 110 | 25 | 2750
6 | Aggregate Base Course, Type B, CA-6, 10" | Tons |  |  | 135 | [7 empty] | 475 | 615 | [5 empty] | 100 | 1325 | 25 | 33125
7 | Aggregate Base Repair, 10" | S.Y. | 52 | 65 |  | 65 | 57 | 35 | 60 | 35 | 32 | 47 |  |  | 37 |  | 27 |  |  |  | 512 | 25 | 12800
8 | Bituminous Materials (Prime Coat) | Gal | 52 | 65 | 47 | 65 | 57 | 35 | 60 | 35 | 32 | 47 | 82 | 110 | 37 | 110 | 27 | 7 |  |  | 868 | 3 | 2604
9 | Aggregate (Prime Coat) | Tons | 5 | 6 | 4 | 6 | 5 | 3 | 6 | 3 | 3 | 4 | 8 | 11 | 3 |  | 3 |  |  |  | 70 | 10 | 700
10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons |  |  | 50 | [7 empty] | 100 | 115 |  |  |  |  | 40 | 100 | 405 | 115 | 46575
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons |  |  | 50 | [7 empty] | 100 | 115 | [5 empty] | 100 | 365 | 115 | 41975
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 75 | 100 |  | 100 | 80 | 50 | 90 | 50 | 50 | 75 |  |  | 60 |  | 40 |  |  | 100 | 870 | 115 | 100050
13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 3" | Tons | [13 empty] | 300 |  | 25 |  |  | 325 | 115 | 37375
14 | Hot-Mix Asphalt, Hand Method | Tons | [17 empty] | 10 | 10 | 300 | 3000
15 | P.C.C. Approach Pavement, 8" | S.Y. | 11 |  |  | 26 | 47 | [5 empty] | 18 | 10 | [5 empty] | 50 | 162 | 85 | 13770
16 | P.C.C. Sidewalk, 4" | S.F. | 200 | 225 |  | 125 | 325 | [5 empty] | 125 | 225 |  |  | 225 |  |  | 1000 | 2450 | 9 | 22050
17 | Combination Curb and Gutter Removal | L.F. | 40 | 55 |  |  | 60 | [5 empty] | 30 | 30 |  | 20 | 25 |  |  | 100 | 360 | 20 | 7200
18 | Sidewalk Removal | S.F. | 200 | 225 |  | 125 | 325 | [5 empty] | 125 | 225 | [5 empty] | 1000 | 2225 | 2.5 | 5562.5
19 | Approach Pavement Removal | S.Y. | 11 |  |  | 26 | 47 | [5 empty] | 18 | 10 | [5 empty] | 100 | 212 | 30 | 6360
20 | Surface Removal, 2" | S.Y. | 525 | 650 |  | 650 | 575 | 350 | 600 | 350 | 325 | 475 |  |  | 375 |  | 275 |  |  | 1000 | 6150 | 6 | 36900
21 | Surface Removal, Butt Joints | S.Y. | [17 empty] | 100 | 100 | 10 | 1000
22 | Aggregate Shoulder | Tons | [17 empty] | 100 | 100 | 40 | 4000
23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [17 empty] | 1 | 1 | 500 | 500
24 | Manholes to be Adjusted | Each |  |  |  | 1 | [14 empty] | 1 | 1000 | 1000
25 | Manholes to be Adjusted with Casting | Each | [17 empty] | 1 | 1 | 1300 | 1300
26 | Combination Concrete Curb and Gutter, Type B-6.12 | L.F. | [13 empty] | 20 |  |  |  |  | 20 | 40 | 800
27 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 40 | 55 |  |  | 60 | [5 empty] | 30 | 30 |  |  | 25 |  |  | 100 | 340 | 40 | 13600
28 | Traffic Control and Protection | Lsum | 0.06 | 0.06 | 0.05 | 0.06 | 0.06 | 0.02 | 0.04 | 0.02 | 0.02 | 0.03 | 0.13 | 0.16 | 0.05 | 0.17 | 0.03 | 0.02 | 0.02 |  | 1 | 10000 | 10000
29 | Non-Special Waste Disposal | C.Y. | [13 empty] | 10 |  |  |  |  | 10 | 35 | 350
30 | Special Waste Disposal | C.Y. | [13 empty] | 10 |  |  |  |  | 10 | 45 | 450
31 | Soil Disposal Analysis | Each | [13 empty] | 1 |  |  |  |  | 1 | 1100 | 1100
32 | Special Waste Plans and Reports (Special) | Lsum | [13 empty] | 1 |  |  |  |  | 1 | 3000 | 3000
33 | Grading and Shaping Special | S.Y. | [13 empty] | 1475 |  |  |  |  | 1475 | 10 | 14750
34 | Stabilized Turf Shoulder | S.Y. | [13 empty] | 400 |  |  |  |  | 400 | 3 | 1200
35 | Subgrade Undercutting | C.Y. | [13 empty] | 10 |  |  |  |  | 10 | 50 | 500
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 20446 | 24367.5 | 23056 | 23907.5 | 28238.5 | 9260 | 16490 | 9260 | 9026 | 13431 | 55108.5 | 67002.5 | 11216 | 67052.5 | 11161 | 5171 | 5600 | 77650 | #VALUE!
|  |  | 4347.7621 | 4427.4946 | 4192.9874 | 4821.4665 | 4685.4524 | 1772.8739 | 3193.9871 | 1571.1978 | 1233.5075 | 2715.5925 | 10304.2432 | 12161.5396 | 4024.1423 | 13132.3991 | 2438.8741 | 1125.6342 | 1500.8456 |  | 477444
|  |  | 24793.7621 | 28794.9946 | 27248.9874 | 28728.9665 | 32923.9524 | 11032.8739 | 19683.9871 | 10831.1978 | 10259.5075 | 16146.5925 | 65412.7432 | 79164.0396 | 15240.1423 | 80184.8991 | 13599.8741 | 6296.6342 | 7100.8456 |  | 477444
|  |  | 23175 | 23600 | 22350 | 25700 | 24975 | 9450 | 17025 | 8375 | 6575 | 14475 | 54925 | 64825 | 21450 | 70000 | 13000 | 6000 | 8000 | 0 | 413900
#REF!
|  |  | 0.055992 | 0.057019 | 0.053999 | 0.062092 | 0.060341 | 0.022832 | 0.041133 | 0.020234 | 0.015885 | 0.034972 | 0.1327 | 0.15662 | 0.051824 | 0.16912 | 0.031409 | 0.014496 | 0.019328 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | NORWEST CONSTRUCTION |  | STENSTROM EXCAVATION |  | N-TRAK GROUP, LLC | [5 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | ROCKFORD, IL |  | ROCKFORD, IL |  | LOVES PARK, IL | [5 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 4 - 2023 (Alleys) | [5 empty] | BID BOND |  | BID BOND |  | BID BOND | [5 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 623-PW-059 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 965 | 40 | 38600 | 32.25 | 31121.25 | 36 | 34740 | 35 | 33775 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 965 | 40 | 38600 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 965 | 40 | 38600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 | 7700 | 7700 | 6081 | 6081 | 9000 | 9000 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 1 | 100 | 100 | 125 | 125 | 131 | 131 | 125 | 125 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 1 | 100 | 100 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 1 | 100 | 100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Perimeter Erosion Barrier | L.F. | 685 | 3.5 | 2397.5 | 3.25 | 2226.25 | 3.5 | 2397.5 | 3.25 | 2226.25 |  | 0 |  | 0 | 4 | Perimeter Erosion Barrier | L.F. | 685 | 3.5 | 2397.5 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Perimeter Erosion Barrier | L.F. | 685 | 3.5 | 2397.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Aggregate Base Course, Type B, CA-6, 8" | Tons | 110 | 25 | 2750 | 18 | 1980 | 32.5 | 3575 | 38 | 4180 |  | 0 |  | 0 | 5 | Aggregate Base Course, Type B, CA-6, 8" | Tons | 110 | 25 | 2750 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Aggregate Base Course, Type B, CA-6, 8" | Tons | 110 | 25 | 2750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 1325 | 25 | 33125 | 18 | 23850 | 34 | 45050 | 29 | 38425 |  | 0 |  | 0 | 6 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 1325 | 25 | 33125 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 1325 | 25 | 33125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Aggregate Base Repair, 10" | S.Y. | 512 | 25 | 12800 | 0.01 | 5.12 | 0.01 | 5.12 | 0.01 | 5.12 |  | 0 |  | 0 | 7 | Aggregate Base Repair, 10" | S.Y. | 512 | 25 | 12800 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Aggregate Base Repair, 10" | S.Y. | 512 | 25 | 12800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Bituminous Materials (Prime Coat) | Gal | 868 | 3 | 2604 | 0.01 | 8.68 | 0.01 | 8.68 | 4.5 | 3906 |  | 0 |  | 0 | 8 | Bituminous Materials (Prime Coat) | Gal | 868 | 3 | 2604 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Bituminous Materials (Prime Coat) | Gal | 868 | 3 | 2604 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Aggregate (Prime Coat) | Tons | 70 | 10 | 700 | 0.01 | 0.7 | 0.01 | 0.7 | 0.01 | 0.7 |  | 0 |  | 0 | 9 | Aggregate (Prime Coat) | Tons | 70 | 10 | 700 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Aggregate (Prime Coat) | Tons | 70 | 10 | 700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 405 | 115 | 46575 | 115.45 | 46757.25 | 136 | 55080 | 140 | 56700 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 405 | 115 | 46575 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 405 | 115 | 46575 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 365 | 115 | 41975 | 115.45 | 42139.25 | 129 | 47085 | 140 | 51100 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 365 | 115 | 41975 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 365 | 115 | 41975 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 870 | 115 | 100050 | 115.45 | 100441.5 | 126 | 109620 | 140 | 121800 |  | 0 |  | 0 | 12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 870 | 115 | 100050 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 870 | 115 | 100050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 3" | Tons | 325 | 115 | 37375 | 115.45 | 37521.25 | 116 | 37700 | 140 | 45500 |  | 0 |  | 0 | 13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 3" | Tons | 325 | 115 | 37375 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 3" | Tons | 325 | 115 | 37375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 | 350 | 3500 | 450 | 4500 | 355 | 3550 |  | 0 |  | 0 | 14 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | P.C.C. Approach Pavement, 8" | S.Y. | 162 | 85 | 13770 | 91 | 14742 | 78.25 | 12676.5 | 96 | 15552 |  | 0 |  | 0 | 15 | P.C.C. Approach Pavement, 8" | S.Y. | 162 | 85 | 13770 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | P.C.C. Approach Pavement, 8" | S.Y. | 162 | 85 | 13770 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | P.C.C. Sidewalk, 4" | S.F. | 2450 | 9 | 22050 | 8.75 | 21437.5 | 8 | 19600 | 8 | 19600 |  | 0 |  | 0 | 16 | P.C.C. Sidewalk, 4" | S.F. | 2450 | 9 | 22050 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | P.C.C. Sidewalk, 4" | S.F. | 2450 | 9 | 22050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Combination Curb and Gutter Removal | L.F. | 360 | 20 | 7200 | 12 | 4320 | 14.5 | 5220 | 15 | 5400 |  | 0 |  | 0 | 17 | Combination Curb and Gutter Removal | L.F. | 360 | 20 | 7200 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Combination Curb and Gutter Removal | L.F. | 360 | 20 | 7200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Sidewalk Removal | S.F. | 2225 | 2.5 | 5562.5 | 2.1 | 4672.5 | 2 | 4450 | 2.25 | 5006.25 |  | 0 |  | 0 | 18 | Sidewalk Removal | S.F. | 2225 | 2.5 | 5562.5 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Sidewalk Removal | S.F. | 2225 | 2.5 | 5562.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Approach Pavement Removal | S.Y. | 212 | 30 | 6360 | 22 | 4664 | 28 | 5936 | 30 | 6360 |  | 0 |  | 0 | 19 | Approach Pavement Removal | S.Y. | 212 | 30 | 6360 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Approach Pavement Removal | S.Y. | 212 | 30 | 6360 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Surface Removal, 2" | S.Y. | 6150 | 6 | 36900 | 8.95 | 55042.5 | 6.5 | 39975 | 8.25 | 50737.5 |  | 0 |  | 0 | 20 | Surface Removal, 2" | S.Y. | 6150 | 6 | 36900 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Surface Removal, 2" | S.Y. | 6150 | 6 | 36900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Surface Removal, Butt Joints | S.Y. | 100 | 10 | 1000 | 3 | 300 | 34.75 | 3475 | 11 | 1100 |  | 0 |  | 0 | 21 | Surface Removal, Butt Joints | S.Y. | 100 | 10 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Surface Removal, Butt Joints | S.Y. | 100 | 10 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Aggregate Shoulder | Tons | 100 | 40 | 4000 | 1 | 100 | 34.75 | 3475 | 30 | 3000 |  | 0 |  | 0 | 22 | Aggregate Shoulder | Tons | 100 | 40 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Aggregate Shoulder | Tons | 100 | 40 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 | 275 | 275 | 515 | 515 | 500 | 500 |  | 0 |  | 0 | 23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Manholes to be Adjusted | Each | 1 | 1000 | 1000 | 800 | 800 | 1305 | 1305 | 1500 | 1500 |  | 0 |  | 0 | 24 | Manholes to be Adjusted | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Manholes to be Adjusted | Each | 1 | 1000 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 430394 |  | 403729.75 |  | 442601.5 |  | 479048.82 | [5 empty] | Page 3 | Sub |  | As read | 430394 | [9 empty] | Page 1 | Sub |  | As read | 430394
| Award to NORWEST CONSTRUCTION | Total |  | As corrected | 430394 |  | 403729.75 |  | 442601.5 |  | 479048.82 | [5 empty] | Award to NORWEST CONSTRUCTION | Total |  | As corrected | 430394 | [9 empty] | Award to NORWEST CONSTRUCTION | Total |  | As corrected | 430394
25 | Manholes to be Adjusted with Casting | Each | 1 | 1300 | 1300 | 1300 | 1300 | 1455 | 1455 | 1800 | 1800 |  | 0 |  | 0 | 25 | Manholes to be Adjusted with Casting | Each | 1 | 1300 | 1300 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Manholes to be Adjusted with Casting | Each | 1 | 1300 | 1300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Combination Concrete Curb and Gutter, Type B-6.12 | L.F. | 20 | 40 | 800 | 34.75 | 695 | 57.5 | 1150 | 47 | 940 |  | 0 |  | 0 | 26 | Combination Concrete Curb and Gutter, Type B-6.12 | L.F. | 20 | 40 | 800 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Combination Concrete Curb and Gutter, Type B-6.12 | L.F. | 20 | 40 | 800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 340 | 40 | 13600 | 34.75 | 11815 | 34 | 11560 | 47 | 15980 |  | 0 |  | 0 | 27 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 340 | 40 | 13600 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 340 | 40 | 13600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Traffic Control and Protection | Lsum | 1 | 10000 | 10000 | 8200 | 8200 | 6232 | 6232 | 30000 | 30000 |  | 0 |  | 0 | 28 | Traffic Control and Protection | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Traffic Control and Protection | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Non-Special Waste Disposal | C.Y. | 10 | 35 | 350 | 105 | 1050 | 110 | 1100 | 67 | 670 |  | 0 |  | 0 | 29 | Non-Special Waste Disposal | C.Y. | 10 | 35 | 350 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Non-Special Waste Disposal | C.Y. | 10 | 35 | 350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Special Waste Disposal | C.Y. | 10 | 45 | 450 | 105 | 1050 | 118 | 1180 | 67 | 670 |  | 0 |  | 0 | 30 | Special Waste Disposal | C.Y. | 10 | 45 | 450 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Special Waste Disposal | C.Y. | 10 | 45 | 450 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Soil Disposal Analysis | Each | 1 | 1100 | 1100 | 1180 | 1180 | 1240 | 1240 | 1180 | 1180 |  | 0 |  | 0 | 31 | Soil Disposal Analysis | Each | 1 | 1100 | 1100 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Soil Disposal Analysis | Each | 1 | 1100 | 1100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Special Waste Plans and Reports (Special) | Lsum | 1 | 3000 | 3000 | 2900 | 2900 | 3040 | 3040 | 2900 | 2900 |  | 0 |  | 0 | 32 | Special Waste Plans and Reports (Special) | Lsum | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Special Waste Plans and Reports (Special) | Lsum | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Grading and Shaping Special | S.Y. | 1475 | 10 | 14750 | 2.25 | 3318.75 | 5 | 7375 | 3.25 | 4793.75 |  | 0 |  | 0 | 33 | Grading and Shaping Special | S.Y. | 1475 | 10 | 14750 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Grading and Shaping Special | S.Y. | 1475 | 10 | 14750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | Stabilized Turf Shoulder | S.Y. | 400 | 3 | 1200 | 11.25 | 4500 | 11.8 | 4720 | 12.5 | 5000 |  | 0 |  | 0 | 34 | Stabilized Turf Shoulder | S.Y. | 400 | 3 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Stabilized Turf Shoulder | S.Y. | 400 | 3 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | Subgrade Undercutting | C.Y. | 10 | 50 | 500 | 50 | 500 | 132 | 1320 | 80 | 800 |  | 0 |  | 0 | 35 | Subgrade Undercutting | C.Y. | 10 | 50 | 500 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Subgrade Undercutting | C.Y. | 10 | 50 | 500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 477444 |  | 440884.72 |  | 482973.5 |  | 543782.57 | [5 empty] | Page 4 | Total |  | As read | 477444 | [9 empty] | Page 2 | Total |  | As read | 477444
| Award to NORWEST CONSTRUCTION | Bid |  | As corrected |  |  | 440238.5 | 0 | 482973.5 | 0 | 543782.57 | [5 empty] | Award to NORWEST CONSTRUCTION | Bid |  | As corrected | #VALUE! | [9 empty] | Award to NORWEST CONSTRUCTION | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to NORWEST CONSTRUCTION | Bid |  | As corrected | [12 empty] | Award to NORWEST CONSTRUCTION | Bid |  | As corrected | [10 empty] | Award to NORWEST CONSTRUCTION | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to NORWEST CONSTRUCTION | Bid |  | As corrected | [12 empty] | Award to NORWEST CONSTRUCTION | Bid |  | As corrected | [10 empty] | Award to NORWEST CONSTRUCTION | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 4 - 2023 (Alleys)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 965 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 1 |  | 0
4 | Perimeter Erosion Barrier | L.F. | 685 |  | 0
5 | Aggregate Base Course, Type B, CA-6, 8" | Tons | 110 |  | 0
6 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 1325 |  | 0
7 | Aggregate Base Repair, 10" | S.Y. | 512 |  | 0
8 | Bituminous Materials (Prime Coat) | Gal | 868 |  | 0
9 | Aggregate (Prime Coat) | Tons | 70 |  | 0
10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 405 |  | 0
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 365 |  | 0
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 870 |  | 0
13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 3" | Tons | 325 |  | 0
14 | Hot-Mix Asphalt, Hand Method | Tons | 10 |  | 0
15 | P.C.C. Approach Pavement, 8" | S.Y. | 162 |  | 0
16 | P.C.C. Sidewalk, 4" | S.F. | 2450 |  | 0
17 | Combination Curb and Gutter Removal | L.F. | 360 |  | 0
18 | Sidewalk Removal | S.F. | 2225 |  | 0
19 | Approach Pavement Removal | S.Y. | 212 |  | 0
20 | Surface Removal, 2" | S.Y. | 6150 |  | 0
21 | Surface Removal, Butt Joints | S.Y. | 100 |  | 0
22 | Aggregate Shoulder | Tons | 100 |  | 0
23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 |  | 0
24 | Manholes to be Adjusted | Each | 1 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Manholes to be Adjusted with Casting | Each | 1 |  | 0
26 | Combination Concrete Curb and Gutter, Type B-6.12 | L.F. | 20
27 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 340
28 | Traffic Control and Protection | Lsum | 1
29 | Non-Special Waste Disposal | C.Y. | 10
30 | Special Waste Disposal | C.Y. | 10
31 | Soil Disposal Analysis | Each | 1
32 | Special Waste Plans and Reports (Special) | Lsum | 1
33 | Grading and Shaping Special | S.Y. | 1475
34 | Stabilized Turf Shoulder | S.Y. | 400
35 | Subgrade Undercutting | C.Y. | 10
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2023 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 965 | 40 | 38600
2 | Parkway Restoration | Lsum | 1 | 10000 | 10000
3 | Inlet and Pipe Protection | Each | 1 | 100 | 100
4 | Perimeter Erosion Barrier | L.F. | 685 | 3.5 | 2397.5
5 | Aggregate Base Course, Type B, CA-6, 8" | Tons | 110 | 25 | 2750
6 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 1325 | 25 | 33125
7 | Aggregate Base Repair, 10" | S.Y. | 512 | 25 | 12800
8 | Bituminous Materials (Prime Coat) | Gal | 868 | 3 | 2604
9 | Aggregate (Prime Coat) | Tons | 70 | 10 | 700
10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 405 | 115 | 46575
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 365 | 115 | 41975
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 870 | 115 | 100050
13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 3" | Tons | 325 | 115 | 37375
14 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000
15 | P.C.C. Approach Pavement, 8" | S.Y. | 162 | 85 | 13770
16 | P.C.C. Sidewalk, 4" | S.F. | 2450 | 9 | 22050
17 | Combination Curb and Gutter Removal | L.F. | 360 | 20 | 7200
18 | Sidewalk Removal | S.F. | 2225 | 2.5 | 5562.5
19 | Approach Pavement Removal | S.Y. | 212 | 30 | 6360
20 | Surface Removal, 2" | S.Y. | 6150 | 6 | 36900
21 | Surface Removal, Butt Joints | S.Y. | 100 | 10 | 1000
22 | Aggregate Shoulder | Tons | 100 | 40 | 4000
23 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500
24 | Manholes to be Adjusted | Each | 1 | 1000 | 1000
|  |  |  | Sub Total | 430394
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2023 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Manholes to be Adjusted with Casting | Each | 1 | 1300 | 1300
26 | Combination Concrete Curb and Gutter, Type B-6.12 | L.F. | 20 | 40 | 800
27 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 340 | 40 | 13600
28 | Traffic Control and Protection | Lsum | 1 | 10000 | 10000
29 | Non-Special Waste Disposal | C.Y. | 10 | 35 | 350
30 | Special Waste Disposal | C.Y. | 10 | 45 | 450
31 | Soil Disposal Analysis | Each | 1 | 1100 | 1100
32 | Special Waste Plans and Reports (Special) | Lsum | 1 | 3000 | 3000
33 | Grading and Shaping Special | S.Y. | 1475 | 10 | 14750
34 | Stabilized Turf Shoulder | S.Y. | 400 | 3 | 1200
35 | Subgrade Undercutting | C.Y. | 10 | 50 | 500
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2023 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2023 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: NORWEST CONSTRUCTION | P.O. #18305125 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: ROCKFORD, IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2023 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 965 | C.Y. | 31121.25 |  |  |  |  | 32.25
2 | Parkway Restoration | 1 | Lsum | 7700 |  |  |  |  | 7700
3 | Inlet and Pipe Protection | 1 | Each | 125 |  |  |  |  | 125
4 | Perimeter Erosion Barrier | 685 | L.F. | 2226.25 |  |  |  |  | 3.25
5 | Aggregate Base Course, Type B, CA-6, 8" | 110 | Tons | 1980 |  |  |  |  | 18
6 | Aggregate Base Course, Type B, CA-6, 10" | 1325 | Tons | 23850 |  |  |  |  | 18
7 | Aggregate Base Repair, 10" | 512 | S.Y. | 5.12 |  |  |  |  | 0.01
8 | Bituminous Materials (Prime Coat) | 868 | Gal | 8.68 |  |  |  |  | 0.01
9 | Aggregate (Prime Coat) | 70 | Tons | 0.7 |  |  |  |  | 0.01
10 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | 405 | Tons | 46757.25 |  |  |  |  | 115.45
11 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | 365 | Tons | 42139.25 |  |  |  |  | 115.45
12 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 870 | Tons | 100441.5 |  |  |  |  | 115.45
13 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 3" | 325 | Tons | 37521.25 |  |  |  |  | 115.45
14 | Hot-Mix Asphalt, Hand Method | 10 | Tons | 3500 |  |  |  |  | 350
15 | P.C.C. Approach Pavement, 8" | 162 | S.Y. | 14742 |  |  |  |  | 91
16 | P.C.C. Sidewalk, 4" | 2450 | S.F. | 21437.5 |  |  |  |  | 8.75
17 | Combination Curb and Gutter Removal | 360 | L.F. | 4320 |  |  |  |  | 12
18 | Sidewalk Removal | 2225 | S.F. | 4672.5 |  |  |  |  | 2.1
19 | Approach Pavement Removal | 212 | S.Y. | 4664 |  |  |  |  | 22
20 | Surface Removal, 2" | 6150 | S.Y. | 55042.5 |  |  |  |  | 8.95
21 | Surface Removal, Butt Joints | 100 | S.Y. | 300 |  |  |  |  | 3
22 | Aggregate Shoulder | 100 | Tons | 100 |  |  |  |  | 1
23 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each | 275 |  |  |  |  | 275
24 | Manholes to be Adjusted | 1 | Each | 800 |  |  |  |  | 800
Sub Total |  |  |  | 403729.75 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: NORWEST CONSTRUCTION | [5 empty] | MUNICIPALITY | City of Rockford
| Address: ROCKFORD, IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2023 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Manholes to be Adjusted with Casting | 1 | Each | 1300 |  |  |  |  | 1300
26 | Combination Concrete Curb and Gutter, Type B-6.12 | 20 | L.F. | 695 |  |  |  |  | 34.75
27 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 340 | L.F. | 11815 |  |  |  |  | 34.75
28 | Traffic Control and Protection | 1 | Lsum | 8200 |  |  |  |  | 8200
29 | Non-Special Waste Disposal | 10 | C.Y. | 1050 |  |  |  |  | 105
30 | Special Waste Disposal | 10 | C.Y. | 1050 |  |  |  |  | 105
31 | Soil Disposal Analysis | 1 | Each | 1180 |  |  |  |  | 1180
32 | Special Waste Plans and Reports (Special) | 1 | Lsum | 2900 |  |  |  |  | 2900
33 | Grading and Shaping Special | 1475 | S.Y. | 3318.75 |  |  |  |  | 2.25
34 | Stabilized Turf Shoulder | 400 | S.Y. | 4500 |  |  |  |  | 11.25
35 | Subgrade Undercutting | 10 | C.Y. | 500 |  |  |  |  | 50
Total |  |  |  | 440238.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
[8 empty] | DEDUCT RETAINAGE | 10% | 0
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: NORWEST CONSTRUCTION | [5 empty] | MUNICIPALITY | City of Rockford
| Address: ROCKFORD, IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2023 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 440238.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 23rd, 2019 to October 18th, 2019 | [7 empty] | (Road District)
| Payable to: NORWEST CONSTRUCTION | [5 empty] | MUNICIPALITY | City of Rockford
| Address: ROCKFORD, IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2023 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 440238.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | NORWEST CONSTRUCTION
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.