## Item List
1268765
No. | Item | Unit | Quant. | Unit Price | Total
1 | UNDERCUT AND BACKFILL UNSUITABLE SUBGRADE | C.Y. | 50 | 25 | 1250
2 | EX. TREE REMOVAL | DIA. | 62 | 25 | 1550
3 | EX. DETECTOR LOOP TO BE REPLACED | LSUM | 2 | 500 | 1000
4 | EX. PAY PHONE, CONCRETE BASE & 4 BOLLARDS TO BE REMOVED | EACH | 1 | 1000 | 1000
5 | REMOVE EX. FENCE | FT. | 8 | 5 | 40
6 | REMOVE & REPLACE EX. FENCE | FT. | 280 | 20 | 5600
7 | PAVEMENT MARKING TO BE REMOVED | FT. | 8 | 2 | 16
8 | REMOVE & REPLACE GUARDRAIL | FT. | 25 | 50 | 1250
9 | METAL GUARDRAIL | FT. | 10 | 50 | 500
10 | HMA SURFACE REMOVAL VARIABLE DEPTH (2.0"-3.0") | S.Y. | 15325 | 4 | 61300
11 | CLASS B PATCH, TYPE I | S.Y. | 200 | 200 | 40000
12 | CLASS B PATCH, TYPE II | S.Y. | 200 | 140 | 28000
13 | CLASS B PATCH, TYPE III | S.Y. | 200 | 120 | 24000
14 | CLASS B PATCH, TYPE IV | S.Y. | 200 | 100 | 20000
15 | HMA FULL DEPTH REMOVAL (AGG. INCLUDED) | S.Y. | 1201 | 6 | 7206
16 | SIDEWALK REMOVAL | S.F. | 21090 | 1 | 21090
17 | EX. CONCRETE SPILLWAY TO BE REMOVED | EACH | 1 | 50 | 50
18 | COMBINATION CONCRETE CURB & GUTTER REMOVAL | FT. | 7346 | 10 | 73460
19 | GRIND CURB TO DEPRESS | FT. | 10 | 10 | 100
20 | DRIVEWAY PAVEMENT REMOVAL CONCRETE | S.Y. | 978 | 5 | 4890
21 | DRIVEWAY PAVEMENT REMOVAL HMA | S.Y. | 781 | 5 | 3905
22 | DRIVEWAY PAVEMENT REMOVAL AGGREGATE | S.Y. | 107 | 5 | 535
23 | EX. STORM INLET TO BE ADJUSTED | EACH | 24 | 500 | 12000
24 | CONNECTION TO EX INLET | EACH | 1 | 2500 | 2500
25 | EX. STORM MANHOLE TO BE ADJUSTED | EACH | 13 | 500 | 6500
26 | ADJUST EXISTING VALVE & VAULT | EACH | 20 | 500 | 10000
27 | EX. HANDHOLE TO BE ADJUSTED | EACH | 1 | 500 | 500
28 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 15 | 500 | 7500
29 | EX. SIGN TO BE RELOCATED | EACH | 4 | 250 | 1000
30 | TRAFFIC CONTROL AND PROTECTION | LSUM | 1 | 25000 | 25000
31 | PERIMETER EROSION CONTROL BARRIER | FT. | 458 | 3 | 1374
32 | INLET PROTECTION | EACH | 35 | 250 | 8750
33 | TEMPORARY EROSION AND SEDIMENT CONTROL MAINT. | LSUM | 1 | 7500 | 7500
34 | 4" TOPSOIL, CLASS 1A SEEDING & EROSION CONTROL BLANKET | S.Y. | 1772 | 5 | 8860
35 | CONSTRUCTION LAYOUT | LSUM | 1 | 40000 | 40000
36 | COMPACTED AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | S.Y. | 1200 | 8 | 9600
37 | SUBBASE GRANULAR MATERIAL TYPE B, CA-2, 6" | S.Y. | 1200 | 8 | 9600
38 | AGGREGATE BASE COURSE, TYPE B, 8" | S.Y. | 564 | 12 | 6768
39 | AGGREGATE SURFACE COURSE, TYPE A, 6" | S.Y. | 87 | 8 | 696
40 | HMA SURFACE COURSE, MIX "D", N50 | TON | 2191 | 90 | 197190
41 | HMA BINDER COURSE, N50, 1.5" | TON | 47 | 90 | 4230
42 | HMA BINDER COURSE, IL-19.0, N50, 4” | TON | 269 | 90 | 24210
43 | COMBINATION CONCRETE CURB AND GUTTER, MODIFIED TYPE M 6.18 | FT. | 7404 | 25 | 185100
44 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" (6" THRU DRIVEWAY) | S.F. | 40395 | 8 | 323160
45 | DETECTABLE WARNINGS | S.F. | 616 | 35 | 21560
46 | P.C. CONCRETE DRIVEWAY PAVEMENT, 6" | S.Y. | 581 | 50 | 29050
47 | THERMOPLASTIC PAVEMENT MARKING – LINE 24” WHITE | FT. | 350 | 5 | 1750
48 | THERMOPLASTIC PAVEMENT MARKING – LINE 8” WHITE | FT. | 59 | 3 | 177
49 | THERMOPLASTIC PAVEMENT MARKING – LINE 6” WHITE | FT. | 1419 | 2 | 2838
50 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" WHITE | FT. | 6434 | 2 | 12868
51 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" YELLOW | FT. | 2288 | 2 | 4576
52 | PAINT PAVEMEMENT MARKING - LINE 24" WHITE | FT. | 22 | 5 | 110
53 | PAINT PAVEMEMENT MARKING - LINE 6" WHITE | FT. | 118 | 2 | 236
54 | THERMOPLASTIC PAVEMENET MARKING - RR SYMBOL | EACH | 2 | 500 | 1000
55 | RCP STORM SEWER, 12" | FT. | 33 | 40 | 1320
56 | 2' DIA. STORM INLET TYPE A | EACH | 1 | 2000 | 2000
57 | STORM INLET 700 | EACH | 1 | 2500 | 2500
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | NTRAK Group |  | Stenstrom Excavation |  | Sjostrom & Sons / DPI Construction
City of Rockford | [5 empty] | Loves Park, IL 61111 |  | Rockford IL 61108 |  | Rockford IL 61104
BROOKE ROAD IMPROVEMENTS
BID NO. 623-PW-062
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | UNDERCUT AND BACKFILL UNSUITABLE SUBGRADE | C.Y. | 50 | 25 | 1250 | 75 | 3750 | 145 | 7250 | 96.17 | 4808.5 |  | 0 |  | 0 |  | 0
2 | EX. TREE REMOVAL | DIA. | 62 | 25 | 1550 | 125 | 7750 | 68.15 | 4225.3 | 139.05 | 8621.1 |  | 0 |  | 0 |  | 0
3 | EX. DETECTOR LOOP TO BE REPLACED | LSUM | 2 | 500 | 1000 | 7000 | 14000 | 7075 | 14150 | 9269.95 | 18539.9 |  | 0 |  | 0 |  | 0
4 | EX. PAY PHONE, CONCRETE BASE & 4 BOLLARDS TO BE REMOVED | EACH | 1 | 1000 | 1000 | 250 | 250 | 1207.08 | 1207.08 | 521.44 | 521.44 |  | 0 |  | 0 |  | 0
5 | REMOVE EX. FENCE | FT. | 8 | 5 | 40 | 60 | 480 | 63 | 504 | 23.17 | 185.36 |  | 0 |  | 0 |  | 0
6 | REMOVE & REPLACE EX. FENCE | FT. | 280 | 20 | 5600 | 60 | 16800 | 63 | 17640 | 69.52 | 19465.6 |  | 0 |  | 0 |  | 0
7 | PAVEMENT MARKING TO BE REMOVED | FT. | 8 | 2 | 16 | 52 | 416 | 52.4 | 419.2 | 57.93 | 463.44 |  | 0 |  | 0 |  | 0
8 | REMOVE & REPLACE GUARDRAIL | FT. | 25 | 50 | 1250 | 120 | 3000 | 227.56 | 5689 | 251.58 | 6289.5 |  | 0 |  | 0 |  | 0
9 | METAL GUARDRAIL | FT. | 10 | 50 | 500 | 140 | 1400 | 227.56 | 2275.6 | 107.07 | 1070.7 |  | 0 |  | 0 |  | 0
10 | HMA SURFACE REMOVAL VARIABLE DEPTH (2.0"-3.0") | S.Y. | 15325 | 4 | 61300 | 2.7 | 41377.5 | 2.9 | 44442.5 | 2.99 | 45821.75 |  | 0 |  | 0 |  | 0
11 | CLASS B PATCH, TYPE I | S.Y. | 200 | 200 | 40000 | 142 | 28400 | 184 | 36800 | 200 | 40000 |  | 0 |  | 0 |  | 0
12 | CLASS B PATCH, TYPE II | S.Y. | 200 | 140 | 28000 | 142 | 28400 | 178 | 35600 | 200 | 40000 |  | 0 |  | 0 |  | 0
13 | CLASS B PATCH, TYPE III | S.Y. | 200 | 120 | 24000 | 145 | 29000 | 178 | 35600 | 175 | 35000 |  | 0 |  | 0 |  | 0
14 | CLASS B PATCH, TYPE IV | S.Y. | 200 | 100 | 20000 | 145 | 29000 | 171 | 34200 | 175 | 35000 |  | 0 |  | 0 |  | 0
15 | HMA FULL DEPTH REMOVAL (AGG. INCLUDED) | S.Y. | 1201 | 6 | 7206 | 12 | 14412 | 32.25 | 38732.25 | 23.17 | 27827.17 |  | 0 |  | 0 |  | 0
16 | SIDEWALK REMOVAL | S.F. | 21090 | 1 | 21090 | 3.25 | 68542.5 | 2.8 | 59052 | 3.07 | 64746.3 |  | 0 |  | 0 |  | 0
17 | EX. CONCRETE SPILLWAY TO BE REMOVED | EACH | 1 | 50 | 50 | 550 | 550 | 2498 | 2498 | 231.75 | 231.75 |  | 0 |  | 0 |  | 0
18 | COMBINATION CONCRETE CURB & GUTTER REMOVAL | FT. | 7346 | 10 | 73460 | 9 | 66114 | 10.85 | 79704.1 | 13.9 | 102109.4 |  | 0 |  | 0 |  | 0
19 | GRIND CURB TO DEPRESS | FT. | 10 | 10 | 100 | 55 | 550 | 105 | 1050 | 8.69 | 86.9 |  | 0 |  | 0 |  | 0
20 | DRIVEWAY PAVEMENT REMOVAL CONCRETE | S.Y. | 978 | 5 | 4890 | 19 | 18582 | 21.25 | 20782.5 | 38.24 | 37398.72 |  | 0 |  | 0 |  | 0
21 | DRIVEWAY PAVEMENT REMOVAL HMA | S.Y. | 781 | 5 | 3905 | 17 | 13277 | 21.2 | 16557.2 | 37.08 | 28959.48 |  | 0 |  | 0 |  | 0
22 | DRIVEWAY PAVEMENT REMOVAL AGGREGATE | S.Y. | 107 | 5 | 535 | 22 | 2354 | 11.95 | 1278.65 | 34.76 | 3719.32 |  | 0 |  | 0 |  | 0
23 | EX. STORM INLET TO BE ADJUSTED | EACH | 24 | 500 | 12000 | 900 | 21600 | 1269 | 30456 | 1158.75 | 27810 |  | 0 |  | 0 |  | 0
24 | CONNECTION TO EX INLET | EACH | 1 | 2500 | 2500 | 1000 | 1000 | 1455 | 1455 | 1738.12 | 1738.12 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 311242 |  | 411005 |  | 491568.38 |  | 550414.45
| Award to NTRAK Group | Total |  | As corrected | 311242 |  | 411005 |  | 491568.38 |  | 550414.45
25 | EX. STORM MANHOLE TO BE ADJUSTED | EACH | 13 | 500 | 6500 | 900 | 11700 | 1000 | 13000 | 1042.87 | 13557.31 |  | 0 |  | 0 |  | 0
26 | ADJUST EXISTING VALVE & VAULT | EACH | 20 | 500 | 10000 | 900 | 18000 | 1000 | 20000 | 521.44 | 10428.8 |  | 0 |  | 0 |  | 0
27 | EX. HANDHOLE TO BE ADJUSTED | EACH | 1 | 500 | 500 | 5000 | 5000 | 5188 | 5188 | 3476.23 | 3476.23 |  | 0 |  | 0 |  | 0
28 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 15 | 500 | 7500 | 1300 | 19500 | 1425 | 21375 | 1425.25 | 21378.75 |  | 0 |  | 0 |  | 0
29 | EX. SIGN TO BE RELOCATED | EACH | 4 | 250 | 1000 | 250 | 1000 | 252 | 1008 | 278.09 | 1112.36 |  | 0 |  | 0 |  | 0
30 | TRAFFIC CONTROL AND PROTECTION | LSUM | 1 | 25000 | 25000 | 20000 | 20000 | 28245 | 28245 | 25000 | 25000 |  | 0 |  | 0 |  | 0
31 | PERIMETER EROSION CONTROL BARRIER | FT. | 458 | 3 | 1374 | 3.5 | 1603 | 3.67 | 1680.86 | 6.95 | 3183.1 |  | 0 |  | 0 |  | 0
32 | INLET PROTECTION | EACH | 35 | 250 | 8750 | 60 | 2100 | 74.85 | 2619.75 | 289.68 | 10138.8 |  | 0 |  | 0 |  | 0
33 | TEMPORARY EROSION AND SEDIMENT CONTROL MAINT. | LSUM | 1 | 7500 | 7500 | 1000 | 1000 | 3250 | 3250 | 11587.43 | 11587.43 |  | 0 |  | 0 |  | 0
34 | 4" TOPSOIL, CLASS 1A SEEDING & EROSION CONTROL BLANKET | S.Y. | 1772 | 5 | 8860 | 7.5 | 13290 | 7.49 | 13272.28 | 10.72 | 18995.84 |  | 0 |  | 0 |  | 0
35 | CONSTRUCTION LAYOUT | LSUM | 1 | 40000 | 40000 | 20000 | 20000 | 25575 | 25575 | 30011.45 | 30011.45 |  | 0 |  | 0 |  | 0
36 | COMPACTED AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | S.Y. | 1200 | 8 | 9600 | 9.5 | 11400 | 10.15 | 12180 | 16.22 | 19464 |  | 0 |  | 0 |  | 0
37 | SUBBASE GRANULAR MATERIAL TYPE B, CA-2, 6" | S.Y. | 1200 | 8 | 9600 | 6.5 | 7800 | 10.75 | 12900 | 23.17 | 27804 |  | 0 |  | 0 |  | 0
38 | AGGREGATE BASE COURSE, TYPE B, 8" | S.Y. | 564 | 12 | 6768 | 11.5 | 6486 | 13.68 | 7715.52 | 16.8 | 9475.2 |  | 0 |  | 0 |  | 0
39 | AGGREGATE SURFACE COURSE, TYPE A, 6" | S.Y. | 87 | 8 | 696 | 14 | 1218 | 21 | 1827 | 28.97 | 2520.39 |  | 0 |  | 0 |  | 0
40 | HMA SURFACE COURSE, MIX "D", N50 | TON | 2191 | 90 | 197190 | 100 | 219100 | 89.09 | 195196.19 | 98.49 | 215791.59 |  | 0 |  | 0 |  | 0
41 | HMA BINDER COURSE, N50, 1.5" | TON | 47 | 90 | 4230 | 325 | 15275 | 186.95 | 8786.65 | 206.68 | 9713.96 |  | 0 |  | 0 |  | 0
42 | HMA BINDER COURSE, IL-19.0, N50, 4” | TON | 269 | 90 | 24210 | 130 | 34970 | 129.96 | 34959.24 | 143.69 | 38652.61 |  | 0 |  | 0 |  | 0
43 | COMBINATION CONCRETE CURB AND GUTTER, MODIFIED TYPE M 6.18 | FT. | 7404 | 25 | 185100 | 28.5 | 211014 | 31.4 | 232485.6 | 26.45 | 195835.8 |  | 0 |  | 0 |  | 0
44 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" (6" THRU DRIVEWAY) | S.F. | 40395 | 8 | 323160 | 7.25 | 292863.75 | 7 | 282765 | 7 | 282765 |  | 0 |  | 0 |  | 0
45 | DETECTABLE WARNINGS | S.F. | 616 | 35 | 21560 | 29 | 17864 | 34.35 | 21159.6 | 33.27 | 20494.32 |  | 0 |  | 0 |  | 0
46 | P.C. CONCRETE DRIVEWAY PAVEMENT, 6" | S.Y. | 581 | 50 | 29050 | 78 | 45318 | 67.2 | 39043.2 | 92.56 | 53777.36 |  | 0 |  | 0 |  | 0
47 | THERMOPLASTIC PAVEMENT MARKING – LINE 24” WHITE | FT. | 350 | 5 | 1750 | 5 | 1750 | 5.03 | 1760.5 | 5.56 | 1946 |  | 0 |  | 0 |  | 0
48 | THERMOPLASTIC PAVEMENT MARKING – LINE 8” WHITE | FT. | 59 | 3 | 177 | 1.65 | 97.35 | 1.68 | 99.12 | 1.85 | 109.15 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 1241317 |  | 1389354.1 |  | 1477659.89 |  | 1577633.9
| Award to NTRAK Group | Total |  | As corrected | 1241317 |  | 1389354.1 |  | 1477659.89 |  | 1577633.9
49 | THERMOPLASTIC PAVEMENT MARKING – LINE 6” WHITE | FT. | 1419 | 2 | 2838 | 1.25 | 1773.75 | 1.26 | 1787.94 | 1.39 | 1972.41 |  | 0 |  | 0 |  | 0
50 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" WHITE | FT. | 6434 | 2 | 12868 | 0.85 | 5468.9 | 0.84 | 5404.56 | 0.93 | 5983.62 |  | 0 |  | 0 |  | 0
51 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" YELLOW | FT. | 2288 | 2 | 4576 | 0.85 | 1944.8 | 0.84 | 1921.92 | 0.93 | 2127.84 |  | 0 |  | 0 |  | 0
52 | PAINT PAVEMEMENT MARKING - LINE 24" WHITE | FT. | 22 | 5 | 110 | 12.5 | 275 | 12.58 | 276.76 | 13.9 | 305.8 |  | 0 |  | 0 |  | 0
53 | PAINT PAVEMEMENT MARKING - LINE 6" WHITE | FT. | 118 | 2 | 236 | 3.1 | 365.8 | 3.14 | 370.52 | 3.48 | 410.64 |  | 0 |  | 0 |  | 0
54 | THERMOPLASTIC PAVEMENET MARKING - RR SYMBOL | EACH | 2 | 500 | 1000 | 205 | 410 | 209.62 | 419.24 | 231.75 | 463.5 |  | 0 |  | 0 |  | 0
55 | RCP STORM SEWER, 12" | FT. | 33 | 40 | 1320 | 145 | 4785 | 133 | 4389 | 133.26 | 4397.58 |  | 0 |  | 0 |  | 0
56 | 2' DIA. STORM INLET TYPE A | EACH | 1 | 2000 | 2000 | 1800 | 1800 | 2100 | 2100 | 2896.86 | 2896.86 |  | 0 |  | 0 |  | 0
57 | STORM INLET 700 | EACH | 1 | 2500 | 2500 | 2000 | 2000 | 3150 | 3150 | 3707.98 | 3707.98 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 1268765 |  | 1408177.35 |  | 1497479.83 |  | 1599900.13
| Award to NTRAK Group | Bid |  | As corrected | 1268765 |  | 1408177.35 |  | 1497479.83 |  | 1599900.13
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
| Page 4 | Total |  | As read
| Award to NTRAK Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
| Page 5 | Total |  | As read
| Award to NTRAK Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 6 | Total |  | As read
| Award to NTRAK Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 7 | Total |  | As read
| Award to NTRAK Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 8 | Total |  | As read
| Award to NTRAK Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 9 | Total |  | As read
| Award to NTRAK Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 10 | Total |  | As read
| Award to NTRAK Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 11 | Total |  | As read
| Award to NTRAK Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 12 | Total |  | As read
| Award to NTRAK Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 13 | Total |  | As read
| Award to NTRAK Group | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
BROOKE ROAD IMPROVEMENTS
Item No. | Items | Units | Quantity | Unit Price | Total
1 | UNDERCUT AND BACKFILL UNSUITABLE SUBGRADE | C.Y. | 50 |  | 0
2 | EX. TREE REMOVAL | DIA. | 62 |  | 0
3 | EX. DETECTOR LOOP TO BE REPLACED | LSUM | 2 |  | 0
4 | EX. PAY PHONE, CONCRETE BASE & 4 BOLLARDS TO BE REMOVED | EACH | 1 |  | 0
5 | REMOVE EX. FENCE | FT. | 8 |  | 0
6 | REMOVE & REPLACE EX. FENCE | FT. | 280 |  | 0
7 | PAVEMENT MARKING TO BE REMOVED | FT. | 8 |  | 0
8 | REMOVE & REPLACE GUARDRAIL | FT. | 25 |  | 0
9 | METAL GUARDRAIL | FT. | 10 |  | 0
10 | HMA SURFACE REMOVAL VARIABLE DEPTH (2.0"-3.0") | S.Y. | 15325 |  | 0
11 | CLASS B PATCH, TYPE I | S.Y. | 200 |  | 0
12 | CLASS B PATCH, TYPE II | S.Y. | 200 |  | 0
13 | CLASS B PATCH, TYPE III | S.Y. | 200 |  | 0
14 | CLASS B PATCH, TYPE IV | S.Y. | 200 |  | 0
15 | HMA FULL DEPTH REMOVAL (AGG. INCLUDED) | S.Y. | 1201 |  | 0
16 | SIDEWALK REMOVAL | S.F. | 21090 |  | 0
17 | EX. CONCRETE SPILLWAY TO BE REMOVED | EACH | 1 |  | 0
18 | COMBINATION CONCRETE CURB & GUTTER REMOVAL | FT. | 7346 |  | 0
19 | GRIND CURB TO DEPRESS | FT. | 10 |  | 0
20 | DRIVEWAY PAVEMENT REMOVAL CONCRETE | S.Y. | 978 |  | 0
21 | DRIVEWAY PAVEMENT REMOVAL HMA | S.Y. | 781 |  | 0
22 | DRIVEWAY PAVEMENT REMOVAL AGGREGATE | S.Y. | 107 |  | 0
23 | EX. STORM INLET TO BE ADJUSTED | EACH | 24 |  | 0
24 | CONNECTION TO EX INLET | EACH | 1 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | EX. STORM MANHOLE TO BE ADJUSTED | EACH | 13 |  | 0
26 | ADJUST EXISTING VALVE & VAULT | EACH | 20 |  | 0
27 | EX. HANDHOLE TO BE ADJUSTED | EACH | 1 |  | 0
28 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 15 |  | 0
29 | EX. SIGN TO BE RELOCATED | EACH | 4 |  | 0
30 | TRAFFIC CONTROL AND PROTECTION | LSUM | 1 |  | 0
31 | PERIMETER EROSION CONTROL BARRIER | FT. | 458 |  | 0
32 | INLET PROTECTION | EACH | 35 |  | 0
33 | TEMPORARY EROSION AND SEDIMENT CONTROL MAINT. | LSUM | 1 |  | 0
34 | 4" TOPSOIL, CLASS 1A SEEDING & EROSION CONTROL BLANKET | S.Y. | 1772 |  | 0
35 | CONSTRUCTION LAYOUT | LSUM | 1 |  | 0
36 | COMPACTED AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | S.Y. | 1200 |  | 0
37 | SUBBASE GRANULAR MATERIAL TYPE B, CA-2, 6" | S.Y. | 1200 |  | 0
38 | AGGREGATE BASE COURSE, TYPE B, 8" | S.Y. | 564 |  | 0
39 | AGGREGATE SURFACE COURSE, TYPE A, 6" | S.Y. | 87 |  | 0
40 | HMA SURFACE COURSE, MIX "D", N50 | TON | 2191 |  | 0
41 | HMA BINDER COURSE, N50, 1.5" | TON | 47 |  | 0
42 | HMA BINDER COURSE, IL-19.0, N50, 4” | TON | 269 |  | 0
43 | COMBINATION CONCRETE CURB AND GUTTER, MODIFIED TYPE M 6.18 | FT. | 7404 |  | 0
44 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" (6" THRU DRIVEWAY) | S.F. | 40395 |  | 0
45 | DETECTABLE WARNINGS | S.F. | 616 |  | 0
46 | P.C. CONCRETE DRIVEWAY PAVEMENT, 6" | S.Y. | 581 |  | 0
47 | THERMOPLASTIC PAVEMENT MARKING – LINE 24” WHITE | FT. | 350 |  | 0
48 | THERMOPLASTIC PAVEMENT MARKING – LINE 8” WHITE | FT. | 59 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | THERMOPLASTIC PAVEMENT MARKING – LINE 6” WHITE | FT. | 1419 |  | 0
50 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" WHITE | FT. | 6434 |  | 0
51 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" YELLOW | FT. | 2288 |  | 0
52 | PAINT PAVEMEMENT MARKING - LINE 24" WHITE | FT. | 22 |  | 0
53 | PAINT PAVEMEMENT MARKING - LINE 6" WHITE | FT. | 118 |  | 0
54 | THERMOPLASTIC PAVEMENET MARKING - RR SYMBOL | EACH | 2 |  | 0
55 | RCP STORM SEWER, 12" | FT. | 33 |  | 0
56 | 2' DIA. STORM INLET TYPE A | EACH | 1 |  | 0
57 | STORM INLET 700 | EACH | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 5 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 6 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 7 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 8 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 9 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 10 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 11 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 12 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 13 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | UNDERCUT AND BACKFILL UNSUITABLE SUBGRADE | C.Y. | 50 | 25 | 1250
2 | EX. TREE REMOVAL | DIA. | 62 | 25 | 1550
3 | EX. DETECTOR LOOP TO BE REPLACED | LSUM | 2 | 500 | 1000
4 | EX. PAY PHONE, CONCRETE BASE & 4 BOLLARDS TO BE REMOVED | EACH | 1 | 1000 | 1000
5 | REMOVE EX. FENCE | FT. | 8 | 5 | 40
6 | REMOVE & REPLACE EX. FENCE | FT. | 280 | 20 | 5600
7 | PAVEMENT MARKING TO BE REMOVED | FT. | 8 | 2 | 16
8 | REMOVE & REPLACE GUARDRAIL | FT. | 25 | 50 | 1250
9 | METAL GUARDRAIL | FT. | 10 | 50 | 500
10 | HMA SURFACE REMOVAL VARIABLE DEPTH (2.0"-3.0") | S.Y. | 15325 | 4 | 61300
11 | CLASS B PATCH, TYPE I | S.Y. | 200 | 200 | 40000
12 | CLASS B PATCH, TYPE II | S.Y. | 200 | 140 | 28000
13 | CLASS B PATCH, TYPE III | S.Y. | 200 | 120 | 24000
14 | CLASS B PATCH, TYPE IV | S.Y. | 200 | 100 | 20000
15 | HMA FULL DEPTH REMOVAL (AGG. INCLUDED) | S.Y. | 1201 | 6 | 7206
16 | SIDEWALK REMOVAL | S.F. | 21090 | 1 | 21090
17 | EX. CONCRETE SPILLWAY TO BE REMOVED | EACH | 1 | 50 | 50
18 | COMBINATION CONCRETE CURB & GUTTER REMOVAL | FT. | 7346 | 10 | 73460
19 | GRIND CURB TO DEPRESS | FT. | 10 | 10 | 100
20 | DRIVEWAY PAVEMENT REMOVAL CONCRETE | S.Y. | 978 | 5 | 4890
21 | DRIVEWAY PAVEMENT REMOVAL HMA | S.Y. | 781 | 5 | 3905
22 | DRIVEWAY PAVEMENT REMOVAL AGGREGATE | S.Y. | 107 | 5 | 535
23 | EX. STORM INLET TO BE ADJUSTED | EACH | 24 | 500 | 12000
24 | CONNECTION TO EX INLET | EACH | 1 | 2500 | 2500
|  |  |  | Sub Total | 311242
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | EX. STORM MANHOLE TO BE ADJUSTED | EACH | 13 | 500 | 6500
26 | ADJUST EXISTING VALVE & VAULT | EACH | 20 | 500 | 10000
27 | EX. HANDHOLE TO BE ADJUSTED | EACH | 1 | 500 | 500
28 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 15 | 500 | 7500
29 | EX. SIGN TO BE RELOCATED | EACH | 4 | 250 | 1000
30 | TRAFFIC CONTROL AND PROTECTION | LSUM | 1 | 25000 | 25000
31 | PERIMETER EROSION CONTROL BARRIER | FT. | 458 | 3 | 1374
32 | INLET PROTECTION | EACH | 35 | 250 | 8750
33 | TEMPORARY EROSION AND SEDIMENT CONTROL MAINT. | LSUM | 1 | 7500 | 7500
34 | 4" TOPSOIL, CLASS 1A SEEDING & EROSION CONTROL BLANKET | S.Y. | 1772 | 5 | 8860
35 | CONSTRUCTION LAYOUT | LSUM | 1 | 40000 | 40000
36 | COMPACTED AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | S.Y. | 1200 | 8 | 9600
37 | SUBBASE GRANULAR MATERIAL TYPE B, CA-2, 6" | S.Y. | 1200 | 8 | 9600
38 | AGGREGATE BASE COURSE, TYPE B, 8" | S.Y. | 564 | 12 | 6768
39 | AGGREGATE SURFACE COURSE, TYPE A, 6" | S.Y. | 87 | 8 | 696
40 | HMA SURFACE COURSE, MIX "D", N50 | TON | 2191 | 90 | 197190
41 | HMA BINDER COURSE, N50, 1.5" | TON | 47 | 90 | 4230
42 | HMA BINDER COURSE, IL-19.0, N50, 4” | TON | 269 | 90 | 24210
43 | COMBINATION CONCRETE CURB AND GUTTER, MODIFIED TYPE M 6.18 | FT. | 7404 | 25 | 185100
44 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" (6" THRU DRIVEWAY) | S.F. | 40395 | 8 | 323160
45 | DETECTABLE WARNINGS | S.F. | 616 | 35 | 21560
46 | P.C. CONCRETE DRIVEWAY PAVEMENT, 6" | S.Y. | 581 | 50 | 29050
47 | THERMOPLASTIC PAVEMENT MARKING – LINE 24” WHITE | FT. | 350 | 5 | 1750
48 | THERMOPLASTIC PAVEMENT MARKING – LINE 8” WHITE | FT. | 59 | 3 | 177
|  |  |  | Sub Total | 1241317
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | THERMOPLASTIC PAVEMENT MARKING – LINE 6” WHITE | FT. | 1419 | 2 | 2838
50 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" WHITE | FT. | 6434 | 2 | 12868
51 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" YELLOW | FT. | 2288 | 2 | 4576
52 | PAINT PAVEMEMENT MARKING - LINE 24" WHITE | FT. | 22 | 5 | 110
53 | PAINT PAVEMEMENT MARKING - LINE 6" WHITE | FT. | 118 | 2 | 236
54 | THERMOPLASTIC PAVEMENET MARKING - RR SYMBOL | EACH | 2 | 500 | 1000
55 | RCP STORM SEWER, 12" | FT. | 33 | 40 | 1320
56 | 2' DIA. STORM INLET TYPE A | EACH | 1 | 2000 | 2000
57 | STORM INLET 700 | EACH | 1 | 2500 | 2500
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1268765
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1268765
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1268765
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 5 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1268765
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 6 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1268765
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 7 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1268765
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 8 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1268765
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 9 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1268765
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 10 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1268765
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 11 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | BROOKE ROAD IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 1268765
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 112 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | UNDERCUT AND BACKFILL UNSUITABLE SUBGRADE | 50 | C.Y. | 3750 |  | 50 |  |  | 75
2 | EX. TREE REMOVAL | 62 | DIA. | 7750 |  | 62 |  |  | 125
3 | EX. DETECTOR LOOP TO BE REPLACED | 2 | LSUM | 14000 |  | 2 |  |  | 7000
4 | EX. PAY PHONE, CONCRETE BASE & 4 BOLLARDS TO BE REMOVED | 1 | EACH | 250 |  | 1 |  |  | 250
5 | REMOVE EX. FENCE | 8 | FT. | 480 |  | 8 |  |  | 60
6 | REMOVE & REPLACE EX. FENCE | 280 | FT. | 16800 |  | 280 |  |  | 60
7 | PAVEMENT MARKING TO BE REMOVED | 8 | FT. | 416 |  | 8 |  |  | 52
8 | REMOVE & REPLACE GUARDRAIL | 25 | FT. | 3000 |  | 25 |  |  | 120
9 | METAL GUARDRAIL | 10 | FT. | 1400 |  | 10 |  |  | 140
10 | HMA SURFACE REMOVAL VARIABLE DEPTH (2.0"-3.0") | 15325 | S.Y. | 41377.5 |  | 15325 |  |  | 2.7
11 | CLASS B PATCH, TYPE I | 200 | S.Y. | 28400 |  | 200 |  |  | 142
12 | CLASS B PATCH, TYPE II | 200 | S.Y. | 28400 |  | 200 |  |  | 142
13 | CLASS B PATCH, TYPE III | 200 | S.Y. | 29000 |  | 200 |  |  | 145
14 | CLASS B PATCH, TYPE IV | 200 | S.Y. | 29000 |  | 200 |  |  | 145
15 | HMA FULL DEPTH REMOVAL (AGG. INCLUDED) | 1201 | S.Y. | 14412 |  | 1201 |  |  | 12
16 | SIDEWALK REMOVAL | 21090 | S.F. | 68542.5 |  | 21090 |  |  | 3.25
17 | EX. CONCRETE SPILLWAY TO BE REMOVED | 1 | EACH | 550 |  | 1 |  |  | 550
18 | COMBINATION CONCRETE CURB & GUTTER REMOVAL | 7346 | FT. | 66114 |  | 7346 |  |  | 9
19 | GRIND CURB TO DEPRESS | 10 | FT. | 550 |  | 10 |  |  | 55
20 | DRIVEWAY PAVEMENT REMOVAL CONCRETE | 978 | S.Y. | 18582 |  | 978 |  |  | 19
21 | DRIVEWAY PAVEMENT REMOVAL HMA | 781 | S.Y. | 13277 |  | 781 |  |  | 17
22 | DRIVEWAY PAVEMENT REMOVAL AGGREGATE | 107 | S.Y. | 2354 |  | 107 |  |  | 22
23 | EX. STORM INLET TO BE ADJUSTED | 24 | EACH | 21600 |  | 24 |  |  | 900
24 | CONNECTION TO EX INLET | 1 | EACH | 1000 |  | 1 |  |  | 1000
Sub Total |  |  |  | 411005 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | EX. STORM MANHOLE TO BE ADJUSTED | 13 | EACH | 11700 |  | 13 |  |  | 900
26 | ADJUST EXISTING VALVE & VAULT | 20 | EACH | 18000 |  | 20 |  |  | 900
27 | EX. HANDHOLE TO BE ADJUSTED | 1 | EACH | 5000 |  | 1 |  |  | 5000
28 | EX. SANITARY MANHOLE TO BE ADJUSTED | 15 | EACH | 19500 |  | 15 |  |  | 1300
29 | EX. SIGN TO BE RELOCATED | 4 | EACH | 1000 |  | 4 |  |  | 250
30 | TRAFFIC CONTROL AND PROTECTION | 1 | LSUM | 20000 |  | 1 |  |  | 20000
31 | PERIMETER EROSION CONTROL BARRIER | 458 | FT. | 1603 |  | 458 |  |  | 3.5
32 | INLET PROTECTION | 35 | EACH | 2100 |  | 35 |  |  | 60
33 | TEMPORARY EROSION AND SEDIMENT CONTROL MAINT. | 1 | LSUM | 1000 |  | 1 |  |  | 1000
34 | 4" TOPSOIL, CLASS 1A SEEDING & EROSION CONTROL BLANKET | 1772 | S.Y. | 13290 |  | 1772 |  |  | 7.5
35 | CONSTRUCTION LAYOUT | 1 | LSUM | 20000 |  | 1 |  |  | 20000
36 | COMPACTED AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | 1200 | S.Y. | 11400 |  | 1200 |  |  | 9.5
37 | SUBBASE GRANULAR MATERIAL TYPE B, CA-2, 6" | 1200 | S.Y. | 7800 |  | 1200 |  |  | 6.5
38 | AGGREGATE BASE COURSE, TYPE B, 8" | 564 | S.Y. | 6486 |  | 564 |  |  | 11.5
39 | AGGREGATE SURFACE COURSE, TYPE A, 6" | 87 | S.Y. | 1218 |  | 87 |  |  | 14
40 | HMA SURFACE COURSE, MIX "D", N50 | 2191 | TON | 219100 |  | 2191 |  |  | 100
41 | HMA BINDER COURSE, N50, 1.5" | 47 | TON | 15275 |  | 47 |  |  | 325
42 | HMA BINDER COURSE, IL-19.0, N50, 4” | 269 | TON | 34970 |  | 269 |  |  | 130
43 | COMBINATION CONCRETE CURB AND GUTTER, MODIFIED TYPE M 6.18 | 7404 | FT. | 211014 |  | 7404 |  |  | 28.5
44 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" (6" THRU DRIVEWAY) | 40395 | S.F. | 292863.75 |  | 40395 |  |  | 7.25
45 | DETECTABLE WARNINGS | 616 | S.F. | 17864 |  | 616 |  |  | 29
46 | P.C. CONCRETE DRIVEWAY PAVEMENT, 6" | 581 | S.Y. | 45318 |  | 581 |  |  | 78
47 | THERMOPLASTIC PAVEMENT MARKING – LINE 24” WHITE | 350 | FT. | 1750 |  | 350 |  |  | 5
48 | THERMOPLASTIC PAVEMENT MARKING – LINE 8” WHITE | 59 | FT. | 97.35 |  | 59 |  |  | 1.65
Sub Total |  |  |  | 1389354.1 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | THERMOPLASTIC PAVEMENT MARKING – LINE 6” WHITE | 1419 | FT. | 1773.75 |  | 1419 |  |  | 1.25
50 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" WHITE | 6434 | FT. | 5468.9 |  | 6434 |  |  | 0.85
51 | THERMOPLASTIC PAVEMENT MARKING - LINE 4" YELLOW | 2288 | FT. | 1944.8 |  | 2288 |  |  | 0.85
52 | PAINT PAVEMEMENT MARKING - LINE 24" WHITE | 22 | FT. | 275 |  | 22 |  |  | 12.5
53 | PAINT PAVEMEMENT MARKING - LINE 6" WHITE | 118 | FT. | 365.8 |  | 118 |  |  | 3.1
54 | THERMOPLASTIC PAVEMENET MARKING - RR SYMBOL | 2 | EACH | 410 |  | 2 |  |  | 205
55 | RCP STORM SEWER, 12" | 33 | FT. | 4785 |  | 33 |  |  | 145
56 | 2' DIA. STORM INLET TYPE A | 1 | EACH | 1800 |  | 1 |  |  | 1800
57 | STORM INLET 700 | 1 | EACH | 2000 |  | 1 |  |  | 2000
Total |  |  |  | 1408177.35 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 1408177.35 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 5189407.4
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 8017342.7
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 14614927.45
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 27821677.55
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 50453947.7
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 92890552.7
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 171166177.95
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 314510678.35
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: NTRAK Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL 61111
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 578567409
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Logistics Parkway - Phase II
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | NTRAK Group
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.