## Item List
| City -Wide Street Repairs Group No. 5 - 2023 (Residential) | [37 empty] | 1145892.5
Summary Of Quantities |  |  | 1st Ward |  |  |  | 1st Ward |  | 4th Ward |  | 4th Ward |  |  |  | 4th Ward |  | 14th Ward |  | 14th Ward |  |  |  | Showplace Drive |  | Winter Repairs |  | Winter Repairs |  |  |  | Winter Repairs |  |  |  | Winter Repairs
No. | Item | Units | 7500 Larwinn Court | 7500/7600 Larwinn Drive | 7700 Meander Drive | 6900 Redansa Drive Patching | 1300 Reid Farm Road | 1100/1200 Tulip Lane | 4500/4700 Brougham Drive | 4600 Crested Butte Trail | 7000 Forest Glen Drive | 6800/6900 Paddock Lane | 2800 Surrey Place | 5700/5800 Tasselbury Close Patching | 5900 Twin Orchard Drive | 3200/3300 Windsong Drive | 1700/1900 Arnold Avenue Patching | 5000 Carol Court | 1000/1100 Esmond Drive | 0700/0900 Phelps Avenue | 1200 Post Drive | 1400 Post Drive | 8300/8400 Chandan Drive | 0100/0200 Showplace Drive | 23rd Avenue | Arnold Avenue | Boeing Drive | 0400 Cedar Street | 1500 Cunningham Road | Fairview Boulevard | 3800 Northridge Drive | 2600/2700 Ridge Avenue | South Rockford Avenue | 7000 Spring Creek Road | 0300/1000 Willoughby Avenue Patching | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Parkway Restoration | LSum | [6 empty] | 0.25 | [6 empty] | 0.1 |  | 0.2 |  | 0.25 | [6 empty] | 0.1 | [7 empty] | 0.1 |  | 1 | 5000 | 5000
2 | Inlet and Pipe Protection | Each | [6 empty] | 4 |  |  |  | 2 |  |  | 2 | 1 |  |  | 1 | [16 empty] | 10 | 75 | 750
3 | Aggregate Base Repair, 10" | S.Y. | 10 | 23 | 5 | 9 | 14 | 23 | 36 | 19 | 34 | 45 | 16 | 7 | 19 | 13 | 23 | 31 | 21 | 34 | 14 | 20 | 22 | 39 | 3 | 9 | 8 | 5 | 6 | 49 | 59 | 10 | 3 | 5 | 12 |  | 646 | 20 | 12920
4 | Bituminous Materials (Prime Coat) | Gal | 105 | 235 | 50 | 90 | 145 | 235 | 365 | 190 | 340 | 450 | 160 | 77 | 195 | 135 | 230 | 310 | 210 | 340 | 140 | 200 | 220 | 395 | 35 | 95 | 80 | 50 | 65 | 490 | 590 | 107 | 30 | 55 | 127 |  | 6541 | 3 | 19623
5 | Aggregate (Prime Coat) | Tons | 10 | 23 | 5 | 9 | 14 | 23 | 36 | 19 | 34 | 45 | 16 | 7 | 19 | 13 | 23 | 31 | 21 | 34 | 14 | 20 | 22 | 39 | 3 | 9 | 8 | 5 | 6 | 49 | 59 | 10 | 3 | 5 | 12 |  | 646 | 10 | 6460
6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | [22 empty] | 40 |  | 75 | 50 | 60 | 400 |  | 100 |  | 50 | 150 | 500 | 1425 | 80 | 114000
7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 125 | 300 | 75 | 125 | 175 | 300 | 425 | 225 | 400 | 525 | 200 | 100 | 250 | 175 | 275 | 375 | 250 | 400 | 175 | 250 | 275 | 475 |  | 125 |  |  |  |  | 700 |  | 50 |  |  | 500 | 7250 | 80 | 580000
8 | Hot-Mix Asphalt, Hand Method | Tons | [33 empty] | 10 | 10 | 300 | 3000
9 | P.C.C. Approach Pavement, 6" | S.Y. | [6 empty] | 36 | [27 empty] | 36 | 80 | 2880
10 | P.C.C. Sidewalk, 4" | S.F. | [6 empty] | 100 | [8 empty] | 100 |  | 450 | [16 empty] | 650 | 8 | 5200
11 | Combination Curb and Gutter Removal | L.F. | [6 empty] | 60 | [6 empty] | 30 | [10 empty] | 25 | [7 empty] | 25 |  | 140 | 20 | 2800
12 | Sidewalk Removal | S.F. | [6 empty] | 100 | [8 empty] | 100 |  | 450 | [16 empty] | 650 | 3 | 1950
13 | Approach Pavement Removal | S.Y. | [6 empty] | 36 | [27 empty] | 36 | 30 | 1080
14 | Surface Removal, 1.25" | S.Y. | [22 empty] | 350 |  | 800 | 500 | 650 | 4900 |  | 1075 |  | 550 | 1275 | 1000 | 11100 | 3 | 33300
15 | Surface Removal, 2" | S.Y. | 1050 | 2350 | 500 | 900 | 1450 | 2350 | 3650 | 1900 | 3400 | 4500 | 1600 | 775 | 1950 | 1350 | 2300 | 3100 | 2100 | 3400 | 1400 | 2000 | 2200 | 3950 |  | 950 |  |  |  |  | 5900 |  | 300 |  |  | 1000 | 56325 | 3 | 168975
16 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [34 empty] | 1 | 500 | 500
17 | Manholes to be Adjusted | Each | [5 empty] | 1 | 3 | 2 | 1 | 1 | 3 | 1 |  | 1 | 3 | 5 | 2 | 3 | 1 | 3 |  | 1 | 1 |  |  |  | 1 | 5 | 2 | 1 | 2 |  |  |  | 43 | 800 | 34400
18 | Manholes to be Adjusted with New Frame and Lid | Each | [6 empty] | 1 | 1 |  |  | 1 |  | 3 | [7 empty] | 1 | [6 empty] | 1 | 2 | [5 empty] | 10 | 1300 | 13000
19 | Manholes to be Reconstructed | Each | [33 empty] | 1 | 1 | 1600 | 1600
20 | Manholes to be Reconstructed with New Frame and Lid | Each | [33 empty] | 1 | 1 | 2200 | 2200
21 | Inlets to be Adjusted | Each | [33 empty] | 1 | 1 | 1200 | 1200
22 | Inlets to be Adjusted with New Frame and Grate | Each | [6 empty] | 2 |  |  |  | 2 |  |  | 1 | [20 empty] | 5 | 1800 | 9000
23 | Inlets to be Reconstructed | Each | [34 empty] | 1 | 1900 | 1900
24 | Inlets to be Reconstructed with New Frame and Grate | Each | [34 empty] | 1 | 2300 | 2300
25 | Inlet Specials to be Repaired | Each | [14 empty] | 1 | [19 empty] | 1 | 2500 | 2500
26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | [6 empty] | 60 | [6 empty] | 30 | [10 empty] | 25 | [7 empty] | 25 |  | 140 | 50 | 7000
27 | Traffic Control and Protection | LSum | 0.01 | 0.06 | 0.01 | 0.01 | 0.02 | 0.03 | 0.07 | 0.03 | 0.03 | 0.04 | 0.03 | 0.01 | 0.03 | 0.02 | 0.03 | 0.04 | 0.04 | 0.04 | 0.02 | 0.03 | 0.03 | 0.1 | 0.01 | 0.04 | 0.01 | 0.01 | 0.01 | 0.04 | 0.09 | 0.01 | 0.02 | 0.01 | 0.02 |  | 1 | 30000 | 30000
28 | Thermoplastic Pavement Markings, 4" | L.F. | [17 empty] | 270 |  |  |  | 20 | 400 | 290 |  |  |  | 3405 | 280 | 130 | 80 | 230 | 350 |  | 5455 | 1.5 | 8182.5
29 | Thermoplastic Pavement Markings, 6" | L.F. | [20 empty] | 100 | 1209 | 53 | 260 |  |  |  | 50 | 455 |  | 40 |  |  |  | 2167 | 2 | 4334
30 | Thermoplastic Pavement Markings, 12" | L.F. | [21 empty] | 37 | 58 | [9 empty] | 20 |  | 115 | 4 | 460
31 | Thermoplastic Pavement Markings, 24" | L.F. | [20 empty] | 16 | [7 empty] | 67 |  | 20 |  |  |  | 103 | 6 | 618
32 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | [20 empty] | 52 | 188 |  | 73 | [6 empty] | 32 |  |  |  | 345 | 8 | 2760
33 | Detector Loops | L.F. | [21 empty] | 700 |  | 700 |  |  |  |  | 400 |  | 400 |  |  |  | 2200 | 30 | 66000
34
35
36
37
38
39
40
41
42 | [37 empty] | 0
43 | [37 empty] | 0
44 | [37 empty] | 0
45 | [37 empty] | 0
46 | [37 empty] | 0
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 14065 | 34245 | 8100 | 13540 | 19805 | 34145 | 67335 | 28640 | 45940 | 60200 | 30110 | 11866 | 31805 | 24795 | 36155 | 48460 | 30360 | 54520 | 20440 | 30500 | 32832 | 81105 | 6483 | 37144 | 11430 | 6100 | 8225 | 61347.5 | 97872 | 13141 | 19856 | 6610 | 20021 | 94000 | #VALUE!
|  |  | 1313.258 | 5768.4395 | 781.3576 | 1045.2462 | 1814.234 | 3288.2992 | 6160.1491 | 2478.0787 | 3152.2316 | 3523.3249 | 2715.1661 | 1236.9777 | 3003.7943 | 2113.1703 | 2758.4604 | 3838.7542 | 3414.0586 | 4150.0603 | 2071.9377 | 2634.7626 | 3298.6073 | 9071.1701 | 618.4889 | 3298.6073 | 989.5822 | 659.7215 | 824.6518 | 4123.2591 | 8246.5183 | 1236.9777 | 1649.3037 | 659.7215 | 2061.6296 |  | 1145892.5
|  |  | 15378.258 | 40013.4395 | 8881.3576 | 14585.2462 | 21619.234 | 37433.2992 | 73495.1491 | 31118.0787 | 49092.2316 | 63723.3249 | 32825.1661 | 13102.9777 | 34808.7943 | 26908.1703 | 38913.4604 | 52298.7542 | 33774.0586 | 58670.0603 | 22511.9377 | 33134.7626 | 36130.6073 | 90176.1701 | 7101.4889 | 40442.6073 | 12419.5822 | 6759.7215 | 9049.6518 | 65470.7591 | 106118.5183 | 14377.9777 | 21505.3037 | 7269.7215 | 22082.6296 |  | 1141192.5
|  |  | 15925 | 69950 | 9475 | 12675 | 22000 | 39875 | 74700 | 30050 | 38225 | 42725 | 32925 | 15000 | 36425 | 25625 | 33450 | 46550 | 41400 | 50325 | 25125 | 31950 | 40000 | 110000 | 7500 | 40000 | 12000 | 8000 | 10000 | 50000 | 100000 | 15000 | 20000 | 8000 | 25000 | 0 | 1139875
#REF!
|  |  | 0.013971 | 0.061366 | 0.0083123 | 0.01112 | 0.0193 | 0.034982 | 0.065534 | 0.026363 | 0.033534 | 0.037482 | 0.028885 | 0.013159 | 0.031955 | 0.022481 | 0.029345 | 0.040838 | 0.03632 | 0.04415 | 0.022042 | 0.028029 | 0.035092 | 0.096502 | 0.0065797 | 0.035092 | 0.010527 | 0.0070183 | 0.0087729 | 0.043864 | 0.087729 | 0.013159 | 0.017546 | 0.0070183 | 0.021932 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Rock Road Companies |  | Curran Contracting | [7 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Janesville, WI |  | Crystal Lake, IL | [7 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 5 - 2023 (Residential) | [5 empty] | Bid Bond |  | Bid Bond | [7 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Vendors Notified: 122, Bid No.: 623-PW-059 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Parkway Restoration | LSum | 1 | 5000 | 5000 | 4848 | 4848 | 19500 | 19500 |  | 0 |  | 0 |  | 0 | 1 | Parkway Restoration | LSum | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Parkway Restoration | LSum | 1 | 5000 | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Inlet and Pipe Protection | Each | 10 | 75 | 750 | 100 | 1000 | 100 | 1000 |  | 0 |  | 0 |  | 0 | 2 | Inlet and Pipe Protection | Each | 10 | 75 | 750 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Inlet and Pipe Protection | Each | 10 | 75 | 750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Aggregate Base Repair, 10" | S.Y. | 646 | 20 | 12920 | 0.01 | 6.46 | 8 | 5168 |  | 0 |  | 0 |  | 0 | 3 | Aggregate Base Repair, 10" | S.Y. | 646 | 20 | 12920 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Aggregate Base Repair, 10" | S.Y. | 646 | 20 | 12920 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Bituminous Materials (Prime Coat) | Gal | 6541 | 3 | 19623 | 0.01 | 65.41 | 2.5 | 16352.5 |  | 0 |  | 0 |  | 0 | 4 | Bituminous Materials (Prime Coat) | Gal | 6541 | 3 | 19623 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Bituminous Materials (Prime Coat) | Gal | 6541 | 3 | 19623 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Aggregate (Prime Coat) | Tons | 646 | 10 | 6460 | 0.01 | 6.46 | 0.01 | 6.46 |  | 0 |  | 0 |  | 0 | 5 | Aggregate (Prime Coat) | Tons | 646 | 10 | 6460 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Aggregate (Prime Coat) | Tons | 646 | 10 | 6460 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | 1425 | 80 | 114000 | 77.78 | 110836.5 | 95 | 135375 |  | 0 |  | 0 |  | 0 | 6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | 1425 | 80 | 114000 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | 1425 | 80 | 114000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 7250 | 80 | 580000 | 79 | 572750 | 79 | 572750 |  | 0 |  | 0 |  | 0 | 7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 7250 | 80 | 580000 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 7250 | 80 | 580000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 | 80 | 800 | 350 | 3500 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | P.C.C. Approach Pavement, 6" | S.Y. | 36 | 80 | 2880 | 230 | 8280 | 95 | 3420 |  | 0 |  | 0 |  | 0 | 9 | P.C.C. Approach Pavement, 6" | S.Y. | 36 | 80 | 2880 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | P.C.C. Approach Pavement, 6" | S.Y. | 36 | 80 | 2880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | P.C.C. Sidewalk, 4" | S.F. | 650 | 8 | 5200 | 11.85 | 7702.5 | 12 | 7800 |  | 0 |  | 0 |  | 0 | 10 | P.C.C. Sidewalk, 4" | S.F. | 650 | 8 | 5200 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | P.C.C. Sidewalk, 4" | S.F. | 650 | 8 | 5200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Combination Curb and Gutter Removal | L.F. | 140 | 20 | 2800 | 15 | 2100 | 35 | 4900 |  | 0 |  | 0 |  | 0 | 11 | Combination Curb and Gutter Removal | L.F. | 140 | 20 | 2800 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Combination Curb and Gutter Removal | L.F. | 140 | 20 | 2800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | Sidewalk Removal | S.F. | 650 | 3 | 1950 | 5 | 3250 | 8 | 5200 |  | 0 |  | 0 |  | 0 | 12 | Sidewalk Removal | S.F. | 650 | 3 | 1950 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | Sidewalk Removal | S.F. | 650 | 3 | 1950 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | Approach Pavement Removal | S.Y. | 36 | 30 | 1080 | 25 | 900 | 45 | 1620 |  | 0 |  | 0 |  | 0 | 13 | Approach Pavement Removal | S.Y. | 36 | 30 | 1080 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | Approach Pavement Removal | S.Y. | 36 | 30 | 1080 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | Surface Removal, 1.25" | S.Y. | 11100 | 3 | 33300 | 2.95 | 32745 | 3.5 | 38850 |  | 0 |  | 0 |  | 0 | 14 | Surface Removal, 1.25" | S.Y. | 11100 | 3 | 33300 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | Surface Removal, 1.25" | S.Y. | 11100 | 3 | 33300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Surface Removal, 2" | S.Y. | 56325 | 3 | 168975 | 2.87 | 161652.75 | 3.25 | 183056.25 |  | 0 |  | 0 |  | 0 | 15 | Surface Removal, 2" | S.Y. | 56325 | 3 | 168975 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Surface Removal, 2" | S.Y. | 56325 | 3 | 168975 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 | 260 | 260 | 250 | 250 |  | 0 |  | 0 |  | 0 | 16 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Manholes to be Adjusted | Each | 43 | 800 | 34400 | 700 | 30100 | 1400 | 60200 |  | 0 |  | 0 |  | 0 | 17 | Manholes to be Adjusted | Each | 43 | 800 | 34400 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Manholes to be Adjusted | Each | 43 | 800 | 34400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Manholes to be Adjusted with New Frame and Lid | Each | 10 | 1300 | 13000 | 1270 | 12700 | 1600 | 16000 |  | 0 |  | 0 |  | 0 | 18 | Manholes to be Adjusted with New Frame and Lid | Each | 10 | 1300 | 13000 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Manholes to be Adjusted with New Frame and Lid | Each | 10 | 1300 | 13000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Manholes to be Reconstructed | Each | 1 | 1600 | 1600 | 1400 | 1400 | 1800 | 1800 |  | 0 |  | 0 |  | 0 | 19 | Manholes to be Reconstructed | Each | 1 | 1600 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Manholes to be Reconstructed | Each | 1 | 1600 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 2200 | 2200 | 1900 | 1900 | 2200 | 2200 |  | 0 |  | 0 |  | 0 | 20 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Inlets to be Adjusted | Each | 1 | 1200 | 1200 | 1236 | 1236 | 1100 | 1100 |  | 0 |  | 0 |  | 0 | 21 | Inlets to be Adjusted | Each | 1 | 1200 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Inlets to be Adjusted | Each | 1 | 1200 | 1200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Inlets to be Adjusted with New Frame and Grate | Each | 5 | 1800 | 9000 | 1836 | 9180 | 1800 | 9000 |  | 0 |  | 0 |  | 0 | 22 | Inlets to be Adjusted with New Frame and Grate | Each | 5 | 1800 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Inlets to be Adjusted with New Frame and Grate | Each | 5 | 1800 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Inlets to be Reconstructed | Each | 1 | 1900 | 1900 | 1996 | 1996 | 1800 | 1800 |  | 0 |  | 0 |  | 0 | 23 | Inlets to be Reconstructed | Each | 1 | 1900 | 1900 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Inlets to be Reconstructed | Each | 1 | 1900 | 1900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 2300 | 2300 | 2336 | 2336 | 2200 | 2200 |  | 0 |  | 0 |  | 0 | 24 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 2300 | 2300 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 2300 | 2300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 1024038 |  | 968051.08 |  | 1093048.21 | [7 empty] | Page 3 | Sub |  | As read | 1024038 | [9 empty] | Page 1 | Sub |  | As read | 1024038
| Award to Rock Road Companies | Total |  | As corrected | 1024038 |  | 968051.08 |  | 1093048.21 | [7 empty] | Award to Rock Road Companies | Total |  | As corrected | 1024038 | [9 empty] | Award to Rock Road Companies | Total |  | As corrected | 1024038
25 | Inlet Specials to be Repaired | Each | 1 | 2500 | 2500 | 2360 | 2360 | 2200 | 2200 |  | 0 |  | 0 |  | 0 | 25 | Inlet Specials to be Repaired | Each | 1 | 2500 | 2500 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Inlet Specials to be Repaired | Each | 1 | 2500 | 2500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 140 | 50 | 7000 | 62 | 8680 | 65 | 9100 |  | 0 |  | 0 |  | 0 | 26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 140 | 50 | 7000 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 140 | 50 | 7000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Traffic Control and Protection | LSum | 1 | 30000 | 30000 | 32000 | 32000 | 65000 | 65000 |  | 0 |  | 0 |  | 0 | 27 | Traffic Control and Protection | LSum | 1 | 30000 | 30000 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Traffic Control and Protection | LSum | 1 | 30000 | 30000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Thermoplastic Pavement Markings, 4" | L.F. | 5455 | 1.5 | 8182.5 | 1.5 | 8182.5 | 1.5 | 8182.5 |  | 0 |  | 0 |  | 0 | 28 | Thermoplastic Pavement Markings, 4" | L.F. | 5455 | 1.5 | 8182.5 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Thermoplastic Pavement Markings, 4" | L.F. | 5455 | 1.5 | 8182.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Thermoplastic Pavement Markings, 6" | L.F. | 2167 | 2 | 4334 | 2.25 | 4875.75 | 2.25 | 4875.75 |  | 0 |  | 0 |  | 0 | 29 | Thermoplastic Pavement Markings, 6" | L.F. | 2167 | 2 | 4334 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Thermoplastic Pavement Markings, 6" | L.F. | 2167 | 2 | 4334 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Thermoplastic Pavement Markings, 12" | L.F. | 115 | 4 | 460 | 4.5 | 517.5 | 4.5 | 517.5 |  | 0 |  | 0 |  | 0 | 30 | Thermoplastic Pavement Markings, 12" | L.F. | 115 | 4 | 460 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Thermoplastic Pavement Markings, 12" | L.F. | 115 | 4 | 460 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Thermoplastic Pavement Markings, 24" | L.F. | 103 | 6 | 618 | 9 | 927 | 9 | 927 |  | 0 |  | 0 |  | 0 | 31 | Thermoplastic Pavement Markings, 24" | L.F. | 103 | 6 | 618 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Thermoplastic Pavement Markings, 24" | L.F. | 103 | 6 | 618 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 345 | 8 | 2760 | 9 | 3105 | 9 | 3105 |  | 0 |  | 0 |  | 0 | 32 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 345 | 8 | 2760 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 345 | 8 | 2760 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Detector Loops | L.F. | 2200 | 30 | 66000 | 27.5 | 60500 | 20.72 | 45584 |  | 0 |  | 0 |  | 0 | 33 | Detector Loops | L.F. | 2200 | 30 | 66000 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Detector Loops | L.F. | 2200 | 30 | 66000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 1145892.5 |  | 1089198.83 |  | 1232539.96 | [7 empty] | Page 4 | Total |  | As read | 1145892.5 | [9 empty] | Page 2 | Total |  | As read | 1145892.5
| Award to Rock Road Companies | Bid |  | As corrected |  |  | 1089198.83 | 0 | 1232539.96 | 0 | [6 empty] | Award to Rock Road Companies | Bid |  | As corrected | #VALUE! | [9 empty] | Award to Rock Road Companies | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Rock Road Companies | Bid |  | As corrected | [12 empty] | Award to Rock Road Companies | Bid |  | As corrected | [10 empty] | Award to Rock Road Companies | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Rock Road Companies | Bid |  | As corrected | [12 empty] | Award to Rock Road Companies | Bid |  | As corrected | [10 empty] | Award to Rock Road Companies | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 5 - 2023 (Residential)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Parkway Restoration | LSum | 1 |  | 0
2 | Inlet and Pipe Protection | Each | 10 |  | 0
3 | Aggregate Base Repair, 10" | S.Y. | 646 |  | 0
4 | Bituminous Materials (Prime Coat) | Gal | 6541 |  | 0
5 | Aggregate (Prime Coat) | Tons | 646 |  | 0
6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | 1425 |  | 0
7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 7250 |  | 0
8 | Hot-Mix Asphalt, Hand Method | Tons | 10 |  | 0
9 | P.C.C. Approach Pavement, 6" | S.Y. | 36 |  | 0
10 | P.C.C. Sidewalk, 4" | S.F. | 650 |  | 0
11 | Combination Curb and Gutter Removal | L.F. | 140 |  | 0
12 | Sidewalk Removal | S.F. | 650 |  | 0
13 | Approach Pavement Removal | S.Y. | 36 |  | 0
14 | Surface Removal, 1.25" | S.Y. | 11100 |  | 0
15 | Surface Removal, 2" | S.Y. | 56325 |  | 0
16 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 |  | 0
17 | Manholes to be Adjusted | Each | 43 |  | 0
18 | Manholes to be Adjusted with New Frame and Lid | Each | 10 |  | 0
19 | Manholes to be Reconstructed | Each | 1 |  | 0
20 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 |  | 0
21 | Inlets to be Adjusted | Each | 1 |  | 0
22 | Inlets to be Adjusted with New Frame and Grate | Each | 5 |  | 0
23 | Inlets to be Reconstructed | Each | 1 |  | 0
24 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Inlet Specials to be Repaired | Each | 1 |  | 0
26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 140 |  | 0
27 | Traffic Control and Protection | LSum | 1 |  | 0
28 | Thermoplastic Pavement Markings, 4" | L.F. | 5455 |  | 0
29 | Thermoplastic Pavement Markings, 6" | L.F. | 2167 |  | 0
30 | Thermoplastic Pavement Markings, 12" | L.F. | 115 |  | 0
31 | Thermoplastic Pavement Markings, 24" | L.F. | 103 |  | 0
32 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 345 |  | 0
33 | Detector Loops | L.F. | 2200 |  | 0
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 5 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Parkway Restoration | LSum | 1 | 5000 | 5000
2 | Inlet and Pipe Protection | Each | 10 | 75 | 750
3 | Aggregate Base Repair, 10" | S.Y. | 646 | 20 | 12920
4 | Bituminous Materials (Prime Coat) | Gal | 6541 | 3 | 19623
5 | Aggregate (Prime Coat) | Tons | 646 | 10 | 6460
6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | Tons | 1425 | 80 | 114000
7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 7250 | 80 | 580000
8 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000
9 | P.C.C. Approach Pavement, 6" | S.Y. | 36 | 80 | 2880
10 | P.C.C. Sidewalk, 4" | S.F. | 650 | 8 | 5200
11 | Combination Curb and Gutter Removal | L.F. | 140 | 20 | 2800
12 | Sidewalk Removal | S.F. | 650 | 3 | 1950
13 | Approach Pavement Removal | S.Y. | 36 | 30 | 1080
14 | Surface Removal, 1.25" | S.Y. | 11100 | 3 | 33300
15 | Surface Removal, 2" | S.Y. | 56325 | 3 | 168975
16 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500
17 | Manholes to be Adjusted | Each | 43 | 800 | 34400
18 | Manholes to be Adjusted with New Frame and Lid | Each | 10 | 1300 | 13000
19 | Manholes to be Reconstructed | Each | 1 | 1600 | 1600
20 | Manholes to be Reconstructed with New Frame and Lid | Each | 1 | 2200 | 2200
21 | Inlets to be Adjusted | Each | 1 | 1200 | 1200
22 | Inlets to be Adjusted with New Frame and Grate | Each | 5 | 1800 | 9000
23 | Inlets to be Reconstructed | Each | 1 | 1900 | 1900
24 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 2300 | 2300
|  |  |  | Sub Total | 1024038
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 5 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Inlet Specials to be Repaired | Each | 1 | 2500 | 2500
26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 140 | 50 | 7000
27 | Traffic Control and Protection | LSum | 1 | 30000 | 30000
28 | Thermoplastic Pavement Markings, 4" | L.F. | 5455 | 1.5 | 8182.5
29 | Thermoplastic Pavement Markings, 6" | L.F. | 2167 | 2 | 4334
30 | Thermoplastic Pavement Markings, 12" | L.F. | 115 | 4 | 460
31 | Thermoplastic Pavement Markings, 24" | L.F. | 103 | 6 | 618
32 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 345 | 8 | 2760
33 | Detector Loops | L.F. | 2200 | 30 | 66000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 5 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 5 - 2023 (Residential)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | P.O. # 19305222 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: Janesville, WI Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 5 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Parkway Restoration | 1 | LSum | 4848 |  |  |  |  | 4848
2 | Inlet and Pipe Protection | 10 | Each | 1000 |  |  |  |  | 100
3 | Aggregate Base Repair, 10" | 646 | S.Y. | 6.46 |  |  | 35 | S.Y. | 0.01 | 0.35
4 | Bituminous Materials (Prime Coat) | 6541 | Gal | 65.41 |  |  |  |  | 0.01
5 | Aggregate (Prime Coat) | 646 | Tons | 6.46 |  |  |  |  | 0.01
6 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.25" | 1425 | Tons | 110836.5 |  |  |  |  | 77.78
7 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 7250 | Tons | 572750 |  |  |  |  | 79
8 | Hot-Mix Asphalt, Hand Method | 10 | Tons | 800 |  |  |  |  | 80
9 | P.C.C. Approach Pavement, 6" | 36 | S.Y. | 8280 |  |  |  |  | 230
10 | P.C.C. Sidewalk, 4" | 650 | S.F. | 7702.5 | 750 |  | 1400 | S.F. | 11.85 | 16590
11 | Combination Curb and Gutter Removal | 140 | L.F. | 2100 |  |  |  |  | 15
12 | Sidewalk Removal | 650 | S.F. | 3250 |  |  |  |  | 5
13 | Approach Pavement Removal | 36 | S.Y. | 900 | 1994 |  | 2030 | S.Y. | 25 | 50750
14 | Surface Removal, 1.25" | 11100 | S.Y. | 32745 |  |  |  |  | 2.95
15 | Surface Removal, 2" | 56325 | S.Y. | 161652.75 |  |  | 292 | S.Y. | 2.87 | 838.04
16 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each | 260 |  |  |  |  | 260
17 | Manholes to be Adjusted | 43 | Each | 30100 | 15051 |  | 15094 | Each | 700 | 10565800
18 | Manholes to be Adjusted with New Frame and Lid | 10 | Each | 12700 | 490 |  | 500 | Each | 1270 | 635000
19 | Manholes to be Reconstructed | 1 | Each | 1400 | 1497 |  | 1498 | Each | 1400 | 2097200
20 | Manholes to be Reconstructed with New Frame and Lid | 1 | Each | 1900 | 15243 |  | 15244 | Each | 1900 | 28963600
21 | Inlets to be Adjusted | 1 | Each | 1236 | 291 |  | 292 | Each | 1236 | 360912
22 | Inlets to be Adjusted with New Frame and Grate | 5 | Each | 9180 |  |  |  |  | 1836
23 | Inlets to be Reconstructed | 1 | Each | 1996 | 18204 |  | 18205 | Each | 1996 | 36337180
24 | Inlets to be Reconstructed with New Frame and Grate | 1 | Each | 2336 | 712 |  | 713 | Each | 2336 | 1665568
Sub Total |  |  |  | 968051.08 | [5 empty] | 80693438.39
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, WI Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 5 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Inlet Specials to be Repaired | 1 | Each | 2360 |  |  |  |  | 2360
26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 140 | L.F. | 8680 |  |  |  |  | 62
27 | Traffic Control and Protection | 1 | LSum | 32000 |  |  |  |  | 32000
28 | Thermoplastic Pavement Markings, 4" | 5455 | L.F. | 8182.5 |  |  |  |  | 1.5
29 | Thermoplastic Pavement Markings, 6" | 2167 | L.F. | 4875.75 |  |  |  |  | 2.25
30 | Thermoplastic Pavement Markings, 12" | 115 | L.F. | 517.5 |  |  | 10 | L.F. | 4.5 | 45
31 | Thermoplastic Pavement Markings, 24" | 103 | L.F. | 927 |  |  |  |  | 9
32 | Thermoplastic Pavement Markings, Letters and Symbols | 345 | S.F. | 3105 |  |  |  |  | 9
33 | Detector Loops | 2200 | L.F. | 60500 |  |  |  |  | 27.5
[7 empty] | 8 |  |  | #VALUE!
[7 empty] | 1 |  |  | #VALUE!
[7 empty] | 1318 |  |  | #VALUE!
[7 empty] | 0.5 |  |  | #VALUE!
Total |  |  |  | 1089198.83 | [5 empty] | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | #VALUE!
[8 empty] | DEDUCT RETAINAGE | 10%
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | #VALUE!
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | #VALUE!
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, WI Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 5 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 1089198.83 | [5 empty] | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | #VALUE!
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | #VALUE!
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | #VALUE!
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: Rock Road Companies | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Janesville, WI Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 5 - 2023 (Residential)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 1089198.83 | [5 empty] | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | #VALUE!
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | #VALUE!
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | #VALUE!
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Rock Road Companies
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.