## Item List
| City -Wide Street Repairs Group No. 3 - 2025 (Concrete) | [59 empty] | 3540380
Summary Of Quantities |  |  | 2nd Ward |  |  |  | 2nd Ward |  |  |  | 2nd Ward |  |  | 5th Ward | 5th Ward |  |  |  | 5th Ward |  | 7th Ward |  | 9th Ward |  |  |  | 9th Ward |  |  |  | 9th Ward |  |  |  | 10th Ward | 11th Ward |  |  | 11th Ward |  |  | 12th Ward | 12th Ward |  | 13th Ward |  | 13th Ward |  |  |  | 14th Ward | Neighborhood Allocation |  |  | Neighborhood Allocation
No. | Item | Units | 2236 10th Avenue Sidewalk | 202-214 12th Street Sidewalk | 2210 16th Avenue Sidewalk | 2326 16th Avenue Curb and Gutter | 2305-2309 18th Avenue Sidewalk | 2134 Charles Street Sidewalk | 1540 Daisy Avenue Sidewalk | 233 Dawson Avenue Sidewalk | 311 Hunter Avenue Approach | 122 Paris Avenue Sidewalk | 0300/0400 South Highland Avenue | 1400/1500 Harding Street | 2300 Lucille Street Approaches | 2112 Martha Street Sidewalk | 802 Montague Street Sidewalk | 1414 Montague Street Sidewalk | 1300/1500 Victoria Avenue | 1308 and 1311 Wisconsin Avenue Approaches | 0700 Furman Street | 1000 Furman Street | 3124 Alida Street Approach/Sidewalk | 3208-3224 Alida Street Sidewalk | 3232 Alida Street Sidewalk | 1620 Bruner Street Sidewalk | 1716 Bruner Street Approach/Sidewalk | 2018 Bruner Street Approach/Sidewalk | 3615 Elva Lane Approach | 1925 Grace Street Sidewalk | 1803 Latham Street Sidewalk | 2204 Pierce Avenue Sidewalk | 1725 Ridge Avenue Sidewalk | 2211 Sauber Avenue Sidewalk | 3700 Wind Point Drive | 1800 9th Street Sidewalk | 1600/2000 17th Avenue Sidewalk | 2100 18th Avenue Sidewalk | 1500 23rd Street Sidewalk | 1500 Arbor Court | 1200 Parmele Street Sidewalk | 0300/0400 Brown Avenue | 2207-2215 Melrose Street Sidewalk | 1405 Pierce Avenue Approach/Sidewalk | 1118 Cedar Street Sidewalk | 1502 Chestnut Street Sidewalk | 1000 Grant Street Sidewalk | 1600/1700 Green Street Sidewalk | 0300 North Johnston Avenue | 1406 School Street Sidewalk | 957-975 Arnold Avenue Approach | 3700/4000 Florida Avenue | 0700/0800 Green Meadow Avenue | 0500 Pearl Street | 0700/0800 Roland Avenue | 1600/1700 Rountree Lane | 1500/1600 Quentin Road | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. | [32 empty] | 45 | [12 empty] | 35 | [9 empty] | 50 | 130 | 30 | 3900
2 | Parkway Restoration | Lsum | 0 | 0.01 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | 0.04 | 0.03 | 0.01 | 0 | 0.01 | 0 | 0.06 | 0 | 0.03 | 0.03 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.02 | 0.01 | 0.05 | 0.01 | 0.01 | 0.03 | 0.01 | 0.04 | 0.01 | 0.01 | 0 | 0.01 | 0.01 | 0.03 | 0.03 | 0 | 0.01 | 0.11 | 0.07 | 0.03 | 0.07 | 0.06 | 0.07 |  | 1 | 175000 | 175000
3 | Inlet and Pipe Protection | Each | [10 empty] | 2 | 2 |  |  |  |  | 3 |  |  | 2 | [12 empty] | 6 | 2 | 13 | 7 |  |  | 2 | 2 |  |  |  |  | 2 | 6 | 4 | 1 |  | 15 | 6 | 2 | 3 |  | 2 |  | 82 | 60 | 4920
4 | Aggregate Base Repair, 10" | S.Y. | [10 empty] | 21 | 17 |  |  |  |  | 35 |  | 13 | 11 | [12 empty] | 14 |  |  |  |  | 9 |  | 19 | [6 empty] | 13 |  |  | 64 | 35 | 8 | 30 | 28 | 32 |  | 349 | 20 | 6980
5 | Bituminous Materials (Prime Coat) | Gal | [10 empty] | 210 | 170 |  |  |  |  | 350 |  | 130 | 110 | [12 empty] | 140 |  |  |  |  | 90 |  | 190 | [6 empty] | 130 |  |  | 640 | 350 | 80 | 300 | 280 | 320 |  | 3490 | 3 | 10470
6 | Aggregate (Prime Coat) | Tons | [10 empty] | 21 | 17 |  |  |  |  | 35 |  | 13 | 11 | [12 empty] | 14 |  |  |  |  | 9 |  | 19 | [6 empty] | 13 |  |  | 64 | 35 | 8 | 30 | 28 | 32 |  | 349 | 10 | 3490
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | [55 empty] | 500 | 500 | 80 | 40000
8 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | [10 empty] | 275 | 225 |  |  |  |  | 450 |  | 175 | 150 | [12 empty] | 175 |  |  |  |  | 125 |  | 250 | [6 empty] | 175 |  |  | 775 | 425 | 100 | 375 | 350 | 400 | 500 | 4925 | 80 | 394000
9 | Hot-Mix Asphalt, Hand Method | Tons | [12 empty] | 5 |  | 3 |  |  | 2 |  |  | 5 | [13 empty] | 20 | 8 | [7 empty] | 3 | 3 | 5 |  |  | 2 | [7 empty] | 56 | 300 | 16800
10 | P.C.C. Approach Pavement, 6" | S.Y. | [8 empty] | 13 |  | 118 | 62 | 32 |  |  |  | 234 | 32 | 180 | 72 | 43 |  |  |  | 16 | 16 | 18 | [10 empty] | 120 |  | 69 |  | 12 |  |  |  | 32 | 182 |  | 38 | 559 | 347 | 80 | 250 | 231 | 146 | 50 | 2952 | 80 | 236160
11 | P.C.C. Approach Pavement, 8" | S.Y. | [10 empty] | 4 |  |  |  | 15 |  |  |  |  | 28 | [19 empty] | 12 | [7 empty] | 9 |  |  |  |  | 57 |  |  | 50 | 175 | 95 | 16625
12 | P.C.C. Sidewalk, 4" | S.F. | 500 | 925 | 450 | 450 | 850 | 200 | 300 | 1000 |  | 150 | 2225 | 875 | 525 | 450 | 400 | 175 | 5175 |  | 2875 | 2000 | 650 | 1250 | 325 | 450 | 325 | 275 |  | 425 | 75 | 150 | 650 | 550 | 1025 | 1600 | 11475 | 3300 | 1675 | 3400 | 1875 | 3575 | 525 | 400 | 400 | 950 | 1475 | 6850 | 3300 | 500 | 750 | 4625 | 4050 | 3150 | 6350 | 1200 | 8375 | 5000 | 100475 | 9 | 904275
13 | Detectable Warnings, ADA Ramps | S.F. | [16 empty] | 20 |  | 80 | 40 | [10 empty] | 20 |  | 90 |  | 250 | 80 | [7 empty] | 20 | 20 | 60 | 40 |  |  | 80 |  |  | 40 | 20 | 80 |  | 940 | 30 | 28200
14 | Combination Curb and Gutter Removal | L.F. |  |  |  | 105 |  |  |  |  | 20 |  | 1200 | 1010 | 115 |  | 70 |  | 1325 | 70 | 785 | 735 | 80 |  |  |  | 20 | 20 | 20 |  |  |  | 25 |  | 200 |  | 455 | 150 |  | 820 |  | 1150 |  | 25 |  | 35 | 35 | 115 | 765 | 25 | 60 | 3165 | 2265 | 570 | 1930 | 1955 | 1775 | 1000 | 22095 | 15 | 331425
15 | Sidewalk Removal | S.F. | 500 | 925 | 450 | 450 | 850 | 200 | 300 | 1000 |  | 150 | 2225 | 875 | 525 | 450 | 400 | 175 | 5275 |  | 2875 | 2000 | 650 | 1250 | 325 | 450 | 325 | 275 |  | 425 | 75 | 150 | 650 | 550 | 1025 | 1600 | 11575 | 3575 | 1675 | 3400 | 1875 | 3575 | 525 | 400 | 400 | 950 | 1475 | 5250 | 3300 | 500 | 750 | 4625 | 4100 | 3150 | 6350 | 1300 | 8375 | 5000 | 99500 | 3 | 298500
16 | Approach Pavement Removal | S.Y. | [8 empty] | 13 |  | 122 | 62 | 32 |  | 24 |  | 234 | 32 | 199 | 117 | 43 |  |  |  | 16 | 16 | 18 | [8 empty] | 15 |  | 120 |  | 81 |  | 12 |  |  |  | 32 | 182 | 9 | 38 | 559 | 347 | 80 | 307 | 231 | 146 | 100 | 3187 | 25 | 79675
17 | Surface Removal, 2" | S.Y. | [10 empty] | 2100 | 1700 |  |  |  |  | 3500 |  | 1300 | 1100 | [12 empty] | 1400 |  |  |  |  | 900 |  | 1900 | [6 empty] | 1300 |  |  | 6400 | 3500 | 800 | 3000 | 2800 | 3200 | 1000 | 35900 | 3 | 107700
18 | Sanitary Riser/Valve Boxes to be Adjusted | Each | [55 empty] | 1 | 1 | 500 | 500
19 | Manholes to be Adjusted | Each | [10 empty] | 2 | 1 |  |  |  |  | 5 |  | 3 | [13 empty] | 7 |  |  |  |  | 3 |  | 1 | [6 empty] | 4 |  |  | 16 | 7 | 1 | 5 | 4 | 3 |  | 62 | 800 | 49600
20 | Manholes to be Reconstructed | Each | [55 empty] | 1 | 1 | 1500 | 1500
21 | Inlets to be Adjusted | Each | [32 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 |  |  | 6 | 4 |  | 2 |  |  |  | 18 | 1100 | 19800
22 | Inlets to be Adjusted with New Frame and Grate | Each | [32 empty] | 1 |  |  | 1 |  |  |  | 1 | [9 empty] | 7 | [6 empty] | 10 | 1700 | 17000
23 | Inlets to be Reconstructed | Each | [55 empty] | 1 | 1 | 1800 | 1800
24 | Inlets to be Reconstructed with New Frame and Grate | Each | [55 empty] | 1 | 1 | 2200 | 2200
25 | Inlet Special to be Repaired | Each | [32 empty] | 1 | [16 empty] | 1 |  |  |  | 7 |  | 1 | 10 | 2200 | 22000
26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. |  |  |  | 105 |  |  |  |  | 20 |  | 1200 | 1010 | 115 |  | 70 |  | 1325 | 70 | 785 | 735 | 80 |  |  |  | 20 | 20 | 20 |  |  |  | 25 |  | 605 |  | 455 | 150 |  | 820 |  | 1150 |  | 25 |  | 35 | 35 | 115 | 765 | 25 | 60 | 3165 | 2265 | 570 | 1930 | 1955 | 1775 | 1000 | 22500 | 30 | 675000
27 | Traffic Control and Protection | LSum | 0 | 0.01 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | 0.04 | 0.03 | 0.01 | 0 | 0.01 | 0 | 0.06 | 0 | 0.03 | 0.03 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.02 | 0.01 | 0.05 | 0.01 | 0.01 | 0.03 | 0.01 | 0.04 | 0.01 | 0.01 | 0 | 0.01 | 0.01 | 0.03 | 0.03 | 0 | 0.01 | 0.11 | 0.07 | 0.03 | 0.07 | 0.06 | 0.07 |  | 1 | 75000 | 75000
28 | Thermoplastic Pavement Markings, 4" | L.F. | [55 empty] | 100 | 100 | 3 | 300
29 | Thermoplastic Pavement Markings, 6" | L.F. | [16 empty] | 62 | [39 empty] | 62 | 4 | 248
30 | Thermoplastic Pavement Markings, 24" | L.F. | [11 empty] | 13 |  |  |  |  | 13 | [39 empty] | 26 | 12 | 312
31 | Subgrade Undercutting | C.Y. | [55 empty] | 50 | 50 | 300 | 15000
32 | Remove and Replace Brick Pavers | S.F. | [53 empty] | 100 |  |  | 100 | 20 | 2000
33 | [59 empty] | 0
34 | [59 empty] | 0
35 | [59 empty] | 0
36 | [59 empty] | 0
37 | [59 empty] | 0
38 | [59 empty] | 0
39 | [59 empty] | 0
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 6000 | 13600 | 5400 | 12625 | 12700 | 2400 | 3600 | 14500 | 2265 | 1800 | 134850 | 95156 | 18835 | 5400 | 13375 | 2100 | 215379 | 7110 | 120180 | 93200 | 19915 | 17500 | 3900 | 5400 | 8980 | 5880 | 2790 | 5100 | 900 | 1800 | 12025 | 9100 | 73600 | 21820 | 185255 | 56970 | 22600 | 113440 | 25120 | 144995 | 8800 | 9685 | 4800 | 16975 | 23395 | 98145 | 126155 | 8265 | 18790 | 405960 | 261570 | 91150 | 262020 | 201210 | 261645 | 224250 | #VALUE!
|  |  | 687.2136 | 887.9185 | 656.7065 | 928.0595 | 812.4535 | 208.7331 | 316.3109 | 895.9467 | 451.1846 | 234.4233 | 8885.6076 | 7111.3762 | 1657.0197 | 451.1846 | 902.3693 | 166.9865 | 13354.1016 | 671.1572 | 7785.7447 | 6483.5713 | 998.7076 | 1315.0185 | 362.8745 | 446.3677 | 656.7065 | 578.0301 | 332.3673 | 446.3677 | 136.4793 | 199.0993 | 796.3971 | 570.0019 | 5321.0885 | 1350.3426 | 12313.6474 | 3049.1089 | 1454.7092 | 7445.3492 | 1557.4701 | 9779.9487 | 682.3967 | 725.7489 | 409.438 | 1006.7358 | 1473.9768 | 7193.2638 | 7649.2654 | 677.5798 | 618.1711 | 27295.8672 | 17662.0317 | 6422.557 | 17662.0317 | 14450.7532 | 17662.0317 |  | 3540380
|  |  | 6687.2136 | 14487.9185 | 6056.7065 | 13553.0595 | 13512.4535 | 2608.7331 | 3916.3109 | 15395.9467 | 2716.1846 | 2034.4233 | 143735.6076 | 102267.3762 | 20492.0197 | 5851.1846 | 14277.3693 | 2266.9865 | 228733.1016 | 7781.1572 | 127965.7447 | 99683.5713 | 20913.7076 | 18815.0185 | 4262.8745 | 5846.3677 | 9636.7065 | 6458.0301 | 3122.3673 | 5546.3677 | 1036.4793 | 1999.0993 | 12821.3971 | 9670.0019 | 78921.0885 | 23170.3426 | 197568.6474 | 60019.1089 | 24054.7092 | 120885.3492 | 26677.4701 | 154774.9487 | 9482.3967 | 10410.7489 | 5209.438 | 17981.7358 | 24868.9768 | 105338.2638 | 133804.2654 | 8942.5798 | 19408.1711 | 433255.8672 | 279232.0317 | 97572.557 | 279682.0317 | 215660.7532 | 279307.0317 |  | 3540380
|  |  | 10700 | 13825 | 10225 | 14450 | 12650 | 3250 | 4925 | 13950 | 7025 | 3650 | 138350 | 110725 | 25800 | 7025 | 14050 | 2600 | 207925 | 10450 | 121225 | 100950 | 15550 | 20475 | 5650 | 6950 | 10225 | 9000 | 5175 | 6950 | 2125 | 3100 | 12400 | 8875 | 82850 | 21025 | 191725 | 47475 | 22650 | 115925 | 24250 | 152275 | 10625 | 11300 | 6375 | 15675 | 22950 | 112000 | 119100 | 10550 | 9625 | 425000 | 275000 | 100000 | 275000 | 225000 | 275000 | 0 | 3491600
#REF!
|  |  | 0.0030645 | 0.0039595 | 0.0029285 | 0.0041385 | 0.003623 | 0.00093081 | 0.0014105 | 0.0039953 | 0.002012 | 0.0010454 | 0.039624 | 0.031712 | 0.0073892 | 0.002012 | 0.0040239 | 0.00074464 | 0.05955 | 0.0029929 | 0.034719 | 0.028912 | 0.0044535 | 0.0058641 | 0.0016182 | 0.0019905 | 0.0029285 | 0.0025776 | 0.0014821 | 0.0019905 | 0.0006086 | 0.00088785 | 0.0035514 | 0.0025418 | 0.023728 | 0.0060216 | 0.05491 | 0.013597 | 0.006487 | 0.033201 | 0.0069452 | 0.043612 | 0.003043 | 0.0032363 | 0.0018258 | 0.0044893 | 0.0065729 | 0.032077 | 0.03411 | 0.0030215 | 0.0027566 | 0.12172 | 0.07876 | 0.02864 | 0.07876 | 0.06444 | 0.07876 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [11 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | TCI CONCRETE |  | Everlast Blacktop |  | Norwest Construction |  | DPI Construction |  | Stenstrom Excavation |  | Sjostrom & Sons
City of Rockford | [15 empty] | City of Rockford | [13 empty] | City of Rockford | [5 empty] | Rockford, IL |  | Elgin, IL |  | S. Beloit, IL |  | Pecatonica, IL |  | Rockford, IL |  | Rockford, IL
Bid On: City-Wide Street Repairs Group No. 3 - 2025 (Concrete) | [15 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name: | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond
Bid No.: 325-PW-033 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 130 | 30 | 3900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 130 | 30 | 3900 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 130 | 30 | 3900 | 425 | 55250 | 40 | 5200 | 74.16 | 9640.8 | 1 | 130 | 154 | 20020 | 75 | 9750
2 | Parkway Restoration | Lsum | 1 | 175000 | 175000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 175000 | 175000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 175000 | 175000 | 10000 | 10000 | 97313.19 | 97313.19 | 18182.2 | 18182.2 | 250000 | 250000 | 226784 | 226784 | 122000 | 122000
3 | Inlet and Pipe Protection | Each | 82 | 60 | 4920 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 82 | 60 | 4920 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 82 | 60 | 4920 | 0.01 | 0.82 | 30 | 2460 | 453.2 | 37162.4 | 75 | 6150 | 262 | 21484 | 230 | 18860
4 | Aggregate Base Repair, 10" | S.Y. | 349 | 20 | 6980 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Repair, 10" | S.Y. | 349 | 20 | 6980 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Repair, 10" | S.Y. | 349 | 20 | 6980 | 20 | 6980 | 17.8 | 6212.2 | 36.05 | 12581.45 | 23 | 8027 | 65.5 | 22859.5 | 15 | 5235
5 | Bituminous Materials (Prime Coat) | Gal | 3490 | 3 | 10470 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Bituminous Materials (Prime Coat) | Gal | 3490 | 3 | 10470 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Bituminous Materials (Prime Coat) | Gal | 3490 | 3 | 10470 | 3.49 | 12180.1 | 0.01 | 34.9 | 3.56 | 12424.4 | 3.49 | 12180.1 | 3.75 | 13087.5 | 4 | 13960
6 | Aggregate (Prime Coat) | Tons | 349 | 10 | 3490 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate (Prime Coat) | Tons | 349 | 10 | 3490 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate (Prime Coat) | Tons | 349 | 10 | 3490 | 0.01 | 3.49 | 0.01 | 3.49 | 0.01 | 3.49 | 0.01 | 3.49 | 0.01 | 3.49 | 0.01 | 3.49
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000 | 87.85 | 43925 | 108 | 54000 | 89.61 | 44805 | 88 | 44000 | 92 | 46000 | 102.3 | 51150
8 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 4925 | 80 | 394000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 4925 | 80 | 394000 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 4925 | 80 | 394000 | 89.37 | 440147.25 | 102 | 502350 | 93.46 | 460290.5 | 90 | 443250 | 93.75 | 461718.75 | 103 | 507275
9 | Hot-Mix Asphalt, Hand Method | Tons | 56 | 300 | 16800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt, Hand Method | Tons | 56 | 300 | 16800 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt, Hand Method | Tons | 56 | 300 | 16800 | 500 | 28000 | 114 | 6384 | 153 | 8568 | 150 | 8400 | 157.25 | 8806 | 170 | 9520
10 | P.C.C. Approach Pavement, 6" | S.Y. | 2952 | 80 | 236160 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | P.C.C. Approach Pavement, 6" | S.Y. | 2952 | 80 | 236160 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | P.C.C. Approach Pavement, 6" | S.Y. | 2952 | 80 | 236160 | 75 | 221400 | 101 | 298152 | 79.01 | 233237.52 | 85 | 250920 | 73.5 | 216972 | 100 | 295200
11 | P.C.C. Approach Pavement, 8" | S.Y. | 175 | 95 | 16625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | P.C.C. Approach Pavement, 8" | S.Y. | 175 | 95 | 16625 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | P.C.C. Approach Pavement, 8" | S.Y. | 175 | 95 | 16625 | 50 | 8750 | 110 | 19250 | 101.36 | 17738 | 85 | 14875 | 99.25 | 17368.75 | 130 | 22750
12 | P.C.C. Sidewalk, 4" | S.F. | 100475 | 9 | 904275 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Sidewalk, 4" | S.F. | 100475 | 9 | 904275 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Sidewalk, 4" | S.F. | 100475 | 9 | 904275 | 9 | 904275 | 10.25 | 1029868.75 | 8.41 | 844994.75 | 9 | 904275 | 8.75 | 879156.25 | 10 | 1004750
13 | Detectable Warnings, ADA Ramps | S.F. | 940 | 30 | 28200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | Detectable Warnings, ADA Ramps | S.F. | 940 | 30 | 28200 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | Detectable Warnings, ADA Ramps | S.F. | 940 | 30 | 28200 | 25 | 23500 | 49 | 46060 | 25 | 23500 | 25 | 23500 | 40.75 | 38305 | 25 | 23500
14 | Combination Curb and Gutter Removal | L.F. | 22095 | 15 | 331425 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | Combination Curb and Gutter Removal | L.F. | 22095 | 15 | 331425 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | Combination Curb and Gutter Removal | L.F. | 22095 | 15 | 331425 | 9 | 198855 | 5.6 | 123732 | 14.32 | 316400.4 | 9 | 198855 | 11 | 243045 | 14.55 | 321482.25
15 | Sidewalk Removal | S.F. | 99500 | 3 | 298500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Sidewalk Removal | S.F. | 99500 | 3 | 298500 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Sidewalk Removal | S.F. | 99500 | 3 | 298500 | 3.5 | 348250 | 1.74 | 173130 | 2.88 | 286560 | 3.5 | 348250 | 2.75 | 273625 | 2.5 | 248750
16 | Approach Pavement Removal | S.Y. | 3187 | 25 | 79675 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Approach Pavement Removal | S.Y. | 3187 | 25 | 79675 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Approach Pavement Removal | S.Y. | 3187 | 25 | 79675 | 22 | 70114 | 16 | 50992 | 28.84 | 91913.08 | 22 | 70114 | 21.25 | 67723.75 | 23 | 73301
17 | Surface Removal, 2" | S.Y. | 35900 | 3 | 107700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Surface Removal, 2" | S.Y. | 35900 | 3 | 107700 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Surface Removal, 2" | S.Y. | 35900 | 3 | 107700 | 2.94 | 105546 | 2.76 | 99084 | 2.94 | 105546 | 3.5 | 125650 | 3.5 | 125650 | 3.85 | 138215
18 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500 | 350 | 350 | 300 | 300 | 699.5 | 699.5 | 350 | 350 | 1524 | 1524 | 265 | 265
19 | Manholes to be Adjusted | Each | 62 | 800 | 49600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Manholes to be Adjusted | Each | 62 | 800 | 49600 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Manholes to be Adjusted | Each | 62 | 800 | 49600 | 550 | 34100 | 400 | 24800 | 1185.5 | 73501 | 800 | 49600 | 795 | 49290 | 1090 | 67580
20 | Manholes to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Manholes to be Reconstructed | Each | 1 | 1500 | 1500 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Manholes to be Reconstructed | Each | 1 | 1500 | 1500 | 1000 | 1000 | 1200 | 1200 | 1730.4 | 1730.4 | 3500 | 3500 | 1805 | 1805 | 1900 | 1900
21 | Inlets to be Adjusted | Each | 18 | 1100 | 19800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Inlets to be Adjusted | Each | 18 | 1100 | 19800 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Inlets to be Adjusted | Each | 18 | 1100 | 19800 | 1000 | 18000 | 400 | 7200 | 1608.62 | 28955.16 | 2000 | 36000 | 1414 | 25452 | 400 | 7200
22 | Inlets to be Adjusted with New Frame and Grate | Each | 10 | 1700 | 17000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Inlets to be Adjusted with New Frame and Grate | Each | 10 | 1700 | 17000 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Inlets to be Adjusted with New Frame and Grate | Each | 10 | 1700 | 17000 | 3500 | 35000 | 680 | 6800 | 2226.62 | 22266.2 | 2300 | 23000 | 2915 | 29150 | 800 | 8000
23 | Inlets to be Reconstructed | Each | 1 | 1800 | 1800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Inlets to be Reconstructed | Each | 1 | 1800 | 1800 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Inlets to be Reconstructed | Each | 1 | 1800 | 1800 | 1200 | 1200 | 1200 | 1200 | 2535.62 | 2535.62 | 2500 | 2500 | 305 | 305 | 1400 | 1400
24 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 2200 | 2200 | 1500 | 1500 | 1600 | 1600 | 3256.62 | 3256.62 | 3300 | 3300 | 4006 | 4006 | 1700 | 1700
| Page 1 | Sub |  | As read | 2750520 | [11 empty] | Page 3 | Sub |  | As read | 2750520 | [9 empty] | Page 1 | Sub |  | As read | 2750520 |  | 2568326.66 |  | 2557326.53 |  | 2656492.49 |  | 2826829.59 |  | 2794140.99 |  | 2953746.74
| Award to | Total |  | As corrected | 2750520 | [11 empty] | Award to | Total |  | As corrected | 2750520 | [9 empty] | Award to | Total |  | As corrected | 2750520 |  | 2568326.66 |  | 2557326.53 |  | 2656492.49 |  | 2826829.59 |  | 2794140.99 |  | 2953746.74
25 | Inlet Special to be Repaired | Each | 10 | 2200 | 22000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Inlet Special to be Repaired | Each | 10 | 2200 | 22000 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Inlet Special to be Repaired | Each | 10 | 2200 | 22000 | 1500 | 15000 | 1200 | 12000 | 2749.7 | 27497 | 2100 | 21000 | 2645 | 26450 | 300 | 3000
26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 22500 | 30 | 675000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 22500 | 30 | 675000 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 22500 | 30 | 675000 | 32 | 720000 | 34 | 765000 | 34.18 | 769050 | 32 | 720000 | 33.25 | 748125 | 44.6 | 1003500
27 | Traffic Control and Protection | LSum | 1 | 75000 | 75000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Traffic Control and Protection | LSum | 1 | 75000 | 75000 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Traffic Control and Protection | LSum | 1 | 75000 | 75000 | 20000 | 20000 | 167054.35 | 167054.35 | 47340 | 47340 | 42000 | 42000 | 55629 | 55629 | 191000 | 191000
28 | Thermoplastic Pavement Markings, 4" | L.F. | 100 | 3 | 300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Thermoplastic Pavement Markings, 4" | L.F. | 100 | 3 | 300 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Thermoplastic Pavement Markings, 4" | L.F. | 100 | 3 | 300 | 9 | 900 | 10 | 1000 | 9.45 | 945 | 3.2 | 320 | 5.5 | 550 | 16 | 1600
29 | Thermoplastic Pavement Markings, 6" | L.F. | 62 | 4 | 248 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Thermoplastic Pavement Markings, 6" | L.F. | 62 | 4 | 248 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Thermoplastic Pavement Markings, 6" | L.F. | 62 | 4 | 248 | 13.5 | 837 | 20 | 1240 | 14.18 | 879.16 | 3.8 | 235.6 | 6 | 372 | 26.55 | 1646.1
30 | Thermoplastic Pavement Markings, 24" | L.F. | 26 | 12 | 312 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Thermoplastic Pavement Markings, 24" | L.F. | 26 | 12 | 312 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Thermoplastic Pavement Markings, 24" | L.F. | 26 | 12 | 312 | 54 | 1404 | 20 | 520 | 56.7 | 1474.2 | 16 | 416 | 15.5 | 403 | 70 | 1820
31 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000 | 350 | 17500 | 40 | 2000 | 80 | 4000 | 150 | 7500 | 250 | 12500 | 135 | 6750
32 | Remove and Replace Brick Pavers | S.F. | 100 | 20 | 2000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Remove and Replace Brick Pavers | S.F. | 100 | 20 | 2000 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Remove and Replace Brick Pavers | S.F. | 100 | 20 | 2000 | 200 | 20000 | 20 | 2000 | 42.5 | 4250 | 50 | 5000 | 68 | 6800 | 58 | 5800
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 3540380 | [11 empty] | Page 4 | Total |  | As read | 3540380 | [9 empty] | Page 2 | Total |  | As read | 3540380 |  | 3363967.66 |  | 3508140.88 |  | 3511927.85 |  | 3623301.19 |  | 3644969.99 |  | 4168862.84
| Award to | Bid |  | As corrected | [5 empty] | 0 | [6 empty] | Award to | Bid |  | As corrected | #VALUE! | [9 empty] | Award to | Bid |  | As corrected | #VALUE! |  | 3363967.66 |  | 3508140.88 |  | 3511927.85 |  | 3623301.19 |  | 3644969.99 |  | 4168862.84
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to | Bid |  | As corrected | [12 empty] | Award to | Bid |  | As corrected | [10 empty] | Award to | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to | Bid |  | As corrected | [12 empty] | Award to | Bid |  | As corrected | [10 empty] | Award to | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 3 - 2025 (Concrete)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 130 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 82 |  | 0
4 | Aggregate Base Repair, 10" | S.Y. | 349 |  | 0
5 | Bituminous Materials (Prime Coat) | Gal | 3490 |  | 0
6 | Aggregate (Prime Coat) | Tons | 349 |  | 0
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 |  | 0
8 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 4925 |  | 0
9 | Hot-Mix Asphalt, Hand Method | Tons | 56 |  | 0
10 | P.C.C. Approach Pavement, 6" | S.Y. | 2952 |  | 0
11 | P.C.C. Approach Pavement, 8" | S.Y. | 175 |  | 0
12 | P.C.C. Sidewalk, 4" | S.F. | 100475 |  | 0
13 | Detectable Warnings, ADA Ramps | S.F. | 940 |  | 0
14 | Combination Curb and Gutter Removal | L.F. | 22095 |  | 0
15 | Sidewalk Removal | S.F. | 99500 |  | 0
16 | Approach Pavement Removal | S.Y. | 3187 |  | 0
17 | Surface Removal, 2" | S.Y. | 35900 |  | 0
18 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 |  | 0
19 | Manholes to be Adjusted | Each | 62 |  | 0
20 | Manholes to be Reconstructed | Each | 1 |  | 0
21 | Inlets to be Adjusted | Each | 18 |  | 0
22 | Inlets to be Adjusted with New Frame and Grate | Each | 10 |  | 0
23 | Inlets to be Reconstructed | Each | 1 |  | 0
24 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Inlet Special to be Repaired | Each | 10 |  | 0
26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 22500 |  | 0
27 | Traffic Control and Protection | LSum | 1 |  | 0
28 | Thermoplastic Pavement Markings, 4" | L.F. | 100 |  | 0
29 | Thermoplastic Pavement Markings, 6" | L.F. | 62 |  | 0
30 | Thermoplastic Pavement Markings, 24" | L.F. | 26 |  | 0
31 | Subgrade Undercutting | C.Y. | 50 |  | 0
32 | Remove and Replace Brick Pavers | S.F. | 100 |  | 0
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2025 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 130 | 30 | 3900
2 | Parkway Restoration | Lsum | 1 | 175000 | 175000
3 | Inlet and Pipe Protection | Each | 82 | 60 | 4920
4 | Aggregate Base Repair, 10" | S.Y. | 349 | 20 | 6980
5 | Bituminous Materials (Prime Coat) | Gal | 3490 | 3 | 10470
6 | Aggregate (Prime Coat) | Tons | 349 | 10 | 3490
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | Tons | 500 | 80 | 40000
8 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 4925 | 80 | 394000
9 | Hot-Mix Asphalt, Hand Method | Tons | 56 | 300 | 16800
10 | P.C.C. Approach Pavement, 6" | S.Y. | 2952 | 80 | 236160
11 | P.C.C. Approach Pavement, 8" | S.Y. | 175 | 95 | 16625
12 | P.C.C. Sidewalk, 4" | S.F. | 100475 | 9 | 904275
13 | Detectable Warnings, ADA Ramps | S.F. | 940 | 30 | 28200
14 | Combination Curb and Gutter Removal | L.F. | 22095 | 15 | 331425
15 | Sidewalk Removal | S.F. | 99500 | 3 | 298500
16 | Approach Pavement Removal | S.Y. | 3187 | 25 | 79675
17 | Surface Removal, 2" | S.Y. | 35900 | 3 | 107700
18 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 1 | 500 | 500
19 | Manholes to be Adjusted | Each | 62 | 800 | 49600
20 | Manholes to be Reconstructed | Each | 1 | 1500 | 1500
21 | Inlets to be Adjusted | Each | 18 | 1100 | 19800
22 | Inlets to be Adjusted with New Frame and Grate | Each | 10 | 1700 | 17000
23 | Inlets to be Reconstructed | Each | 1 | 1800 | 1800
24 | Inlets to be Reconstructed with New Frame and Grate | Each | 1 | 2200 | 2200
|  |  |  | Sub Total | 2750520
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2025 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Inlet Special to be Repaired | Each | 10 | 2200 | 22000
26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 22500 | 30 | 675000
27 | Traffic Control and Protection | LSum | 1 | 75000 | 75000
28 | Thermoplastic Pavement Markings, 4" | L.F. | 100 | 3 | 300
29 | Thermoplastic Pavement Markings, 6" | L.F. | 62 | 4 | 248
30 | Thermoplastic Pavement Markings, 24" | L.F. | 26 | 12 | 312
31 | Subgrade Undercutting | C.Y. | 50 | 300 | 15000
32 | Remove and Replace Brick Pavers | S.F. | 100 | 20 | 2000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2025 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 3 - 2025 (Concrete)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from June 20, 2022 to July 7, 2022 | [7 empty] | (Road District)
| Payable to: | P.O. # 22305291 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2025 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 130 | C.Y.
2 | Parkway Restoration | 1 | Lsum
3 | Inlet and Pipe Protection | 82 | Each
4 | Aggregate Base Repair, 10" | 349 | S.Y.
5 | Bituminous Materials (Prime Coat) | 3490 | Gal
6 | Aggregate (Prime Coat) | 349 | Tons
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.25" | 500 | Tons
8 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 4925 | Tons
9 | Hot-Mix Asphalt, Hand Method | 56 | Tons
10 | P.C.C. Approach Pavement, 6" | 2952 | S.Y.
11 | P.C.C. Approach Pavement, 8" | 175 | S.Y.
12 | P.C.C. Sidewalk, 4" | 100475 | S.F.
13 | Detectable Warnings, ADA Ramps | 940 | S.F.
14 | Combination Curb and Gutter Removal | 22095 | L.F.
15 | Sidewalk Removal | 99500 | S.F.
16 | Approach Pavement Removal | 3187 | S.Y.
17 | Surface Removal, 2" | 35900 | S.Y.
18 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | Each
19 | Manholes to be Adjusted | 62 | Each
20 | Manholes to be Reconstructed | 1 | Each
21 | Inlets to be Adjusted | 18 | Each
22 | Inlets to be Adjusted with New Frame and Grate | 10 | Each
23 | Inlets to be Reconstructed | 1 | Each
24 | Inlets to be Reconstructed with New Frame and Grate | 1 | Each
Sub Total |  |  |  | 0 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from June 20, 2022 to July 7, 2022 | [7 empty] | (Road District)
| Payable to: | [5 empty] | MUNICIPALITY | City of Rockford
| Address: | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2025 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Inlet Special to be Repaired | 10 | Each
26 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 22500 | L.F.
27 | Traffic Control and Protection | 1 | LSum
28 | Thermoplastic Pavement Markings, 4" | 100 | L.F.
29 | Thermoplastic Pavement Markings, 6" | 62 | L.F.
30 | Thermoplastic Pavement Markings, 24" | 26 | L.F.
31 | Subgrade Undercutting | 50 | C.Y.
32 | Remove and Replace Brick Pavers | 100 | S.F.
Total |  |  |  | 0 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
[8 empty] | DEDUCT RETAINAGE | 10% | 0
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from June 20, 2022 to July 7, 2022 | [7 empty] | (Road District)
| Payable to: | [5 empty] | MUNICIPALITY | City of Rockford
| Address: | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2025 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 0 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from June 20, 2022 to July 7, 2022 | [7 empty] | (Road District)
| Payable to: | [5 empty] | MUNICIPALITY | City of Rockford
| Address: | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 3 - 2025 (Concrete)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 0 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | 0
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.