## Item List
| City -Wide Street Repairs Group No. 4 - 2025 (Alleys) | [17 empty] | 538850
Summary Of Quantities |  |  | 2nd Ward |  |  | 5th Ward | 6th Ward |  | 7th Ward | 11th Ward | 11th Ward |  | 12th Ward | 13th Ward | 13th Ward
No. | Item | Units | Alley 448 | Alley 737 | Alley 772 | Alley 190 | Alley 32 | Alley 56 | Alleys 419 and 420 | Alley 67 | Alley 465 | Alley 488 | Alley 572 | Alley 888 | Alley 991 | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. |  |  |  |  | 145 | 235 | 290 | [7 empty] | 670 | 40 | 26800
2 | Parkway Restoration | Lsum | 0.08 | 0.04 | 0.08 | 0.1 | 0.07 | 0.08 | 0.15 | 0.02 | 0.03 | 0.12 | 0.08 | 0.07 | 0.08 |  | 1 | 10000 | 10000
3 | Inlet and Pipe Protection | Each | [13 empty] | 1 | 1 | 100 | 100
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons |  |  |  |  | 225 | 265 | 445 | [7 empty] | 935 | 25 | 23375
5 | Aggregate Base Repair, 10" | S.Y. | 65 | 55 | 60 | 100 |  |  | 40 | 40 |  | 80 | 70 | 60 | 95 |  | 665 | 25 | 16625
6 | Bituminous Materials (Prime Coat) | Gal | 65 | 55 | 60 | 100 | 40 | 65 | 120 | 40 |  | 80 | 70 | 60 | 95 |  | 850 | 3 | 2550
7 | Aggregate (Prime Coat) | Tons | 7 | 5 | 6 | 10 | 4 | 6 | 12 | 4 |  | 8 | 7 | 6 | 10 |  | 85 | 10 | 850
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons |  |  |  |  | 50 | 75 | 100 | [6 empty] | 100 | 325 | 115 | 37375
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons |  |  |  |  | 50 | 75 | 100 | [6 empty] | 100 | 325 | 115 | 37375
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 100 | 75 | 90 | 135 |  |  | 60 | 60 |  | 125 | 100 | 100 | 140 | 100 | 1085 | 115 | 124775
11 | Hot-Mix Asphalt, Hand Method | Tons | [13 empty] | 10 | 10 | 300 | 3000
12 | P.C.C. Approach Pavement, 6" | S.Y. | [13 empty] | 50 | 50 | 70 | 3500
13 | P.C.C. Approach Pavement, 8" | S.Y. | 39 |  | 28 | 23 | 22 | 19 | 10 |  | 117 | 225 | 19 | 25 | 18 | 50 | 595 | 85 | 50575
14 | P.C.C. Sidewalk, 4" | S.F. | 500 |  | 600 | 425 | 225 |  | 125 |  |  |  |  | 200 | 225 | 500 | 2800 | 9 | 25200
15 | Combination Curb and Gutter Removal | L.F. | 100 |  | 95 | 60 | 50 |  | 30 |  |  |  | 25 | 40 | 30 | 100 | 530 | 20 | 10600
16 | Sidewalk Removal | S.F. | 500 |  | 600 | 425 | 225 |  | 125 |  |  |  |  | 200 | 225 | 500 | 2800 | 2.5 | 7000
17 | Approach Pavement Removal | S.Y. | 39 |  | 28 | 23 | 22 | 19 | 10 |  | 117 | 225 | 19 | 25 | 18 | 100 | 645 | 30 | 19350
18 | Surface Removal, 2" | S.Y. | 650 | 550 | 600 | 1000 |  |  | 400 | 400 |  | 800 | 700 | 600 | 950 | 1000 | 7650 | 6 | 45900
19 | Sanitary Riser/Valve Boxes to be Adjusted | S.Y. | [13 empty] | 1 | 1 | 500 | 500
20 | Manholes to be Adjusted | Each | 1 | [5 empty] | 1 |  |  | 2 |  |  |  |  | 4 | 1000 | 4000
21 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 100 |  | 95 | 60 | 50 |  | 30 |  |  |  | 25 | 40 | 30 | 100 | 530 | 40 | 21200
22 | Traffic Control and Protection | Lsum | 0.08 | 0.04 | 0.08 | 0.1 | 0.07 | 0.08 | 0.15 | 0.02 | 0.03 | 0.12 | 0.08 | 0.07 | 0.08 |  | 1 | 25000 | 25000
23 | Remove and Replace Brick Pavers | S.F. | [11 empty] | 160 |  |  | 160 | 20 | 3200
24 | Non-Special Waste Disposal | C.Y. | [13 empty] | 200 | 200 | 35 | 7000
25 | Special Waste Disposal | C.Y. | [13 empty] | 200 | 200 | 45 | 9000
26 | Soil Disposal Analysis | Each | [13 empty] | 10 | 10 | 1100 | 11000
27 | Special Waste Plans and Reports (Special) | Lsum | [13 empty] | 1 | 1 | 3000 | 3000
28 | Subgrade Undercutting | C.Y. | [13 empty] | 50 | 50 | 200 | 10000
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 37325 | 14915 | 34310 | 39057.5 | 33652.5 | 38515 | 67142.5 | 11160 | 14505 | 53570 | 24215 | 30065 | 33817.5 | 106600 | #VALUE!
|  |  | 9183.7018 | 3822.5038 | 8311.3713 | 10540.6603 | 7311.8259 | 8323.487 | 15804.9327 | 2641.2229 | 3374.2229 | 12285.3214 | 8814.1729 | 7608.6606 | 8577.9167 |  | 538850
|  |  | 46508.7018 | 18737.5038 | 42621.3713 | 49598.1603 | 40964.3259 | 46838.487 | 82947.4327 | 13801.2229 | 17879.2229 | 65855.3214 | 33029.1729 | 37673.6606 | 42395.4167 |  | 538850
|  |  | 37900 | 15775 | 34300 | 43500 | 30175 | 34350 | 65225 | 10900 | 13925 | 50700 | 36375 | 31400 | 35400 | 0 | 439925
#REF!
|  |  | 0.086151 | 0.035858 | 0.077968 | 0.09888 | 0.068591 | 0.078081 | 0.14826 | 0.024777 | 0.031653 | 0.11525 | 0.082685 | 0.071376 | 0.080468 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | Stenstrom Excavation |  | Norwest Construction |  | DPI Construction | [5 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | Rockford, IL |  | South Beloit, IL |  | Pecatonica, IL | [5 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 4 - 2025 (Alleys) | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond | [5 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
Bid No.: 425-PW-040 Vendors Notified: 236 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 670 | 40 | 26800 | 45.5 | 30485 | 35 | 23450 | 48.87 | 32742.9 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 670 | 40 | 26800 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 670 | 40 | 26800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 | 8100 | 8100 | 43215 | 43215 | 9684.08 | 9684.08 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 10000 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 1 | 100 | 100 | 121 | 121 | 125 | 125 | 212.83 | 212.83 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 1 | 100 | 100 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 1 | 100 | 100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 935 | 25 | 23375 | 34.75 | 32491.25 | 10.5 | 9817.5 | 39.47 | 36904.45 |  | 0 |  | 0 | 4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 935 | 25 | 23375 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 935 | 25 | 23375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Aggregate Base Repair, 10" | S.Y. | 665 | 25 | 16625 | 0.01 | 6.65 | 0.01 | 6.65 | 0.01 | 6.65 |  | 0 |  | 0 | 5 | Aggregate Base Repair, 10" | S.Y. | 665 | 25 | 16625 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Aggregate Base Repair, 10" | S.Y. | 665 | 25 | 16625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Bituminous Materials (Prime Coat) | Gal | 850 | 3 | 2550 | 0.01 | 8.5 | 0.01 | 8.5 | 13.36 | 11356 |  | 0 |  | 0 | 6 | Bituminous Materials (Prime Coat) | Gal | 850 | 3 | 2550 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Bituminous Materials (Prime Coat) | Gal | 850 | 3 | 2550 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Aggregate (Prime Coat) | Tons | 85 | 10 | 850 | 0.01 | 0.85 | 0.01 | 0.85 | 73.09 | 6212.65 |  | 0 |  | 0 | 7 | Aggregate (Prime Coat) | Tons | 85 | 10 | 850 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Aggregate (Prime Coat) | Tons | 85 | 10 | 850 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 325 | 115 | 37375 | 124 | 40300 | 118.11 | 38385.75 | 136.77 | 44450.25 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 325 | 115 | 37375 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 325 | 115 | 37375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 325 | 115 | 37375 | 130 | 42250 | 118.11 | 38385.75 | 136.77 | 44450.25 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 325 | 115 | 37375 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 325 | 115 | 37375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1085 | 115 | 124775 | 136.5 | 148102.5 | 118.11 | 128149.35 | 130.88 | 142004.8 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1085 | 115 | 124775 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1085 | 115 | 124775 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 | 356 | 3560 | 400 | 4000 | 234 | 2340 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 50 | 70 | 3500 | 58.75 | 2937.5 | 52 | 2600 | 118.14 | 5907 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 50 | 70 | 3500 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 50 | 70 | 3500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 595 | 85 | 50575 | 94 | 55930 | 90 | 53550 | 131.12 | 78016.4 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 595 | 85 | 50575 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 595 | 85 | 50575 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 2800 | 9 | 25200 | 9 | 25200 | 10.45 | 29260 | 10.17 | 28476 |  | 0 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 2800 | 9 | 25200 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 2800 | 9 | 25200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Combination Curb and Gutter Removal | L.F. | 530 | 20 | 10600 | 19 | 10070 | 14.5 | 7685 | 11.87 | 6291.1 |  | 0 |  | 0 | 15 | Combination Curb and Gutter Removal | L.F. | 530 | 20 | 10600 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Combination Curb and Gutter Removal | L.F. | 530 | 20 | 10600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Sidewalk Removal | S.F. | 2800 | 2.5 | 7000 | 3.25 | 9100 | 2.9 | 8120 | 1.87 | 5236 |  | 0 |  | 0 | 16 | Sidewalk Removal | S.F. | 2800 | 2.5 | 7000 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Sidewalk Removal | S.F. | 2800 | 2.5 | 7000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Approach Pavement Removal | S.Y. | 645 | 30 | 19350 | 22.75 | 14673.75 | 43.25 | 27896.25 | 24.97 | 16105.65 |  | 0 |  | 0 | 17 | Approach Pavement Removal | S.Y. | 645 | 30 | 19350 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Approach Pavement Removal | S.Y. | 645 | 30 | 19350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Surface Removal, 2" | S.Y. | 7650 | 6 | 45900 | 6.75 | 51637.5 | 9.11 | 69691.5 | 9.54 | 72981 |  | 0 |  | 0 | 18 | Surface Removal, 2" | S.Y. | 7650 | 6 | 45900 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Surface Removal, 2" | S.Y. | 7650 | 6 | 45900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Sanitary Riser/Valve Boxes to be Adjusted | S.Y. | 1 | 500 | 500 | 535 | 535 | 275 | 275 | 278.5 | 278.5 |  | 0 |  | 0 | 19 | Sanitary Riser/Valve Boxes to be Adjusted | S.Y. | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Sanitary Riser/Valve Boxes to be Adjusted | S.Y. | 1 | 500 | 500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | Manholes to be Adjusted | Each | 4 | 1000 | 4000 | 1546 | 6184 | 850 | 3400 | 928.33 | 3713.32 |  | 0 |  | 0 | 20 | Manholes to be Adjusted | Each | 4 | 1000 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | Manholes to be Adjusted | Each | 4 | 1000 | 4000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 530 | 40 | 21200 | 50 | 26500 | 41.3 | 21889 | 50.52 | 26775.6 |  | 0 |  | 0 | 21 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 530 | 40 | 21200 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 530 | 40 | 21200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Traffic Control and Protection | Lsum | 1 | 25000 | 25000 | 19989 | 19989 | 67817.45 | 67817.45 | 3851.87 | 3851.87 |  | 0 |  | 0 | 22 | Traffic Control and Protection | Lsum | 1 | 25000 | 25000 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Traffic Control and Protection | Lsum | 1 | 25000 | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Remove and Replace Brick Pavers | S.F. | 160 | 20 | 3200 | 20 | 3200 | 18 | 2880 | 63.87 | 10219.2 |  | 0 |  | 0 | 23 | Remove and Replace Brick Pavers | S.F. | 160 | 20 | 3200 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Remove and Replace Brick Pavers | S.F. | 160 | 20 | 3200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Non-Special Waste Disposal | C.Y. | 200 | 35 | 7000 | 0.01 | 2 | 32 | 6400 | 0.01 | 2 |  | 0 |  | 0 | 24 | Non-Special Waste Disposal | C.Y. | 200 | 35 | 7000 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Non-Special Waste Disposal | C.Y. | 200 | 35 | 7000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 505850 |  | 531384.5 |  | 587008.55 |  | 588218.5 | [5 empty] | Page 3 | Sub |  | As read | 505850 | [9 empty] | Page 1 | Sub |  | As read | 505850
| Award to Stenstrom Excavation | Total |  | As corrected | 505850 |  | 531384.5 |  | 587008.55 |  | 588218.5 | [5 empty] | Award to Stenstrom Excavation | Total |  | As corrected | 505850 | [9 empty] | Award to Stenstrom Excavation | Total |  | As corrected | 505850
25 | Special Waste Disposal | C.Y. | 200 | 45 | 9000 | 0.01 | 2 | 37 | 7400 | 0.01 | 2 |  | 0 |  | 0 | 25 | Special Waste Disposal | C.Y. | 200 | 45 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Special Waste Disposal | C.Y. | 200 | 45 | 9000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Soil Disposal Analysis | Each | 10 | 1100 | 11000 | 0.01 | 0.1 | 750 | 7500 | 1250 | 12500 |  | 0 |  | 0 | 26 | Soil Disposal Analysis | Each | 10 | 1100 | 11000 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Soil Disposal Analysis | Each | 10 | 1100 | 11000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Special Waste Plans and Reports (Special) | Lsum | 1 | 3000 | 3000 | 0.01 | 0.01 | 2000 | 2000 | 4200 | 4200 |  | 0 |  | 0 | 27 | Special Waste Plans and Reports (Special) | Lsum | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Special Waste Plans and Reports (Special) | Lsum | 1 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Subgrade Undercutting | C.Y. | 50 | 200 | 10000 | 93 | 4650 | 80 | 4000 | 104.07 | 5203.5 |  | 0 |  | 0 | 28 | Subgrade Undercutting | C.Y. | 50 | 200 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Subgrade Undercutting | C.Y. | 50 | 200 | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
#VALUE! | * AS READ |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
#VALUE! | √ AS CORRECTED |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 538850 |  | 536036.61 |  | 607908.55 |  | 610124.02 | [5 empty] | Page 4 | Total |  | As read | 538850 | [9 empty] | Page 2 | Total |  | As read | 538850
| Award to Stenstrom Excavation | Bid |  | As corrected |  |  | 536036.61 | 0 | 607908.55 | 0 | 610124 | [5 empty] | Award to Stenstrom Excavation | Bid |  | As corrected | #VALUE! | [9 empty] | Award to Stenstrom Excavation | Bid |  | As corrected | #VALUE!
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | [12 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to Stenstrom Excavation | Bid |  | As corrected |  |  | 1608109.83 | [9 empty] | Award to Stenstrom Excavation | Bid |  | As corrected | [10 empty] | Award to Stenstrom Excavation | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to Stenstrom Excavation | Bid |  | As corrected | [12 empty] | Award to Stenstrom Excavation | Bid |  | As corrected | [10 empty] | Award to Stenstrom Excavation | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 4 - 2025 (Alleys)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 670 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 1 |  | 0
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 935 |  | 0
5 | Aggregate Base Repair, 10" | S.Y. | 665 |  | 0
6 | Bituminous Materials (Prime Coat) | Gal | 850 |  | 0
7 | Aggregate (Prime Coat) | Tons | 85 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 325 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 325 |  | 0
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1085 |  | 0
11 | Hot-Mix Asphalt, Hand Method | Tons | 10 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 50 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 595 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 2800 |  | 0
15 | Combination Curb and Gutter Removal | L.F. | 530 |  | 0
16 | Sidewalk Removal | S.F. | 2800 |  | 0
17 | Approach Pavement Removal | S.Y. | 645 |  | 0
18 | Surface Removal, 2" | S.Y. | 7650 |  | 0
19 | Sanitary Riser/Valve Boxes to be Adjusted | S.Y. | 1 |  | 0
20 | Manholes to be Adjusted | Each | 4 |  | 0
21 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 530 |  | 0
22 | Traffic Control and Protection | Lsum | 1 |  | 0
23 | Remove and Replace Brick Pavers | S.F. | 160 |  | 0
24 | Non-Special Waste Disposal | C.Y. | 200 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Special Waste Disposal | C.Y. | 200 |  | 0
26 | Soil Disposal Analysis | Each | 10
27 | Special Waste Plans and Reports (Special) | Lsum | 1
28 | Subgrade Undercutting | C.Y. | 50
#VALUE! | * AS READ
#VALUE! | √ AS CORRECTED
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | #VALUE!
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2025 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 670 | 40 | 26800
2 | Parkway Restoration | Lsum | 1 | 10000 | 10000
3 | Inlet and Pipe Protection | Each | 1 | 100 | 100
4 | Aggregate Base Course, Type B, CA-6, 10" | Tons | 935 | 25 | 23375
5 | Aggregate Base Repair, 10" | S.Y. | 665 | 25 | 16625
6 | Bituminous Materials (Prime Coat) | Gal | 850 | 3 | 2550
7 | Aggregate (Prime Coat) | Tons | 85 | 10 | 850
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | Tons | 325 | 115 | 37375
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | Tons | 325 | 115 | 37375
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | Tons | 1085 | 115 | 124775
11 | Hot-Mix Asphalt, Hand Method | Tons | 10 | 300 | 3000
12 | P.C.C. Approach Pavement, 6" | S.Y. | 50 | 70 | 3500
13 | P.C.C. Approach Pavement, 8" | S.Y. | 595 | 85 | 50575
14 | P.C.C. Sidewalk, 4" | S.F. | 2800 | 9 | 25200
15 | Combination Curb and Gutter Removal | L.F. | 530 | 20 | 10600
16 | Sidewalk Removal | S.F. | 2800 | 2.5 | 7000
17 | Approach Pavement Removal | S.Y. | 645 | 30 | 19350
18 | Surface Removal, 2" | S.Y. | 7650 | 6 | 45900
19 | Sanitary Riser/Valve Boxes to be Adjusted | S.Y. | 1 | 500 | 500
20 | Manholes to be Adjusted | Each | 4 | 1000 | 4000
21 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 530 | 40 | 21200
22 | Traffic Control and Protection | Lsum | 1 | 25000 | 25000
23 | Remove and Replace Brick Pavers | S.F. | 160 | 20 | 3200
24 | Non-Special Waste Disposal | C.Y. | 200 | 35 | 7000
|  |  |  | Sub Total | 505850
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2025 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Special Waste Disposal | C.Y. | 200 | 45 | 9000
26 | Soil Disposal Analysis | Each | 10 | 1100 | 11000
27 | Special Waste Plans and Reports (Special) | Lsum | 1 | 3000 | 3000
28 | Subgrade Undercutting | C.Y. | 50 | 200 | 10000
|  |  |  | 0 | #VALUE!
#VALUE! | * AS READ |  |  | 0 | #VALUE!
#VALUE! | √ AS CORRECTED |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2025 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 4 - 2025 (Alleys)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 9, 2024 to October 11, 2024 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2025 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 670 | C.Y. | 23450 |  |  |  |  | 35
2 | Parkway Restoration | 1 | Lsum | 43215 |  |  |  |  | 43215
3 | Inlet and Pipe Protection | 1 | Each | 125 |  |  |  |  | 125
4 | Aggregate Base Course, Type B, CA-6, 10" | 935 | Tons | 9817.5 |  |  |  |  | 10.5
5 | Aggregate Base Repair, 10" | 665 | S.Y. | 6.65 |  |  |  |  | 0.01
6 | Bituminous Materials (Prime Coat) | 850 | Gal | 8.5 |  |  |  |  | 0.01
7 | Aggregate (Prime Coat) | 85 | Tons | 0.85 |  |  |  |  | 0.01
8 | Hot-Mix Asphalt Binder Course, IL-9.5, N50, 1.5" | 325 | Tons | 38385.75 |  |  |  |  | 118.11
9 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 1.5" | 325 | Tons | 38385.75 |  |  |  |  | 118.11
10 | Hot-Mix Asphalt Surface Course, Mix "D", N50, 2" | 1085 | Tons | 128149.35 |  |  |  |  | 118.11
11 | Hot-Mix Asphalt, Hand Method | 10 | Tons | 4000 |  |  |  |  | 400
12 | P.C.C. Approach Pavement, 6" | 50 | S.Y. | 2600 |  |  |  |  | 52
13 | P.C.C. Approach Pavement, 8" | 595 | S.Y. | 53550 |  |  |  |  | 90
14 | P.C.C. Sidewalk, 4" | 2800 | S.F. | 29260 |  |  |  |  | 10.45
15 | Combination Curb and Gutter Removal | 530 | L.F. | 7685 |  |  |  |  | 14.5
16 | Sidewalk Removal | 2800 | S.F. | 8120 |  |  |  |  | 2.9
17 | Approach Pavement Removal | 645 | S.Y. | 27896.25 |  |  |  |  | 43.25
18 | Surface Removal, 2" | 7650 | S.Y. | 69691.5 |  |  |  |  | 9.11
19 | Sanitary Riser/Valve Boxes to be Adjusted | 1 | S.Y. | 275 |  |  |  |  | 275
20 | Manholes to be Adjusted | 4 | Each | 3400 |  |  |  |  | 850
21 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 530 | L.F. | 21889 |  |  |  |  | 41.3
22 | Traffic Control and Protection | 1 | Lsum | 67817.45 |  |  |  |  | 67817.45
23 | Remove and Replace Brick Pavers | 160 | S.F. | 2880 |  |  |  |  | 18
24 | Non-Special Waste Disposal | 200 | C.Y. | 6400 |  |  |  |  | 32
Sub Total |  |  |  | 587008.55 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2024 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2024 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S PAYMENT ESTIMATE
| Estimate No. 1 from September 9, 2024 to October 11, 2024 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2025 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Special Waste Disposal | 200 | C.Y. | 7400 |  |  |  |  | 37
26 | Soil Disposal Analysis | 10 | Each | 7500 |  |  |  |  | 750
27 | Special Waste Plans and Reports (Special) | 1 | Lsum | 2000 |  |  |  |  | 2000
28 | Subgrade Undercutting | 50 | C.Y. | 4000 |  |  |  |  | 80
#VALUE! | * AS READ
#VALUE! | √ AS CORRECTED
Total |  |  |  | 607908.55 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
[8 empty] | DEDUCT RETAINAGE | 5% | 0
[8 empty] | BALANCE DUE ON COMPLETED WORK | . | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2024 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2024. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6302
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 9, 2024 to October 11, 2024 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2025 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 607908.55 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from September 9, 2024 to October 11, 2024 | [7 empty] | (Road District)
| Payable to: Norwest Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: South Beloit, IL Bid Bond | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 4 - 2025 (Alleys)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 607908.55 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | Stenstrom Excavation
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.