## Item List
97770
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | PAVEMENT REMOVAL | SQ YD | 450 | 15 | 6750
2 | PAVEMENT MARKING TO BE REMOVED, 6" | FOOT | 286 | 5 | 1430
3 | PAVEMENT MARKING TO BE REMOVED, 24" | FOOT | 34 | 8 | 272
4 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 1 | 1000 | 1000
5 | EX. HANDHOLE TO BE ADJUSTED | EACH | 2 | 1000 | 2000
6 | EX. PEDESTRIAN PUSH BUTTON TO BE REPLACED | EACH | 2 | 500 | 1000
7 | EX. SIGN TO BE REMOVED AND REPLACED | EACH | 1 | 200 | 200
8 | EX. SIGN TO BE RELOCATED | EACH | 2 | 200 | 400
9 | EX. BENCH TO BE REMOVED AND REINSTALLED | EACH | 1 | 500 | 500
10 | PCC SIDEWALK, 4" (6" THRU DRIVEWAY) | SQ FT | 2175 | 10 | 21750
11 | PCC PAVEMENT, 6" (DRIVEWAY) | SQ YD | 31 | 75 | 2325
12 | CLASS B PAVEMENT PATCH | SQ YD | 70 | 80 | 5600
13 | HMA SURFACE COURSE, 3" | SQ YD | 46 | 50 | 2300
14 | AGGREGATE BASE COURSE, TYPE B, 10" | FOOT | 46 | 20 | 920
15 | PCC CURB, TYPE B- 6.24 | FOOT | 300 | 60 | 18000
16 | DETECTABLE WARNINGS | SQ FT | 31 | 40 | 1240
17 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" WHITE | FOOT | 273 | 3 | 819
18 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" WHITE | FOOT | 33 | 8 | 264
19 | TRAFFIC CONTROL & PROTECTION | LSUM | 1 | 20000 | 20000
20 | MOBILIZATION | LSUM | 1 | 10000 | 10000
21 | PARKWAY RESTORATION | LSUM | 1 | 1000 | 1000
22 |  |  |  | 0
23 |  |  |  | 0
24 |  |  |  | 0
25 |  |  |  | 0
26 |  |  |  | 0
27 |  |  |  | 0
28 |  |  |  | 0
29 |  |  |  | 0
30 |  |  |  | 0
31 |  |  |  | 0
32 |  |  |  | 0
33 |  |  |  | 0
34 |  |  |  | 0
35 |  |  |  | 0
36 |  |  |  | 0
37 |  |  |  | 0
38 |  |  |  | 0
39 |  |  |  | 0
40 |  |  |  | 0
41 |  |  |  | 0
42 |  |  |  | 0
43 |  |  |  | 0
44 |  |  |  | 0
45 |  |  |  | 0
46 |  |  |  | 0
47 |  |  |  | 0
48 |  |  |  | 0
49 |  |  |  | 0
50 |  |  |  | 0
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | DPI Construction |  | Stenstrom Excavation |  | N-Trak Group |  | Rockford Concrete |  | Norwest Construction |  | Alliance Contractors
City of Rockford | [5 empty] | Pecatonica, IL |  | Rockford, IL |  | Loves Park, IL |  | Rockford, IL |  | South Beloit, IL |  | Woodstock, IL
E. State St. Sidewalk Improvements | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond |  | Bid Bond
Bid No.:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | PAVEMENT REMOVAL | SQ YD | 450 | 15 | 6750 | 11.5 | 5175 | 38 | 17100 | 22 | 9900 | 57 | 25650 | 100 | 45000 | 25 | 11250
2 | PAVEMENT MARKING TO BE REMOVED, 6" | FOOT | 286 | 5 | 1430 | 7.5 | 2145 | 6.15 | 1758.9 | 6 | 1716 | 6 | 1716 | 6.6 | 1887.6 | 6 | 1716
3 | PAVEMENT MARKING TO BE REMOVED, 24" | FOOT | 34 | 8 | 272 | 29.5 | 1003 | 24.75 | 841.5 | 24 | 816 | 24 | 816 | 26.4 | 897.6 | 24 | 816
4 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 1 | 1000 | 1000 | 2000 | 2000 | 2492 | 2492 | 250 | 250 | 2750 | 2750 | 2500 | 2500 | 750 | 750
5 | EX. HANDHOLE TO BE ADJUSTED | EACH | 2 | 1000 | 2000 | 2300 | 4600 | 2436 | 4872 | 2375 | 4750 | 2375 | 4750 | 2612.5 | 5225 | 10635 | 21270
6 | EX. PEDESTRIAN PUSH BUTTON TO BE REPLACED | EACH | 2 | 500 | 1000 | 1500 | 3000 | 888 | 1776 | 865 | 1730 | 865 | 1730 | 951.5 | 1903 | 12763 | 25526
7 | EX. SIGN TO BE REMOVED AND REPLACED | EACH | 1 | 200 | 200 | 613 | 613 | 512 | 512 | 500 | 500 | 500 | 500 | 550 | 550 | 500 | 500
8 | EX. SIGN TO BE RELOCATED | EACH | 2 | 200 | 400 | 430 | 860 | 359 | 718 | 700 | 1400 | 350 | 700 | 385 | 770 | 350 | 700
9 | EX. BENCH TO BE REMOVED AND REINSTALLED | EACH | 1 | 500 | 500 | 690 | 690 | 1994 | 1994 | 310 | 310 | 1200 | 1200 | 1000 | 1000 | 100 | 100
10 | PCC SIDEWALK, 4" (6" THRU DRIVEWAY) | SQ FT | 2175 | 10 | 21750 | 7.7 | 16747.5 | 12.25 | 26643.75 | 10 | 21750 | 11 | 23925 | 11.13 | 24207.75 | 13 | 28275
11 | PCC PAVEMENT, 6" (DRIVEWAY) | SQ YD | 31 | 75 | 2325 | 130 | 4030 | 87 | 2697 | 117 | 3627 | 88 | 2728 | 100.17 | 3105.27 | 91 | 2821
12 | CLASS B PAVEMENT PATCH | SQ YD | 70 | 80 | 5600 | 182 | 12740 | 96 | 6720 | 113 | 7910 | 275 | 19250 | 350 | 24500 | 241 | 16870
13 | HMA SURFACE COURSE, 3" | SQ YD | 46 | 50 | 2300 | 97 | 4462 | 67 | 3082 | 72 | 3312 | 96 | 4416 | 175 | 8050 | 81 | 3726
14 | AGGREGATE BASE COURSE, TYPE B, 10" | FOOT | 46 | 20 | 920 | 35 | 1610 | 45.5 | 2093 | 17 | 782 | 60 | 2760 | 100 | 4600 | 14 | 644
15 | PCC CURB, TYPE B- 6.24 | FOOT | 300 | 60 | 18000 | 44 | 13200 | 51 | 15300 | 33 | 9900 | 49.4 | 14820 | 39.12 | 11736 | 84.5 | 25350
16 | DETECTABLE WARNINGS | SQ FT | 31 | 40 | 1240 | 25 | 775 | 42 | 1302 | 23 | 713 | 35 | 1085 | 27 | 837 | 40 | 1240
17 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" WHITE | FOOT | 273 | 3 | 819 | 7 | 1911 | 7 | 1911 | 7 | 1911 | 7 | 1911 | 7.7 | 2102.1 | 7 | 1911
18 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" WHITE | FOOT | 33 | 8 | 264 | 28 | 924 | 28.75 | 948.75 | 28 | 924 | 28 | 924 | 30.8 | 1016.4 | 28 | 924
19 | TRAFFIC CONTROL & PROTECTION | LSUM | 1 | 20000 | 20000 | 6000 | 6000 | 5026 | 5026 | 20000 | 20000 | 5000 | 5000 | 5500.28 | 5500.28 | 8700 | 8700
20 | MOBILIZATION | LSUM | 1 | 10000 | 10000 | 1100 | 1100 | 6665 | 6665 | 25000 | 25000 | 10000 | 10000 | 5000 | 5000 | 15230 | 15230
21 | PARKWAY RESTORATION | LSUM | 1 | 1000 | 1000 | 5000 | 5000 | 4420 | 4420 | 3400 | 3400 | 5800 | 5800 | 2500 | 2500 | 3808.5 | 3808.5
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Total |  | As read | 97770 |  | 88290.5 |  | 108872.9 |  | 120601 |  | 132431 |  | 152888 |  | 172127.5
| Award to DPI Construction | Bid |  | As corrected | 97770 |  | 88585.5 |  | 108872.9 |  | 120601 |  | 132431 |  | 152888 |  | 172127.5
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
#VALUE! | AS READ |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
#VALUE! | AS CORRECTED |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
E. State St. Sidewalk Improvements
Item No. | Items | Units | Quantity | Unit Price | Total
1 | PAVEMENT REMOVAL | SQ YD | 450 |  | 0
2 | PAVEMENT MARKING TO BE REMOVED, 6" | FOOT | 286 |  | 0
3 | PAVEMENT MARKING TO BE REMOVED, 24" | FOOT | 34 |  | 0
4 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 1 |  | 0
5 | EX. HANDHOLE TO BE ADJUSTED | EACH | 2 |  | 0
6 | EX. PEDESTRIAN PUSH BUTTON TO BE REPLACED | EACH | 2 |  | 0
7 | EX. SIGN TO BE REMOVED AND REPLACED | EACH | 1 |  | 0
8 | EX. SIGN TO BE RELOCATED | EACH | 2 |  | 0
9 | EX. BENCH TO BE REMOVED AND REINSTALLED | EACH | 1 |  | 0
10 | PCC SIDEWALK, 4" (6" THRU DRIVEWAY) | SQ FT | 2175 |  | 0
11 | PCC PAVEMENT, 6" (DRIVEWAY) | SQ YD | 31 |  | 0
12 | CLASS B PAVEMENT PATCH | SQ YD | 70 |  | 0
13 | HMA SURFACE COURSE, 3" | SQ YD | 46 |  | 0
14 | AGGREGATE BASE COURSE, TYPE B, 10" | FOOT | 46 |  | 0
15 | PCC CURB, TYPE B- 6.24 | FOOT | 300 |  | 0
16 | DETECTABLE WARNINGS | SQ FT | 31 |  | 0
17 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" WHITE | FOOT | 273 |  | 0
18 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" WHITE | FOOT | 33 |  | 0
19 | TRAFFIC CONTROL & PROTECTION | LSUM | 1 |  | 0
20 | MOBILIZATION | LSUM | 1 |  | 0
21 | PARKWAY RESTORATION | LSUM | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 1 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
#VALUE! | AS READ |  | 0 |  | 0
#VALUE! | AS CORRECTED |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | E. State St. Sidewalk Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | PAVEMENT REMOVAL | SQ YD | 450 | 15 | 6750
2 | PAVEMENT MARKING TO BE REMOVED, 6" | FOOT | 286 | 5 | 1430
3 | PAVEMENT MARKING TO BE REMOVED, 24" | FOOT | 34 | 8 | 272
4 | EX. SANITARY MANHOLE TO BE ADJUSTED | EACH | 1 | 1000 | 1000
5 | EX. HANDHOLE TO BE ADJUSTED | EACH | 2 | 1000 | 2000
6 | EX. PEDESTRIAN PUSH BUTTON TO BE REPLACED | EACH | 2 | 500 | 1000
7 | EX. SIGN TO BE REMOVED AND REPLACED | EACH | 1 | 200 | 200
8 | EX. SIGN TO BE RELOCATED | EACH | 2 | 200 | 400
9 | EX. BENCH TO BE REMOVED AND REINSTALLED | EACH | 1 | 500 | 500
10 | PCC SIDEWALK, 4" (6" THRU DRIVEWAY) | SQ FT | 2175 | 10 | 21750
11 | PCC PAVEMENT, 6" (DRIVEWAY) | SQ YD | 31 | 75 | 2325
12 | CLASS B PAVEMENT PATCH | SQ YD | 70 | 80 | 5600
13 | HMA SURFACE COURSE, 3" | SQ YD | 46 | 50 | 2300
14 | AGGREGATE BASE COURSE, TYPE B, 10" | FOOT | 46 | 20 | 920
15 | PCC CURB, TYPE B- 6.24 | FOOT | 300 | 60 | 18000
16 | DETECTABLE WARNINGS | SQ FT | 31 | 40 | 1240
17 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" WHITE | FOOT | 273 | 3 | 819
18 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" WHITE | FOOT | 33 | 8 | 264
19 | TRAFFIC CONTROL & PROTECTION | LSUM | 1 | 20000 | 20000
20 | MOBILIZATION | LSUM | 1 | 10000 | 10000
21 | PARKWAY RESTORATION | LSUM | 1 | 1000 | 1000
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 97770
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | E. State St. Sidewalk Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
#VALUE! | AS READ |  | 0 | 0 | 0
#VALUE! | AS CORRECTED |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 97770
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | E. State St. Sidewalk Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 97770
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | E. State St. Sidewalk Improvements
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 97770
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Pecatonica, IL Bid Bond | [5 empty] | SECTION | E. State St. Sidewalk Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | PAVEMENT REMOVAL | 450 | SQ YD | 5175 |  | 450 |  |  | 11.5
2 | PAVEMENT MARKING TO BE REMOVED, 6" | 286 | FOOT | 2145 |  | 286 |  |  | 7.5
3 | PAVEMENT MARKING TO BE REMOVED, 24" | 34 | FOOT | 1003 |  | 34 |  |  | 29.5
4 | EX. SANITARY MANHOLE TO BE ADJUSTED | 1 | EACH | 2000 |  | 1 |  |  | 2000
5 | EX. HANDHOLE TO BE ADJUSTED | 2 | EACH | 4600 |  | 2 |  |  | 2300
6 | EX. PEDESTRIAN PUSH BUTTON TO BE REPLACED | 2 | EACH | 3000 |  | 2 |  |  | 1500
7 | EX. SIGN TO BE REMOVED AND REPLACED | 1 | EACH | 613 |  | 1 |  |  | 613
8 | EX. SIGN TO BE RELOCATED | 2 | EACH | 860 |  | 2 |  |  | 430
9 | EX. BENCH TO BE REMOVED AND REINSTALLED | 1 | EACH | 690 |  | 1 |  |  | 690
10 | PCC SIDEWALK, 4" (6" THRU DRIVEWAY) | 2175 | SQ FT | 16747.5 |  | 2175 |  |  | 7.7
11 | PCC PAVEMENT, 6" (DRIVEWAY) | 31 | SQ YD | 4030 |  | 31 |  |  | 130
12 | CLASS B PAVEMENT PATCH | 70 | SQ YD | 12740 |  | 70 |  |  | 182
13 | HMA SURFACE COURSE, 3" | 46 | SQ YD | 4462 |  | 46 |  |  | 97
14 | AGGREGATE BASE COURSE, TYPE B, 10" | 46 | FOOT | 1610 |  | 46 |  |  | 35
15 | PCC CURB, TYPE B- 6.24 | 300 | FOOT | 13200 |  | 300 |  |  | 44
16 | DETECTABLE WARNINGS | 31 | SQ FT | 775 |  | 31 |  |  | 25
17 | THERMOPLASTIC PAVEMENT MARKING - LINE 6" WHITE | 273 | FOOT | 1911 |  | 273 |  |  | 7
18 | THERMOPLASTIC PAVEMENT MARKING - LINE 24" WHITE | 33 | FOOT | 924 |  | 33 |  |  | 28
19 | TRAFFIC CONTROL & PROTECTION | 1 | LSUM | 6000 |  | 1 |  |  | 6000
20 | MOBILIZATION | 1 | LSUM | 1100 |  | 1 |  |  | 1100
21 | PARKWAY RESTORATION | 1 | LSUM | 5000 |  | 1 |  |  | 5000
Total |  |  |  | 88585.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Pecatonica, IL Bid Bond | [5 empty] | SECTION | E. State St. Sidewalk Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
#VALUE! | AS READ
#VALUE! | AS CORRECTED
Total |  |  |  | 88585.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Pecatonica, IL Bid Bond | [5 empty] | SECTION | E. State St. Sidewalk Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 88585.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
| Address: Pecatonica, IL Bid Bond | [5 empty] | SECTION | E. State St. Sidewalk Improvements
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 88585.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | E. State St. Sidewalk Improvements
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | DPI Construction
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.