## Item List
348928.5
No. | Item |  | Quant. | Unit Price | Total
BASE BID (N. MAIN STREET) ITEMS
1 | SIDEWALK REMOVAL | SQ FT | 422.1 | 10 | 4221
2 | HANDRAIL REMOVAL, TYPE 1 | FOOT | 829 | 25 | 20725
3 | HANDRAIL POST CONCRETE REPAIR, TYPE 1 | EACH | 150 | 100 | 15000
4 | PORTLAND CEMENT CONCRETE SIDEWALK, 5" (SPECIAL) | SQ FT | 422.1 | 25 | 10552.5
5 | PEDESTRIAN HANDRAIL, SPECIAL | FOOT | 894 | 230 | 205620
6 | TRAFFIC CONTROL AND PROTECTION | L SUM | 1 | 25000 | 25000
7 | MOBILIZATION | L SUM | 1 | 25000 | 25000
SEE ALTERNATES ON PAGE 2
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23 | ALTERNATE ADD-ON BID (SALEM STREET) ITEMS
24 | HANDRAIL REMOVAL, TYPE 2 | FOOT | 144 | 35 | 5040
25 | HANDRAIL POST CONCRETE REPAIR, TYPE 2 | EACH | 31 | 150 | 4650
26 | PEDESTRIAN HANDRAIL, SPECIAL | FOOT | 144 | 230 | 33120
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | DPI Construction
City of Rockford | [5 empty] | Pecatonica, IL
N. Main St. Handrail Replacement | [5 empty] | Bid Bond
Vendors Notified: 236 Bid No. 825-PW-104
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total |  |  | Unit Price | Total | Unit Price | Total | Unit Price | Total
| BASE BID (N. MAIN STREET) ITEMS |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0
1 | SIDEWALK REMOVAL | SQ FT | 422.1 | 10 | 4221 | 9.5 | 4009.95 |  |  |  | 0 |  | 0 |  | 0
2 | HANDRAIL REMOVAL, TYPE 1 | FOOT | 829 | 25 | 20725 | 85 | 70465 |  |  |  | 0 |  | 0 |  | 0
3 | HANDRAIL POST CONCRETE REPAIR, TYPE 1 | EACH | 150 | 100 | 15000 | 105 | 15750 |  |  |  | 0 |  | 0 |  | 0
4 | PORTLAND CEMENT CONCRETE SIDEWALK, 5" (SPECIAL) | SQ FT | 422.1 | 25 | 10552.5 | 34 | 14351.4 |  |  |  | 0 |  | 0 |  | 0
5 | PEDESTRIAN HANDRAIL, SPECIAL | FOOT | 894 | 230 | 205620 | 363 | 324522 |  |  |  | 0 |  | 0 |  | 0
6 | TRAFFIC CONTROL AND PROTECTION | L SUM | 1 | 25000 | 25000 | 47500 | 47500 |  |  |  | 0 |  | 0 |  | 0
7 | MOBILIZATION | L SUM | 1 | 25000 | 25000 | 40000 | 40000 |  |  |  | 0 |  | 0 |  | 0
| SEE ALTERNATES ON PAGE 2 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Total |  | As read | 306118.5 |  | 516598.35
| Award to DPI Construction | Bid |  | As corrected | 306118.5 |  | 516598.35
| ALTERNATE ADD-ON BID (SALEM STREET) ITEMS |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| HANDRAIL REMOVAL, TYPE 2 | FOOT | 144 | 35 | 5040 | 98 | 14112 |  |  |  | 0 |  | 0 |  | 0
| HANDRAIL POST CONCRETE REPAIR, TYPE 2 | EACH | 31 | 150 | 4650 | 110 | 3410 |  |  |  | 0 |  | 0 |  | 0
| PEDESTRIAN HANDRAIL, SPECIAL | FOOT | 144 | 230 | 33120 | 363 | 52272 |  |  |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read | 348928.5 |  | 69794
| Award to DPI Construction | Bid |  | As corrected | 348928.5 |  | 69794
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
| Page 4 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
| Page 5 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 6 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 7 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 8 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 9 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 10 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 11 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 12 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Page 13 | Total |  | As read
| Award to DPI Construction | Bid |  | As corrected
0

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
N. Main St. Handrail Replacement
Item No. | Items | Units | Quantity | Unit Price | Total
0 | BASE BID (N. MAIN STREET) ITEMS |  | 0 |  | 0
1 | SIDEWALK REMOVAL | SQ FT | 422.1 |  | 0
2 | HANDRAIL REMOVAL, TYPE 1 | FOOT | 829 |  | 0
3 | HANDRAIL POST CONCRETE REPAIR, TYPE 1 | EACH | 150 |  | 0
4 | PORTLAND CEMENT CONCRETE SIDEWALK, 5" (SPECIAL) | SQ FT | 422.1 |  | 0
5 | PEDESTRIAN HANDRAIL, SPECIAL | FOOT | 894 |  | 0
6 | TRAFFIC CONTROL AND PROTECTION | L SUM | 1 |  | 0
7 | MOBILIZATION | L SUM | 1 |  | 0
0 | SEE ALTERNATES ON PAGE 2 |  | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 1 | Total Base |  | As read | 0
|  | Bid |  | As corrected | 0
0 | ALTERNATE ADD-ON BID (SALEM STREET) ITEMS |  | 0 |  | 0
8 | HANDRAIL REMOVAL, TYPE 2 | FOOT | 144 |  | 0
9 | HANDRAIL POST CONCRETE REPAIR, TYPE 2 | EACH | 31 |  | 0
10 | PEDESTRIAN HANDRAIL, SPECIAL | FOOT | 144 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 2 | Alternate |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 5 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 6 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 7 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 8 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 9 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 10 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 11 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 12 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 13 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
0 | BASE BID (N. MAIN STREET) ITEMS |  | 0 | 0 | 0
1 | SIDEWALK REMOVAL | SQ FT | 422.1 | 10 | 4221
2 | HANDRAIL REMOVAL, TYPE 1 | FOOT | 829 | 25 | 20725
3 | HANDRAIL POST CONCRETE REPAIR, TYPE 1 | EACH | 150 | 100 | 15000
4 | PORTLAND CEMENT CONCRETE SIDEWALK, 5" (SPECIAL) | SQ FT | 422.1 | 25 | 10552.5
5 | PEDESTRIAN HANDRAIL, SPECIAL | FOOT | 894 | 230 | 205620
6 | TRAFFIC CONTROL AND PROTECTION | L SUM | 1 | 25000 | 25000
7 | MOBILIZATION | L SUM | 1 | 25000 | 25000
0 | SEE ALTERNATES ON PAGE 2 |  | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Sub Total | 306118.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
0 | ALTERNATE ADD-ON BID (SALEM STREET) ITEMS |  | 0 | 0 | 0
0 | HANDRAIL REMOVAL, TYPE 2 | FOOT | 144 | 35 | 5040
0 | HANDRAIL POST CONCRETE REPAIR, TYPE 2 | EACH | 31 | 150 | 4650
0 | PEDESTRIAN HANDRAIL, SPECIAL | FOOT | 144 | 230 | 33120
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 5 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 6 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 7 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 8 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 9 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 10 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 11 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | N. Main St. Handrail Replacement
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 348928.5
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 112 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
BASE BID (N. MAIN STREET) ITEMS
1 | SIDEWALK REMOVAL | 422.1 | SQ FT | 4009.95 |  | 422.1 |  |  | 9.5
2 | HANDRAIL REMOVAL, TYPE 1 | 829 | FOOT | 70465 |  | 829 |  |  | 85
3 | HANDRAIL POST CONCRETE REPAIR, TYPE 1 | 150 | EACH | 15750 |  | 150 |  |  | 105
4 | PORTLAND CEMENT CONCRETE SIDEWALK, 5" (SPECIAL) | 422.1 | SQ FT | 14351.4 |  | 422.1 |  |  | 34
5 | PEDESTRIAN HANDRAIL, SPECIAL | 894 | FOOT | 324522 |  | 894 |  |  | 363
6 | TRAFFIC CONTROL AND PROTECTION | 1 | L SUM | 47500 |  | 1 |  |  | 47500
7 | MOBILIZATION | 1 | L SUM | 40000 |  | 1 |  |  | 40000
SEE ALTERNATES ON PAGE 2
Total |  |  |  | 516598.35 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
ALTERNATE ADD-ON BID (SALEM STREET) ITEMS
| HANDRAIL REMOVAL, TYPE 2 | 144 | FOOT | 14112 |  | 144 |  |  | 98
| HANDRAIL POST CONCRETE REPAIR, TYPE 2 | 31 | EACH | 3410 |  | 31 |  |  | 110
| PEDESTRIAN HANDRAIL, SPECIAL | 144 | FOOT | 52272 |  | 144 |  |  | 363
#VALUE!
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: DPI Construction | [5 empty] | MUNICIPALITY | City of Rockford
Address: Pecatonica, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | #VALUE!
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Logistics Parkway - Phase II
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | DPI Construction
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.