## Item List
| City -Wide Street Repairs Group No. 1 - 2025 (Arterial) | [10 empty] | 11304569
Summary Of Quantities |  |  | W2510 | W2511 |  | W2513 | W2512
No. | Item | Units | North Alpine Road - Highcrest Road to Brookview Road | Mulford Road - Fincham Drive to Guilford Road | Mulford Road - Gale Drive to Churchview Drive | Spring Creek Road - Spring Brook Road to North Mulford Road | West Riverside Boulevard - Latham Street to North Rockton Avenue | West Riverside Boulevard - Packard Parkway to North Central Avenue | Contingency | TOTAL QUANTITY | Unit Price | Total
1 | Earth Excavation | C.Y. | 15 | 125 |  | 100 |  | 10 |  | 250 | 60 | 15000
2 | Parkway Restoration | Lsum | 0.1 | 0.4 | 0.1 | 0.25 | 0.1 | 0.05 |  | 1 | 400000 | 400000
3 | Inlet and Pipe Protection | Each | 25 | 50 | 10 | 30 | 30 |  |  | 145 | 75 | 10875
4 | Aggregate Base Repair, 10" | S.Y. | 192 | 616 | 89 |  |  |  |  | 897 | 25 | 22425
5 | Bituminous Materials (Prime Coat) | Gal | 1925 | 6160 | 890 | 5620 | 3610 | 3030 |  | 21235 | 3 | 63705
6 | Aggregate (Prime Coat) | Tons | 192 | 616 | 89 | 562 | 361 | 303 |  | 2123 | 10 | 21230
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N70, 1.25 | Tons |  |  | 800 | 4300 | 2950 | 2000 | 250 | 10300 | 100 | 1030000
8 | Hot-Mix Asphalt Binder Course, IL-19.0, N70, 2.5" | Tons | 2900 | 9300 |  |  |  |  | 250 | 12450 | 80 | 996000
9 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | Tons | 2300 | 7100 | 1100 | 6500 | 4200 | 3550 | 500 | 25250 | 80 | 2020000
10 | Pot Hole Patching | Tons |  |  | 150 | 600 | 450 | 300 | 100 | 1600 | 300 | 480000
11 | Pavement Fabric | S.Y. |  |  | 8900 | 52500 | 36100 | 24500 |  | 122000 | 10 | 1220000
12 | P.C.C. Approach Pavement, 6" | S.Y. |  | 347 | 137 | 325 | 25 |  | 50 | 884 | 80 | 70720
13 | P.C.C. Approach Pavement, 8" | S.Y. | 91 | 537 |  |  |  |  | 50 | 678 | 95 | 64410
14 | P.C.C. Sidewalk, 4" | S.F. | 4300 | 9000 |  | 7650 | 5625 | 1475 | 5000 | 33050 | 9 | 297450
15 | Detectable Warnings, ADA Ramps | S.F. | 180 | 180 |  | 70 | 180 | 60 |  | 670 | 30 | 20100
16 | Class B Patch, Type II, 10" | S.Y. |  |  |  | 80 |  |  |  | 80 | 150 | 12000
17 | Class B Patch, Type III, 10" | S.Y. |  |  |  | 230 | 100 | 100 |  | 430 | 150 | 64500
18 | Class B Patch, Type IV, 10" | S.Y. |  |  |  | 876 | 300 | 300 |  | 1476 | 150 | 221400
19 | Dowel Bars | Each |  |  |  | 1000 | 400 | 400 |  | 1800 | 15 | 27000
20 | No. 6 Transverse Tie Bars | Each |  |  |  | 1000 | 400 | 400 |  | 1800 | 15 | 27000
21 | Welded Wire Reinforcement | S.Y. |  |  |  | 876 | 300 | 300 |  | 1476 | 10 | 14760
22 | Combination Curb and Gutter Removal | L.F. | 630 | 18765 | 2655 | 8225 | 495 | 95 | 1000 | 31865 | 15 | 477975
23 | Sidewalk Removal | S.F. | 3500 | 3125 |  | 2675 | 5625 | 1525 | 5000 | 21450 | 2.5 | 53625
24 | Approach Pavement Removal | S.Y. | 91 | 884 | 137 | 325 | 25 |  | 100 | 1562 | 30 | 46860
25 | Median Removal | S.F. |  | 11800 |  | 550 |  |  |  | 12350 | 5 | 61750
26 | Surface Removal, 2" | S.Y. |  |  |  | 3700 |  | 5800 | 1000 | 10500 | 3 | 31500
27 | Surface Removal, 3.25" | S.Y. |  |  | 8900 | 28250 | 36100 | 24500 | 1000 | 98750 | 4 | 395000
28 | Surface Removal, 4.5" | S.Y. | 19250 | 61600 |  |  |  |  | 1000 | 81850 | 5 | 409250
29 | Concrete Surface Removal, 1" | S.Y. |  |  |  | 24250 |  |  |  | 24250 | 7 | 169750
30 | Hand Holes to be Adjusted | Each | 1 | 4 | [5 empty] | 5 | 4000 | 20000
31 | Sanitary Riser/Valve Boxes to be Adjusted | Each |  | 5 |  | 4 | 1 | 2 |  | 12 | 500 | 6000
32 | Manholes to be Adjusted | Each | 16 | 38 | 1 | 24 | 31 |  |  | 110 | 800 | 88000
33 | Manholes to be Adjusted (AT&T) | Each |  | 4 |  | 9 |  |  |  | 13 | 3000 | 39000
34 | Manholes to be Reconstructed | Each |  |  |  | 1 |  |  |  | 1 | 1800 | 1800
35 | Inlets to be Adjusted | Each | 2 |  |  | 16 | 7 |  |  | 25 | 1400 | 35000
36 | Inlets to be Adjusted with New Frame and Grate | Each |  | 30 |  | 7 | 1 |  |  | 38 | 1700 | 64600
37 | Inlets to be Reconstructed | Each |  |  |  |  | 1 |  |  | 1 | 2200 | 2200
38 | Inlets to be Reconstructed with New Frame and Grate | Each |  |  |  | 2 |  |  |  | 2 | 2300 | 4600
39 | Inlet Specials to be Repaired | Each | 1 | 11 | 8 |  |  |  |  | 20 | 3000 | 60000
40 | Combination Concrete Curb and Gutter, Type M-6.12 | L.F. |  | 7105 |  | 365 |  |  |  | 7470 | 35 | 261450
41 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 630 | 11280 | 2655 | 7860 | 495 | 95 | 1000 | 24015 | 30 | 720450
42 | Combination Concrete Curb and Gutter, Type M-6.24 | L.F. |  | 340 | [5 empty] | 340 | 50 | 17000
43 | P.C.C. Median Pavement, 4" | S.F. |  | 11700 |  | 550 |  |  |  | 12250 | 10 | 122500
44 | Traffic Control and Protection | Lsum | 0.15 | 0.2 | 0.1 | 0.2 | 0.2 | 0.15 |  | 1 | 600000 | 600000
45 | Thermoplastic Pavement Markings, 4" | L.F. | 7650 | 17785 | 4375 | 29125 | 18275 | 17190 |  | 94400 | 2 | 188800
46 | Thermoplastic Pavement Markings, 6" | L.F. | 1882 | 7843 | 555 | 7440 | 5487 | 3292 |  | 26499 | 3 | 79497
47 | Thermoplastic Pavement Markings, 12" | L.F. | 60 | 325 | 143 | 2445 | 1833 | 1575 |  | 6381 | 5 | 31905
48 | Thermoplastic Pavement Markings, 24" | L.F. | 265 | 1095 | 39 | 506 | 206 | 208 |  | 2319 | 10 | 23190
49 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 396 | 1920 | 209 | 1350 | 775 | 541 |  | 5191 | 12 | 62292
50 | Detector Loops | L.F. | 600 | 3800 | [5 empty] | 4400 | 30 | 132000
51
52
53
54
55
56
57
58
59
60
61
62
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
|  |  | 819343 | 3565961.5 | 617508 | 3112782.5 | 1730738.5 | 1216985.5 | 241250 | #VALUE!
|  |  | 30156.25 | 75390.625 | 15078.125 | 60312.5 | 36187.5 | 24125 |  | 11304569
|  |  | 849499.25 | 3641352.125 | 632586.125 | 3173095 | 1766926 | 1241110.5 |  | 11304569
|  |  | 1500000 | 3750000 | 750000 | 3000000 | 1800000 | 1200000 | 0 | 12000000
#REF!
|  |  | 0.125 | 0.3125 | 0.0625 | 0.25 | 0.15 | 0.1 | 0

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | ROCK ROAD CO. | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: | [9 empty] | TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER:
City of Rockford | [5 empty] | JANESVILLE, IL | [9 empty] | City of Rockford | [13 empty] | City of Rockford
Bid On: City-Wide Street Repairs Group No. 1 - 2025 (Arterials) | [5 empty] | BID BOND | [9 empty] | Project Name: City Wide Street Repairs Group No. 6 | [13 empty] | Project Name:
VENDORS NOTIFIED: 206 BID NO. 1124-PW-122 | [15 empty] | Bid No.: Opened:
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Earth Excavation | C.Y. | 250 | 60 | 15000 | 75 | 18750 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 250 | 60 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | Earth Excavation | C.Y. | 250 | 60 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Parkway Restoration | Lsum | 1 | 400000 | 400000 | 183139.6 | 183139.6 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 400000 | 400000 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | Parkway Restoration | Lsum | 1 | 400000 | 400000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Inlet and Pipe Protection | Each | 145 | 75 | 10875 | 0.01 | 1.45 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 145 | 75 | 10875 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | Inlet and Pipe Protection | Each | 145 | 75 | 10875 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Aggregate Base Repair, 10" | S.Y. | 897 | 25 | 22425 | 0.01 | 8.97 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Repair, 10" | S.Y. | 897 | 25 | 22425 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | Aggregate Base Repair, 10" | S.Y. | 897 | 25 | 22425 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Bituminous Materials (Prime Coat) | Gal | 21235 | 3 | 63705 | 3.07 | 65191.45 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Bituminous Materials (Prime Coat) | Gal | 21235 | 3 | 63705 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | Bituminous Materials (Prime Coat) | Gal | 21235 | 3 | 63705 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | Aggregate (Prime Coat) | Tons | 2123 | 10 | 21230 | 0.01 | 21.23 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate (Prime Coat) | Tons | 2123 | 10 | 21230 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | Aggregate (Prime Coat) | Tons | 2123 | 10 | 21230 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N70, 1.25 | Tons | 10300 | 100 | 1030000 | 83.26 | 857578 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Hot-Mix Asphalt Binder Course, IL-9.5, N70, 1.25 | Tons | 10300 | 100 | 1030000 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | Hot-Mix Asphalt Binder Course, IL-9.5, N70, 1.25 | Tons | 10300 | 100 | 1030000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-19.0, N70, 2.5" | Tons | 12450 | 80 | 996000 | 82.76 | 1030362 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-19.0, N70, 2.5" | Tons | 12450 | 80 | 996000 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | Hot-Mix Asphalt Binder Course, IL-19.0, N70, 2.5" | Tons | 12450 | 80 | 996000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | Tons | 25250 | 80 | 2020000 | 84.23 | 2126807.5 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | Tons | 25250 | 80 | 2020000 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | Tons | 25250 | 80 | 2020000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | Pot Hole Patching | Tons | 1600 | 300 | 480000 | 125 | 200000 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Pot Hole Patching | Tons | 1600 | 300 | 480000 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | Pot Hole Patching | Tons | 1600 | 300 | 480000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 | Pavement Fabric | S.Y. | 122000 | 10 | 1220000 | 6.31 | 769820 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Pavement Fabric | S.Y. | 122000 | 10 | 1220000 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | Pavement Fabric | S.Y. | 122000 | 10 | 1220000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 884 | 80 | 70720 | 85 | 75140 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 884 | 80 | 70720 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | P.C.C. Approach Pavement, 6" | S.Y. | 884 | 80 | 70720 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 678 | 95 | 64410 | 95 | 64410 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 678 | 95 | 64410 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | P.C.C. Approach Pavement, 8" | S.Y. | 678 | 95 | 64410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 33050 | 9 | 297450 | 8.5 | 280925 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 33050 | 9 | 297450 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | P.C.C. Sidewalk, 4" | S.F. | 33050 | 9 | 297450 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
15 | Detectable Warnings, ADA Ramps | S.F. | 670 | 30 | 20100 | 25 | 16750 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Detectable Warnings, ADA Ramps | S.F. | 670 | 30 | 20100 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | Detectable Warnings, ADA Ramps | S.F. | 670 | 30 | 20100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
16 | Class B Patch, Type II, 10" | S.Y. | 80 | 150 | 12000 | 225 | 18000 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Class B Patch, Type II, 10" | S.Y. | 80 | 150 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 | 16 | Class B Patch, Type II, 10" | S.Y. | 80 | 150 | 12000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
17 | Class B Patch, Type III, 10" | S.Y. | 430 | 150 | 64500 | 200 | 86000 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Class B Patch, Type III, 10" | S.Y. | 430 | 150 | 64500 |  | 0 |  | 0 |  | 0 |  | 0 | 17 | Class B Patch, Type III, 10" | S.Y. | 430 | 150 | 64500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
18 | Class B Patch, Type IV, 10" | S.Y. | 1476 | 150 | 221400 | 150 | 221400 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Class B Patch, Type IV, 10" | S.Y. | 1476 | 150 | 221400 |  | 0 |  | 0 |  | 0 |  | 0 | 18 | Class B Patch, Type IV, 10" | S.Y. | 1476 | 150 | 221400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
19 | Dowel Bars | Each | 1800 | 15 | 27000 | 7 | 12600 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Dowel Bars | Each | 1800 | 15 | 27000 |  | 0 |  | 0 |  | 0 |  | 0 | 19 | Dowel Bars | Each | 1800 | 15 | 27000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
20 | No. 6 Transverse Tie Bars | Each | 1800 | 15 | 27000 | 3 | 5400 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | No. 6 Transverse Tie Bars | Each | 1800 | 15 | 27000 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | No. 6 Transverse Tie Bars | Each | 1800 | 15 | 27000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
21 | Welded Wire Reinforcement | S.Y. | 1476 | 10 | 14760 | 4 | 5904 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Welded Wire Reinforcement | S.Y. | 1476 | 10 | 14760 |  | 0 |  | 0 |  | 0 |  | 0 | 21 | Welded Wire Reinforcement | S.Y. | 1476 | 10 | 14760 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
22 | Combination Curb and Gutter Removal | L.F. | 31865 | 15 | 477975 | 9 | 286785 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Combination Curb and Gutter Removal | L.F. | 31865 | 15 | 477975 |  | 0 |  | 0 |  | 0 |  | 0 | 22 | Combination Curb and Gutter Removal | L.F. | 31865 | 15 | 477975 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
23 | Sidewalk Removal | S.F. | 21450 | 2.5 | 53625 | 3 | 64350 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Sidewalk Removal | S.F. | 21450 | 2.5 | 53625 |  | 0 |  | 0 |  | 0 |  | 0 | 23 | Sidewalk Removal | S.F. | 21450 | 2.5 | 53625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
24 | Approach Pavement Removal | S.Y. | 1562 | 30 | 46860 | 25 | 39050 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Approach Pavement Removal | S.Y. | 1562 | 30 | 46860 |  | 0 |  | 0 |  | 0 |  | 0 | 24 | Approach Pavement Removal | S.Y. | 1562 | 30 | 46860 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 7677035 |  | 6428394.2 | [9 empty] | Page 3 | Sub |  | As read | 7677035 | [9 empty] | Page 1 | Sub |  | As read | 7677035
| Award to ROCK ROAD CO. | Total |  | As corrected | 7677035 |  | 6428394.2 | [9 empty] | Award to ROCK ROAD CO. | Total |  | As corrected | 7677035 | [9 empty] | Award to ROCK ROAD CO. | Total |  | As corrected | 7677035
25 | Median Removal | S.F. | 12350 | 5 | 61750 | 2 | 24700 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Median Removal | S.F. | 12350 | 5 | 61750 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | Median Removal | S.F. | 12350 | 5 | 61750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
26 | Surface Removal, 2" | S.Y. | 10500 | 3 | 31500 | 2.87 | 30135 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Surface Removal, 2" | S.Y. | 10500 | 3 | 31500 |  | 0 |  | 0 |  | 0 |  | 0 | 26 | Surface Removal, 2" | S.Y. | 10500 | 3 | 31500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
27 | Surface Removal, 3.25" | S.Y. | 98750 | 4 | 395000 | 3.52 | 347600 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Surface Removal, 3.25" | S.Y. | 98750 | 4 | 395000 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | Surface Removal, 3.25" | S.Y. | 98750 | 4 | 395000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
28 | Surface Removal, 4.5" | S.Y. | 81850 | 5 | 409250 | 4.16 | 340496 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Surface Removal, 4.5" | S.Y. | 81850 | 5 | 409250 |  | 0 |  | 0 |  | 0 |  | 0 | 28 | Surface Removal, 4.5" | S.Y. | 81850 | 5 | 409250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
29 | Concrete Surface Removal, 1" | S.Y. | 24250 | 7 | 169750 | 3.28 | 79540 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Concrete Surface Removal, 1" | S.Y. | 24250 | 7 | 169750 |  | 0 |  | 0 |  | 0 |  | 0 | 29 | Concrete Surface Removal, 1" | S.Y. | 24250 | 7 | 169750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
30 | Hand Holes to be Adjusted | Each | 5 | 4000 | 20000 | 1200 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Hand Holes to be Adjusted | Each | 5 | 4000 | 20000 |  | 0 |  | 0 |  | 0 |  | 0 | 30 | Hand Holes to be Adjusted | Each | 5 | 4000 | 20000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
31 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 12 | 500 | 6000 | 350 | 4200 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 12 | 500 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 12 | 500 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
32 | Manholes to be Adjusted | Each | 110 | 800 | 88000 | 950 | 104500 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Manholes to be Adjusted | Each | 110 | 800 | 88000 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | Manholes to be Adjusted | Each | 110 | 800 | 88000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
33 | Manholes to be Adjusted (AT&T) | Each | 13 | 3000 | 39000 | 950 | 12350 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Manholes to be Adjusted (AT&T) | Each | 13 | 3000 | 39000 |  | 0 |  | 0 |  | 0 |  | 0 | 33 | Manholes to be Adjusted (AT&T) | Each | 13 | 3000 | 39000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
34 | Manholes to be Reconstructed | Each | 1 | 1800 | 1800 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Manholes to be Reconstructed | Each | 1 | 1800 | 1800 |  | 0 |  | 0 |  | 0 |  | 0 | 34 | Manholes to be Reconstructed | Each | 1 | 1800 | 1800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
35 | Inlets to be Adjusted | Each | 25 | 1400 | 35000 | 850 | 21250 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Inlets to be Adjusted | Each | 25 | 1400 | 35000 |  | 0 |  | 0 |  | 0 |  | 0 | 35 | Inlets to be Adjusted | Each | 25 | 1400 | 35000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
36 | Inlets to be Adjusted with New Frame and Grate | Each | 38 | 1700 | 64600 | 850 | 32300 |  | 0 |  | 0 |  | 0 |  | 0 | 36 | Inlets to be Adjusted with New Frame and Grate | Each | 38 | 1700 | 64600 |  | 0 |  | 0 |  | 0 |  | 0 | 36 | Inlets to be Adjusted with New Frame and Grate | Each | 38 | 1700 | 64600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
37 | Inlets to be Reconstructed | Each | 1 | 2200 | 2200 | 3000 | 3000 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | Inlets to be Reconstructed | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 | 37 | Inlets to be Reconstructed | Each | 1 | 2200 | 2200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
38 | Inlets to be Reconstructed with New Frame and Grate | Each | 2 | 2300 | 4600 | 3000 | 6000 |  | 0 |  | 0 |  | 0 |  | 0 | 38 | Inlets to be Reconstructed with New Frame and Grate | Each | 2 | 2300 | 4600 |  | 0 |  | 0 |  | 0 |  | 0 | 38 | Inlets to be Reconstructed with New Frame and Grate | Each | 2 | 2300 | 4600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 | Inlet Specials to be Repaired | Each | 20 | 3000 | 60000 | 2200 | 44000 |  | 0 |  | 0 |  | 0 |  | 0 | 39 | Inlet Specials to be Repaired | Each | 20 | 3000 | 60000 |  | 0 |  | 0 |  | 0 |  | 0 | 39 | Inlet Specials to be Repaired | Each | 20 | 3000 | 60000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
40 | Combination Concrete Curb and Gutter, Type M-6.12 | L.F. | 7470 | 35 | 261450 | 32 | 239040 |  | 0 |  | 0 |  | 0 |  | 0 | 40 | Combination Concrete Curb and Gutter, Type M-6.12 | L.F. | 7470 | 35 | 261450 |  | 0 |  | 0 |  | 0 |  | 0 | 40 | Combination Concrete Curb and Gutter, Type M-6.12 | L.F. | 7470 | 35 | 261450 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
41 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 24015 | 30 | 720450 | 32 | 768480 |  | 0 |  | 0 |  | 0 |  | 0 | 41 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 24015 | 30 | 720450 |  | 0 |  | 0 |  | 0 |  | 0 | 41 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 24015 | 30 | 720450 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
42 | Combination Concrete Curb and Gutter, Type M-6.24 | L.F. | 340 | 50 | 17000 | 42 | 14280 |  | 0 |  | 0 |  | 0 |  | 0 | 42 | Combination Concrete Curb and Gutter, Type M-6.24 | L.F. | 340 | 50 | 17000 |  | 0 |  | 0 |  | 0 |  | 0 | 42 | Combination Concrete Curb and Gutter, Type M-6.24 | L.F. | 340 | 50 | 17000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
43 | P.C.C. Median Pavement, 4" | S.F. | 12250 | 10 | 122500 | 7 | 85750 |  | 0 |  | 0 |  | 0 |  | 0 | 43 | P.C.C. Median Pavement, 4" | S.F. | 12250 | 10 | 122500 |  | 0 |  | 0 |  | 0 |  | 0 | 43 | P.C.C. Median Pavement, 4" | S.F. | 12250 | 10 | 122500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
44 | Traffic Control and Protection | Lsum | 1 | 600000 | 600000 | 276260.31 | 276260.31 |  | 0 |  | 0 |  | 0 |  | 0 | 44 | Traffic Control and Protection | Lsum | 1 | 600000 | 600000 |  | 0 |  | 0 |  | 0 |  | 0 | 44 | Traffic Control and Protection | Lsum | 1 | 600000 | 600000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
45 | Thermoplastic Pavement Markings, 4" | L.F. | 94400 | 2 | 188800 | 0.6 | 56640 |  | 0 |  | 0 |  | 0 |  | 0 | 45 | Thermoplastic Pavement Markings, 4" | L.F. | 94400 | 2 | 188800 |  | 0 |  | 0 |  | 0 |  | 0 | 45 | Thermoplastic Pavement Markings, 4" | L.F. | 94400 | 2 | 188800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
46 | Thermoplastic Pavement Markings, 6" | L.F. | 26499 | 3 | 79497 | 0.9 | 23849.1 |  | 0 |  | 0 |  | 0 |  | 0 | 46 | Thermoplastic Pavement Markings, 6" | L.F. | 26499 | 3 | 79497 |  | 0 |  | 0 |  | 0 |  | 0 | 46 | Thermoplastic Pavement Markings, 6" | L.F. | 26499 | 3 | 79497 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
47 | Thermoplastic Pavement Markings, 12" | L.F. | 6381 | 5 | 31905 | 1.8 | 11485.8 |  | 0 |  | 0 |  | 0 |  | 0 | 47 | Thermoplastic Pavement Markings, 12" | L.F. | 6381 | 5 | 31905 |  | 0 |  | 0 |  | 0 |  | 0 | 47 | Thermoplastic Pavement Markings, 12" | L.F. | 6381 | 5 | 31905 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
48 | Thermoplastic Pavement Markings, 24" | L.F. | 2319 | 10 | 23190 | 3.6 | 8348.4 |  | 0 |  | 0 |  | 0 |  | 0 | 48 | Thermoplastic Pavement Markings, 24" | L.F. | 2319 | 10 | 23190 |  | 0 |  | 0 |  | 0 |  | 0 | 48 | Thermoplastic Pavement Markings, 24" | L.F. | 2319 | 10 | 23190 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 11110277 |  | 8971598.81 | [9 empty] | Page 4 | Total |  | As read | 11110277 | [9 empty] | Page 2 | Total |  | As read | 11110277
| Award to ROCK ROAD CO. | Total |  | As corrected |  |  | 8971598.81 | 0 |  | 0 | [6 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected | 11110277 | [9 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected | 11110277
49 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 5191 | 12 | 62292 | 4 | 20764 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
50 | Detector Loops | L.F. | 4400 | 30 | 132000 | 16.5 | 72600 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 11304569 |  | 9064962.81 | [9 empty] | Page 3 | Total |  | As read | [10 empty] | Page 3 | Total |  | As read
| Award to ROCK ROAD CO. | Bid |  | As corrected | [12 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected | [10 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | #REF! | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read | [12 empty] | Page 4 | Total |  | As read | [10 empty] | Page 4 | Total |  | As read
| Award to ROCK ROAD CO. | Bid |  | As corrected | [12 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected | [10 empty] | Award to ROCK ROAD CO. | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bid On: City-Wide Street Repairs Group No. 1 - 2025 (Arterials)
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 250 |  | 0
2 | Parkway Restoration | Lsum | 1 |  | 0
3 | Inlet and Pipe Protection | Each | 145 |  | 0
4 | Aggregate Base Repair, 10" | S.Y. | 897 |  | 0
5 | Bituminous Materials (Prime Coat) | Gal | 21235 |  | 0
6 | Aggregate (Prime Coat) | Tons | 2123 |  | 0
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N70, 1.25 | Tons | 10300 |  | 0
8 | Hot-Mix Asphalt Binder Course, IL-19.0, N70, 2.5" | Tons | 12450 |  | 0
9 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | Tons | 25250 |  | 0
10 | Pot Hole Patching | Tons | 1600 |  | 0
11 | Pavement Fabric | S.Y. | 122000 |  | 0
12 | P.C.C. Approach Pavement, 6" | S.Y. | 884 |  | 0
13 | P.C.C. Approach Pavement, 8" | S.Y. | 678 |  | 0
14 | P.C.C. Sidewalk, 4" | S.F. | 33050 |  | 0
15 | Detectable Warnings, ADA Ramps | S.F. | 670 |  | 0
16 | Class B Patch, Type II, 10" | S.Y. | 80 |  | 0
17 | Class B Patch, Type III, 10" | S.Y. | 430 |  | 0
18 | Class B Patch, Type IV, 10" | S.Y. | 1476 |  | 0
19 | Dowel Bars | Each | 1800 |  | 0
20 | No. 6 Transverse Tie Bars | Each | 1800 |  | 0
21 | Welded Wire Reinforcement | S.Y. | 1476 |  | 0
22 | Combination Curb and Gutter Removal | L.F. | 31865 |  | 0
23 | Sidewalk Removal | S.F. | 21450 |  | 0
24 | Approach Pavement Removal | S.Y. | 1562 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | Median Removal | S.F. | 12350 |  | 0
26 | Surface Removal, 2" | S.Y. | 10500 |  | 0
27 | Surface Removal, 3.25" | S.Y. | 98750 |  | 0
28 | Surface Removal, 4.5" | S.Y. | 81850 |  | 0
29 | Concrete Surface Removal, 1" | S.Y. | 24250 |  | 0
30 | Hand Holes to be Adjusted | Each | 5 |  | 0
31 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 12 |  | 0
32 | Manholes to be Adjusted | Each | 110 |  | 0
33 | Manholes to be Adjusted (AT&T) | Each | 13 |  | 0
34 | Manholes to be Reconstructed | Each | 1 |  | 0
35 | Inlets to be Adjusted | Each | 25
36 | Inlets to be Adjusted with New Frame and Grate | Each | 38
37 | Inlets to be Reconstructed | Each | 1
38 | Inlets to be Reconstructed with New Frame and Grate | Each | 2
39 | Inlet Specials to be Repaired | Each | 20
40 | Combination Concrete Curb and Gutter, Type M-6.12 | L.F. | 7470
41 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 24015
42 | Combination Concrete Curb and Gutter, Type M-6.24 | L.F. | 340
43 | P.C.C. Median Pavement, 4" | S.F. | 12250
44 | Traffic Control and Protection | Lsum | 1
45 | Thermoplastic Pavement Markings, 4" | L.F. | 94400
46 | Thermoplastic Pavement Markings, 6" | L.F. | 26499
47 | Thermoplastic Pavement Markings, 12" | L.F. | 6381
48 | Thermoplastic Pavement Markings, 24" | L.F. | 2319
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected
49 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 5191
50 | Detector Loops | L.F. | 4400
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
|  |  | #REF! |  | #REF!
| Page 4 | Total |  | As read | #REF!
|  | Bid |  | As corrected | #REF!

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2025 (Arterials)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Earth Excavation | C.Y. | 250 | 60 | 15000
2 | Parkway Restoration | Lsum | 1 | 400000 | 400000
3 | Inlet and Pipe Protection | Each | 145 | 75 | 10875
4 | Aggregate Base Repair, 10" | S.Y. | 897 | 25 | 22425
5 | Bituminous Materials (Prime Coat) | Gal | 21235 | 3 | 63705
6 | Aggregate (Prime Coat) | Tons | 2123 | 10 | 21230
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N70, 1.25 | Tons | 10300 | 100 | 1030000
8 | Hot-Mix Asphalt Binder Course, IL-19.0, N70, 2.5" | Tons | 12450 | 80 | 996000
9 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | Tons | 25250 | 80 | 2020000
10 | Pot Hole Patching | Tons | 1600 | 300 | 480000
11 | Pavement Fabric | S.Y. | 122000 | 10 | 1220000
12 | P.C.C. Approach Pavement, 6" | S.Y. | 884 | 80 | 70720
13 | P.C.C. Approach Pavement, 8" | S.Y. | 678 | 95 | 64410
14 | P.C.C. Sidewalk, 4" | S.F. | 33050 | 9 | 297450
15 | Detectable Warnings, ADA Ramps | S.F. | 670 | 30 | 20100
16 | Class B Patch, Type II, 10" | S.Y. | 80 | 150 | 12000
17 | Class B Patch, Type III, 10" | S.Y. | 430 | 150 | 64500
18 | Class B Patch, Type IV, 10" | S.Y. | 1476 | 150 | 221400
19 | Dowel Bars | Each | 1800 | 15 | 27000
20 | No. 6 Transverse Tie Bars | Each | 1800 | 15 | 27000
21 | Welded Wire Reinforcement | S.Y. | 1476 | 10 | 14760
22 | Combination Curb and Gutter Removal | L.F. | 31865 | 15 | 477975
23 | Sidewalk Removal | S.F. | 21450 | 2.5 | 53625
24 | Approach Pavement Removal | S.Y. | 1562 | 30 | 46860
|  |  |  | Sub Total | 7677035
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2025 (Arterials)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | Median Removal | S.F. | 12350 | 5 | 61750
26 | Surface Removal, 2" | S.Y. | 10500 | 3 | 31500
27 | Surface Removal, 3.25" | S.Y. | 98750 | 4 | 395000
28 | Surface Removal, 4.5" | S.Y. | 81850 | 5 | 409250
29 | Concrete Surface Removal, 1" | S.Y. | 24250 | 7 | 169750
30 | Hand Holes to be Adjusted | Each | 5 | 4000 | 20000
31 | Sanitary Riser/Valve Boxes to be Adjusted | Each | 12 | 500 | 6000
32 | Manholes to be Adjusted | Each | 110 | 800 | 88000
33 | Manholes to be Adjusted (AT&T) | Each | 13 | 3000 | 39000
34 | Manholes to be Reconstructed | Each | 1 | 1800 | 1800
35 | Inlets to be Adjusted | Each | 25 | 1400 | 35000
36 | Inlets to be Adjusted with New Frame and Grate | Each | 38 | 1700 | 64600
37 | Inlets to be Reconstructed | Each | 1 | 2200 | 2200
38 | Inlets to be Reconstructed with New Frame and Grate | Each | 2 | 2300 | 4600
39 | Inlet Specials to be Repaired | Each | 20 | 3000 | 60000
40 | Combination Concrete Curb and Gutter, Type M-6.12 | L.F. | 7470 | 35 | 261450
41 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | L.F. | 24015 | 30 | 720450
42 | Combination Concrete Curb and Gutter, Type M-6.24 | L.F. | 340 | 50 | 17000
43 | P.C.C. Median Pavement, 4" | S.F. | 12250 | 10 | 122500
44 | Traffic Control and Protection | Lsum | 1 | 600000 | 600000
45 | Thermoplastic Pavement Markings, 4" | L.F. | 94400 | 2 | 188800
46 | Thermoplastic Pavement Markings, 6" | L.F. | 26499 | 3 | 79497
47 | Thermoplastic Pavement Markings, 12" | L.F. | 6381 | 5 | 31905
48 | Thermoplastic Pavement Markings, 24" | L.F. | 2319 | 10 | 23190
|  |  |  | Sub Total | 11110277
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2025 (Arterials)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | Thermoplastic Pavement Markings, Letters and Symbols | S.F. | 5191 | 12 | 62292
50 | Detector Loops | L.F. | 4400 | 30 | 132000
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  |  | 0 | #VALUE!
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | #VALUE!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bid On: City-Wide Street Repairs Group No. 1 - 2025 (Arterials)
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  | #REF! | 0 | #REF!
|  |  |  | Total | #REF!
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: ROCK ROAD CO. | P.O. # 19305222 |  |  |  |  | MUNICIPALITY | City of Rockford
| Address: JANESVILLE, IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2025 (Arterials)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Earth Excavation | 250 | C.Y. | 18750 |  | 250 |  |  | 75
2 | Parkway Restoration | 1 | Lsum | 183139.6 |  | 1 |  |  | 183139.6
3 | Inlet and Pipe Protection | 145 | Each | 1.45 |  | 110 | 35 | Each | 0.01 | 0.35
4 | Aggregate Base Repair, 10" | 897 | S.Y. | 8.97 |  | 897 |  |  | 0.01
5 | Bituminous Materials (Prime Coat) | 21235 | Gal | 65191.45 |  | 21235 |  |  | 3.07
6 | Aggregate (Prime Coat) | 2123 | Tons | 21.23 |  | 2123 |  |  | 0.01
7 | Hot-Mix Asphalt Binder Course, IL-9.5, N70, 1.25 | 10300 | Tons | 857578 |  | 10300 |  |  | 83.26
8 | Hot-Mix Asphalt Binder Course, IL-19.0, N70, 2.5" | 12450 | Tons | 1030362 |  | 12450 |  |  | 82.76
9 | Hot-Mix Asphalt Surface Course, Mix "D", N70, 2" | 25250 | Tons | 2126807.5 |  | 25250 |  |  | 84.23
10 | Pot Hole Patching | 1600 | Tons | 200000 |  | 200 | 1400 | Tons | 125 | 175000
11 | Pavement Fabric | 122000 | S.Y. | 769820 |  | 122000 |  |  | 6.31
12 | P.C.C. Approach Pavement, 6" | 884 | S.Y. | 75140 |  | 884 |  |  | 85
13 | P.C.C. Approach Pavement, 8" | 678 | S.Y. | 64410 | 1352 |  | 2030 | S.Y. | 95 | 192850
14 | P.C.C. Sidewalk, 4" | 33050 | S.F. | 280925 |  | 33050 |  |  | 8.5
15 | Detectable Warnings, ADA Ramps | 670 | S.F. | 16750 |  | 378 | 292 | S.F. | 25 | 7300
16 | Class B Patch, Type II, 10" | 80 | S.Y. | 18000 |  | 80 |  |  | 225
17 | Class B Patch, Type III, 10" | 430 | S.Y. | 86000 | 14664 |  | 15094 | S.Y. | 200 | 3018800
18 | Class B Patch, Type IV, 10" | 1476 | S.Y. | 221400 |  | 976 | 500 | S.Y. | 150 | 75000
19 | Dowel Bars | 1800 | Each | 12600 |  | 302 | 1498 | Each | 7 | 10486
20 | No. 6 Transverse Tie Bars | 1800 | Each | 5400 | 13444 |  | 15244 | Each | 3 | 45732
21 | Welded Wire Reinforcement | 1476 | S.Y. | 5904 |  | 1184 | 292 | S.Y. | 4 | 1168
22 | Combination Curb and Gutter Removal | 31865 | L.F. | 286785 |  | 31865 |  |  | 9
23 | Sidewalk Removal | 21450 | S.F. | 64350 |  | 3245 | 18205 | S.F. | 3 | 54615
24 | Approach Pavement Removal | 1562 | S.Y. | 39050 |  | 849 | 713 | S.Y. | 25 | 17825
Sub Total |  |  |  | 6428394.2 | [5 empty] | 3598776.35
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: ROCK ROAD CO. | [5 empty] | MUNICIPALITY | City of Rockford
| Address: JANESVILLE, IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2025 (Arterials)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | Median Removal | 12350 | S.F. | 24700 |  | 12350 |  |  | 2
26 | Surface Removal, 2" | 10500 | S.Y. | 30135 |  | 10500 |  |  | 2.87
27 | Surface Removal, 3.25" | 98750 | S.Y. | 347600 |  | 98750 |  |  | 3.52
28 | Surface Removal, 4.5" | 81850 | S.Y. | 340496 |  | 81850 |  |  | 4.16
29 | Concrete Surface Removal, 1" | 24250 | S.Y. | 79540 |  | 24250 |  |  | 3.28
30 | Hand Holes to be Adjusted | 5 | Each | 6000 | 5 |  | 10 | Each | 1200 | 12000
31 | Sanitary Riser/Valve Boxes to be Adjusted | 12 | Each | 4200 |  | 12 |  |  | 350
32 | Manholes to be Adjusted | 110 | Each | 104500 |  | 110 |  |  | 950
33 | Manholes to be Adjusted (AT&T) | 13 | Each | 12350 |  | 13 |  |  | 950
34 | Manholes to be Reconstructed | 1 | Each | 3000 | 7 |  | 8 | Each | 3000 | 24000
35 | Inlets to be Adjusted | 25 | Each | 21250 |  | 25 |  |  | 850
36 | Inlets to be Adjusted with New Frame and Grate | 38 | Each | 32300 |  | 38 |  |  | 850
37 | Inlets to be Reconstructed | 1 | Each | 3000 |  | 1 |  |  | 3000
38 | Inlets to be Reconstructed with New Frame and Grate | 2 | Each | 6000 |  | 1 | 1 | Each | 3000 | 3000
39 | Inlet Specials to be Repaired | 20 | Each | 44000 | 1298 |  | 1318 | Each | 2200 | 2899600
40 | Combination Concrete Curb and Gutter, Type M-6.12 | 7470 | L.F. | 239040 |  | 7469.5 | 0.5 | L.F. | 32 | 16
41 | Combination Concrete Curb and Gutter, Type M-6.18 (Modified) | 24015 | L.F. | 768480 |  | 24015 |  |  | 32
42 | Combination Concrete Curb and Gutter, Type M-6.24 | 340 | L.F. | 14280 |  | 340 |  |  | 42
43 | P.C.C. Median Pavement, 4" | 12250 | S.F. | 85750 |  | 12250 |  |  | 7
44 | Traffic Control and Protection | 1 | Lsum | 276260.31 |  | 1 |  |  | 276260.31
45 | Thermoplastic Pavement Markings, 4" | 94400 | L.F. | 56640 |  | 94400 |  |  | 0.6
46 | Thermoplastic Pavement Markings, 6" | 26499 | L.F. | 23849.1 |  | 26499 |  |  | 0.9
47 | Thermoplastic Pavement Markings, 12" | 6381 | L.F. | 11485.8 |  | 6381 |  |  | 1.8
48 | Thermoplastic Pavement Markings, 24" | 2319 | L.F. | 8348.4 |  | 2319 |  |  | 3.6
Sub Total |  |  |  | 8971598.81 | [5 empty] | 6537392.35
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
[8 empty] | DEDUCT RETAINAGE | 10% | #VALUE!
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2019 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2019. BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: ROCK ROAD CO. | [5 empty] | MUNICIPALITY | City of Rockford
| Address: JANESVILLE, IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2025 (Arterials)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | Thermoplastic Pavement Markings, Letters and Symbols | 5191 | S.F. | 20764 |  | 5191 |  |  | 4
50 | Detector Loops | 4400 | L.F. | 72600 |  | 4400 |  |  | 16.5
Total |  |  |  | 9064962.81 | [5 empty] | 6537392.35
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 6537392.35
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 6537392.35
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 6537392.35
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnebago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from July 22nd, 2019 to August 26th, 2019 | [7 empty] | (Road District)
| Payable to: ROCK ROAD CO. | [5 empty] | MUNICIPALITY | City of Rockford
| Address: JANESVILLE, IL BID BOND | [5 empty] | SECTION | Bid On: City-Wide Street Repairs Group No. 1 - 2025 (Arterials)
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
Total |  |  |  | 9064962.81 | [5 empty] | 6537392.35
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 6537392.35
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 6537392.35
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 6537392.35
| SIGNED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2009 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | #REF!
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | ROCK ROAD CO.
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2009 | Signed: |  | , 2009
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2009
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.