## Item List
752017.6
Summary of Quantities
No. | Item | Unit | Quant. | Unit Price | Total
1 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 10000 | 10000
2 | INLET AND PIPE PROTECTION | EA | 8 | 300 | 2400
3 | SUBBASE GRANULAR MATERIAL, TYPE B, CS-01, 9" | TON | 279 | 45 | 12555
4 | AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | TON | 186 | 50 | 9300
5 | SUBGRADE UNDERCUTTING | CY | 50 | 70 | 3500
6 | BITUMINOUS MATERIALS (PRIME COAT) | GAL | 68 | 0.2 | 13.6
7 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 152 | 145 | 22040
8 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N50, 2" | TON | 76 | 115 | 8740
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SF | 215 | 15 | 3225
10 | DETECTABLE WARNINGS | SF | 42 | 50 | 2100
11 | COMBINATION CURB AND GUTTER REMOVAL | LF | 53 | 11 | 583
12 | SIDEWALK REMOVAL | SF | 215 | 3 | 645
13 | REMOVE EXISTING MANHOLE | EA | 3 | 500 | 1500
14 | STORM MANHOLE, TYPE A, 4' DIA, TYPE 1 FRAME, CLOSED LID | EA | 8 | 4700 | 37600
15 | STORM MANHOLE, TYPE A, 8' DIA, TYPE 1 FRAME, CLOSED LID | EA | 1 | 15000 | 15000
16 | INLET REMOVAL | EA | 3 | 400 | 1200
17 | INLET, TYPE B, 3' DIA, TYPE 3V FRAME AND GRATE | EA | 3 | 3200 | 9600
18 | COMBINATION CONCRETE CURB AND GUTTER, B-6.12 | LF | 38 | 40 | 1520
19 | COMBINATION CONCRETE CURB AND GUTTER, DEPRESSED | LF | 15 | 40 | 600
20 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 10000 | 10000
21 | MOBILIZATION | LS | 1 | 75000 | 75000
22 | NON-SPECIAL WASTE DISPOSAL | CY | 100 | 100 | 10000
23 | SPECIAL WASTE DISPOSAL | CY | 25 | 150 | 3750
24 | SPECIAL WASTE PLANS AND REPORTS | LS | 1 | 7500 | 7500
25 | SOIL DISPOSAL ANALYSIS | EA | 1 | 1500 | 1500
26 | STORM SEWER REMOVAL, LESS THAN OR EQUAL TO 30" | LF | 140 | 27 | 3780
27 | STORM SEWER ABANDONMENT AND FILL, LESS THAN OR EQUAL TO 30" | LF | 435 | 42 | 18270
28 | WATER MAIN REMOVAL, LESS THAN OR EQUAL TO 12" | LF | 379 | 15 | 5685
29 | PAVEMENT REMOVAL, FULL DEPTH | SY | 733 | 12 | 8796
30 | BRICK PAVERS TO BE RECONSTRUCTED | LS | 1 | 10000 | 10000
31 | STORM SEWER CONNECT TO EXISTING | EA | 1 | 1250 | 1250
32 | STORM SEWER, CLASS A, TYPE 2, RCP, 12" | LF | 7 | 115 | 805
33 | STORM SEWER, CLASS A, TYPE 2, RCP, 15" | LF | 36 | 125 | 4500
34 | STORM SEWER, CLASS A, TYPE 2, RCP, 24" | LF | 351 | 145 | 50895
35 | STORM SEWER, ASTM F679, BORED AND JACKED, 24" | LF | 73 | 145 | 10585
36 | STEEL CASING PIPE, BORED AND JACKED, 36" | LF | 67 | 3700 | 247900
37 | SANITARY SEWER REMOVAL AND REPLACEMENT | LF | 24 | 195 | 4680
38 | SANITARY SERVICE REMOVAL AND REPLACEMENT | LF | 45 | 175 | 7875
39 | UPRR PERMIT COMPLIANCE | LS | 1 | 45000 | 45000
40 | PRECAST REINFORCED CONCRETE FLARED END SECTION, 24" | EA | 1 | 3000 | 3000
41 | RIP-RAP RR-4, CLASS A3 | SY | 142 | 165 | 23430
42 | COFFERDAM | EA | 1 | 3000 | 3000
43 | FLOATING SILT CURTAIN | LF | 90 | 12 | 1080
44 | CONCRETE SHORELINE REMOVAL | LF | 45 | 100 | 4500
45 | BOULDER SHORELINE STABILIZATION | SY | 25 | 1100 | 27500
46 | CONCRETE COLLAR | EA | 1 | 2000 | 2000
47 | BYPASS PUMPING | LS | 1 | 15000 | 15000
48 | RECORD DRAWINGS | LS | 1 | 2500 | 2500
49 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT, 3" | SY | 1 | 115 | 115
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | N-Trak Group |  | Northern Illinois Services |  | Everlast Blacktop
City of Rockford | [5 empty] | Loves Park, IL |  | Rockford, IL |  | St. Charles, IL
JEFFERSON STREET STORM SEWER IMPROVEMENTS | [5 empty] | Bid Bond |  | Bid Bond |  | Bid Bond
Vendors Notified: 236 BID NO. 126-PW-004
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 10000 | 10000 | 5500 | 5500 | 3500 | 3500 | 12000 | 12000 |  | 0 |  | 0 |  | 0
2 | INLET AND PIPE PROTECTION | EA | 8 | 300 | 2400 | 125 | 1000 | 300 | 2400 | 200 | 1600 |  | 0 |  | 0 |  | 0
3 | SUBBASE GRANULAR MATERIAL, TYPE B, CS-01, 9" | TON | 279 | 45 | 12555 | 19 | 5301 | 50 | 13950 | 45 | 12555 |  | 0 |  | 0 |  | 0
4 | AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | TON | 186 | 50 | 9300 | 25 | 4650 | 50 | 9300 | 44 | 8184 |  | 0 |  | 0 |  | 0
5 | SUBGRADE UNDERCUTTING | CY | 50 | 70 | 3500 | 45 | 2250 | 95 | 4750 | 80 | 4000 |  | 0 |  | 0 |  | 0
6 | BITUMINOUS MATERIALS (PRIME COAT) | GAL | 68 | 0.2 | 13.6 | 5 | 340 | 10 | 680 | 1 | 68 |  | 0 |  | 0 |  | 0
7 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 152 | 145 | 22040 | 140 | 21280 | 150 | 22800 | 260.14 | 39541.28 |  | 0 |  | 0 |  | 0
8 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N50, 2" | TON | 76 | 115 | 8740 | 140 | 10640 | 150 | 11400 | 374.9 | 28492.4 |  | 0 |  | 0 |  | 0
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SF | 215 | 15 | 3225 | 18 | 3870 | 15 | 3225 | 24 | 5160 |  | 0 |  | 0 |  | 0
10 | DETECTABLE WARNINGS | SF | 42 | 50 | 2100 | 30 | 1260 | 40 | 1680 | 75 | 3150 |  | 0 |  | 0 |  | 0
11 | COMBINATION CURB AND GUTTER REMOVAL | LF | 53 | 11 | 583 | 15 | 795 | 15 | 795 | 14 | 742 |  | 0 |  | 0 |  | 0
12 | SIDEWALK REMOVAL | SF | 215 | 3 | 645 | 2 | 430 | 10 | 2150 | 8 | 1720 |  | 0 |  | 0 |  | 0
13 | REMOVE EXISTING MANHOLE | EA | 3 | 500 | 1500 | 1200 | 3600 | 1250 | 3750 | 80 | 240 |  | 0 |  | 0 |  | 0
14 | STORM MANHOLE, TYPE A, 4' DIA, TYPE 1 FRAME, CLOSED LID | EA | 8 | 4700 | 37600 | 6000 | 48000 | 7000 | 56000 | 500 | 4000 |  | 0 |  | 0 |  | 0
15 | STORM MANHOLE, TYPE A, 8' DIA, TYPE 1 FRAME, CLOSED LID | EA | 1 | 15000 | 15000 | 15000 | 15000 | 19000 | 19000 | 20000 | 20000 |  | 0 |  | 0 |  | 0
16 | INLET REMOVAL | EA | 3 | 400 | 1200 | 600 | 1800 | 750 | 2250 | 500 | 1500 |  | 0 |  | 0 |  | 0
17 | INLET, TYPE B, 3' DIA, TYPE 3V FRAME AND GRATE | EA | 3 | 3200 | 9600 | 3500 | 10500 | 5500 | 16500 | 3000 | 9000 |  | 0 |  | 0 |  | 0
18 | COMBINATION CONCRETE CURB AND GUTTER, B-6.12 | LF | 38 | 40 | 1520 | 85 | 3230 | 100 | 3800 | 48 | 1824 |  | 0 |  | 0 |  | 0
19 | COMBINATION CONCRETE CURB AND GUTTER, DEPRESSED | LF | 15 | 40 | 600 | 110 | 1650 | 100 | 1500 | 200 | 3000 |  | 0 |  | 0 |  | 0
20 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 10000 | 10000 | 30000 | 30000 | 5000 | 5000 | 63861.52 | 63861.52 |  | 0 |  | 0 |  | 0
21 | MOBILIZATION | LS | 1 | 75000 | 75000 | 35000 | 35000 | 22580 | 22580 | 67693.21 | 67693.21 |  | 0 |  | 0 |  | 0
22 | NON-SPECIAL WASTE DISPOSAL | CY | 100 | 100 | 10000 | 0.01 | 1 | 0.01 | 1 | 110 | 11000 |  | 0 |  | 0 |  | 0
23 | SPECIAL WASTE DISPOSAL | CY | 25 | 150 | 3750 | 0.01 | 0.25 | 0.01 | 0.25 | 110 | 2750 |  | 0 |  | 0 |  | 0
24 | SPECIAL WASTE PLANS AND REPORTS | LS | 1 | 7500 | 7500 | 0.01 | 0.01 | 0.01 | 0.01 | 3900 | 3900 |  | 0 |  | 0 |  | 0
| Page 1 | Sub |  | As read | 248371.6 |  | 206097.26 |  | 207011.26 |  | 305981.41
| Award to N-Trak Group | Total |  | As corrected | 248371.6 |  | 206097.26 |  | 207011.26 |  | 305981.41
25 | SOIL DISPOSAL ANALYSIS | EA | 1 | 1500 | 1500 | 0.01 | 0.01 | 0.01 | 0.01 | 3000 | 3000 |  | 0 |  | 0 |  | 0
26 | STORM SEWER REMOVAL, LESS THAN OR EQUAL TO 30" | LF | 140 | 27 | 3780 | 35 | 4900 | 40 | 5600 | 210 | 29400 |  | 0 |  | 0 |  | 0
27 | STORM SEWER ABANDONMENT AND FILL, LESS THAN OR EQUAL TO 30" | LF | 435 | 42 | 18270 | 45 | 19575 | 65 | 28275 | 89 | 38715 |  | 0 |  | 0 |  | 0
28 | WATER MAIN REMOVAL, LESS THAN OR EQUAL TO 12" | LF | 379 | 15 | 5685 | 35 | 13265 | 15 | 5685 | 60 | 22740 |  | 0 |  | 0 |  | 0
29 | PAVEMENT REMOVAL, FULL DEPTH | SY | 733 | 12 | 8796 | 15 | 10995 | 30 | 21990 | 29 | 21257 |  | 0 |  | 0 |  | 0
30 | BRICK PAVERS TO BE RECONSTRUCTED | LS | 1 | 10000 | 10000 | 6000 | 6000 | 15000 | 15000 | 8500 | 8500 |  | 0 |  | 0 |  | 0
31 | STORM SEWER CONNECT TO EXISTING | EA | 1 | 1250 | 1250 | 2500 | 2500 | 1000 | 1000 | 5000 | 5000 |  | 0 |  | 0 |  | 0
32 | STORM SEWER, CLASS A, TYPE 2, RCP, 12" | LF | 7 | 115 | 805 | 370 | 2590 | 300 | 2100 | 375 | 2625 |  | 0 |  | 0 |  | 0
33 | STORM SEWER, CLASS A, TYPE 2, RCP, 15" | LF | 36 | 125 | 4500 | 197 | 7092 | 330 | 11880 | 266 | 9576 |  | 0 |  | 0 |  | 0
34 | STORM SEWER, CLASS A, TYPE 2, RCP, 24" | LF | 351 | 145 | 50895 | 250 | 87750 | 370 | 129870 | 179 | 62829 |  | 0 |  | 0 |  | 0
35 | STORM SEWER, ASTM F679, BORED AND JACKED, 24" | LF | 73 | 145 | 10585 | 400 | 29200 | 200 | 14600 | 1650 | 120450 |  | 0 |  | 0 |  | 0
36 | STEEL CASING PIPE, BORED AND JACKED, 36" | LF | 67 | 3700 | 247900 | 1000 | 67000 | 1375 | 92125 | 4400 | 294800 |  | 0 |  | 0 |  | 0
37 | SANITARY SEWER REMOVAL AND REPLACEMENT | LF | 24 | 195 | 4680 | 155 | 3720 | 300 | 7200 | 790 | 18960 |  | 0 |  | 0 |  | 0
38 | SANITARY SERVICE REMOVAL AND REPLACEMENT | LF | 45 | 175 | 7875 | 140 | 6300 | 255 | 11475 | 840 | 37800 |  | 0 |  | 0 |  | 0
39 | UPRR PERMIT COMPLIANCE | LS | 1 | 45000 | 45000 | 0.01 | 0.01 | 25000 | 25000 | 35000 | 35000 |  | 0 |  | 0 |  | 0
40 | PRECAST REINFORCED CONCRETE FLARED END SECTION, 24" | EA | 1 | 3000 | 3000 | 3000 | 3000 | 2000 | 2000 | 3500 | 3500 |  | 0 |  | 0 |  | 0
41 | RIP-RAP RR-4, CLASS A3 | SY | 142 | 165 | 23430 | 140 | 19880 | 125 | 17750 | 125 | 17750 |  | 0 |  | 0 |  | 0
42 | COFFERDAM | EA | 1 | 3000 | 3000 | 0.01 | 0.01 | 100000 | 100000 | 60000 | 60000 |  | 0 |  | 0 |  | 0
43 | FLOATING SILT CURTAIN | LF | 90 | 12 | 1080 | 0.01 | 0.9 | 50 | 4500 | 42 | 3780 |  | 0 |  | 0 |  | 0
44 | CONCRETE SHORELINE REMOVAL | LF | 45 | 100 | 4500 | 85 | 3825 | 250 | 11250 | 300 | 13500 |  | 0 |  | 0 |  | 0
45 | BOULDER SHORELINE STABILIZATION | SY | 25 | 1100 | 27500 | 800 | 20000 | 400 | 10000 | 590 | 14750 |  | 0 |  | 0 |  | 0
46 | CONCRETE COLLAR | EA | 1 | 2000 | 2000 | 2500 | 2500 | 3500 | 3500 | 6000 | 6000 |  | 0 |  | 0 |  | 0
47 | BYPASS PUMPING | LS | 1 | 15000 | 15000 | 0.01 | 0.01 | 15000 | 15000 | 45000 | 45000 |  | 0 |  | 0 |  | 0
48 | RECORD DRAWINGS | LS | 1 | 2500 | 2500 | 1500 | 1500 | 3000 | 3000 | 10000 | 10000 |  | 0 |  | 0 |  | 0
| Page 2 | Sub |  | As read | 751902.6 |  | 517690.2 |  | 745811.27 |  | 1190913.41
| Award to N-Trak Group | Total |  | As corrected | 751902.6 |  | 517690.2 |  | 745811.27 |  | 1190913.41
49 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT, 3" | SY | 1 | 115 | 115 | 400 | 400 | 500 | 500 | 5000 | 5000 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read | 752017.6 |  | 518090.2 |  | 746311.27 |  | 1195913.41
| Award to N-Trak Group | Bid |  | As corrected | 752017.6 |  | 518090.2 |  | 746311.27 |  | 1195913.41
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
| Page 4 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
| Page 5 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 6 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 7 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 8 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 9 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 10 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 11 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 12 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 13 | Total |  | As read
| Award to N-Trak Group | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
JEFFERSON STREET STORM SEWER IMPROVEMENTS
Item No. | Items | Units | Quantity | Unit Price | Total
1 | CONSTRUCTION LAYOUT STAKES | LS | 1 |  | 0
2 | INLET AND PIPE PROTECTION | EA | 8 |  | 0
3 | SUBBASE GRANULAR MATERIAL, TYPE B, CS-01, 9" | TON | 279 |  | 0
4 | AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | TON | 186 |  | 0
5 | SUBGRADE UNDERCUTTING | CY | 50 |  | 0
6 | BITUMINOUS MATERIALS (PRIME COAT) | GAL | 68 |  | 0
7 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 152 |  | 0
8 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N50, 2" | TON | 76 |  | 0
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SF | 215 |  | 0
10 | DETECTABLE WARNINGS | SF | 42 |  | 0
11 | COMBINATION CURB AND GUTTER REMOVAL | LF | 53 |  | 0
12 | SIDEWALK REMOVAL | SF | 215 |  | 0
13 | REMOVE EXISTING MANHOLE | EA | 3 |  | 0
14 | STORM MANHOLE, TYPE A, 4' DIA, TYPE 1 FRAME, CLOSED LID | EA | 8 |  | 0
15 | STORM MANHOLE, TYPE A, 8' DIA, TYPE 1 FRAME, CLOSED LID | EA | 1 |  | 0
16 | INLET REMOVAL | EA | 3 |  | 0
17 | INLET, TYPE B, 3' DIA, TYPE 3V FRAME AND GRATE | EA | 3 |  | 0
18 | COMBINATION CONCRETE CURB AND GUTTER, B-6.12 | LF | 38 |  | 0
19 | COMBINATION CONCRETE CURB AND GUTTER, DEPRESSED | LF | 15 |  | 0
20 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 |  | 0
21 | MOBILIZATION | LS | 1 |  | 0
22 | NON-SPECIAL WASTE DISPOSAL | CY | 100 |  | 0
23 | SPECIAL WASTE DISPOSAL | CY | 25 |  | 0
24 | SPECIAL WASTE PLANS AND REPORTS | LS | 1 |  | 0
| Page 1 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
25 | SOIL DISPOSAL ANALYSIS | EA | 1 |  | 0
26 | STORM SEWER REMOVAL, LESS THAN OR EQUAL TO 30" | LF | 140 |  | 0
27 | STORM SEWER ABANDONMENT AND FILL, LESS THAN OR EQUAL TO 30" | LF | 435 |  | 0
28 | WATER MAIN REMOVAL, LESS THAN OR EQUAL TO 12" | LF | 379 |  | 0
29 | PAVEMENT REMOVAL, FULL DEPTH | SY | 733 |  | 0
30 | BRICK PAVERS TO BE RECONSTRUCTED | LS | 1 |  | 0
31 | STORM SEWER CONNECT TO EXISTING | EA | 1 |  | 0
32 | STORM SEWER, CLASS A, TYPE 2, RCP, 12" | LF | 7 |  | 0
33 | STORM SEWER, CLASS A, TYPE 2, RCP, 15" | LF | 36 |  | 0
34 | STORM SEWER, CLASS A, TYPE 2, RCP, 24" | LF | 351 |  | 0
35 | STORM SEWER, ASTM F679, BORED AND JACKED, 24" | LF | 73 |  | 0
36 | STEEL CASING PIPE, BORED AND JACKED, 36" | LF | 67 |  | 0
37 | SANITARY SEWER REMOVAL AND REPLACEMENT | LF | 24 |  | 0
38 | SANITARY SERVICE REMOVAL AND REPLACEMENT | LF | 45 |  | 0
39 | UPRR PERMIT COMPLIANCE | LS | 1 |  | 0
40 | PRECAST REINFORCED CONCRETE FLARED END SECTION, 24" | EA | 1 |  | 0
41 | RIP-RAP RR-4, CLASS A3 | SY | 142 |  | 0
42 | COFFERDAM | EA | 1 |  | 0
43 | FLOATING SILT CURTAIN | LF | 90 |  | 0
44 | CONCRETE SHORELINE REMOVAL | LF | 45 |  | 0
45 | BOULDER SHORELINE STABILIZATION | SY | 25 |  | 0
46 | CONCRETE COLLAR | EA | 1 |  | 0
47 | BYPASS PUMPING | LS | 1 |  | 0
48 | RECORD DRAWINGS | LS | 1 |  | 0
| Page 2 | Sub |  | As read | 0
|  | Total |  | As corrected | 0
49 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT, 3" | SY | 1 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 5 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 6 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 7 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 8 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 9 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 10 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 11 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 12 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 13 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | CONSTRUCTION LAYOUT STAKES | LS | 1 | 10000 | 10000
2 | INLET AND PIPE PROTECTION | EA | 8 | 300 | 2400
3 | SUBBASE GRANULAR MATERIAL, TYPE B, CS-01, 9" | TON | 279 | 45 | 12555
4 | AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | TON | 186 | 50 | 9300
5 | SUBGRADE UNDERCUTTING | CY | 50 | 70 | 3500
6 | BITUMINOUS MATERIALS (PRIME COAT) | GAL | 68 | 0.2 | 13.6
7 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 152 | 145 | 22040
8 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N50, 2" | TON | 76 | 115 | 8740
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SF | 215 | 15 | 3225
10 | DETECTABLE WARNINGS | SF | 42 | 50 | 2100
11 | COMBINATION CURB AND GUTTER REMOVAL | LF | 53 | 11 | 583
12 | SIDEWALK REMOVAL | SF | 215 | 3 | 645
13 | REMOVE EXISTING MANHOLE | EA | 3 | 500 | 1500
14 | STORM MANHOLE, TYPE A, 4' DIA, TYPE 1 FRAME, CLOSED LID | EA | 8 | 4700 | 37600
15 | STORM MANHOLE, TYPE A, 8' DIA, TYPE 1 FRAME, CLOSED LID | EA | 1 | 15000 | 15000
16 | INLET REMOVAL | EA | 3 | 400 | 1200
17 | INLET, TYPE B, 3' DIA, TYPE 3V FRAME AND GRATE | EA | 3 | 3200 | 9600
18 | COMBINATION CONCRETE CURB AND GUTTER, B-6.12 | LF | 38 | 40 | 1520
19 | COMBINATION CONCRETE CURB AND GUTTER, DEPRESSED | LF | 15 | 40 | 600
20 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1 | 10000 | 10000
21 | MOBILIZATION | LS | 1 | 75000 | 75000
22 | NON-SPECIAL WASTE DISPOSAL | CY | 100 | 100 | 10000
23 | SPECIAL WASTE DISPOSAL | CY | 25 | 150 | 3750
24 | SPECIAL WASTE PLANS AND REPORTS | LS | 1 | 7500 | 7500
|  |  |  | Sub Total | 248371.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
25 | SOIL DISPOSAL ANALYSIS | EA | 1 | 1500 | 1500
26 | STORM SEWER REMOVAL, LESS THAN OR EQUAL TO 30" | LF | 140 | 27 | 3780
27 | STORM SEWER ABANDONMENT AND FILL, LESS THAN OR EQUAL TO 30" | LF | 435 | 42 | 18270
28 | WATER MAIN REMOVAL, LESS THAN OR EQUAL TO 12" | LF | 379 | 15 | 5685
29 | PAVEMENT REMOVAL, FULL DEPTH | SY | 733 | 12 | 8796
30 | BRICK PAVERS TO BE RECONSTRUCTED | LS | 1 | 10000 | 10000
31 | STORM SEWER CONNECT TO EXISTING | EA | 1 | 1250 | 1250
32 | STORM SEWER, CLASS A, TYPE 2, RCP, 12" | LF | 7 | 115 | 805
33 | STORM SEWER, CLASS A, TYPE 2, RCP, 15" | LF | 36 | 125 | 4500
34 | STORM SEWER, CLASS A, TYPE 2, RCP, 24" | LF | 351 | 145 | 50895
35 | STORM SEWER, ASTM F679, BORED AND JACKED, 24" | LF | 73 | 145 | 10585
36 | STEEL CASING PIPE, BORED AND JACKED, 36" | LF | 67 | 3700 | 247900
37 | SANITARY SEWER REMOVAL AND REPLACEMENT | LF | 24 | 195 | 4680
38 | SANITARY SERVICE REMOVAL AND REPLACEMENT | LF | 45 | 175 | 7875
39 | UPRR PERMIT COMPLIANCE | LS | 1 | 45000 | 45000
40 | PRECAST REINFORCED CONCRETE FLARED END SECTION, 24" | EA | 1 | 3000 | 3000
41 | RIP-RAP RR-4, CLASS A3 | SY | 142 | 165 | 23430
42 | COFFERDAM | EA | 1 | 3000 | 3000
43 | FLOATING SILT CURTAIN | LF | 90 | 12 | 1080
44 | CONCRETE SHORELINE REMOVAL | LF | 45 | 100 | 4500
45 | BOULDER SHORELINE STABILIZATION | SY | 25 | 1100 | 27500
46 | CONCRETE COLLAR | EA | 1 | 2000 | 2000
47 | BYPASS PUMPING | LS | 1 | 15000 | 15000
48 | RECORD DRAWINGS | LS | 1 | 2500 | 2500
|  |  |  | Sub Total | 751902.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
49 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT, 3" | SY | 1 | 115 | 115
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 752017.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 752017.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 752017.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 5 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 752017.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 6 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 752017.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 7 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 752017.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 8 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 752017.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 9 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 752017.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 10 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 752017.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 11 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | JEFFERSON STREET STORM SEWER IMPROVEMENTS
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 752017.6
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 112 |  |  |  |  | BLR 5730 (Rev 8/87)

## Estaimate of Cost - to CAD
Item No. | Items | Unit | Quantity
1 | CONSTRUCTION LAYOUT STAKES | LS | 1
2 | INLET AND PIPE PROTECTION | EA | 8
3 | SUBBASE GRANULAR MATERIAL, TYPE B, CS-01, 9" | TON | 279
4 | AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | TON | 186
5 | SUBGRADE UNDERCUTTING | CY | 50
6 | BITUMINOUS MATERIALS (PRIME COAT) | GAL | 68
7 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | TON | 152
8 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N50, 2" | TON | 76
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | SF | 215
10 | DETECTABLE WARNINGS | SF | 42
11 | COMBINATION CURB AND GUTTER REMOVAL | LF | 53
12 | SIDEWALK REMOVAL | SF | 215
13 | REMOVE EXISTING MANHOLE | EA | 3
14 | STORM MANHOLE, TYPE A, 4' DIA, TYPE 1 FRAME, CLOSED LID | EA | 8
15 | STORM MANHOLE, TYPE A, 8' DIA, TYPE 1 FRAME, CLOSED LID | EA | 1
16 | INLET REMOVAL | EA | 3
17 | INLET, TYPE B, 3' DIA, TYPE 3V FRAME AND GRATE | EA | 3
18 | COMBINATION CONCRETE CURB AND GUTTER, B-6.12 | LF | 38
19 | COMBINATION CONCRETE CURB AND GUTTER, DEPRESSED | LF | 15
20 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | LS | 1
21 | MOBILIZATION | LS | 1
22 | NON-SPECIAL WASTE DISPOSAL | CY | 100
23 | SPECIAL WASTE DISPOSAL | CY | 25
24 | SPECIAL WASTE PLANS AND REPORTS | LS | 1
25 | SOIL DISPOSAL ANALYSIS | EA | 1
26 | STORM SEWER REMOVAL, LESS THAN OR EQUAL TO 30" | LF | 140
27 | STORM SEWER ABANDONMENT AND FILL, LESS THAN OR EQUAL TO 30" | LF | 435
28 | WATER MAIN REMOVAL, LESS THAN OR EQUAL TO 12" | LF | 379
29 | PAVEMENT REMOVAL, FULL DEPTH | SY | 733
30 | BRICK PAVERS TO BE RECONSTRUCTED | LS | 1
31 | STORM SEWER CONNECT TO EXISTING | EA | 1
32 | STORM SEWER, CLASS A, TYPE 2, RCP, 12" | LF | 7
33 | STORM SEWER, CLASS A, TYPE 2, RCP, 15" | LF | 36
34 | STORM SEWER, CLASS A, TYPE 2, RCP, 24" | LF | 351
35 | STORM SEWER, ASTM F679, BORED AND JACKED, 24" | LF | 73
36 | STEEL CASING PIPE, BORED AND JACKED, 36" | LF | 67
37 | SANITARY SEWER REMOVAL AND REPLACEMENT | LF | 24
38 | SANITARY SERVICE REMOVAL AND REPLACEMENT | LF | 45
39 | UPRR PERMIT COMPLIANCE | LS | 1
40 | PRECAST REINFORCED CONCRETE FLARED END SECTION, 24" | EA | 1
41 | RIP-RAP RR-4, CLASS A3 | SY | 142
42 | COFFERDAM | EA | 1
43 | FLOATING SILT CURTAIN | LF | 90
44 | CONCRETE SHORELINE REMOVAL | LF | 45
45 | BOULDER SHORELINE STABILIZATION | SY | 25
46 | CONCRETE COLLAR | EA | 1
47 | BYPASS PUMPING | LS | 1
48 | RECORD DRAWINGS | LS | 1
49 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT, 3" | SY | 1

## Pay Estimate
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | CONSTRUCTION LAYOUT STAKES | 1 | LS | 5500 |  | 1 |  |  | 5500
2 | INLET AND PIPE PROTECTION | 8 | EA | 1000 |  | 8 |  |  | 125
3 | SUBBASE GRANULAR MATERIAL, TYPE B, CS-01, 9" | 279 | TON | 5301 |  | 279 |  |  | 19
4 | AGGREGATE BASE COURSE, TYPE B, CA-6, 6" | 186 | TON | 4650 |  | 186 |  |  | 25
5 | SUBGRADE UNDERCUTTING | 50 | CY | 2250 |  | 50 |  |  | 45
6 | BITUMINOUS MATERIALS (PRIME COAT) | 68 | GAL | 340 |  | 68 |  |  | 5
7 | HOT-MIX ASPHALT BINDER COURSE, IL-19.0, N50, 4" | 152 | TON | 21280 |  | 152 |  |  | 140
8 | HOT-MIX ASPHALT SURFACE COURSE, MIX "D", N50, 2" | 76 | TON | 10640 |  | 76 |  |  | 140
9 | PORTLAND CEMENT CONCRETE SIDEWALK, 4" | 215 | SF | 3870 |  | 215 |  |  | 18
10 | DETECTABLE WARNINGS | 42 | SF | 1260 |  | 42 |  |  | 30
11 | COMBINATION CURB AND GUTTER REMOVAL | 53 | LF | 795 |  | 53 |  |  | 15
12 | SIDEWALK REMOVAL | 215 | SF | 430 |  | 215 |  |  | 2
13 | REMOVE EXISTING MANHOLE | 3 | EA | 3600 |  | 3 |  |  | 1200
14 | STORM MANHOLE, TYPE A, 4' DIA, TYPE 1 FRAME, CLOSED LID | 8 | EA | 48000 |  | 8 |  |  | 6000
15 | STORM MANHOLE, TYPE A, 8' DIA, TYPE 1 FRAME, CLOSED LID | 1 | EA | 15000 |  | 1 |  |  | 15000
16 | INLET REMOVAL | 3 | EA | 1800 |  | 3 |  |  | 600
17 | INLET, TYPE B, 3' DIA, TYPE 3V FRAME AND GRATE | 3 | EA | 10500 |  | 3 |  |  | 3500
18 | COMBINATION CONCRETE CURB AND GUTTER, B-6.12 | 38 | LF | 3230 |  | 38 |  |  | 85
19 | COMBINATION CONCRETE CURB AND GUTTER, DEPRESSED | 15 | LF | 1650 |  | 15 |  |  | 110
20 | TRAFFIC CONTROL AND PROTECTION, SPECIAL | 1 | LS | 30000 |  | 1 |  |  | 30000
21 | MOBILIZATION | 1 | LS | 35000 |  | 1 |  |  | 35000
22 | NON-SPECIAL WASTE DISPOSAL | 100 | CY | 1 |  | 100 |  |  | 0.01
23 | SPECIAL WASTE DISPOSAL | 25 | CY | 0.25 |  | 25 |  |  | 0.01
24 | SPECIAL WASTE PLANS AND REPORTS | 1 | LS | 0.01 |  | 1 |  |  | 0.01
Sub Total |  |  |  | 206097.26 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
25 | SOIL DISPOSAL ANALYSIS | 1 | EA | 0.01 |  | 1 |  |  | 0.01
26 | STORM SEWER REMOVAL, LESS THAN OR EQUAL TO 30" | 140 | LF | 4900 |  | 140 |  |  | 35
27 | STORM SEWER ABANDONMENT AND FILL, LESS THAN OR EQUAL TO 30" | 435 | LF | 19575 |  | 435 |  |  | 45
28 | WATER MAIN REMOVAL, LESS THAN OR EQUAL TO 12" | 379 | LF | 13265 |  | 379 |  |  | 35
29 | PAVEMENT REMOVAL, FULL DEPTH | 733 | SY | 10995 |  | 733 |  |  | 15
30 | BRICK PAVERS TO BE RECONSTRUCTED | 1 | LS | 6000 |  | 1 |  |  | 6000
31 | STORM SEWER CONNECT TO EXISTING | 1 | EA | 2500 |  | 1 |  |  | 2500
32 | STORM SEWER, CLASS A, TYPE 2, RCP, 12" | 7 | LF | 2590 |  | 7 |  |  | 370
33 | STORM SEWER, CLASS A, TYPE 2, RCP, 15" | 36 | LF | 7092 |  | 36 |  |  | 197
34 | STORM SEWER, CLASS A, TYPE 2, RCP, 24" | 351 | LF | 87750 |  | 351 |  |  | 250
35 | STORM SEWER, ASTM F679, BORED AND JACKED, 24" | 73 | LF | 29200 |  | 73 |  |  | 400
36 | STEEL CASING PIPE, BORED AND JACKED, 36" | 67 | LF | 67000 |  | 67 |  |  | 1000
37 | SANITARY SEWER REMOVAL AND REPLACEMENT | 24 | LF | 3720 |  | 24 |  |  | 155
38 | SANITARY SERVICE REMOVAL AND REPLACEMENT | 45 | LF | 6300 |  | 45 |  |  | 140
39 | UPRR PERMIT COMPLIANCE | 1 | LS | 0.01 |  | 1 |  |  | 0.01
40 | PRECAST REINFORCED CONCRETE FLARED END SECTION, 24" | 1 | EA | 3000 |  | 1 |  |  | 3000
41 | RIP-RAP RR-4, CLASS A3 | 142 | SY | 19880 |  | 142 |  |  | 140
42 | COFFERDAM | 1 | EA | 0.01 |  | 1 |  |  | 0.01
43 | FLOATING SILT CURTAIN | 90 | LF | 0.9 |  | 90 |  |  | 0.01
44 | CONCRETE SHORELINE REMOVAL | 45 | LF | 3825 |  | 45 |  |  | 85
45 | BOULDER SHORELINE STABILIZATION | 25 | SY | 20000 |  | 25 |  |  | 800
46 | CONCRETE COLLAR | 1 | EA | 2500 |  | 1 |  |  | 2500
47 | BYPASS PUMPING | 1 | LS | 0.01 |  | 1 |  |  | 0.01
48 | RECORD DRAWINGS | 1 | LS | 1500 |  | 1 |  |  | 1500
Sub Total |  |  |  | 517690.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
TOTAL VALUE OF COMPLETED WORK
DEDUCT RETAINAGE
BALANCE DUE ON COMPLETED WORK
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
NET AMOUNT DUE
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
49 | HOT-MIX ASPHALT DRIVEWAY PAVEMENT, 3" | 1 | SY | 400 |  | 1 |  |  | 400
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6303
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302
ENGINEER'S FINAL PAYMENT ESTIMATE
Estimate No. 1 from to
| Payable to: N-Trak Group | [5 empty] | MUNICIPALITY | City of Rockford
Address: Loves Park, IL Bid Bond
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 518090.2 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2022 BY:
|  |  | SIGNED | [6 empty] | TITLE
BLR 6302

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Logistics Parkway - Phase II
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | N-Trak Group
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.