## Item List
| 4 sheet bid tab has 96 Items total "BidTab COR 010909.xlt" |  |  |  | 663250
Summary Of Quantities
No. | Item | Units | Quant. | Unit Price | Total
1 | Class "D" Patches, Type I, 4" | S.Y. | 75 | 75 | 5625
2 | Class "D" Patches, Type II, 4" | S.Y. | 800 | 85 | 68000
3 | Class "D" Patches, Type III, 4" | S.Y. | 1500 | 75 | 112500
4 | Class "D" Patches, Type IV, 4" | S.Y. | 2500 | 75 | 187500
5 | Class "D" Patches, Type I, 6" | S.Y. | 50 | 90 | 4500
6 | Class "D" Patches, Type II, 6" | S.Y. | 75 | 90 | 6750
7 | Class "D" Patches, Type III, 6" | S.Y. | 150 | 85 | 12750
8 | Class "D" Patches, Type IV, 6" | S.Y. | 500 | 85 | 42500
9 | Class "D" Patches, Type I, 8" | S.Y. | 25 | 90 | 2250
10 | Class "D" Patches, Type II, 8" | S.Y. | 25 | 95 | 2375
11 | Class "D" Patches, Type III, 8" | S.Y. | 25 | 95 | 2375
12 | Class "D" Patches, Type IV, 8" | S.Y. | 25 | 95 | 2375
13 | Class "D" Patches, Type I, 10" | S.Y. | 25 | 110 | 2750
14 | Class "D" Patches, Type II, 10" | S.Y. | 25 | 100 | 2500
15 | Class "D" Patches, Type III, 10" | S.Y. | 25 | 100 | 2500
16 | Class "D" Patches, Type IV, 10" | S.Y. | 25 | 100 | 2500
17 | Cold Weather Utility Patch, Type 1, 2" | TON | 20 | 350 | 7000
18 | Cold Weather Utility Patch, Type 2, 2" | TON | 250 | 300 | 75000
19 | Cold Weather Utility Patch, Type 3, 2" | TON | 300 | 250 | 75000
20 | Cold Weather Utility Patch, Type 4, 2" | TON | 150 | 250 | 37500
21 | Aggregate Surface Course | TON | 300 | 30 | 9000
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96

## Tabulation of Bids
TABULATION OF BIDS |  |  |  | NAME AND ADDRESS OF BIDDER: |  | DPI CONSTRUCTION |  | STENSTROM EXCAVATION
City of Rockford | [5 empty] | PECATONICA, IL |  | ROCKFORD, IL
Bituminous Patching 2026 | [5 empty] | BID BOND |  | BID BOND
Vendors Notified: 236 Bid No.: 1125-W-135
Item No. | Items | Units | Quantity | ENGINEER'S Unit Price | ESTIMATE Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total | Unit Price | Total
1 | Class "D" Patches, Type I, 4" | S.Y. | 75 | 75 | 5625 | 84.5 | 6337.5 | 83 | 6225 |  | 0 |  | 0 |  | 0 |  | 0
2 | Class "D" Patches, Type II, 4" | S.Y. | 800 | 85 | 68000 | 105 | 84000 | 125 | 100000 |  | 0 |  | 0 |  | 0 |  | 0
3 | Class "D" Patches, Type III, 4" | S.Y. | 1500 | 75 | 112500 | 84.5 | 126750 | 91 | 136500 |  | 0 |  | 0 |  | 0 |  | 0
4 | Class "D" Patches, Type IV, 4" | S.Y. | 2500 | 75 | 187500 | 50 | 125000 | 72 | 180000 |  | 0 |  | 0 |  | 0 |  | 0
5 | Class "D" Patches, Type I, 6" | S.Y. | 50 | 90 | 4500 | 130 | 6500 | 77 | 3850 |  | 0 |  | 0 |  | 0 |  | 0
6 | Class "D" Patches, Type II, 6" | S.Y. | 75 | 90 | 6750 | 106 | 7950 | 76 | 5700 |  | 0 |  | 0 |  | 0 |  | 0
7 | Class "D" Patches, Type III, 6" | S.Y. | 150 | 85 | 12750 | 84.5 | 12675 | 65 | 9750 |  | 0 |  | 0 |  | 0 |  | 0
8 | Class "D" Patches, Type IV, 6" | S.Y. | 500 | 85 | 42500 | 52 | 26000 | 55 | 27500 |  | 0 |  | 0 |  | 0 |  | 0
9 | Class "D" Patches, Type I, 8" | S.Y. | 25 | 90 | 2250 | 150 | 3750 | 50 | 1250 |  | 0 |  | 0 |  | 0 |  | 0
10 | Class "D" Patches, Type II, 8" | S.Y. | 25 | 95 | 2375 | 160 | 4000 | 50 | 1250 |  | 0 |  | 0 |  | 0 |  | 0
11 | Class "D" Patches, Type III, 8" | S.Y. | 25 | 95 | 2375 | 137 | 3425 | 48 | 1200 |  | 0 |  | 0 |  | 0 |  | 0
12 | Class "D" Patches, Type IV, 8" | S.Y. | 25 | 95 | 2375 | 54 | 1350 | 47 | 1175 |  | 0 |  | 0 |  | 0 |  | 0
13 | Class "D" Patches, Type I, 10" | S.Y. | 25 | 110 | 2750 | 155 | 3875 | 50 | 1250 |  | 0 |  | 0 |  | 0 |  | 0
14 | Class "D" Patches, Type II, 10" | S.Y. | 25 | 100 | 2500 | 162 | 4050 | 50 | 1250 |  | 0 |  | 0 |  | 0 |  | 0
15 | Class "D" Patches, Type III, 10" | S.Y. | 25 | 100 | 2500 | 142 | 3550 | 48 | 1200 |  | 0 |  | 0 |  | 0 |  | 0
16 | Class "D" Patches, Type IV, 10" | S.Y. | 25 | 100 | 2500 | 60 | 1500 | 47 | 1175 |  | 0 |  | 0 |  | 0 |  | 0
17 | Cold Weather Utility Patch, Type 1, 2" | TON | 20 | 350 | 7000 | 600 | 12000 | 565 | 11300 |  | 0 |  | 0 |  | 0 |  | 0
18 | Cold Weather Utility Patch, Type 2, 2" | TON | 250 | 300 | 75000 | 350 | 87500 | 610 | 152500 |  | 0 |  | 0 |  | 0 |  | 0
19 | Cold Weather Utility Patch, Type 3, 2" | TON | 300 | 250 | 75000 | 350 | 105000 | 435 | 130500 |  | 0 |  | 0 |  | 0 |  | 0
20 | Cold Weather Utility Patch, Type 4, 2" | TON | 150 | 250 | 37500 | 350 | 52500 | 360 | 54000 |  | 0 |  | 0 |  | 0 |  | 0
21 | Aggregate Surface Course | TON | 300 | 30 | 9000 | 24 | 7200 | 0.01 | 3 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 1 | Total |  | As read | 663250 |  | 684912.5 |  | 827578
| Award to DPI CONSTRUCTION | Bid |  | As corrected | 663250 |  | 684912.5 |  | 827578
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 2 | Total |  | As read
| Award to DPI CONSTRUCTION | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 3 | Total |  | As read
| Award to DPI CONSTRUCTION | Bid |  | As corrected
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Page 4 | Total |  | As read
| Award to DPI CONSTRUCTION | Bid |  | As corrected

## Schedule of Prices
SCHEDULE OF PRICES
City of Rockford
Bituminous Patching 2026
Item No. | Items | Units | Quantity | Unit Price | Total
1 | Class "D" Patches, Type I, 4" | S.Y. | 75 |  | 0
2 | Class "D" Patches, Type II, 4" | S.Y. | 800 |  | 0
3 | Class "D" Patches, Type III, 4" | S.Y. | 1500 |  | 0
4 | Class "D" Patches, Type IV, 4" | S.Y. | 2500 |  | 0
5 | Class "D" Patches, Type I, 6" | S.Y. | 50 |  | 0
6 | Class "D" Patches, Type II, 6" | S.Y. | 75 |  | 0
7 | Class "D" Patches, Type III, 6" | S.Y. | 150 |  | 0
8 | Class "D" Patches, Type IV, 6" | S.Y. | 500 |  | 0
9 | Class "D" Patches, Type I, 8" | S.Y. | 25 |  | 0
10 | Class "D" Patches, Type II, 8" | S.Y. | 25 |  | 0
11 | Class "D" Patches, Type III, 8" | S.Y. | 25 |  | 0
12 | Class "D" Patches, Type IV, 8" | S.Y. | 25 |  | 0
13 | Class "D" Patches, Type I, 10" | S.Y. | 25 |  | 0
14 | Class "D" Patches, Type II, 10" | S.Y. | 25 |  | 0
15 | Class "D" Patches, Type III, 10" | S.Y. | 25 |  | 0
16 | Class "D" Patches, Type IV, 10" | S.Y. | 25 |  | 0
17 | Cold Weather Utility Patch, Type 1, 2" | TON | 20 |  | 0
18 | Cold Weather Utility Patch, Type 2, 2" | TON | 250 |  | 0
19 | Cold Weather Utility Patch, Type 3, 2" | TON | 300 |  | 0
20 | Cold Weather Utility Patch, Type 4, 2" | TON | 150 |  | 0
21 | Aggregate Surface Course | TON | 300 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 1 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 2 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 3 | Total |  | As read | 0
|  | Bid |  | As corrected | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Page 4 | Total |  | As read | 0
|  | Bid |  | As corrected | 0

## Estimate of Cost
|  | Municipality |  | City of Rockford
Road District
|  | County | Winnebago
| ESTIMATE OF COST | Section | Bituminous Patching 2026
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
1 | Class "D" Patches, Type I, 4" | S.Y. | 75 | 75 | 5625
2 | Class "D" Patches, Type II, 4" | S.Y. | 800 | 85 | 68000
3 | Class "D" Patches, Type III, 4" | S.Y. | 1500 | 75 | 112500
4 | Class "D" Patches, Type IV, 4" | S.Y. | 2500 | 75 | 187500
5 | Class "D" Patches, Type I, 6" | S.Y. | 50 | 90 | 4500
6 | Class "D" Patches, Type II, 6" | S.Y. | 75 | 90 | 6750
7 | Class "D" Patches, Type III, 6" | S.Y. | 150 | 85 | 12750
8 | Class "D" Patches, Type IV, 6" | S.Y. | 500 | 85 | 42500
9 | Class "D" Patches, Type I, 8" | S.Y. | 25 | 90 | 2250
10 | Class "D" Patches, Type II, 8" | S.Y. | 25 | 95 | 2375
11 | Class "D" Patches, Type III, 8" | S.Y. | 25 | 95 | 2375
12 | Class "D" Patches, Type IV, 8" | S.Y. | 25 | 95 | 2375
13 | Class "D" Patches, Type I, 10" | S.Y. | 25 | 110 | 2750
14 | Class "D" Patches, Type II, 10" | S.Y. | 25 | 100 | 2500
15 | Class "D" Patches, Type III, 10" | S.Y. | 25 | 100 | 2500
16 | Class "D" Patches, Type IV, 10" | S.Y. | 25 | 100 | 2500
17 | Cold Weather Utility Patch, Type 1, 2" | TON | 20 | 350 | 7000
18 | Cold Weather Utility Patch, Type 2, 2" | TON | 250 | 300 | 75000
19 | Cold Weather Utility Patch, Type 3, 2" | TON | 300 | 250 | 75000
20 | Cold Weather Utility Patch, Type 4, 2" | TON | 150 | 250 | 37500
21 | Aggregate Surface Course | TON | 300 | 30 | 9000
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 663250
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 1 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bituminous Patching 2026
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 663250
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 2 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bituminous Patching 2026
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 663250
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 3 |  |  |  |  | BLR 5730 (Rev 8/87)
|  | Municipality |  | City of Rockford
|  | Road District |  | 0
|  | County |  | Winnebago
| ESTIMATE OF COST | Section | Bituminous Patching 2026
Location (Sta. and land description of beginning; Sta. only for end for county and road district; street limits for municipality.)
0
0
0
0
a total distance of _________feet, of which ___________ feet (____________ miles) are to be improved
Station ______________ is approximately ________________ miles by road from the ______________
railroad siding at ______________________________________
Type ______________________ Width ____________ Thickness ___________ Shoulders ___________
Average Length of Haul _________________________________
Item No. | Items | Unit | Quantity | Unit Price | Total
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | Total | 663250
Made by: |  |  | Date:
Checked by: |  |  | Date:
Page 4 |  |  |  |  | BLR 5730 (Rev 8/87)

## Pay Estimate
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: DPI CONSTRUCTION | [5 empty] | MUNICIPALITY | City of Rockford
| Address: PECATONICA, IL BID BOND | [5 empty] | SECTION | Bituminous Patching 2026
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
1 | Class "D" Patches, Type I, 4" | 75 | S.Y. | 6337.5 |  | 75 |  |  | 84.5
2 | Class "D" Patches, Type II, 4" | 800 | S.Y. | 84000 |  | 800 |  |  | 105
3 | Class "D" Patches, Type III, 4" | 1500 | S.Y. | 126750 |  | 1500 |  |  | 84.5
4 | Class "D" Patches, Type IV, 4" | 2500 | S.Y. | 125000 |  | 2500 |  |  | 50
5 | Class "D" Patches, Type I, 6" | 50 | S.Y. | 6500 |  | 50 |  |  | 130
6 | Class "D" Patches, Type II, 6" | 75 | S.Y. | 7950 |  | 75 |  |  | 106
7 | Class "D" Patches, Type III, 6" | 150 | S.Y. | 12675 |  | 150 |  |  | 84.5
8 | Class "D" Patches, Type IV, 6" | 500 | S.Y. | 26000 |  | 500 |  |  | 52
9 | Class "D" Patches, Type I, 8" | 25 | S.Y. | 3750 |  | 25 |  |  | 150
10 | Class "D" Patches, Type II, 8" | 25 | S.Y. | 4000 |  | 25 |  |  | 160
11 | Class "D" Patches, Type III, 8" | 25 | S.Y. | 3425 |  | 25 |  |  | 137
12 | Class "D" Patches, Type IV, 8" | 25 | S.Y. | 1350 |  | 25 |  |  | 54
13 | Class "D" Patches, Type I, 10" | 25 | S.Y. | 3875 |  | 25 |  |  | 155
14 | Class "D" Patches, Type II, 10" | 25 | S.Y. | 4050 |  | 25 |  |  | 162
15 | Class "D" Patches, Type III, 10" | 25 | S.Y. | 3550 |  | 25 |  |  | 142
16 | Class "D" Patches, Type IV, 10" | 25 | S.Y. | 1500 |  | 25 |  |  | 60
17 | Cold Weather Utility Patch, Type 1, 2" | 20 | TON | 12000 |  | 20 |  |  | 600
18 | Cold Weather Utility Patch, Type 2, 2" | 250 | TON | 87500 |  | 250 |  |  | 350
19 | Cold Weather Utility Patch, Type 3, 2" | 300 | TON | 105000 |  | 300 |  |  | 350
20 | Cold Weather Utility Patch, Type 4, 2" | 150 | TON | 52500 |  | 150 |  |  | 350
21 | Aggregate Surface Course | 300 | TON | 7200 |  | 300 |  |  | 24
Total |  |  |  | 684912.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: DPI CONSTRUCTION | [5 empty] | MUNICIPALITY | City of Rockford
| Address: PECATONICA, IL BID BOND | [5 empty] | SECTION | Bituminous Patching 2026
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 684912.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 2013 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: DPI CONSTRUCTION | [5 empty] | MUNICIPALITY | City of Rockford
| Address: PECATONICA, IL BID BOND | [5 empty] | SECTION | Bituminous Patching 2026
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 684912.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)
STATE OF ILLINOIS | [6 empty] | COUNTY OF | Winnbago
ENGINEER'S FINAL PAYMENT ESTIMATE
| Estimate No. 1 from to | [7 empty] | (Road District)
| Payable to: DPI CONSTRUCTION | [5 empty] | MUNICIPALITY | City of Rockford
| Address: PECATONICA, IL BID BOND | [5 empty] | SECTION | Bituminous Patching 2026
|  | *AWARDED |  |  | Added | Deducted | COMPLETED
ITEMS |  | Quantity |  | Values | Quantity | Quantity | Quantity |  | Unit Price | Values
Total |  |  |  | 684912.5 | [5 empty] | 0
MISCELLANEOUS EXTRAS AND CREDITS | [8 empty] | Values
TOTAL MISCELLANEOUS EXTRAS AND CREDITS
[8 empty] | TOTAL VALUE OF COMPLETED WORK |  | 0
DEDUCT RETAINAGE
[8 empty] | BALANCE DUE ON COMPLETED WORK |  | 0
MISCELLANEOUS DEBITS | [8 empty] | Values
TOTAL OF DEBITS
[8 empty] | NET AMOUNT DUE |  | 0
| SIGNED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
| APPROVED | , 20 BY:
|  |  | SIGNED | [6 empty] | TITLE
*FOR DAY LABOR SECTIONS SHOW ESTIMATED QUANTITIES AND VALUES. | [9 empty] | BLR 6303
SUBMIT 1 COPY TO DISTRICT ENGINEER | [9 empty] | (4-84)

## Change Order p1
Request for Approval
of Change In Plans
|  |  | Municipality | City of Rockford
Township
|  |  | County | Winnebago
To: |  |  | Section | Bituminous Patching 2026
Department of Transportation |  |  | Request No. | 1
Date:
Dixon, Illinois |  |  | Contractor | DPI CONSTRUCTION
I recommend that (a deduction an addition) be made to the above contract.
(between Station __________ and Station __________ a net length of __________ lineal feet.)
(Do not fill in unless a change in length is involved.)
The estimated quantities are shown below and the contractor agrees to furnish the materials and do the work at the contract
unit prices. Show station location for major items.
Items |  | Quantity | Unit Price | Additions | Deductions
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total net (deduction addition) to date ____ which is __% of Contract price. |  |  | Totals | 0 | 0
|  |  | Net Change | 0 | 0
BLR 6301
State fully the nature and reason for the change:
When the net increase or decrease in the cost of the contract is $10,000 or more or the time of completion is
increased or decreased by 30 days or more, one of the following statement shall be checked.
The undersigned determine that the circumstances which necessitate this change
were not reasonably foreseeable at the time the contract was signed.
The undersigned determine that the circumstances which necessitate this change
were not within the contemplation of the contract as signed.
The undersigned determine that this change is in the best interest of the local
agency and is authorized by law.
Signed: |  | , 2013 | Signed: |  | , 2013
Highway Commissioner |  |  | Municipal Officer
Approved
Recommended
| County Superintendent of Highways |  | (Title of Municipal Officer)
Note: Make out separate form for change in length quantities. |  |  | Approved |  | , 2013
Give net quantities only.
Submit 3 copies of this form to District Engineer
(4 copies for road district.) |  |  | District Engineer
If plans are required attach three sets.